## PlanFileName (hidden)
isdp_boonchot.b_56A0S0Q_20261002072744 | 56A0S0Q | V3 | 149 | 1911 | 1911 | M3T1A1969N1312696804393537694 | M3T1A1969N1312696807027585125
|  |  | {"headerType":"extarr","itemName":"DU ID","itemChildName":"","activityId":null,"id":"DUCODE","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83337424123 | 12BBM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"extarr","itemName":"DU Name","itemChildName":"","activityId":null,"id":"DUNAME","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81144424123 | 1CONB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"extarr","itemName":"Daily Plan","itemChildName":"","activityId":null,"id":"taskFlowNode_1213076123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1213076123","fieldType":null,"attributeType":"2","sourceType":"4","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 79622434123 | 333RB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  | {"headerType":"extarr","itemName":"TL Name & Tel.","itemChildName":"","activityId":null,"id":"taskFlowNode_1206216123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1206216123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 83467447123 | A016A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"extarr","itemName":"Daily work","itemChildName":"","activityId":null,"id":"taskFlowNode_1206215123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1206215123","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"{597901123:\"Install & Integrate\",597903123:\"Take Photo & Clear Pending\",597905123:\"Clear Alarm\",597907123:\"Add GPS\",597909123:\"Take Photo\",597911123:\"Dismantel\",597902123:\"Clear Pending\",597904123:\"Commissionning\",597906123:\"Add Card CE\",597908123:\"QA\",597910123:\"Training\",597912123:\"Cancel\"}","enumValueArray":["Install & Integrate","Clear Pending","Take Photo & Clear Pending","Commissionning","Clear Alarm","Add Card CE","Add GPS","QA","Take Photo","Training","Dismantel","Cancel"],"beginRownum":1,"endRownum":13,"editFlag":true} | 81135430123 | A048A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Plan Start Date","activityId":"97316123","id":"planStart_97316123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88105423123 | A254A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Plan End Date","activityId":"97316123","id":"plan_97316123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88113422123 | A263A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Actual Start Date","activityId":"97316123","id":"actualStart_97316123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83467446123 | A311A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Actual End Date","activityId":"97316123","id":"actual_97316123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88114424123 | A311A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Owner","activityId":"97316123","id":"resPonsible_97316123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83420447123 | A323A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Approve State","activityId":"97316123","id":"tas_97316123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83420446123 | A691A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Activity State","activityId":"97316123","id":"tms_97316123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81145421123 | A765A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Close Time","activityId":"97316123","id":"cst_97316123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 87049422123 | A777A_2025 Coverage Expansion Ph1_New_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Delivery Attachment Required","activityId":"97316123","id":"rid_97316123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 87759429123 | AANKM_2025 Capacity Expansion Ph6_EXP_ER
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Delivery Attachment Uploaded","activityId":"97316123","id":"aid_97316123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83420444123 | AB9VM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Delivery Attachment Upload Date","activityId":"97316123","id":"daud_97316123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81774428123 | AB9VM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Installation-Completed","itemChildName":"Remarks","activityId":"97316123","id":"remarks_97316123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 82189423123 | ABB3M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Plan Start Date","activityId":"97318123","id":"planStart_97318123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81150424123 | ACSCM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Plan End Date","activityId":"97318123","id":"plan_97318123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81821422123 | ACSCM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Actual Start Date","activityId":"97318123","id":"actualStart_97318123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 85350437123 | AIUNR_2025 Capacity Expansion Ph4_EXP_SR
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Actual End Date","activityId":"97318123","id":"actual_97318123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88429546123 | AKPGM_2025 Capacity Expansion Ph6_EXP_ER
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Owner","activityId":"97318123","id":"resPonsible_97318123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83337423123 | AM31M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Approve State","activityId":"97318123","id":"tas_97318123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 84040424123 | AMPSM_2025 Capacity Expansion Ph4_EXP_ER
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Activity State","activityId":"97318123","id":"tms_97318123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83337422123 | AN20M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Close Time","activityId":"97318123","id":"cst_97318123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 89426423123 | ANBTK_2025 Capacity Expansion Ph7_EXP_SR
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Delivery Attachment Required","activityId":"97318123","id":"rid_97318123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83462436123 | ANCKM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Delivery Attachment Uploaded","activityId":"97318123","id":"aid_97318123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88446434123 | ANMAM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Delivery Attachment Upload Date","activityId":"97318123","id":"daud_97318123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 79622433123 | APRWB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Smart QC","itemChildName":"Remarks","activityId":"97318123","id":"remarks_97318123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81145420123 | ARSCB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Plan End Date","activityId":"97328123","id":"plan_97328123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"UAT/PAT","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 79622432123 | ARSCB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Actual End Date","activityId":"97328123","id":"actual_97328123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"UAT/PAT","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91377441123 | AS11M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Owner","activityId":"97328123","id":"resPonsible_97328123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"UAT/PAT","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81794422123 | ASB3M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Approve State","activityId":"97328123","id":"tas_97328123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 79622431123 | ASEPB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Activity State","activityId":"97328123","id":"tms_97328123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 90439426123 | ASEPB_DPU40_OPM30_Replacement_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Close Time","activityId":"97328123","id":"cst_97328123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88085427123 | ASEWB_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Delivery Attachment Required","activityId":"97328123","id":"rid_97328123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 79622430123 | ASPIB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Delivery Attachment Uploaded","activityId":"97328123","id":"aid_97328123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 79611462123 | ASTNB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Delivery Attachment Upload Date","activityId":"97328123","id":"daud_97328123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 79611461123 | ASYPB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  | {"headerType":"activity","itemName":"PAT Subcon submit","itemChildName":"Remarks","activityId":"97328123","id":"remarks_97328123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"UAT/PAT","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 89867427123 | ATTIB_2025 Capacity Expansion Ph7_EXP_BKK
|  |  | {"headerType":"extarr","itemName":"Sub PAT Pass Status","itemChildName":"","activityId":null,"id":"taskFlowNode_1234613123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1234613123","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"{605029123:\"Pass\",605028123:\"Not Pass\",605030123:\"First Time Pass\"}","enumValueArray":["Not Pass","Pass","First Time Pass"],"beginRownum":14,"endRownum":17,"editFlag":false} | 81100423123 | AUCSB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Plan End Date","activityId":"97351123","id":"plan_97351123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88454422123 | AUT2M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Actual End Date","activityId":"97351123","id":"actual_97351123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81756424123 | AYR8M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Owner","activityId":"97351123","id":"resPonsible_97351123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81131420123 | B045A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Approve State","activityId":"97351123","id":"tas_97351123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88096424123 | B072A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Activity State","activityId":"97351123","id":"tms_97351123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88113424123 | B102A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Close Time","activityId":"97351123","id":"cst_97351123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83468440123 | B103A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Delivery Attachment Required","activityId":"97351123","id":"rid_97351123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88112420123 | B105A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Delivery Attachment Uploaded","activityId":"97351123","id":"aid_97351123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88108423123 | B108A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Delivery Attachment Upload Date","activityId":"97351123","id":"daud_97351123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88108422123 | B160A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Return","itemChildName":"Remarks","activityId":"97351123","id":"remarks_97351123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88113423123 | B182A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Plan End Date","activityId":"97480123","id":"plan_97480123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88108421123 | B208A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Actual End Date","activityId":"97480123","id":"actual_97480123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88109424123 | B215A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Owner","activityId":"97480123","id":"resPonsible_97480123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88085425123 | B222A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Approve State","activityId":"97480123","id":"tas_97480123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88103427123 | B271A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Activity State","activityId":"97480123","id":"tms_97480123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88455424123 | B283A_2025 Capacity Expansion Ph6_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Close Time","activityId":"97480123","id":"cst_97480123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83469427123 | B335A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Delivery Attachment Required","activityId":"97480123","id":"rid_97480123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88121423123 | B349A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Delivery Attachment Uploaded","activityId":"97480123","id":"aid_97480123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 82189422123 | B461A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Delivery Attachment Upload Date","activityId":"97480123","id":"daud_97480123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83469426123 | B472A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Withdraw EQ&MAT","itemChildName":"Remarks","activityId":"97480123","id":"remarks_97480123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88121424123 | B482A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Plan End Date","activityId":"97355123","id":"plan_97355123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"PAC","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83470425123 | B527A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Actual End Date","activityId":"97355123","id":"actual_97355123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"PAC","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88114423123 | B540A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Owner","activityId":"97355123","id":"resPonsible_97355123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"PAC","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83470422123 | B564A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Approve State","activityId":"97355123","id":"tas_97355123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81101423123 | B582A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Activity State","activityId":"97355123","id":"tms_97355123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83418440123 | B586A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Close Time","activityId":"97355123","id":"cst_97355123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88453422123 | B593A_2025 Capacity Expansion Ph6_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Delivery Attachment Required","activityId":"97355123","id":"rid_97355123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81118434123 | B636A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Delivery Attachment Uploaded","activityId":"97355123","id":"aid_97355123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83420438123 | B654A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Delivery Attachment Upload Date","activityId":"97355123","id":"daud_97355123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83420437123 | B658A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"TPT(Service)Approve","itemChildName":"Remarks","activityId":"97355123","id":"remarks_97355123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"PAC","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 89867426123 | B663A_2025 Capacity Expansion Ph7_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Plan End Date","activityId":"97334123","id":"plan_97334123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Site Survey","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88454421123 | B743M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Actual End Date","activityId":"97334123","id":"actual_97334123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Site Survey","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81782424123 | B743M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Owner","activityId":"97334123","id":"resPonsible_97334123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Site Survey","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 79611447123 | B77AB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Approve State","activityId":"97334123","id":"tas_97334123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91938427123 | BAIMM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Activity State","activityId":"97334123","id":"tms_97334123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91689424123 | BBDBM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Close Time","activityId":"97334123","id":"cst_97334123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81793427123 | BBK2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Delivery Attachment Required","activityId":"97334123","id":"rid_97334123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91395420123 | BCCPM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Delivery Attachment Uploaded","activityId":"97334123","id":"aid_97334123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81808423123 | BCD2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Delivery Attachment Upload Date","activityId":"97334123","id":"daud_97334123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81808422123 | BCD3M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Submit SSR","itemChildName":"Remarks","activityId":"97334123","id":"remarks_97334123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Site Survey","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 89403435123 | BCHFG_2025 Capacity Expansion Ph7_EXP_SR
|  |  | {"headerType":"extarr","itemName":"On Service Date","itemChildName":"","activityId":null,"id":"taskFlowNode_1241641123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1241641123","fieldType":null,"attributeType":"2","sourceType":"4","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83436428123 | BCI1M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Plan End Date","activityId":"103408123","id":"plan_103408123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88464421123 | BCI1M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Actual End Date","activityId":"103408123","id":"actual_103408123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83272429123 | BFBSC_2025 Capacity Expansion Ph2_EXP_SR
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Owner","activityId":"103408123","id":"resPonsible_103408123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88683421123 | BGNRM_2025 Capacity Expansion Ph6_EXP_ER
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Approve State","activityId":"103408123","id":"tas_103408123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81786438123 | BGNUM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Activity State","activityId":"103408123","id":"tms_103408123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91277422123 | BHTAG_2025 Coverage Expansion Ph1_New_SR
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Close Time","activityId":"103408123","id":"cst_103408123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 82550421123 | BHUYM_2025 Capacity Expansion Ph2_EXP_ER
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Delivery Attachment Required","activityId":"103408123","id":"rid_103408123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81809421123 | BIONM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Delivery Attachment Uploaded","activityId":"103408123","id":"aid_103408123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83473430123 | BK9BM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Delivery Attachment Upload Date","activityId":"103408123","id":"daud_103408123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88116424123 | BK9BM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Verify completed","itemChildName":"Remarks","activityId":"103408123","id":"remarks_103408123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81803421123 | BKE3M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"extarr","itemName":"Date Of Site Verify","itemChildName":"","activityId":null,"id":"taskFlowNode_1200903123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1200903123","fieldType":null,"attributeType":"4","sourceType":"3","templateFieldId":null,"standardName":"Date Of Site Verify","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 83472446123 | BKN4M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Plan End Date","activityId":"97377123","id":"plan_97377123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81794427123 | BKN4M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Actual End Date","activityId":"97377123","id":"actual_97377123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83272425123 | BKNMI_2025 Capacity Expansion Ph2_EXP_SR
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Owner","activityId":"97377123","id":"resPonsible_97377123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81793423123 | BKP2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Approve State","activityId":"97377123","id":"tas_97377123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 84345422123 | BKPYK_2025 Coverage Expansion Ph1_New_SR
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Activity State","activityId":"97377123","id":"tms_97377123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91331424123 | BKWNM_2025 Capacity Expansion Ph8_EXP_ER
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Close Time","activityId":"97377123","id":"cst_97377123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83272422123 | BLTHE_2025 Capacity Expansion Ph2_EXP_SR
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Delivery Attachment Required","activityId":"97377123","id":"rid_97377123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81682426123 | BMEGM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Delivery Attachment Uploaded","activityId":"97377123","id":"aid_97377123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 80820420123 | BMYIM_2025 Capacity Expansion Ph2_EXP_ER
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Delivery Attachment Upload Date","activityId":"97377123","id":"daud_97377123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88629421123 | BNHUY_2025 Capacity Expansion Ph6_EXP_SR
|  |  | {"headerType":"activity","itemName":"Site Integration (OMC)","itemChildName":"Remarks","activityId":"97377123","id":"remarks_97377123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 80326432123 | BNPHK_2025 Capacity Expansion Ph1_EXP_SR
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Plan End Date","activityId":"97360123","id":"plan_97360123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83262430123 | BNWGN_2025 Capacity Expansion Ph2_EXP_SR
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Actual End Date","activityId":"97360123","id":"actual_97360123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81682433123 | BP23M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Owner","activityId":"97360123","id":"resPonsible_97360123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91955431123 | BPM2M_2025 Capacity Expansion Ph8_EXP_BKK
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Approve State","activityId":"97360123","id":"tas_97360123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 89871429123 | BPM3M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Activity State","activityId":"97360123","id":"tms_97360123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91955430123 | BPM4M_2025 Capacity Expansion Ph8_EXP_BKK
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Close Time","activityId":"97360123","id":"cst_97360123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83754435123 | BPWFM_2025 Capacity Expansion Ph3_EXP_SR
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Delivery Attachment Required","activityId":"97360123","id":"rid_97360123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91387436123 | BRHPA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Delivery Attachment Uploaded","activityId":"97360123","id":"aid_97360123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81682432123 | BRMWM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Delivery Attachment Upload Date","activityId":"97360123","id":"daud_97360123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91710420123 | BS02B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  | {"headerType":"activity","itemName":"On Service","itemChildName":"Remarks","activityId":"97360123","id":"remarks_97360123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88120423123 | BSCWB_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Plan End Date","activityId":"100623123","id":"plan_100623123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81781424123 | BSN2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Actual End Date","activityId":"100623123","id":"actual_100623123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88683420123 | BSNTM_2025 Capacity Expansion Ph6_EXP_ER
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Owner","activityId":"100623123","id":"resPonsible_100623123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 89034421123 | BSPHS_2025 Coverage Expansion Ph1_New_SR
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Approve State","activityId":"100623123","id":"tas_100623123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81086424123 | BSRCB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Activity State","activityId":"100623123","id":"tms_100623123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83271421123 | BSSAK_2025 Capacity Expansion Ph2_EXP_SR
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Close Time","activityId":"100623123","id":"cst_100623123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 77663422123 | BSTFM_2025 Capacity Expansion Ph1_EXP_ER
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Delivery Attachment Required","activityId":"100623123","id":"rid_100623123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81163420123 | BT32M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Delivery Attachment Uploaded","activityId":"100623123","id":"aid_100623123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83455423123 | BT32M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Delivery Attachment Upload Date","activityId":"100623123","id":"daud_100623123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83455421123 | BTPJM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"OMC Script","itemChildName":"Remarks","activityId":"100623123","id":"remarks_100623123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91941427123 | BTT1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Plan End Date","activityId":"97317123","id":"plan_97317123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91963427123 | BTTRB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Actual End Date","activityId":"97317123","id":"actual_97317123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 91941426123 | BTTRM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Owner","activityId":"97317123","id":"resPonsible_97317123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83468429123 | BUAGM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Approve State","activityId":"97317123","id":"tas_97317123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 83468428123 | BUKHM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Activity State","activityId":"97317123","id":"tms_97317123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 89871427123 | BUR2M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Close Time","activityId":"97317123","id":"cst_97317123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 89871426123 | BUR4M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Delivery Attachment Required","activityId":"97317123","id":"rid_97317123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81811423123 | BWK2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Delivery Attachment Uploaded","activityId":"97317123","id":"aid_97317123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88112422123 | C002A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Delivery Attachment Upload Date","activityId":"97317123","id":"daud_97317123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88112423123 | C004A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"EHS","itemChildName":"Remarks","activityId":"97317123","id":"remarks_97317123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88122424123 | C017A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"extarr","itemName":"SQC Remark","itemChildName":"","activityId":null,"id":"taskFlowNode_1557371123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1557371123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88122423123 | C020A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"extarr","itemName":"Subcon/ PE Remark","itemChildName":"","activityId":null,"id":"taskFlowNode_1224594123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1224594123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 88112421123 | C026A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Plan End Date","activityId":"97381123","id":"plan_97381123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Material On Site","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81140432123 | C030A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Actual End Date","activityId":"97381123","id":"actual_97381123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Material On Site","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88113421123 | C035A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Owner","activityId":"97381123","id":"resPonsible_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Material On Site","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81154424123 | C037A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Approve State","activityId":"97381123","id":"tas_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88098421123 | C047A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Activity State","activityId":"97381123","id":"tms_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81109426123 | C048A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Close Time","activityId":"97381123","id":"cst_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81110428123 | C093A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Delivery Attachment Required","activityId":"97381123","id":"rid_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88098420123 | C098A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Delivery Attachment Uploaded","activityId":"97381123","id":"aid_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88102424123 | C139A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Delivery Attachment Upload Date","activityId":"97381123","id":"daud_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88099424123 | C150A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Remarks","activityId":"97381123","id":"remarks_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Material On Site","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 88460420123 | C159A_2025 Capacity Expansion Ph6_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"DN Number","activityId":"97381123","id":"dnNumber_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81140431123 | C255A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"DN Status","activityId":"97381123","id":"dnStatus_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81110433123 | C263A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"Delivery Purpose","activityId":"97381123","id":"deliveryPurpose_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 82181420123 | C268A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"ASD","activityId":"97381123","id":"actualShippingDate_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 89871425123 | C268A_2025 Capacity Expansion Ph7_EXP_BKK
|  |  | {"headerType":"activity","itemName":"Material On Site","itemChildName":"ATA","activityId":"97381123","id":"actualArriveDate_97381123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 81110431123 | C276A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 82179424123 | C277A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88116421123 | C296A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81137422123 | C7Y9M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81801424123 | C940M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81706425123 | CBTKM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 88467424123 | CCCBM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 82762443123 | CCKGM_2025 Coverage Expansion CO-NT Tower_EXP_ER
|  |  |  | 88455427123 | CDTEM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 91933429123 | CEKMB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81101424123 | CFSMB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91696432123 | CH16M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81811422123 | CHBNM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 80819421123 | CHGNM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 81139423123 | CHLCA_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91867457123 | CHLRB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91867464123 | CHLRM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91947431123 | CHU1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91388469123 | CHWGM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83420430123 | CHYPM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91867472123 | CIL1B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79611446123 | CIL1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91867471123 | CIL2B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79611445123 | CIL2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 83265426123 | CINTN_2025 Capacity Expansion Ph2_EXP_SR
|  |  |  | 91689425123 | CK39M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81809426123 | CK53M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81141421123 | CK91M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 89573426123 | CKHMM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 89880427123 | CKPOM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 83420429123 | CLDBM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81811420123 | CLMMM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81786425123 | CLP7M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 80320423123 | CMKOM_2025 Capacity Expansion Ph1_EXP_SR
|  |  |  | 81814420123 | CMSPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91712424123 | CN18M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91712422123 | CN45M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91712421123 | CN47M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89880426123 | CN47M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 91711424123 | CNNWM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79618436123 | COA1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79618435123 | COC1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 83457444123 | COSDM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 77292423123 | CP24M_2025 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 91330429123 | CPCEM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 80813437123 | CPRGM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 88104422123 | CPT2A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 91330428123 | CPTCM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 91949422123 | CPTHB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89869427123 | CS39M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 83457442123 | CSR2M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91388468123 | CVSLM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91449421123 | CVSLM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 88103424123 | CW15M_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81797421123 | CWMSM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 88404428123 | CWT2M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 91948426123 | CYP1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91689422123 | D020A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91963426123 | D028A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83457440123 | D094A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81089435123 | D201A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88457429123 | D230A_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 91709423123 | D232A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91867468123 | D243A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83474446123 | D305A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88102422123 | D354A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 83466434123 | D410A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 83466433123 | D412A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 82179421123 | D565A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83472444123 | D676A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81155430123 | D685A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88102420123 | D711A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 91935426123 | D801A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91690423123 | D834A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81154423123 | D845A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83472443123 | D878A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91867470123 | D894A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89880424123 | D933A_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 91946424123 | D941A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91709422123 | D973A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91693428123 | DAVTM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91378425123 | DHASA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81780427123 | DHYSM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81141424123 | DINCA_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 77292421123 | DLTCM_2025 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 88404427123 | DLTCM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 89471421123 | DNSOM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 79614429123 | DSK1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 80320422123 | DWOGM_2025 Capacity Expansion Ph1_EXP_SR
|  |  |  | 91947420123 | E048A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88096429123 | E069A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 82178423123 | E074A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81154427123 | E076A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91679426123 | E082A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81132422123 | E099A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 82176421123 | E100A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83474442123 | E100A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81029425123 | E131A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81118432123 | E136A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91679427123 | E142A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91378433123 | E178A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 77291424123 | E178A_2025 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 91365466123 | E186A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91867452123 | E189A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83474440123 | E202A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88103426123 | E220A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81143420123 | E276A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91949421123 | E388A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91949423123 | E504A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 82180425123 | E506A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91365460123 | E520A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91949424123 | E521A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91867473123 | E611A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91944439123 | E625A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81134429123 | E639A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81130420123 | E682A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81137421123 | E715A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91708424123 | E717A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91693425123 | E858A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91953421123 | E88BB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81107426123 | E910A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81159420123 | E935A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 82178422123 | E942A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81159421123 | E961A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81126422123 | E964A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83472428123 | E968A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81140430123 | E989A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 89369428123 | EBRUT_2025 Capacity Expansion Ph7_EXP_SR
|  |  |  | 81810425123 | EDKLM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 88460421123 | EKBRM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81786423123 | EKBRM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83467432123 | EKTNM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 86062420123 | EKTSM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91948425123 | EM21M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91937429123 | EM30M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91933428123 | ES23B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 85686423123 | ETEBM_2025 Capacity Expansion Ph5_EXP_ER
|  |  |  | 85686422123 | ETETM_2025 Capacity Expansion Ph5_EXP_ER
|  |  |  | 91960423123 | EXHLM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91947430123 | FBKIM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88322421123 | FLK7M_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 81784422123 | FS4VM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91388467123 | FURMM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81123425123 | G009A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91867469123 | G016A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91958434123 | G016A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 83424441123 | G050A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88110424123 | G097A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 91709420123 | G117A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81155427123 | G157A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81132426123 | G236A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81157422123 | G252A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91948420123 | G289A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91713427123 | G321A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81089427123 | G325A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81114432123 | G334A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88105421123 | G346A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 91717423123 | G355A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91944444123 | G357A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91949420123 | G386A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91946420123 | G388A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 82177423123 | G402A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91942440123 | G450A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 83463433123 | G473A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81157420123 | G505A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91354428123 | G511A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79613424123 | G527B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81130424123 | G545A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91693424123 | G546A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88115425123 | G551A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81142421123 | G558A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91948421123 | G559A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 90439420123 | G563A_DPU40_OPM30_Replacement_BKK
|  |  |  | 81155429123 | G565A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 90439433123 | G576A_DPU40_OPM30_Replacement_BKK
|  |  |  | 91951421123 | G591A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 90441421123 | G602A_DPU40_OPM30_Replacement_BKK
|  |  |  | 90441420123 | G603A_DPU40_OPM30_Replacement_BKK
|  |  |  | 90439434123 | G604A_DPU40_OPM30_Replacement_BKK
|  |  |  | 81142422123 | G611A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81149423123 | G613A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83470435123 | G620A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88102421123 | G625A_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 90438420123 | G625A_DPU40_OPM30_Replacement_BKK
|  |  |  | 91951422123 | G627A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89876426123 | G627A_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 83470434123 | G633A_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91708423123 | G635A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91690422123 | G652A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91390459123 | G658A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 80818429123 | GEPCM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 81816424123 | GOCPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91938428123 | GSP2P_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91867462123 | GSPZM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91940421123 | GSPZP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 80818428123 | GSTPM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 91933427123 | GTICB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91937428123 | GTICM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91867474123 | GVEMB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81784420123 | HAAWM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81814421123 | HCU2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83477423123 | HK72M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 77291423123 | HKG2M_2025 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 87754435123 | HLEKM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 91941425123 | HLP1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91962422123 | HLP2M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89881421123 | HNDAN_2025 Coverage Expansion Ph2_New_SR
|  |  |  | 89470423123 | HUSRM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 83264429123 | HYIPM_2025 Capacity Expansion Ph2_EXP_SR
|  |  |  | 83264428123 | HYMUM_2025 Capacity Expansion Ph2_EXP_SR
|  |  |  | 84020432123 | IBNGM_2025 Capacity Expansion Ph4_EXP_ER
|  |  |  | 83477420123 | IDBSB_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 79628424123 | IDCIB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91946422123 | IS71B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79613423123 | ITICB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81127425123 | ITLSM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 89878424123 | IVA1B_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 79613422123 | IVA1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91951423123 | JAV1A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91945423123 | JAVNP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88097420123 | JJS05_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 79613421123 | JNTWB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81156420123 | JTDOM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81129428123 | K100M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91151420123 | K100M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81818423123 | K100M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81129427123 | K107M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81780421123 | K122M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 82157434123 | K546M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83470426123 | KAN2M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 83476424123 | KB11M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91473422123 | KBGYM_2025 Coverage Expansion Ph2_New_BKK
|  |  |  | 81805426123 | KBL1M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 79613420123 | KBW3B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 85351426123 | KCDPO_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 79614428123 | KCT1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81154426123 | KEKCB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79612424123 | KEKCB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 83424433123 | KFSNM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81799434123 | KFSNM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83418434123 | KGSOM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 89939421123 | KGSRM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 83418432123 | KH74M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 85684425123 | KHDNM_2025 Capacity Expansion Ph5_EXP_ER
|  |  |  | 81129425123 | KHHKM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83465425123 | KHHKM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 89878421123 | KHNWM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 82187420123 | KHRHM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88100423123 | KHS4B_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 90439424123 | KHS4B_DPU40_OPM30_Replacement_BKK
|  |  |  | 89876424123 | KHTRM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 88100420123 | KIMHB_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 89876423123 | KJP9M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 84039423123 | KKIUM_2025 Capacity Expansion Ph4_EXP_ER
|  |  |  | 88109421123 | KL05M_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 88096428123 | KL07M_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81802421123 | KL6RM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81035435123 | KL85M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91942432123 | KL85M_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 81804444123 | KL85M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89876421123 | KLKXM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 83476422123 | KLWSM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 89982420123 | KMTAM_2025 Small DC Inb Cov Ex_Ph1
|  |  |  | 91330422123 | KNBPM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 85318428123 | KNOEM_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 83269424123 | KOKEW_2025 Capacity Expansion Ph2_EXP_SR
|  |  |  | 86885434123 | KOKEW_2025 Capacity Expansion Ph5_EXP_SR
|  |  |  | 85683427123 | KOMLM_2025 Capacity Expansion Ph5_EXP_ER
|  |  |  | 80813431123 | KPEAM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 81795427123 | KPKUM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91330420123 | KPWTM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 83269423123 | KRCGM_2025 Capacity Expansion Ph2_EXP_SR
|  |  |  | 91708420123 | KRGIB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91377444123 | KRGIM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81796424123 | KRNYM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81796423123 | KRSPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 88462422123 | KS13M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 86063420123 | KS13M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 88100424123 | KS42B_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 90439423123 | KS42B_DPU40_OPM30_Replacement_BKK
|  |  |  | 81796421123 | KSBBM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89401423123 | KSOGC_2025 Capacity Expansion Ph7_EXP_SR
|  |  |  | 91956426123 | KSSRM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 85683426123 | KTFPM_2025 Capacity Expansion Ph5_EXP_ER
|  |  |  | 88443435123 | KTFPM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 89576424123 | KTHNM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 80818424123 | KTINM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 81822428123 | KTKIM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81785423123 | KTL2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81822427123 | KTLTM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91952424123 | KTN1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81785422123 | KTNAM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83465446123 | KV69M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81817429123 | KW12M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81152424123 | KWAPM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81804440123 | KWAPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81804431123 | L133M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81804430123 | L13EM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 82162427123 | LATWM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 82186424123 | LB50M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79613430123 | LBP1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79615439123 | LBP2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79615438123 | LBP3B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79612423123 | LBRAB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79612422123 | LBRBB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81164422123 | LBRDB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79614427123 | LET1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79614425123 | LET3B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79617429123 | LET4B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79615437123 | LF18B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81792437123 | LK12M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81792436123 | LK13M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83475421123 | LK83M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81806428123 | LK92M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83475420123 | LKBSM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81822425123 | LKG9M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81755440123 | LKL6M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81796420123 | LKRPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81785433123 | LL12M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81812427123 | LL13M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81755436123 | LLK2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81785432123 | LLK8M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 88122421123 | LMA1B_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81785430123 | LMN2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81161431123 | LNS2B_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88461424123 | LP35M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 83465440123 | LPG2M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 83474439123 | LPG3M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 83474437123 | LPG5M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88100422123 | LPNLB_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 86063421123 | LR49M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 79628423123 | LRS1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79615435123 | LRS2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79628422123 | LRS3B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91933425123 | LS67B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88624432123 | LSHPT_2025 Capacity Expansion Ph6_EXP_SR
|  |  |  | 88624431123 | LSN1M_2025 Capacity Expansion Ph6_EXP_SR
|  |  |  | 88446431123 | LTDBM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81790420123 | LU10M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81788424123 | LWREM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91952423123 | M3Y2M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91954424123 | MA31M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91951424123 | MARCB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83418430123 | MBCDM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81785420123 | MBHPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91944441123 | MBK1P_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91944440123 | MBK2P_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83418428123 | MBLWM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 82189420123 | MBPLM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91277421123 | MBTKD_2025 Coverage Expansion Ph1_New_SR
|  |  |  | 87791421123 | MBYYM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81787423123 | MEMGM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 80818422123 | MEPHP_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 81811428123 | MI21M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89469423123 | MKHRM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 91935429123 | MKTNM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89870426123 | MKTNM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81783424123 | MLLSM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91935428123 | MMCTM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81151425123 | MNTLM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91378430123 | MONTB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89854432123 | MPBST_2025 Coverage Expansion Ph1_New_SR
|  |  |  | 88404431123 | MPCHM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81804422123 | MPRUM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81804421123 | MPS5M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 79467420123 | MRTBM_2025 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 83457433123 | MRTBM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81755429123 | MSOTM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 84872440123 | MSPPM_2025 Capacity Expansion Ph4_EXP_ER
|  |  |  | 89469421123 | MSPPM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 79467421123 | MTF1A_2025 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 81144425123 | MTF2A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88456423123 | MTKTM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 83474433123 | MTRNM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 79617428123 | MWRIB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 82181429123 | MWRPM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 77660423123 | MYGMM_2025 Capacity Expansion Ph1_EXP_ER
|  |  |  | 77662423123 | MYSPM_2025 Capacity Expansion Ph1_EXP_ER
|  |  |  | 84038424123 | NAAHM_2025 Capacity Expansion Ph4_EXP_ER
|  |  |  | 87758424123 | NATWM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 83462433123 | NBKUB_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 82186421123 | NBPUM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88456421123 | NBPUM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 91951420123 | NBRCB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88681424123 | NBRPM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 81813424123 | NC21M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83462432123 | NCFMM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91713434123 | NDP1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89453441123 | NGETM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 88110423123 | NIBKA_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 90439437123 | NIBKA_DPU40_OPM30_Replacement_BKK
|  |  |  | 79617427123 | NIMCB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91948424123 | NISTA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88115427123 | NISTA_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 88515421123 | NIVRB_2025 Coverage Expansion Ph2_New_BKK
|  |  |  | 91713431123 | NK12M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91713430123 | NK15M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81142420123 | NK15M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88455430123 | NK15M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 88119420123 | NKB3M_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 89871423123 | NKB3M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 87758420123 | NKLAM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 87754434123 | NKLHM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 87754433123 | NKLLM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 88628424123 | NKRIM_2025 Capacity Expansion Ph6_EXP_SR
|  |  |  | 87754432123 | NKSHM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 87754431123 | NKSNM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 81775426123 | NL20M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81029426123 | NLK5M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91716423123 | NLYCM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89871421123 | NMS2A_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81790444123 | NN03M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81775423123 | NNMIM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91945422123 | NNSQP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 80817422123 | NOGWM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 84035429123 | NPDNM_2025 Capacity Expansion Ph4_EXP_ER
|  |  |  | 91713424123 | NPSCB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79617443123 | NPSCB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79617426123 | NPTPB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81129422123 | NRCCM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88456420123 | NRK3M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 86068420123 | NRRTK_2025 Coverage Expansion Ph1_New_SR
|  |  |  | 88625421123 | NSNRS_2025 Capacity Expansion Ph6_EXP_SR
|  |  |  | 91954423123 | NSW3M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81817428123 | NTC1M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 82189424123 | NTCDM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91937427123 | NUNIM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88107421123 | NUNIM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 91945421123 | NVTSM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81809429123 | NW48M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 88599420123 | NWKSK_2025 Coverage Expansion Ph2_New_SR
|  |  |  | 88455423123 | OCVLM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81806424123 | ON80M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91692429123 | ORT1B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91692428123 | ORT2B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91692427123 | ORT3B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79617441123 | OYP1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79617440123 | OYP2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81755435123 | P18KM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83418443123 | P219M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81822424123 | P234M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83418442123 | P2M2M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88455426123 | P316M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81755434123 | P316M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 82180433123 | P3BWM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91679425123 | PARCB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79617425123 | PARCB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91954428123 | PARMM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 91952422123 | PAY2M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81755432123 | PBBMM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81153423123 | PCH1M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81118438123 | PCHPM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83457430123 | PCHPM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81790442123 | PCHPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81792434123 | PCHSM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83471424123 | PCK2M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81792433123 | PCKRM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81153420123 | PCR1M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81126421123 | PCRTB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91716421123 | PCS2M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81792432123 | PCS4M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91716420123 | PCSTM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81758432123 | PDPMM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81118430123 | PDS2B_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79619437123 | PDS2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79612420123 | PDS3B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 88462420123 | PEARM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 91942456123 | PEARM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 79611424123 | PGT1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79611423123 | PGT2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79611422123 | PGT3B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 88096425123 | PH49M_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81795421123 | PHCFM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89417425123 | PHOWY_2025 Capacity Expansion Ph7_EXP_SR
|  |  |  | 87752429123 | PHRAM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 88433434123 | PIANM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 83471422123 | PIN3M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91365462123 | PIPTA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83471421123 | PJN4M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91143425123 | PK15M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 91143423123 | PK16M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 80816420123 | PKLGM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 81133424123 | PKLPB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79611421123 | PKLPB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79619436123 | PLA1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79622429123 | PLB1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81133422123 | PLCUM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81790440123 | PLCUM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89575425123 | PLGYM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 88096423123 | PLLSB_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81133421123 | PLP1M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79608429123 | PLPTB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79608428123 | PLRTB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 89467420123 | PLSTM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 79622428123 | PLT1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79622427123 | PLT2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79622426123 | PLW1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81161429123 | PMRPA_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79622425123 | PMRSB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 83436421123 | PN30M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 89982422123 | PNCAM_2025_Small DC_4K_with_MOEH_ER
|  |  |  | 83469424123 | PNGNM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81820422123 | PNT3M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91329421123 | PNTHM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 83754432123 | POLYT_2025 Capacity Expansion Ph3_EXP_SR
|  |  |  | 89466423123 | PPMWM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 81792445123 | PRS4M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83469420123 | PS10M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88433433123 | PS4TM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81136422123 | PS54M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91962423123 | PSDTM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88628420123 | PSKLN_2025 Capacity Expansion Ph6_EXP_SR
|  |  |  | 81160423123 | PSV4M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83465438123 | PSV4M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81094433123 | PT15M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 89865429123 | PT15M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 88452423123 | PTRNM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81138423123 | PTS1B_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83465435123 | PWBRM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 83463429123 | PWK2M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81812424123 | PWK2M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 85683422123 | PWMSM_2025 Capacity Expansion Ph5_EXP_ER
|  |  |  | 88115420123 | PY83M_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 83463427123 | PYPNM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91718422123 | PYTSM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83463426123 | PYWRM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81758431123 | PYWRM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 82184423123 | R116M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88464422123 | R116M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 83463425123 | R209M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81109428123 | R250M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81810421123 | R292M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81159422123 | R301A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 89859426123 | R431M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81130421123 | R522M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81162423123 | R532M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 89865426123 | R533A_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 91962421123 | R613M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 85327421123 | RAKKW_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 88096426123 | RAMAM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81114431123 | RBC1B_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83460428123 | RBPOM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91474423123 | RCNVB_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 81161428123 | RG20B_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79619431123 | RHR1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79619430123 | RHR2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81133423123 | RKBKM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83460427123 | RKBKM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 84816423123 | RL11M_New site by Co-NT_New_BKK
|  |  |  | 91679424123 | RM4XA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 82175433123 | RMIRM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91962420123 | RMPOM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89868423123 | RMPOM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 91947434123 | RMS5M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88457427123 | RMU1M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81121428123 | RNWDM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81121426123 | ROOGM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91388464123 | ROSHM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79619422123 | ROSTB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 89868422123 | RP08M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81051424123 | RPBSB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 77287422123 | RPN6M_2025 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 88446435123 | RPPTM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 91867467123 | RPV1B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79622424123 | RS42B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 83465430123 | RS72M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 83764442123 | RSDAM_2025 Capacity Expansion Ph3_EXP_SR
|  |  |  | 81785428123 | RSK7M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83474424123 | RSK8M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 89867424123 | RSP2M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81785426123 | RSPTM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83468421123 | RT21M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 82815420123 | RT64A_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 91153420123 | RTABM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81785425123 | RTBPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 88096422123 | RUJTM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 83462429123 | RUNSM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81773438123 | RUNSM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81773437123 | RUYDM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 79608427123 | RV21B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79608426123 | RVS1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81773436123 | RWRPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81790434123 | S192M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83418423123 | S742M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81804429123 | SA13M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 87157421123 | SAENM_2025 Coverage Expansion Ph2_New_BKK
|  |  |  | 83466422123 | SAPRM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 89867420123 | SARAM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 91954422123 | SATGM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 82157432123 | SAVOA_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81816422123 | SBK9M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 84872435123 | SBLBM_2025 Capacity Expansion Ph4_EXP_ER
|  |  |  | 88096421123 | SCMTM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 89865423123 | SCMTM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81161434123 | SCYNM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91944435123 | SDCPP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91937426123 | SEK9M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 82547420123 | SESWM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 81819421123 | SFAPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91474422123 | SGLPA_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 89868430123 | SHALM_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 89081420123 | SHNKM_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 86892426123 | SHSCM_2025 Capacity Expansion Ph5_EXP_SR
|  |  |  | 88469420123 | SJIEM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 91867466123 | SK23B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91958426123 | SK33M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91963423123 | SK37M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88113420123 | SK37M_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 91963422123 | SK49M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91947424123 | SK63B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91954420123 | SK63M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81785435123 | SKDPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89865421123 | SKE1M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81824423123 | SKKBM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89865420123 | SKP5M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 91947433123 | SKPMM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81807421123 | SKROM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81812422123 | SKTPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91953423123 | SKW1B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91935427123 | SKWCM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 82181428123 | SLBLM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91718420123 | SLD1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91717424123 | SLEGM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91365468123 | SLLSM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83474420123 | SM34M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88452420123 | SMBKM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81132434123 | SMGMM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81763431123 | SMGMM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89864423123 | SN21M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 84036420123 | SOKDM_2025 Capacity Expansion Ph4_EXP_ER
|  |  |  | 81126429123 | SOKKM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81089426123 | SOMCM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83472432123 | SOMCM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81763427123 | SP34M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81792429123 | SP37M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81792428123 | SPABM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81792427123 | SPKNM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91938444123 | SPKWA_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 81149422123 | SPKWB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83455435123 | SPN2M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88457426123 | SPNYM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 85351436123 | SPPNM_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 81089425123 | SPRVB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 88106421123 | SPTMM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 91395421123 | SPY1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91718424123 | SQ1PP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83455434123 | SR41M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 88461423123 | SR41M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 82168426123 | SRK9A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91907420123 | SRKJN_2025 Coverage Expansion Ph1_New_SR
|  |  |  | 82791424123 | SRPBM_2025 Coverage Expansion CO-NT Tower_EXP_ER
|  |  |  | 79608425123 | SRRCB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91365464123 | SRWEA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91947422123 | SS59B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88443433123 | SSEAM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 88116420123 | SSHNM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 83264421123 | SSKNF_2025 Capacity Expansion Ph2_EXP_SR
|  |  |  | 82815421123 | SSNGM_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 91365469123 | SSQOM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91681572123 | SSRWB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 87749420123 | SSSLM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 81135420123 | SSTPM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81109429123 | SSW8A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91714422123 | STEXM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91365461123 | STN8A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81752422123 | STPVM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 88099420123 | STRXM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81795434123 | SU34M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 90439435123 | SU3AB_DPU40_OPM30_Replacement_BKK
|  |  |  | 88453423123 | SUDSM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81147420123 | SUKTB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91713423123 | SUPLA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 88104421123 | SUPMB_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 81140421123 | SUTLB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 91948423123 | SVSUB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81820424123 | SW13M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81824421123 | SW53M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 82157429123 | SW57M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81795431123 | SW57M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91937432123 | SWCRM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 81161426123 | SWK2M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81795430123 | SWORM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83462425123 | SYBYM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 89422422123 | SYKMS_2025 Capacity Expansion Ph7_EXP_SR
|  |  |  | 91944442123 | SYMTB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 85351435123 | SYNKM_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 81815424123 | SYPGM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83468433123 | T11BM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 91947432123 | TABBM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89422420123 | TACIF_2025 Capacity Expansion Ph7_EXP_SR
|  |  |  | 79610424123 | TBASB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91327425123 | TBKDM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 87752422123 | TBYJM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 89877422123 | TC30M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 85354422123 | TCNHM_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 88624428123 | TCRBE_2025 Capacity Expansion Ph6_EXP_SR
|  |  |  | 81762424123 | TE09M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 90437428123 | TECBA_DPU40_OPM30_Replacement_BKK
|  |  |  | 90437429123 | TECDA_DPU40_OPM30_Replacement_BKK
|  |  |  | 91963425123 | TEM10_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 90437430123 | TESEA_DPU40_OPM30_Replacement_BKK
|  |  |  | 83457426123 | THBPM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81135425123 | THEBB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79610423123 | THEBB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81149420123 | THLHB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81799423123 | TIM5M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83457425123 | TK10M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 89877420123 | TK11M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 83424426123 | TK24M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 79610422123 | TKS1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79622423123 | TKSCB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79610421123 | TKUSB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81134422123 | TL3CB_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79610420123 | TL3CB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91328422123 | TLBIM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 81132425123 | TLDMM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 86886424123 | TLDNS_2025 Capacity Expansion Ph5_EXP_SR
|  |  |  | 91328420123 | TLRPM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 88110420123 | TMC2M_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 88680423123 | TMCPM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 81110425123 | TMSRM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83463423123 | TMSRM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 82791422123 | TMYAM_2025 Coverage Expansion CO-NT Tower_EXP_ER
|  |  |  | 89573424123 | TNBAM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 91390456123 | TNCSA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83763421123 | TNNIB_2025 Capacity Expansion Ph3_EXP_SR
|  |  |  | 83468430123 | TNRMM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 83463420123 | TP25M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81762422123 | TPCSM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 85639436123 | TPLBM_2025 Capacity Expansion Ph5_EXP_ER
|  |  |  | 89454428123 | TPMPM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 88122420123 | TPN1B_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 89573423123 | TPPAM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 91867465123 | TPSVB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91947423123 | TR21B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91945424123 | TR69B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89875422123 | TRBSM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 88103423123 | TRKLM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 91960422123 | TRP2B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 79609424123 | TRV1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91963420123 | TSHUM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81682430123 | TT19M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81151429123 | TT33B_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 82157427123 | TT40M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81132420123 | TT72M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83473425123 | TT72M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81818424123 | TT72M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91311427123 | TTBPM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 89454427123 | TTGWM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 87747423123 | TTPTM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 91365459123 | TTWHA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83424423123 | TUR1M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 83467441123 | TW46M_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81790439123 | TW46M_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83473423123 | TWRSM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 83473422123 | TWSHM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 86886420123 | TWTTH_2025 Capacity Expansion Ph5_EXP_SR
|  |  |  | 79609423123 | UB12B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79622422123 | UB22B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79620430123 | UBNAB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79615454123 | UBNBB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79622421123 | UBS1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79622420123 | UBS2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79621424123 | UCK1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79621423123 | UCK2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79621422123 | UCK3B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79621421123 | UDP1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79621420123 | UDP2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79620424123 | UDR3B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 83473420123 | UDSPM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 79620423123 | UDTPB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79620422123 | UHWAB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79609422123 | UHWCB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79609421123 | UHWDB_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81792454123 | UNCOM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 79609420123 | UON1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79608424123 | UP31B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79608423123 | UP32B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 81089432123 | UR26M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 79620421123 | URB1B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 79608422123 | URB2B_2025 Coverage Expansion Ph1_EXP_BKK
|  |  |  | 91933426123 | VEVBB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 80814421123 | VINTM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 89873420123 | VS11M_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 91944437123 | W77BB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91944438123 | W77FB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81823424123 | WARSM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 87049425123 | WBAKM_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 88453421123 | WBCLM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 87746424123 | WBHNM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 83420443123 | WBKDM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81787428123 | WBKDM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81682428123 | WBPKM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91944449123 | WBRWM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 89369424123 | WBTOM_2025 Capacity Expansion Ph7_EXP_SR
|  |  |  | 81787427123 | WCDHM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89864428123 | WCLHM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 91378435123 | WGLEM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 83420440123 | WHKBM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 77285422123 | WHLPM_2025 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 84020429123 | WKBYM_2025 Capacity Expansion Ph4_EXP_ER
|  |  |  | 81148420123 | WKGSM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 83420439123 | WKGSM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81819423123 | WKGSM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 88457425123 | WKN2M_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 85299427123 | WKUSB_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 88453420123 | WLAIM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81790427123 | WLFPM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89573420123 | WLGWM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 91321424123 | WNALM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 90250420123 | WNHST_2025 Coverage Expansion Ph1_New_SR
|  |  |  | 80812424123 | WNPNM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 88436426123 | WNSRZ_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 81723426123 | WNSWM_2025 Capacity Expansion Ph2_EXP_ER
|  |  |  | 81774426123 | WPBCM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91326420123 | WPNRM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 81823420123 | WPPMM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 83419423123 | WPWSM_2025 Capacity Expansion Ph3_EXP_BKK
|  |  |  | 81763430123 | WSLTM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91287453123 | WSNIM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 89572423123 | WSNOM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 81763422123 | WSRIM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 81763428123 | WSROM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 87745420123 | WSRVM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 88436425123 | WSTKM_2025 Capacity Expansion Ph6_EXP_BKK
|  |  |  | 89864426123 | WSTOM_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 81161427123 | WT38M_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 89464422123 | WTGWM_2025 Capacity Expansion Ph7_EXP_ER
|  |  |  | 87049423123 | WTHBA_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 82180434123 | WTKOM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81162422123 | WTM2A_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 87744424123 | WTPBM_2025 Capacity Expansion Ph6_EXP_ER
|  |  |  | 81818422123 | WTPWM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91287450123 | WTWAM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 91944436123 | WVPMM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81760433123 | WWBWM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89982421123 | WYMSM_2025 Small DC Inb Cov Ex_Ph1
|  |  |  | 91706434123 | WYNWM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91714424123 | XTSPM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 81760430123 | YANIM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 89369422123 | YANSM_2025 Capacity Expansion Ph7_EXP_SR
|  |  |  | 82157425123 | YBKKM_2025 Capacity Expansion Ph2_EXP_BKK
|  |  |  | 81810434123 | YNCKM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 85351431123 | YNGNM_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 91713426123 | YNPOA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91713425123 | YNPOB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 85350438123 | YRWSH_2025 Capacity Expansion Ph4_EXP_SR
|  |  |  | 88099422123 | YS24M_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 88109423123 | YSBNM_2025 Capacity Expansion Ph5_EXP_BKK
|  |  |  | 88624420123 | YSMAI_2025 Capacity Expansion Ph6_EXP_SR
|  |  |  | 81810433123 | YTTRM_2025 Coverage Expansion Ph2_EXP_BKK
|  |  |  | 91714423123 | ZSRSM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92627428123 | 41IBM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92363423123 | 5S4AB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104978456123 | A183A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104978453123 | A184A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104978455123 | A185A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104978454123 | A186A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104972454123 | A311A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104977455123 | A314A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91967434123 | AB9VM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 105619456123 | ABHPM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 91970422123 | ADDCB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98669455123 | AGWNM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 102680469123 | AKBBM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92615432123 | AKW2M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102677469123 | AMNKM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92627426123 | ARI4M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92327428123 | ASC2M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104977456123 | ASNWB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92617440123 | ASREB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92364424123 | AWBPM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100553458123 | B024A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 100553457123 | B025A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 100569453123 | B026A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 98820453123 | B486A_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 98820452123 | B508A_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 106313465123 | B615A_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99749455123 | BACHO_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 91971434123 | BASBM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 104974454123 | BBBDP_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99782463123 | BBCPN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 101023461123 | BBMNE_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 100245466123 | BBPNM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98678453123 | BBPNM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 106291534123 | BCD2M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99753473123 | BCHAN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 101023459123 | BCHLS_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 99745466123 | BDATO_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99722456123 | BDYBT_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 91985434123 | BFAYM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 98667453123 | BHKJM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 105618455123 | BHMFM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 105618454123 | BHPBM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 102699452123 | BJRMM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99721463123 | BKFCM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100728470123 | BKJNM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99746456123 | BKMOM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99741465123 | BKNGS_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105616461123 | BKSBM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99744461123 | BKTAM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99745470123 | BMERI_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 101025464123 | BMHTG_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 92615422123 | BMRRB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91968440123 | BN29M_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 99751460123 | BNACH_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99751457123 | BNBKB_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99760472123 | BNGYK_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 101017465123 | BNIKM_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 98635477123 | BNMFM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99498456123 | BNPCB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99758464123 | BNRIG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92516425123 | BOBKM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 92432422123 | BOKNT_2025 Coverage Expansion (Co NT)_New_SR
|  |  |  | 99753468123 | BPDBE_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105616458123 | BPDSM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99748465123 | BPDYR_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 98840458123 | BPGSM_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 92516424123 | BPGYM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 99753467123 | BPHAA_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99742466123 | BPJNS_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 101020458123 | BPKKD_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 105610458123 | BPMJM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99740456123 | BPSPM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99780453123 | BPTHO_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99516478123 | BR63M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99759469123 | BRPEM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99759468123 | BRTDN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99759467123 | BRTPM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104544470123 | BS11M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106322465123 | BS11M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99738470123 | BSAKU_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99738468123 | BSGPU_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102705461123 | BSHSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99761479123 | BSKPG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99761478123 | BSLUI_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 98697453123 | BSWHM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99736466123 | BSWNS_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 91977424123 | BSY1B_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 99736465123 | BTACH_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99736464123 | BTAKH_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 98697452123 | BTDMM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99779456123 | BTGBN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92569433123 | BTJMM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 99746471123 | BTL1M_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99746469123 | BTMKG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99749464123 | BTMOM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99739460123 | BTPYM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99739459123 | BTSAN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 101026457123 | BTUSM_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 98698456123 | BTWWM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 100184454123 | BUNAM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104484481123 | BW77M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99747466123 | BWSNM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99747464123 | BYGNG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105558465123 | BYKKM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99736477123 | BYNGS_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100247457123 | BZBLM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98666454123 | BZBLM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 92615421123 | C241B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100563457123 | C277A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 92615420123 | C341B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99515454123 | C418M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98666453123 | CAKCM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 105616455123 | CASHM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 102709460123 | CATBM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 96558452123 | CBTKM_2026 Coverage Expansion Ph1-existing_EXP_ER
|  |  |  | 99515452123 | CC43M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102709458123 | CCCHM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 100250461123 | CITYM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98668456123 | CITYM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 92213420123 | CK42M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99502457123 | CK78M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104974459123 | CKBNM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100750457123 | CKNKM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98679455123 | CMPHM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 97979454123 | CMPIM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER
|  |  |  | 104972460123 | CMSKM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104969459123 | CMT3M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100734469123 | CMTNM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 103794454123 | CN02M_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 99541453123 | CN24M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102677467123 | CNAPM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98664456123 | CNPHM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 105611460123 | CNWNM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92639421123 | CONEP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105605452123 | CPRGM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 100745464123 | CPWHM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 91963429123 | CRMJA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91993421123 | CRWSM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 92356420123 | CSPKM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98680455123 | CTLNM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99389452123 | CTRGM_2025 Coverage Expansion Ph1_New BBU-2nd_ER
|  |  |  | 99388454123 | CTRGM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 100754456123 | CTSVM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 100754455123 | CTUSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104972456123 | CW15M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104974465123 | CW15M_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 92570422123 | CWKWM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 99736475123 | CYACB_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92363425123 | D033A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92342428123 | D052A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99516474123 | D085A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92610422123 | D088A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92632426123 | D113A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92463434123 | D132A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91985429123 | D132A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 103794453123 | D141A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92342427123 | D145A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92361421123 | D168A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92063421123 | D186A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92342426123 | D205A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92327430123 | D206A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92059428123 | D220A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92061420123 | D222A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92463431123 | D227A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92059429123 | D228A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92059425123 | D229A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92645420123 | D270A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92594432123 | D292B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92641420123 | D377A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92063422123 | D444A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106300504123 | D523A_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106300503123 | D525A_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92059424123 | D689A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92611429123 | D733A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98833454123 | D819A_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 104975458123 | D841A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99545455123 | D857A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99545452123 | D860A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98841454123 | D934A_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 92627424123 | D947A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92063429123 | D958A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92322424123 | DDG2M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92634428123 | DINCA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92570420123 | DKBKM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 99736474123 | DMMUG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99721462123 | DMSKH_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92206422123 | DOHFM_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 99508483123 | DRCHM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100229454123 | DRCHM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 99742458123 | DSFPM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92063424123 | E041A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99498463123 | E085A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99485483123 | E127A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92646421123 | E170A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99455501123 | E193A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92061424123 | E308A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99455500123 | E333A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99455499123 | E367A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104975459123 | E396A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92645422123 | E400A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92059431123 | E405A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98826457123 | E492A_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 91979423123 | E717A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 99509473123 | E744A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92610423123 | E795A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91979421123 | E858A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 92060421123 | E864A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91973435123 | E864A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 92060424123 | E865A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92063428123 | E892A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92064421123 | E898A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92060420123 | E931A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92063427123 | E945A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92361424123 | E958A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98664453123 | EBSMM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 102351460123 | EM21M_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 91965420123 | EM22M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92622428123 | ESPCP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100734481123 | ESPNM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105611457123 | ETLDM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 95372457123 | FACOM_2026 Antenna Dualbeam_Replacement_BKK
|  |  |  | 92607424123 | FATWB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102696457123 | FMSYM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104976456123 | FS04M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99748458123 | FSKPL_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92065421123 | G090A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99525455123 | G097A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91979420123 | G117A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 92628432123 | G139A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92607429123 | G191A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92064422123 | G203A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92361423123 | G256A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92061423123 | G299A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92059430123 | G311A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92607435123 | G317A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92634427123 | G319A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 103222457123 | G323A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91968434123 | G330A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 92628434123 | G335A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92059422123 | G356A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92633421123 | G367A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92064420123 | G368A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99518453123 | G380A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92633422123 | G392A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92463430123 | G396A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92063423123 | G404A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91982421123 | G404A_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 92425445123 | G410A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92357424123 | G411A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92357423123 | G431A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91963428123 | G451A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99516460123 | G473A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92366421123 | G475A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92425437123 | G505A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92642421123 | G534A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92642420123 | G547A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92059423123 | G550A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92634429123 | G553A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104974457123 | G566A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99532453123 | G577A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98824464123 | G614A_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 104974460123 | G659A_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 97327455123 | G844A_2025 Coverage Expansion Ph1_New_BKK
|  |  |  | 92594429123 | GATEP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104544473123 | GBCEP_L3_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 102680465123 | GCPKM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 100737481123 | GJTHM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104974463123 | GMBSA_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104974464123 | GMBSP_L1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 104974462123 | GMCNB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104544471123 | GMCPP_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 99753464123 | GMNWT_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104484478123 | GOCPM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92630420123 | GS32B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98032454123 | GS32B_2025 Capacity Expansion Ph7_EXP_BKK
|  |  |  | 92521433123 | HAMHM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 105599454123 | HBONM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 98680453123 | HCPNM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 100737479123 | HCSHM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99749473123 | HDTNM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99749472123 | HJRNM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105599452123 | HJTKM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92322423123 | HKG2M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105582459123 | HKMJM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 102703459123 | HKPIM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105558462123 | HKTTM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 104978452123 | HMR1M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98680452123 | HMTFM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 105614461123 | HNRNM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99732454123 | HPHTB_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99732453123 | HPTNM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102636455123 | HRRYM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 100247456123 | HTPGM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 106291533123 | HTRTM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99765463123 | HTSLA_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99721459123 | HUALT_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92062434123 | HUCBA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105558455123 | HUSRM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92628431123 | HVLXB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102697454123 | INNEM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92322421123 | IT36M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 103778466123 | ITBHP_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 104484480123 | IW36M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106300502123 | IW36M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99478460123 | IYRMM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100229453123 | IYRMM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 100247455123 | JKPAM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92365427123 | JMGRA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100224458123 | JOASM_D2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 105252456123 | JOMPM_RET_2025_RepSGR_NER
|  |  |  | 106252573123 | K7RNM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99761472123 | KAKIM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99753461123 | KANUM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99758461123 | KAPOM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99758460123 | KATGM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99758459123 | KBOIS_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102680462123 | KCGDM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99747460123 | KDINM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105253460123 | KDRGM_KKN_2025_RepSGR_NER
|  |  |  | 102709454123 | KDSSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104972459123 | KGP1M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92521430123 | KHASM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 99727476123 | KHGPO_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99729454123 | KHHAN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 106318472123 | KHRHM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 98670455123 | KHWKM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 105603453123 | KJUKM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 100742459123 | KKCPM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 93520422123 | KKFJM_2025 Capacity Expansion Ph5_EXP_ER_Add
|  |  |  | 102704471123 | KKFJM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105253459123 | KKHBM_KKN_2025_RepSGR_NER
|  |  |  | 99723470123 | KKLWN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104977454123 | KLG9M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99753455123 | KLPMM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92437434123 | KLS1B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92437433123 | KLS2B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92437432123 | KLS3B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92437431123 | KLS4B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105253458123 | KLSIM_RET_2025_RepSGR_NER
|  |  |  | 99753454123 | KLTOM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99753453123 | KMAFG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100742457123 | KMCPM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99729452123 | KMKWA_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99753452123 | KMLGM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100736457123 | KMOKM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105252455123 | KMYTL_RET_2025_RepSGR_NER
|  |  |  | 98819462123 | KN27M_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 105255453123 | KNSKK_KKN_2025_RepSGR_NER
|  |  |  | 92366429123 | KNT1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92623430123 | KNTRM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102704469123 | KNWAM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 101026452123 | KNWNE_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 98648457123 | KOCNM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99726471123 | KOPHM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 98648456123 | KOPOM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 100246456123 | KOSHM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99749457123 | KOSKM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99761471123 | KOTEM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104484477123 | KP22M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99761470123 | KPAKH_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104976452123 | KPMTM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99761468123 | KPOEM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99725460123 | KPPRM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99751452123 | KPSRM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99731466123 | KRN1M_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99731465123 | KRSNK_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100246455123 | KSCSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104976453123 | KSLSM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106322464123 | KSLSM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 104974461123 | KSLYM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99725457123 | KSNIM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105604460123 | KSOHM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99441562123 | KTK8M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92342429123 | KTMTB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92349421123 | KTMTM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106319471123 | KTNAM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92063425123 | KTPZP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104974452123 | KTSCM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100757465123 | KTSUM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105604459123 | KTSUM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99734473123 | KTTRM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104969460123 | KW60M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106291532123 | KW60M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 100246453123 | KYBSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99721454123 | KYUBK_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104389454123 | KZBPA_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 99516457123 | L107M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99517456123 | L109M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99517455123 | L110M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100229452123 | L110M_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 92366420123 | L4ASA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92634432123 | LAR9B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104972453123 | LB50M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105611456123 | LDPYM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 98826484123 | LIE9A_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 106252572123 | LLK4M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 91966420123 | LMBKP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99733459123 | LMPYM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104965453123 | LNIRB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91970420123 | LOWLB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102771455123 | LP25M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92608424123 | LP4KB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102704464123 | LPCTM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92459436123 | LPHSB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100757460123 | LPJTM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104974456123 | LPNGM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100757459123 | LPNIM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104965452123 | LPPAB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104974455123 | LPPBB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102771453123 | LPS3M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104977452123 | LRB1B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104965466123 | LRB2B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104965465123 | LRB3B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104965464123 | LRB4B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104965463123 | LRB5B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104965462123 | LRB6B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104977453123 | LRBSB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99741476123 | LSGVM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 91989421123 | LSMKB_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 105253457123 | LUPHM_RET_2025_RepSGR_NER
|  |  |  | 93263421123 | LWASE_2025 Coverage Expansion Ph1_New_SR
|  |  |  | 99737463123 | MARTM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100227456123 | MB88P_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 100227455123 | MB88P_2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 98829453123 | MBBVM_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 92569423123 | MBGAM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 91966424123 | MBK3P_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91966423123 | MBK4P_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91966422123 | MBK5P_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91966421123 | MBK6P_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98663456123 | MBLBM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 92617433123 | MEAKB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92569429123 | MECPM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 99761462123 | MGKLM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102680460123 | MGMHM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105611453123 | MGVPM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 98663454123 | MHBTM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 104969458123 | MJA2B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104969457123 | MJA3B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104972461123 | MJANB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99768452123 | MJSKA_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104969461123 | MK86M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92569420123 | MKAOM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 99765454123 | MKERO_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105608467123 | MKRBM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99741459123 | MKTTR_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102696456123 | MKVLM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98837456123 | MLLYM_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 99504473123 | MMT3M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99741458123 | MNAKT_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99741457123 | MNATH_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102693469123 | MNKWM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 102636453123 | MNMNM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 92638422123 | MNTLM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98663452123 | MONKM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 101021462123 | MPBST_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 98698452123 | MPHIM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 92615424123 | MPHKB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105602456123 | MPIEM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 104972458123 | MPINM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100749456123 | MPJSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 91965424123 | MPTNP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106322461123 | MS22M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106322460123 | MSDPM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92214420123 | MSKHH_2025 Coverage Expansion Ph1_New_SR
|  |  |  | 99728458123 | MSSPA_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100734465123 | MSSRM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 106313464123 | MSUPM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105615454123 | MSYYM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99728457123 | MTARY_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100734464123 | MTJCM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99724494123 | MTLCH_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92361431123 | MUDDM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 95318452123 | MWATM_2025 Capacity Expansion Ph5_EXP_ER_Add
|  |  |  | 105600456123 | MWHTM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 105600455123 | MYGMM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 101024455123 | NABLA_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 99746462123 | NAIR7_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105750455123 | NANJM_2026 Capacity Expansion Modernize_BBU_EXP_ER
|  |  |  | 101024454123 | NARIG_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 106291529123 | NBGCM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106322456123 | NBKDM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 100244452123 | NBLEM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 102693464123 | NBRPM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98672454123 | NCHKM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99738466123 | NCHSG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102693462123 | NCTSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99738465123 | NGBUA_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99729462123 | NGKOK_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 98672452123 | NGKTM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99738464123 | NGLKD_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 98648454123 | NGSUM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 98690456123 | NHINM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 103975452123 | NIRNM_2025 Coverage Expansion Ph2_New Site_Remote-BBU_ER
|  |  |  | 106322466123 | NISTA_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106313463123 | NKBPM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 98659458123 | NKMHM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 105604457123 | NKMHM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 100758453123 | NKNVM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 102694460123 | NKOWM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105252466123 | NKPYN_KKN_2025_RepSGR_NER
|  |  |  | 102770456123 | NKRFM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 101064462123 | NKRFM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 98690453123 | NKSOM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 106322452123 | NMBRM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106313462123 | NMDGM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 100748454123 | NODBM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 100245459123 | NOGKM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98659456123 | NOGKM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 100748452123 | NPHAM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105604453123 | NPHBM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 98659455123 | NPHWM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 93507426123 | NREKM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 92521439123 | NSCGM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 105214460123 | NSHMM_KKN_2025_RepSGR_NER
|  |  |  | 106252577123 | NSN1M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 98666460123 | NSSKM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99728481123 | NTGPO_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100734459123 | NUMRM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99759459123 | NUTAM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100734458123 | NVEWM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 100243452123 | NVOTM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92628426123 | NVPAB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100734457123 | NVPSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104544475123 | NWCBM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106297474123 | NWCBM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 93518428123 | NWKYM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 106319470123 | NWLDM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105256455123 | NWRIM_KKN_2025_RepSGR_NER
|  |  |  | 99777456123 | NWTPT_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105565464123 | NYNGM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 100747455123 | NYOAM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 100747454123 | NYOBM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 102697460123 | OBTNM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 100242455123 | OTCPM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98673454123 | OTSVM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 106322459123 | P110M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106313461123 | P117M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92610424123 | P21MA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106322458123 | P2M2M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106322457123 | P3BWM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106291526123 | P634M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105214465123 | PAPUM_KKN_2025_RepSGR_NER
|  |  |  | 100242454123 | PARHM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92459438123 | PB19A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92621424123 | PBR5M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100743466123 | PBSTM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99763455123 | PBTMM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105567459123 | PCOPM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 106313460123 | PCR3M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 98829456123 | PCTUM_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 106322471123 | PCTUM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 98666457123 | PDAGM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 102636456123 | PEAMM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 102636452123 | PEBKM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 98682455123 | PGASM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 91970424123 | PHCNM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98682454123 | PHIKM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 105597457123 | PHIKM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 105214457123 | PHKWM_NMA_2025_RepSGR_NER
|  |  |  | 105214464123 | PHNXM_KKN_2025_RepSGR_NER
|  |  |  | 92627421123 | PHTCB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91982435123 | PIANM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 99489466123 | PJNTM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 101063465123 | PJNTM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 104972455123 | PK11M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98674458123 | PKFAM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99763452123 | PKTNG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99777453123 | PLATM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100948460123 | PLIKR_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 100241455123 | PLOCM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99750457123 | PLRKM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100728464123 | PMCDM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 91989432123 | PN27M_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 92607436123 | PNDDA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105614455123 | PNIMM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92459439123 | PNK1A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92059432123 | PNK2A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106322470123 | PNK3M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106322469123 | PNP3M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99752475123 | PNPMS_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 103230466123 | PP13M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92635421123 | PP15M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100241452123 | PPKSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92633426123 | PR20A_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92620430123 | PR25M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104975461123 | PRARM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105064453123 | PRDSM_2025 Coverage Expansion Ph2_New Site_Remote-BBU_ER
|  |  |  | 100739459123 | PRDSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 102636454123 | PRDVM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 102637452123 | PRILM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 106322468123 | PS08M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92437430123 | PS38B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106291525123 | PS81M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106291524123 | PS88M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92361427123 | PSB5M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 95386453123 | PSN2M_2026 Antenna Dualbeam_Replacement_BKK
|  |  |  | 98261454123 | PSNMS_2025_Imp_UPS_SR
|  |  |  | 104484479123 | PST1M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99727469123 | PSTAM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99727468123 | PSYWO_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92521438123 | PTHAM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 105614454123 | PTIMM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92592424123 | PTPDP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104484482123 | PTPKM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99741455123 | PURGM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 106300511123 | PY16M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 103818452123 | PY24M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 101066457123 | PY24M_D2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 98184453123 | PYMRP_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER
|  |  |  | 102614481123 | PZAAM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98183452123 | QPHTM_2025 Coverage Expansion Ph1_New Site_Change SFP bidi_ER
|  |  |  | 99724484123 | RAKCM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104976454123 | RB11M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106322455123 | RCH1M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 100733456123 | RCTNM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 100746455123 | RCTRM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92361426123 | RD13M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99722464123 | RGANG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105606460123 | RGDNM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 98184454123 | RGPPP_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER
|  |  |  | 102702474123 | RGRNM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 103736452123 | RJLBM_2025 Coverage Expansion Ph2_New Site_NodeB_ER
|  |  |  | 105214463123 | RKHBP_KKN_2025_RepSGR_NER
|  |  |  | 99528456123 | RM65M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91982426123 | RMA6M_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 92521437123 | RMBTM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 105512455123 | RNRNM_NMA_2025_RepSGR_NER
|  |  |  | 92620422123 | RPR1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99773453123 | RPTST_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104974458123 | RRPMM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106313459123 | RRPMM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 102614478123 | RRWKM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105606458123 | RSJNM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92568421123 | RSKBM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 99773452123 | RTDAD_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92634433123 | RTS1B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92365421123 | RVE1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92594431123 | S241B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104972457123 | SAFNM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 91977420123 | SAKLM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104544476123 | SAMPM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99725466123 | SAPIM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 106291523123 | SAPRM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92637429123 | SAS1B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92612431123 | SAS2B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106313458123 | SBKWM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92521436123 | SBWMM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 105750454123 | SCHOM_2026 Capacity Expansion Modernize_BBU_EXP_ER
|  |  |  | 101060458123 | SCM1B_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 103818455123 | SCM2B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92367428123 | SCYNB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92367429123 | SCYNM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100240455123 | SEAHM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105562465123 | SECOM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 102350454123 | SENFP_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 105597454123 | SESWM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 100743461123 | SFCPM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98694461123 | SFDCM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 98183453123 | SFHSM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER
|  |  |  | 100745456123 | SFSMM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98183456123 | SFTPM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER
|  |  |  | 92625432123 | SHKVB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98184452123 | SHSSM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER
|  |  |  | 105562462123 | SIBTM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 101069452123 | SIHCP_L1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 101062465123 | SIHCP_L2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 101062466123 | SIHCP_L3_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 91968431123 | SK33M_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 102701464123 | SKBTM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99738457123 | SKHNM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105562461123 | SKKYM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 106300510123 | SKN4M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 102701462123 | SKRKM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 106369453123 | SKROM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 91968430123 | SKV1M_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 106322467123 | SLA2M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92616424123 | SLDSM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99776453123 | SLLSD_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105562460123 | SLRSM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92422421123 | SMANT_2025 Coverage Expansion (Co NT)_New_SR
|  |  |  | 102696465123 | SMATM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 106252581123 | SMBLM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99775456123 | SMHKW_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 106297473123 | SMPAM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99722462123 | SMPNG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 98830454123 | SMR1M_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 99728462123 | SNDPS_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 106291522123 | SNIWM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105597453123 | SNNCM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 101022455123 | SPAJB_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 106318476123 | SPBBM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105602459123 | SPGKM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 100240453123 | SPGTM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105602458123 | SPGTM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 106313457123 | SPKPM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 92459437123 | SPKWA_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102677457123 | SPOCM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99755464123 | SPPNM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 93520421123 | SPROM_2025 Capacity Expansion Ph5_EXP_ER_Add
|  |  |  | 97763452123 | SPRYM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER
|  |  |  | 92638426123 | SPSNM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99487457123 | SPT1M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106318475123 | SPT1M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105565462123 | SRRYM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 106297472123 | SS43M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99500475123 | SS99M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99500474123 | SSD4M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105610456123 | SSGKM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 98826461123 | SSIAA_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 102645464123 | SSKSM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99775453123 | SSPPN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 106322463123 | SSRTM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105565461123 | SSSLM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 98183454123 | SSSNM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER
|  |  |  | 91977421123 | SSTPM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99775452123 | SSWNH_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99532466123 | STAWM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99728477123 | STGGV_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100239456123 | STMLM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 92620428123 | STN3M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92617441123 | STRXM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98183455123 | STSGM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER
|  |  |  | 99769459123 | SUKSB_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92571424123 | SUNGM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 99751465123 | SUNTM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92620427123 | SUT1M_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99769458123 | SUTNM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105610455123 | SVPHM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 106291528123 | SW12M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106252580123 | SWAPM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99769457123 | SWE1M_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99487455123 | SWPPM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106318474123 | SWPPM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106300509123 | SWRDM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 98825455123 | SWSWM_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 106291536123 | SWSWM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105610465123 | SYANM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99751463123 | SYBKG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99751462123 | SYCPH_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100741460123 | SYKYM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105610453123 | SYKYM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 102677455123 | SYLLM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 91965423123 | SYMTP_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99753480123 | SYNYM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99737456123 | SYSAM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 101020455123 | SYTTO_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 99767461123 | TANGM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99737452123 | TANKM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100742456123 | TANPM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 106252579123 | TB45M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106252578123 | TB51M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99760452123 | TBALO_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 103794452123 | TBENA_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102693456123 | TBKBM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 100236458123 | TBNCM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 93518424123 | TBSVM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 100251471123 | TBSVM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 98689459123 | TBSVM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99731459123 | TBTHM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100733479123 | TBYJM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 106252571123 | TC42M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99537457123 | TCA1B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99451476123 | TCBBB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104976455123 | TCM1M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106322454123 | TCM1M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99451475123 | TDP2B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99451474123 | TECBA_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99451473123 | TECDA_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 103818454123 | TESBI_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 103818453123 | TESBO_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99451472123 | TESEA_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99508456123 | TESHM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99774455123 | TGKMN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92610437123 | THLHB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105253452123 | THMDM_KKN_2025_RepSGR_NER
|  |  |  | 99730467123 | TIRAT_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 101542463123 | TITHM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100737460123 | TJHTM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99766455123 | TKBRM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102702460123 | TKNDM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 104975460123 | TKPOA_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104544474123 | TKS1B_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 102702459123 | TKUMM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99501480123 | TL3CB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99501479123 | TL64M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99758454123 | TLBGN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 106252570123 | TLK6M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105256452123 | TLKHM_RET_2025_RepSGR_NER
|  |  |  | 99724478123 | TLKSA_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99723466123 | TLTAI_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102701461123 | TLVWM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 101019452123 | TLYRU_2026 Capacity Expansion NW Modernization_EXP_SR
|  |  |  | 102701459123 | TMFTM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99487454123 | TMK1M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106318473123 | TMK1M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 98691452123 | TMKCM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 99755461123 | TNATM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102645457123 | TNBAM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99755459123 | TNPYM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100227454123 | TOSMP_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 100227453123 | TOSMP_L1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 105608456123 | TPLBM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 105608464123 | TPPAM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92567420123 | TPRTM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 92567428123 | TPSEM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 105608455123 | TPSEM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99726476123 | TPUPE_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 102614491123 | TRAPM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99771455123 | TRCGM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99726474123 | TRKOM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99748476123 | TSHSM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105252465123 | TSKIM_RET_2025_RepSGR_NER
|  |  |  | 95021452123 | TSLNT_2025 Coverage Expansion (Co NT)_New_SR
|  |  |  | 105608463123 | TSOWM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 102614489123 | TSSCM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 93520420123 | TSTMM_2025 Capacity Expansion Ph5_EXP_ER_Add
|  |  |  | 105597466123 | TSTMM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92432421123 | TTKNT_2025 Coverage Expansion (Co NT)_New_SR
|  |  |  | 99755454123 | TTMYN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 104544472123 | TTP2M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99747470123 | TTSAM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100733461123 | TUGMM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 105566461123 | TUGMM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 105608453123 | TUGNM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 98692455123 | TUHGM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 102699461123 | TUNMM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99515475123 | TVBCM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 92638423123 | TWCHM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99754456123 | TYOGM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99726456123 | TYTKM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99741470123 | UAICI_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 100220474123 | UK54M_D2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 101065453123 | UNMAP_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 101061458123 | UNMAP_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 101061457123 | UNMAP_D2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 92342430123 | VALHB_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 104975457123 | VDE1M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 103194461123 | VHCSA_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 103778467123 | VJRHP_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106291535123 | VSTNM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99534463123 | WABNB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98686453123 | WAGWM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 106322462123 | WBACM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 98834467123 | WBCNM_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 101541458123 | WBENM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 95370456123 | WBLKM_2026 Antenna Dualbeam_Replacement_BKK
|  |  |  | 106319469123 | WBMGM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 101542458123 | WCHRM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100227452123 | WCHRM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK
|  |  |  | 106291531123 | WCKRM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105214458123 | WCWPT_RET_2025_RepSGR_NER
|  |  |  | 95370455123 | WDAOM_2026 Antenna Dualbeam_Replacement_BKK
|  |  |  | 105566458123 | WFMPM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 105565471123 | WHCMM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 105565470123 | WHCSM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 105565469123 | WHCWM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99748467123 | WHYIM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99534462123 | WIHHB_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106297476123 | WKD2M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 98696452123 | WKHYM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 95370453123 | WKKHM_2026 Antenna Dualbeam_Replacement_BKK
|  |  |  | 99749471123 | WKKOB_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99749470123 | WKNSI_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 105563466123 | WKPTM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 99754454123 | WKSTG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 92615425123 | WKTNM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106300506123 | WLBKM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 103742454123 | WLGTM_2025 Coverage Expansion Ph2_New Site_Remote-BBU_ER
|  |  |  | 105613460123 | WLGWM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 106300508123 | WMCRM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 95369452123 | WMSGM_2026 Antenna Dualbeam_Replacement_BKK
|  |  |  | 98697456123 | WNBGM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 105563463123 | WNBGM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 98697455123 | WNIBM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 100237456123 | WNSWM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 93518421123 | WNUKM_2025 Capacity Expansion Ph8_EXP_ER
|  |  |  | 92364421123 | WPASM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99721477123 | WPHKN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99724459123 | WPKRA_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99504461123 | WPPNM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 105252454123 | WPPSM_RET_2025_RepSGR_NER
|  |  |  | 106291530123 | WPRNM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 102701455123 | WRDRM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 91979429123 | WRSTM_2025 Capacity Expansion Ph8_EXP_BKK
|  |  |  | 95368454123 | WRTPM_2026 Antenna Dualbeam_Replacement_BKK
|  |  |  | 106322453123 | WSLKM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99721473123 | WSSWN_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99511457123 | WT32M_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 98830453123 | WTC2M_2026 Capacity Expansion Ph1_EXP_BKK
|  |  |  | 106291527123 | WTC2M_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106252574123 | WTKOM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 106297475123 | WTMKM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99765459123 | WTMPG_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 98673466123 | WTNLM_2026 Capacity Expansion Ph1_EXP_ER
|  |  |  | 92630428123 | WTNSM_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 100737455123 | WTPBM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 106319468123 | WTPGM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 102701452123 | WTPNM_2026 Capacity Expansion Modernize_EXP_ER
|  |  |  | 99532460123 | WTSTM_2026 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 106300505123 | WWNTM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 105613456123 | WWTRM_2026 Capacity Expansion Ph2_EXP_ER
|  |  |  | 92607422123 | WYN1B_2025 Capacity Expansion NW Modernization_EXP_BKK
|  |  |  | 99724467123 | YBNUE_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 106319467123 | YKTTM_2026 Capacity Expansion Ph2_BKK
|  |  |  | 99724454123 | YMWNM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99729461123 | YNGNM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99762478123 | YNGPS_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99723455123 | YPYRM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 99724476123 | YRAGM_2026 Capacity Expansion Ph1_EXP_SR
|  |  |  | 106300507123 | YWBGM_2026 Capacity Expansion Ph2_BKK

## Site Rollout Plan
DU ID | DU Name | Daily Plan | TL Name & Tel. | Daily work | Installation-Completed | [11 empty] | Smart QC | [11 empty] | PAT Subcon submit | [9 empty] | Sub PAT Pass Status | Return | [9 empty] | Withdraw EQ&MAT | [9 empty] | TPT(Service)Approve | [9 empty] | Submit SSR | [9 empty] | On Service Date | Site Verify completed | [9 empty] | Date Of Site Verify | Site Integration (OMC) | [9 empty] | On Service | [9 empty] | OMC Script | [9 empty] | EHS | [9 empty] | SQC Remark | Subcon/ PE Remark | Material On Site
[5 empty] | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks |  | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks |  | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks |  | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks |  |  | Plan End Date | Actual End Date | Owner | Approve State | Activity State | Close Time | Delivery Attachment Required | Delivery Attachment Uploaded | Delivery Attachment Upload Date | Remarks | DN Number | DN Status | Delivery Purpose | ASD | ATA
12BBM_2025 Capacity Expansion Ph3_EXP_BKK | SOI 12 B-NIKHOM BANGPU | 2025-08-13 |  | Install & Integrate | 2025-08-13 | 2025-08-31 | 2025-08-13 | 2025-08-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-08-29 15:14:11 | No | No |  |  |  | 2025-09-30 | 2025-09-01 | 2025-11-04 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-11-04 09:36:13 | Yes | Yes | 2025-11-04 09:37:19 |  | 2025-09-30 | 2025-09-22 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-09-26 16:35:46 | Yes | Yes | 2026-02-18 14:25:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:57 | Yes | Yes | 2025-10-06 14:24:28 |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:05 | Yes | Yes | 2026-07-14 22:35:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-23 18:45:46 | No | No |  | 23-08-2025. Replace RRU5516 L18 Sec.J |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-28 |  | N/A | Not assigned |  | No | No
1CONB_2025 Capacity Expansion Ph2_EXP_BKK | NUENG CONDOMINIUM | 2025-09-23 |  |  |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-24 09:52:34 | No | No |  |  |  | 2025-09-30 | 2025-10-15 | 2025-10-28 | V Contribute Co., Ltd | N/A | Closed | 2025-10-28 21:05:40 | Yes | Yes | 2025-10-28 21:05:40 |  | 2025-10-01 | 2025-10-01 | Chonradee Suwapan | Approved | Closed | 2025-10-16 16:35:33 | Yes | Yes | 2026-01-02 14:47:29 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-21 14:49:36 |  | 2025-10-01 | 2025-10-01 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-01 18:14:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-23 18:31:18 | No | No |  | 27-Nov-2025 Clear Pending work Add UBBPg3a remove eb 23-Sep-2025 Add RRU5516 (700900) SA SB Add g2 0/4 0/5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-09-23 |  | N/A | Not assigned |  | No | No
333RB_2025 Coverage Expansion Ph1_EXP_BKK | 333 RIVER SIDE | 2025-09-03 |  |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-03 18:12:42 | No | No |  |  |  | 2025-09-30 | 2026-05-22 | 2026-05-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-05-22 11:30:34 | Yes | Yes | 2026-05-22 09:25:37 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:45:39 | Yes | Yes | 2025-09-19 20:23:03 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:57 | Yes | Yes | 2025-10-06 14:25:43 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-19 20:34:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-03 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-03 19:44:30 | No | No |  | 2025-09-03_Replace to Ant Vertical Dual Beam Sector A#，B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-02 |  | N/A | Not assigned |  | No | No
A016A_2025 Capacity Expansion Ph3_EXP_BKK | Ban Jitnarong 4 (Bang Kruay-Jongtanom Rd.) | 2025-09-26 |  |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 12:05:22 | No | No |  |  |  | 2025-09-30 | 2025-10-17 | 2025-10-17 | V Contribute Co., Ltd | N/A | Closed | 2025-10-17 16:39:51 | Yes | Yes | 2025-10-17 16:39:52 |  | 2025-10-01 | 2025-10-01 | Chonradee Suwapan | Approved | Closed | 2025-10-15 14:27:54 | Yes | Yes | 2025-10-25 10:59:19 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-21 14:55:05 |  | 2025-10-01 | 2025-10-01 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-01 18:14:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-26 17:42:50 | No | No |  | 26-09-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， RRU5818#， Ant.12 port Sec.A#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-09-30 |  | N/A | Not assigned |  | No | No
A048A_2025 Capacity Expansion Ph2_EXP_BKK | Soi Chaeng Watthana-Pak Kret 40 |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-31 | 2025-10-27 | 2025-11-03 | V Contribute Co., Ltd | N/A | Closed | 2025-11-03 17:29:41 | Yes | Yes | 2025-11-03 17:29:41 |  | 2025-10-27 | 2025-10-27 | Chonradee Suwapan | Approved | Closed | 2025-10-30 12:55:24 | Yes | Yes | 2025-10-27 20:55:25 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:22 | Yes | Yes | 2025-12-01 14:47:52 |  | 2025-10-27 | 2025-10-27 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-27 21:07:57 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-16 18:19:53 | No | No |  | 16-Oct-2025 Add RRU5516 (700900) SA Add RRU5502*2 SA SB Remove RRU5507 *2 Replace Ant 12port *2 No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
A254A_2025 Capacity Expansion Ph5_EXP_BKK | TOT Pole SOI SO LAE | [5 empty] | 2025-12-07 | 2025-12-07 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  |  | 2025-11-21 | 2025-11-22 | 2025-11-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-23 15:17:16 | Yes | Yes | 2025-12-03 15:03:33 |  | 2025-12-09 | 2025-12-09 | Muhamadnase Chesamae | Approved | Closed | 2025-12-19 17:39:21 | Yes | Yes | 2026-01-14 15:03:39 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 10:08:26 |  | 2025-12-19 | 2025-12-19 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2025-12-19 19:54:53 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-21 18:41:17 | No | No |  | 21-Nov-2025 Replace BBU5900 UMPTg2 Add GPS g3a g2 Add RRU5818 SA Replace Ant *2 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A263A_2025 Capacity Expansion Ph5_EXP_BKK | MU BAN REGENCY |  |  |  | 2025-12-03 | 2025-12-09 | 2025-12-10 | 2025-12-10 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-12-18 11:53:14 | No | No |  |  |  | 2025-11-20 | 2025-12-11 | 2025-12-11 | Teloneer Company Limited | N/A | Closed | 2025-12-11 19:49:25 | Yes | Yes | 2025-12-12 09:49:00 |  |  | 2025-12-12 | Apichart Kampuang | Approved | Closed | 2025-12-19 17:39:21 | Yes | Yes | 2026-01-15 11:52:25 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 10:09:41 |  | 2025-12-02 | 2025-12-02 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:24:21 | Yes | Yes | 2025-12-02 22:39:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-04 15:40:32 | No | No |  | 4-Dec-2025 Add RRU5818 *1 Sector AB Replace ant 12port No RET Add g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | wait OSP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A311A_2025 Capacity Expansion Ph3_EXP_BKK | NONTHABURI MANSION | [5 empty] | 2025-12-01 | 2025-12-01 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  |  |  | 2025-10-01 | 2025-10-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-04 21:31:00 | Yes | Yes | 2025-12-03 12:40:28 |  | 2025-12-03 | 2025-12-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-11 09:20:07 | Yes | Yes | 2025-12-03 16:01:30 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 10:10:55 |  | 2025-12-03 | 2025-12-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:24:21 | No | Yes | 2025-12-03 18:00:50 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-26 17:33:26 | No | No |  | 26-11-2025. Add RRU5818 Sec.B //30-09-2025. Add UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-30 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
A311A_2025 Capacity Expansion Ph5_EXP_BKK | NONTHABURI MANSION | [5 empty] | 2025-12-11 | 2025-12-11 | Akhom Srinara | N/A | Closed | 2025-12-18 11:53:12 | No | No |  |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-08 20:33:36 | Yes | Yes | 2025-12-08 20:33:37 |  | 2025-12-13 | 2026-01-20 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-22 15:33:02 | Yes | Yes | 2026-01-20 20:46:58 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:35:07 |  | 2025-12-13 | 2025-12-13 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:22:43 | Yes | Yes | 2025-12-13 15:55:32 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-05 11:47:34 | No | No |  | 5-Dec-2025 Add RRU5818 Sector C Add g2 Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A323A_2025 Capacity Expansion Ph3_EXP_BKK | MU BAN KANCHANALAK |  |  |  | 2026-01-29 | 2026-02-05 | 2026-02-16 | 2026-02-16 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2026-02-24 14:14:06 | No | No |  |  | 2026-02-17 | 2026-02-24 | 2026-02-17 | 2026-02-17 | Teloneer Company Limited | N/A | Closed | 2026-02-17 14:54:06 | Yes | Yes | 2026-02-18 11:03:57 |  |  | 2026-02-18 | Apichart Kampuang | Approved | Closed | 2026-03-19 16:33:13 | Yes | Yes | 2026-03-08 09:59:39 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-16 | 2026-03-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:36:04 |  | 2026-02-16 | 2026-07-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-07-23 17:58:49 | Yes | Yes | 2026-07-23 17:11:31 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-16 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-16 16:47:08 | No | No |  | 16 Feb 2026 Add RRU5516 sector1 add 1UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-25 | Nattawoot Suwan | N/A | Closed | 2026-06-25 14:50:06 | No | No |  |  |  | 100% |  | 2026-02-15 |  | N/A | Not assigned |  | No | No
A691A_2025 Capacity Expansion Ph3_EXP_BKK | BUA THONG MARKET SPOTLIGHT POLE 2 | 2025-09-26 |  |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-17 16:18:56 | No | No |  |  |  | 2025-09-30 | 2025-10-17 | 2025-10-24 | V Contribute Co., Ltd | N/A | Closed | 2025-10-24 11:26:02 | Yes | Yes | 2025-10-24 11:26:03 |  | 2025-11-20 | 2025-11-20 | Chonradee Suwapan | Approved | Closed | 2025-11-26 16:16:17 | Yes | Yes | 2025-11-20 19:43:44 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:22 | Yes | Yes | 2025-12-01 14:50:24 |  | 2025-11-20 | 2025-11-20 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-11-20 22:44:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-12 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-11-12 17:04:10 | No | No |  | 2025-11-12_Add RRU5818 Sector A//26-Sep-2025 ***Pinding Add RRU5818 SA (5/2) ///Replace BBU5900 UMPTg2 Add g3a GPS Replace Ant 12 port No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-11-14 |  | N/A | Not assigned |  | No | No
A765A_2025 Capacity Expansion Ph2_EXP_BKK | Ban Uea Athon Bang Bua Thong1_7 | 2025-09-13 |  |  |  | 2025-09-13 | 2025-09-13 | 2025-09-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-13 18:36:57 | No | No |  |  |  | 2025-09-30 | 2025-09-29 | 2025-10-02 | V Contribute Co., Ltd | N/A | Closed | 2025-10-02 14:58:32 | Yes | Yes | 2025-10-02 14:58:32 |  | 2025-09-23 | 2025-09-23 | Chonradee Suwapan | Approved | Closed | 2025-10-10 16:47:05 | Yes | Yes | 2025-09-23 20:21:12 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:22 | Yes | Yes | 2025-12-01 14:52:50 |  | 2025-09-23 | 2025-09-23 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:20:11 | No | Yes | 2025-09-23 20:32:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-13 18:31:51 | No | No |  | 13-Sep-2025 Replace BBU5900 UMPTg2 g3a GPS Add RRU5818 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-12 |  | N/A | Not assigned |  | No | No
A777A_2025 Coverage Expansion Ph1_New_BKK | Small Cell Wat Khema Phirataram |  |  |  |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-04 15:40:36 | No | No |  |  |  | 2025-11-15 | 2025-11-26 | 2025-11-27 | V Contribute Co., Ltd | N/A | Closed | 2025-11-27 10:22:30 | Yes | Yes | 2025-11-27 10:22:30 |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2026-02-09 17:33:30 | Yes | Yes | 2025-11-11 19:25:04 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-04-28 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-11-11 19:32:18 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-04 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-04 17:52:43 | No | No |  | 04-11-2025. New Site Small Cell Add RRU3962#， Ant.4 port x2 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
AANKM_2025 Capacity Expansion Ph6_EXP_ER | Ban UEA Arthorn Na Kluea | 2025-11-17 | thcp_Phet.s | Clear Pending |  | 2025-11-30 | 2025-11-05 | 2025-11-05 | Teloneer Company Limited | N/A | Closed | 2025-11-05 13:29:52 | No | No |  |  |  | 2025-11-30 | 2025-11-05 | 2025-11-06 | Teloneer Company Limited | N/A | Closed | 2025-11-06 14:46:33 | Yes | Yes | 2025-11-12 07:10:22 |  | 2025-11-30 | 2025-11-08 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-11 13:43:39 | Yes | Yes | 2025-11-08 23:29:14 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 14:08:54 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:37:13 | Yes | Yes | 2025-11-04 08:53:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-05 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-05 18:42:04 | No | No |  | Replace 1RRU5508 to (RRU5516_900) + 4T4R S2#，3 |  | 2025-11-05 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-05 18:42:04 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AB9VM_2025 Capacity Expansion Ph3_EXP_BKK | AEKBURI 9 VILLAGE |  |  |  |  | 2025-09-09 | 2025-09-17 | 2025-09-17 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-26 | 2025-09-18 | 2025-09-18 | V Contribute Co., Ltd | N/A | Closed | 2025-09-18 21:43:13 | Yes | Yes | 2025-09-18 21:43:14 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-10-10 14:08:42 | Yes | Yes | 2025-10-27 11:22:42 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:27 | Yes | Yes | 2025-11-06 11:50:28 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 21:26:22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-09 18:51:40 | No | No |  | 9-Sep-2025 Add AAU5636w S2 Add RRU5516(18002100) S2 S3 Remove RRU5507*2 Replace Ant 8port S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan Wk37 |  | 2025-09-16 |  | N/A | Not assigned |  | No | No
AB9VM_2025 Coverage Expansion Ph2_EXP_BKK | AEKBURI 9 VILLAGE | 2025-08-04 |  |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-04 14:49:49 | No | No |  |  |  | 2025-08-22 | 2025-08-14 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 10:29:07 | Yes | Yes | 2025-08-15 10:30:22 |  | 2025-08-22 | 2025-08-22 | Chonradee Suwapan | Approved | Closed | 2025-08-25 17:35:50 | Yes | Yes | 2025-08-22 07:50:47 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:14 | Yes | Yes | 2025-08-26 17:44:33 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:40:47 | No | Yes | 2025-08-05 09:05:18 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-04 18:25:07 | No | No |  | 4-Aug-2025 Add RRU3953 S1 Add Ant. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-01 |  | N/A | Not assigned |  | No | No
ABB3M_2025 Capacity Expansion Ph2_EXP_BKK | ABAC BANGNA STATION 3 |  |  |  | 2025-08-18 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-18 | 2025-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-19 17:26:51 | Yes | Yes | 2025-09-03 14:45:17 |  | 2025-08-28 | 2025-08-28 | Aomchun Jittreemit | Approved | Closed | 2025-09-16 13:40:08 | Yes | Yes | 2025-10-27 11:33:38 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:19 | Yes | Yes | 2025-09-22 16:48:18 |  | 2025-09-03 | 2025-09-04 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 14:55:48 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-19 17:52:35 | No | No |  | 2025-08-19_Add UBBPg3a#， Add AAU5636w Sector 1#，2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
ACSCM_2025 Capacity Expansion Ph2_EXP_BKK | AIR COMMAND AND STAFF COLLEGE | 2025-10-06 |  |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-10 18:33:54 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-28 | V Contribute Co., Ltd | N/A | Closed | 2025-10-28 20:17:27 | Yes | Yes | 2025-10-28 20:17:28 |  | 2025-10-16 | 2025-10-16 | Chonradee Suwapan | Approved | Closed | 2025-10-22 17:31:20 | Yes | Yes | 2025-10-16 17:17:17 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-27 16:14:29 |  | 2025-10-16 | 2025-10-16 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-16 17:23:00 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-06 14:48:06 | No | No |  | 6-Oct-2025 Add RRU5516 (1800-2100) S3 Remove RRU5507 Replace Ant.8port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-09 |  | N/A | Not assigned |  | No | No
ACSCM_2025 Coverage Expansion Ph2_EXP_BKK | AIR COMMAND AND STAFF COLLEGE | 2025-10-06 |  |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-10 18:33:54 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-28 | V Contribute Co., Ltd | N/A | Closed | 2025-10-28 21:10:44 | Yes | Yes | 2025-10-28 21:10:44 |  | 2025-10-16 | 2025-10-16 | Chonradee Suwapan | Approved | Closed | 2025-10-22 17:31:20 | Yes | Yes | 2025-10-16 17:18:32 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-27 16:15:46 |  | 2025-10-16 | 2025-10-16 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-16 17:25:25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-06 14:48:58 | No | No |  | 6-Oct-2025 Add RRU3953 S1 Add Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-09 |  | N/A | Not assigned |  | No | No
AIUNR_2025 Capacity Expansion Ph4_EXP_SR | Ai Un Riso |  |  |  | 2025-10-08 | 2025-10-08 | 2025-10-08 | 2025-10-08 | Nattawoot Suwan | N/A | Closed | 2025-10-10 13:01:25 | No | No |  |  |  | 2025-09-26 | 2025-10-08 | 2025-10-08 | Teloneer Company Limited | N/A | Closed | 2025-10-08 20:58:56 | Yes | Yes | 2025-10-10 11:48:23 |  | 2025-10-10 | 2025-10-10 | Nattawoot Suwan | Approved | Closed | 2025-10-14 09:16:09 | Yes | Yes | 2025-10-15 14:41:01 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-27 16:16:58 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-10-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-08 | 2025-10-08 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-10-08 16:55:35 | No | No |  | Add new S4 5516LB > Ant 4 port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-07 |  | N/A | Not assigned |  | No | No
AKPGM_2025 Capacity Expansion Ph6_EXP_ER | Angkapong | 2025-11-22 | thcp_Adirek.k | Install & Integrate |  | 2025-11-30 | 2025-11-22 | 2025-11-22 | Teloneer Company Limited | N/A | Closed | 2025-11-22 15:50:08 | No | No |  |  |  | 2025-11-30 | 2025-11-22 | 2025-11-22 | Teloneer Company Limited | N/A | Closed | 2025-11-22 16:06:35 | Yes | Yes | 2025-11-23 23:23:28 |  | 2025-11-30 | 2025-11-25 | Thanakit Chaleechai | Approved | Closed | 2025-11-27 15:09:50 | Yes | Yes | 2025-11-25 20:19:54 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 14:11:24 |  | 2025-11-30 | 2025-11-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-25 18:20:01 | Yes | Yes | 2025-11-22 12:20:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-22 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-22 16:50:21 | No | No |  | **waiting on-service LNR26 -- Add UBBPg2 New L26F5 + NR26 (New AAU5636w) H_4 |  | 2025-11-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-24 16:39:22 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AM31M_2025 Capacity Expansion Ph3_EXP_BKK | SOI ANAMAI NGAAM JAREAN 31 | 2025-08-22 |  | Install & Integrate | 2025-08-22 | 2025-08-31 | 2025-08-22 | 2025-08-22 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2025-08-29 15:14:46 | No | No |  |  |  | 2025-09-30 | 2025-09-14 | 2025-09-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-09-17 16:44:01 | Yes | Yes | 2025-09-18 09:27:57 |  | 2025-09-30 | 2025-09-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-09-30 15:29:58 | Yes | Yes | 2025-10-27 14:56:36 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:57 | Yes | Yes | 2025-10-06 14:36:57 |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:05 | Yes | Yes | 2026-07-14 22:37:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-22 16:59:37 | No | No |  | 22-Aug-2025 Add AAU5636w S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-28 |  | N/A | Not assigned |  | No | No
AMPSM_2025 Capacity Expansion Ph4_EXP_ER | Amata co Tower City Chonburi2 Bo Nam Phase10 | 2025-10-04 |  | Clear Pending |  | 2025-09-30 | 2025-09-19 | 2025-09-19 | Teloneer Company Limited | N/A | Closed | 2025-09-19 16:37:44 | No | No |  |  |  | 2025-09-30 | 2025-09-22 | 2025-10-08 | Teloneer Company Limited | N/A | Closed | 2025-10-08 16:25:56 | Yes | Yes | 2025-10-08 16:48:48 |  | 2025-09-30 | 2025-10-08 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-10 10:16:30 | Yes | Yes | 2025-11-07 13:34:49 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:27 | Yes | Yes | 2025-11-06 11:56:01 |  | 2025-09-30 | 2025-10-11 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-15 12:07:51 | Yes | Yes | 2025-10-11 09:37:12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-19 |  | 2025-09-19 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-19 18:12:00 | No | No |  | **need on-service LNR26 -- Replace UBBPg1 to UBBPg2 + Co L21F2 S1 #，Replace RRU5505 to (RRU5516_1800) + 4T4R S2 #，Co L21F2 S4 #，Co L21F2 S8 #，Replace RRU5508 to (RRU5516_900) + 4T4R S1 #，New L26F5 + NR26 (New AAU5636w) S4 |  | 2025-09-22 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-22 17:07:27 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AN20M_2025 Capacity Expansion Ph3_EXP_BKK | ANNEX 20 | 2025-08-19 |  | Install & Integrate | 2025-08-19 | 2025-08-31 | 2025-08-19 | 2025-08-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-08-21 08:59:40 | No | No |  |  |  | 2025-08-31 | 2025-08-21 | 2025-09-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-09-11 20:32:53 | Yes | Yes | 2025-09-16 13:22:52 |  | 2025-09-30 | 2025-09-16 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-10-16 15:00:10 | Yes | Yes | 2026-06-19 16:48:42 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-11-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-10-21 14:58:48 |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:05 | Yes | Yes | 2026-07-14 22:37:30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-19 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-19 17:45:16 | No | No |  | 19-08-2025. Add AIRU5636w Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-18 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 05:58:50 | No | No
ANBTK_2025 Capacity Expansion Ph7_EXP_SR | Anamai Ban Ta Krop |  |  |  |  | 2025-12-25 | 2026-01-06 | 2026-01-06 | Teloneer Company Limited | N/A | Closed | 2026-01-06 15:29:52 | No | No |  |  |  | 2025-12-08 | 2026-01-06 | 2026-01-12 | Teloneer Company Limited | N/A | Closed | 2026-01-12 09:39:47 | Yes | Yes | 2026-01-12 09:44:45 |  | 2026-01-08 | 2026-01-08 | Nattawoot Suwan | Approved | Closed | 2026-01-27 11:42:01 | Yes | Yes | 2026-01-08 22:29:05 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-14 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:03 | Yes | Yes | 2026-01-15 10:15:46 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-07 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-06 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-01-06 17:24:02 | No | No |  | Rep BBU 5900/add g3a*1/-WBBPf6*1/add gps Add AAU5636w Sector 2 Set Alarm Door HIGH |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-24 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-24 16:49:35 | Yes | Yes | 2025-12-24 16:04:18 |  |  | 2026-01-20 | Nattawoot Suwan | N/A | Closed | 2026-01-20 14:02:40 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ANCKM_2025 Capacity Expansion Ph3_EXP_BKK | SOI AMNUANCHOK | 2025-08-30 |  |  |  | 2025-08-30 | 2025-08-31 | 2025-08-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-31 12:17:45 | No | No |  |  |  | 2025-09-05 | 2025-09-06 | 2025-09-08 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:11:44 | Yes | Yes | 2025-09-30 10:11:44 |  | 2025-09-10 | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-10-03 12:01:59 | Yes | Yes | 2025-09-10 16:58:25 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:57 | Yes | Yes | 2025-10-06 14:40:41 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-10 21:24:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-30 20:42:29 | No | No |  | 30-Aug-2025 Add AAU5636w S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-28 |  | N/A | Not assigned |  | No | No
ANMAM_2025 Capacity Expansion Ph6_EXP_BKK | ANAMAI ALLEY SAMKHOK |  |  |  |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-22 09:18:28 | No | No |  |  |  | 2025-12-31 | 2025-12-22 | 2025-12-24 | V Contribute Co., Ltd | N/A | Closed | 2025-12-24 17:43:03 | Yes | Yes | 2025-12-24 17:43:04 |  | 2026-01-07 | 2026-01-07 | Chonradee Suwapan | Approved | Closed | 2026-04-28 16:54:50 | Yes | Yes | 2026-01-07 21:55:36 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-07 | 2026-01-07 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:02:00 | Yes | Yes | 2026-01-07 22:34:25 |  |  | 2025-12-31 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  |  | 2025-12-19 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-19 17:43:25 | No | No |  | 19-12-2025. Add UBBPg3a#， AIRU5614 Sec.2#， 3#， AIRU5636w Sec.6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
APRWB_2025 Coverage Expansion Ph1_EXP_BKK | ASPIRE RATCHADA - WONGSAWANG | 2025-09-12 |  |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-12 18:29:38 | No | No |  |  |  | 2025-09-30 | 2025-09-22 | 2025-09-23 | V Contribute Co., Ltd | N/A | Closed | 2025-09-23 17:24:56 | Yes | Yes | 2025-09-23 17:24:56 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-10-06 16:26:47 | Yes | Yes | 2025-09-20 20:08:16 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:03 | Yes | Yes | 2025-10-09 19:10:35 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:05:32 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-12 18:07:29 | No | No |  | 12-09-2025. Replace Ant.12 port x4 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
ARSCB_2025 Capacity Expansion Ph2_EXP_BKK | ASPIRE SATHORN -TAKSIN(COPPER ZONE) | 2025-09-16 |  |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-19 12:21:44 | No | No |  |  |  | 2025-09-30 | 2025-09-16 | 2025-09-17 | V Contribute Co., Ltd | N/A | Closed | 2025-09-17 16:50:05 | Yes | Yes | 2025-09-17 16:50:06 |  | 2025-09-25 | 2025-09-25 | Chonradee Suwapan | Approved | Closed | 2025-10-08 14:52:51 | Yes | Yes | 2025-10-27 16:19:01 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:03 | Yes | Yes | 2025-10-09 19:11:51 |  | 2025-09-25 | 2025-09-25 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:38 | No | Yes | 2025-09-25 18:46:26 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-16 17:05:42 | No | No |  | 16-09-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， RRU5818 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-18 |  | N/A | Not assigned |  | No | No
ARSCB_2025 Coverage Expansion Ph1_EXP_BKK | ASPIRE SATHORN -TAKSIN(COPPER ZONE) |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-24 | 2025-10-18 | 2025-10-21 | V Contribute Co., Ltd | N/A | Closed | 2025-10-21 11:48:03 | Yes | Yes | 2025-10-21 11:48:03 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-05 16:33:10 | Yes | Yes | 2025-10-30 20:38:31 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:27 | Yes | Yes | 2025-11-06 11:58:32 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-30 20:48:13 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-17 17:31:31 | No | No |  | 17-Oct-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam SA 84 E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
AS11M_2025 Capacity Expansion NW Modernization_EXP_BKK | AT-SATHON BUILDING SOI SATHON11 |  |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-19 11:55:40 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-02-02 | 2026-02-03 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-03 14:40:15 | Yes | Yes | 2026-02-06 10:52:38 | SQC Close | 2026-02-19 | 2026-02-19 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-04-07 13:12:18 | Yes | Yes | 2026-02-19 11:56:44 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-09 | 2026-03-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:54:11 |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:05 | Yes | Yes | 2026-07-14 22:38:46 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-19 16:43:59 | No | No |  | 2026-01-19_Replace RRU5508 to RRU5516(LB)#， Replace Ant to 8 port Sector 2#，3#， Add RRU5507 Sector 2.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASB3M_2025 Coverage Expansion Ph2_EXP_BKK | AUEARTHON SUVARNABHUMI BANGBO 3 | [5 empty] | 2025-09-13 | 2025-09-13 | Akhom Srinara(Future Telecom Co.,Ltd.) | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  |  | 2025-09-03 | 2025-09-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-16 17:36:43 | Yes | Yes | 2025-12-16 17:39:30 |  | 2025-09-14 | 2025-09-14 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-03 20:59:11 | Yes | Yes | 2025-09-14 19:18:56 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-11-02 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:27 | Yes | Yes | 2025-11-06 12:03:42 |  | 2025-09-12 | 2025-09-12 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:28:45 | No | Yes | 2025-09-14 19:07:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-04 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-04 18:31:27 | No | No |  | 04-09-2025. Add RRU3953#， Ant.8 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | PDB เต็ม Request ติด PDB เพิ่ม |  | 2025-09-12 | Jia Rui 80023782 | N/A | Closed | 2025-10-01 20:48:30 | No | No
ASEPB_2025 Coverage Expansion Ph1_EXP_BKK | ASPIRE ERAWAN PRIME CONDO |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-24 | 2025-11-04 | 2025-11-04 | V Contribute Co., Ltd | N/A | Closed | 2025-11-04 14:09:40 | Yes | Yes | 2025-11-04 14:09:40 |  | 2025-10-29 | 2025-10-29 | Chonradee Suwapan | Approved | Closed | 2025-11-03 20:57:07 | Yes | Yes | 2026-01-03 09:30:28 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:27 | Yes | Yes | 2025-11-06 12:04:55 |  | 2025-10-29 | 2025-10-29 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-29 20:22:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-17 17:35:25 | No | No |  | 17-10-2025. Replace Ant.12 port x2 Sec.D#， E |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
ASEPB_DPU40_OPM30_Replacement_BKK | ASPIRE ERAWAN PRIME CONDO |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-26 | 2025-12-27 | V Contribute Co., Ltd | N/A | Closed | 2025-12-27 13:45:08 | Yes | Yes | 2025-12-27 13:45:08 |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-01-26 09:23:37 | Yes | Yes | 2026-01-18 19:48:02 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:38:22 |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-18 20:14:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-26 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-26 15:51:54 | No | No |  | 26-Dec-2025 Replace DPU30 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
ASEWB_2025 Capacity Expansion Ph5_EXP_BKK | ASPIRE ERAWAN |  |  |  |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-18 11:47:42 | No | No |  |  |  | 2025-12-28 | 2025-12-23 | 2025-12-23 | V Contribute Co., Ltd | N/A | Closed | 2025-12-23 21:05:12 | Yes | Yes | 2025-12-23 21:05:12 |  | 2025-12-24 | 2025-12-24 | Chonradee Suwapan | Approved | Closed | 2026-01-09 17:03:57 | Yes | Yes | 2025-12-24 17:57:42 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-15 10:19:51 |  | 2025-12-24 | 2025-12-24 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:14:57 | Yes | Yes | 2026-01-15 21:10:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-17 16:36:59 | No | No |  | 17-12-2025. Add RRU5818 Sec.A#， Replace UBBPd5 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-25 06:10:09 | Yes | Yes | 2025-12-12 10:10:31 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASPIB_2025 Coverage Expansion Ph1_EXP_BKK | ASPIRE LADPRAO 113 |  |  |  |  | 2025-10-21 | 2025-10-21 | 2025-10-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-21 17:43:19 | No | No |  |  |  | 2025-10-18 | 2025-10-10 | 2025-10-16 | V Contribute Co., Ltd | N/A | Closed | 2025-10-16 15:24:15 | Yes | Yes | 2025-10-16 15:24:16 |  | 2025-10-24 | 2025-10-24 | Chonradee Suwapan | Approved | Closed | 2025-10-29 17:02:35 | Yes | Yes | 2025-10-24 19:42:28 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:22 | Yes | Yes | 2025-12-01 15:01:42 |  | 2025-10-24 | 2025-10-24 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-10-24 19:57:10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-10 16:53:49 | No | No |  | 10-10-2025. Replace Ant.12 port Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Complted |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
ASTNB_2025 Coverage Expansion Ph1_EXP_BKK | THE ADDRESS SATHORN | [5 empty] | 2025-09-22 | 2025-09-22 | Akhom Srinara | N/A | Closed | 2025-09-25 13:54:36 | No | No |  |  |  |  | 2025-09-17 | 2025-09-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-17 17:50:34 | Yes | Yes | 2025-09-19 14:24:38 |  | 2025-09-19 | 2025-09-24 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-16 16:35:33 | Yes | Yes | 2025-09-24 20:28:46 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:03:42 |  | 2025-09-22 | 2025-09-22 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:28:19 | No | Yes | 2025-09-22 11:52:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-17 18:18:58 | No | No |  | 17-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A#，B E tili -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-21 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
ASYPB_2025 Coverage Expansion Ph1_EXP_BKK | ABSTRACTS PHAHONYOTHIN PARK | [5 empty] | 2025-10-17 | 2025-10-17 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-17 | 2025-10-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-18 11:53:34 | Yes | Yes | 2025-10-27 13:58:32 |  | 2025-10-28 | 2025-10-28 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-30 12:49:26 | Yes | Yes | 2025-10-28 15:21:14 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:22 | Yes | Yes | 2025-12-01 15:02:57 |  | 2025-10-31 | 2025-10-31 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-31 15:26:22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-16 17:03:25 | No | No |  | 16-10-2025. Replace Ant.12 port Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-10-16 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
ATTIB_2025 Capacity Expansion Ph7_EXP_BKK | ATTITUDE BU CONDOMINIUM |  |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2026-04-23 14:25:10 | No | No |  |  |  | 2026-02-28 | 2026-02-24 | 2026-05-09 | V Contribute Co., Ltd | N/A | Closed | 2026-05-09 16:01:59 | Yes | Yes | 2026-05-09 16:01:59 |  | 2026-04-01 | 2026-04-01 | Chonradee Suwapan | Approved | Closed | 2026-07-09 09:18:10 | Yes | Yes | 2026-05-14 15:23:46 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-16 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | No | No |  |  | 2026-04-01 | 2026-04-01 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-01 00:48:36 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-24 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-24 17:47:27 | No | No |  | 24-Feb-26 Add UBBPg3a Add RRU5818 SAB SCD |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AUCSB_2025 Capacity Expansion Ph2_EXP_BKK | ALTITUDE UNICORN SATHORN-THAPRA | 2025-09-22 |  |  |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-24 09:51:37 | No | No |  |  |  | 2025-09-30 | 2025-10-03 | 2025-10-08 | V Contribute Co., Ltd | N/A | Closed | 2025-10-08 10:35:10 | Yes | Yes | 2025-10-08 10:35:10 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2025-10-15 22:31:52 | Yes | Yes | 2025-09-29 16:58:07 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:04:56 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-09-29 12:40:29 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-22 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-22 19:00:13 | No | No |  | 2025-09-22_Add RRU5516(LB)#， Replace to Ant 12 port Combine 18-21 (No RET) Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-09-23 |  | N/A | Not assigned |  | No | No
AUT2M_2025 Capacity Expansion Ph6_EXP_BKK | SOI AUTHONG2 (OPPOSITE MEGA BANGNA) | [5 empty] | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:42:22 | No | No |  |  |  | 2025-12-12 | 2025-12-23 | 2025-12-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-24 13:54:08 | Yes | Yes | 2025-12-24 20:17:48 |  | 2025-12-25 | 2025-12-25 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-09 12:20:36 | Yes | Yes | 2025-12-25 20:31:57 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-15 10:21:04 |  | 2026-01-06 | 2026-01-06 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-06 18:38:53 |  |  | 2025-12-31 | 2025-12-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-23 16:15:12 | No | No |  |  |  |  | 2025-12-15 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-15 17:11:18 | No | No |  | 15-12-2025. Add RRU5526 Sec.7#， Replace Ant.8 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AYR8M_2025 Coverage Expansion Ph2_EXP_BKK | SOI AIYARA 8 | 2025-08-26 |  | Install & Integrate | 2025-08-26 | 2025-09-30 | 2025-08-26 | 2025-08-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-09-05 11:06:04 | No | No |  |  |  | 2025-09-30 | 2025-09-13 | 2025-09-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-09-16 14:44:41 | Yes | Yes | 2025-09-16 14:44:42 |  | 2025-09-30 | 2025-09-19 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-09-22 16:55:47 | Yes | Yes | 2025-10-27 16:26:09 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:57 | Yes | Yes | 2025-10-06 14:51:33 |  | 2025-08-09 | 2025-08-09 | Sattaya Parakij | Approved | Closed | 2025-09-03 22:41:31 | No | Yes | 2025-08-09 00:24:51 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-26 16:58:07 | No | No |  | 2025-08-27_Add RRU3953 Sector 2#，3//26-08-2025. ***Need RRU3953 Sec.2#， 3 //Replace Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | หน้างานทำถนน ไม่มีทางเข้าไซต์ แผนติดตั้งปลานเฟส |  | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-09-09 08:32:17 | No | No
B045A_2025 Capacity Expansion Ph2_EXP_BKK | SAMUT PRAKAN CITY HALL_1 |  |  |  |  | 2025-10-03 | 2025-10-03 | 2025-10-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-03 10:03:04 | No | No |  |  |  | 2025-10-16 | 2025-10-06 | 2025-10-08 | V Contribute Co., Ltd | N/A | Closed | 2025-10-08 10:01:02 | Yes | Yes | 2025-10-09 17:03:15 |  | 2025-10-09 | 2025-10-09 | Chonradee Suwapan | Approved | Closed | 2025-11-05 18:20:28 | Yes | Yes | 2026-01-22 11:50:20 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:27 | Yes | Yes | 2025-11-06 12:13:28 |  | 2025-10-09 | 2025-10-09 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-09 20:47:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-02 18:47:52 | No | No |  | 2-Oct-2025 Replace BBU5900 UMPTg2 Add g3a Addd RRU5818 SA SC Replace Ant 12port No Ret SA SC 5/2 5/4 GPS ไมได้ Add พื้นที่ไม่ได้ |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-02 |  | N/A | Not assigned |  | No | No
B072A_2025 Capacity Expansion Ph5_EXP_BKK | Ban Uea Athon Kajornvit_6 |  |  |  |  | 2025-11-24 | 2025-11-24 | 2025-11-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:45:54 | No | No |  |  |  | 2025-12-28 | 2025-11-21 | 2025-12-02 | V Contribute Co., Ltd | N/A | Closed | 2025-12-02 18:31:54 | Yes | Yes | 2025-12-02 18:31:54 |  | 2025-11-24 | 2025-11-24 | Chonradee Suwapan | Approved | Closed | 2026-01-15 09:42:31 | Yes | Yes | 2025-11-24 21:52:39 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:00 | Yes | Yes | 2026-03-19 14:44:16 |  | 2025-11-24 | 2025-11-24 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-11-24 22:16:35 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-21 17:57:01 | No | No |  | 21-11-2025. Add UBBPg2 //20-Nov-2025 Replace BBU5900 UMPTg2 Add GPS g3a Add AAU5246 SA Remove AAU3940 5/5 Done dea cell 126 226 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B102A_2025 Capacity Expansion Ph5_EXP_BKK | KAN KHEKA BANG PHLI1_3 | [5 empty] | 2025-12-05 | 2025-12-05 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  |  | 2025-11-26 | 2025-11-26 | 2025-12-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-04 16:19:20 | Yes | Yes | 2025-12-04 16:20:23 |  | 2025-12-07 | 2026-02-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-02-19 16:15:42 | Yes | Yes | 2026-02-02 17:54:29 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:39:02 |  | 2025-12-07 | 2025-12-07 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:23:57 | Yes | Yes | 2025-12-07 17:49:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-25 17:30:39 | No | No |  | 25-Nov-2025 Add AAU5246 sector A Remove AAU3940 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B103A_2025 Capacity Expansion Ph3_EXP_BKK | KAN KHEKA BANG PHLI1_4 |  |  |  |  | 2025-10-03 | 2025-10-03 | 2025-10-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-03 10:03:34 | No | No |  |  |  | 2025-10-16 | 2025-10-21 | 2025-10-24 | V Contribute Co., Ltd | N/A | Closed | 2025-10-24 11:05:57 | Yes | Yes | 2025-10-24 11:05:57 |  | 2025-10-09 | 2025-10-09 | Chonradee Suwapan | Approved | Closed | 2025-10-31 16:11:34 | Yes | Yes | 2025-10-09 18:27:17 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-11-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:27 | Yes | Yes | 2025-11-06 12:14:46 |  | 2025-10-09 | 2025-10-09 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-09 20:48:34 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-02 18:48:58 | No | No |  | 2-Oct-2025 Add RRU5516 (700900) SA Add Ant smallcell 12 port No Ret Add g2 remove d6 0/3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-02 |  | N/A | Not assigned |  | No | No
B105A_2025 Capacity Expansion Ph5_EXP_BKK | KAN KHEKA BANG PHLI1_6 | [5 empty] | 2025-12-02 | 2025-12-02 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  |  | 2025-11-26 | 2025-11-27 | 2025-11-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-28 10:47:18 | Yes | Yes | 2025-11-28 10:47:18 |  | 2025-12-04 | 2025-12-04 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-16 15:59:15 | Yes | Yes | 2025-12-04 19:37:51 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 14:22:18 |  | 2025-12-04 | 2025-12-04 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:23:57 | Yes | Yes | 2025-12-04 19:35:29 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-25 17:30:19 | No | No |  | 25-Nov-2025 Add AAU5246 sector A Remove AAU3940 5/5 85 106 dea cell 126 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B108A_2025 Capacity Expansion Ph5_EXP_BKK | KAN KHEKA BANG PHLI1_9 | [5 empty] | 2025-12-05 | 2025-12-05 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  |  | 2025-11-26 | 2025-11-28 | 2025-12-01 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-01 11:02:51 | Yes | Yes | 2025-12-03 13:09:28 |  | 2025-12-07 | 2025-12-07 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-27 09:26:03 | Yes | Yes | 2025-12-08 11:29:54 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:39:20 |  | 2025-12-07 | 2025-12-07 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:23:57 | Yes | Yes | 2025-12-07 23:27:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-26 17:33:26 | No | No |  | 26-11-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg2#， UBBPg3a#， RRU5818 Sec.B#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B160A_2025 Capacity Expansion Ph5_EXP_BKK | Ban Uea Athon Praksa_9 |  |  |  | 2025-11-21 | 2025-11-28 | 2025-11-23 | 2025-11-23 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-11-26 17:26:31 | No | No |  |  | 2025-11-28 | 2025-11-30 | 2025-11-22 | 2025-11-24 | Teloneer Company Limited | N/A | Closed | 2025-11-24 15:09:14 | Yes | Yes | 2025-11-24 16:42:52 |  |  | 2025-11-25 | Apichart Kampuang | Approved | Closed | 2025-12-15 14:40:35 | Yes | Yes | 2026-01-03 10:48:10 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 14:23:32 |  | 2025-11-20 | 2025-11-20 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:24:43 | Yes | Yes | 2025-11-21 15:24:28 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-21 18:40:28 | No | No |  | 21-Nov-2025 Replace BBU5900 UMPTg2 Add GPS g3a g2 Add AAU5246 SA Remove AAU3940 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B182A_2025 Capacity Expansion Ph5_EXP_BKK | Ban Uea Athon samutprakarn_1_2 |  |  |  | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-19 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-12-19 13:10:27 | No | No |  |  |  | 2025-11-20 | 2025-12-19 | 2025-12-20 | Teloneer Company Limited | N/A | Closed | 2025-12-20 15:01:55 | Yes | Yes | 2025-12-22 09:55:30 |  |  | 2025-12-22 | Apichart Kampuang | Approved | Closed | 2026-01-09 17:03:57 | Yes | Yes | 2025-12-23 12:05:31 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 10:25:07 |  |  | 2025-12-05 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:23:57 | Yes | Yes | 2025-12-05 09:04:02 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-08 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-08 17:40:06 | No | No |  | 08-12-2025. Add UBBPg2#， RRU5818 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B208A_2025 Capacity Expansion Ph5_EXP_BKK | SOI SUKSAWAT 78_1 |  |  |  |  | 2025-12-25 | 2025-12-25 | 2025-12-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-25 15:32:50 | No | No |  |  |  | 2025-12-28 | 2025-12-26 | 2025-12-27 | V Contribute Co., Ltd | N/A | Closed | 2025-12-27 15:57:23 | Yes | Yes | 2025-12-27 15:57:24 |  | 2026-01-20 | 2026-01-20 | Chonradee Suwapan | Approved | Closed | 2026-02-24 10:33:37 | Yes | Yes | 2026-02-26 10:16:24 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:40:06 |  | 2026-01-20 | 2026-01-20 | Chonradee Suwapan | Approved | Closed | 2026-01-29 17:09:02 | Yes | Yes | 2026-01-20 22:55:35 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-25 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-25 18:11:52 | No | No |  | 25-12-2025. Add RRU5818 Sec.C Co Sec.A //16-Dec-2025 Prework wait core optic |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B215A_2025 Capacity Expansion Ph5_EXP_BKK | SUKSAWAT 76_3 |  |  |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-15 18:16:03 | No | No |  |  |  | 2025-12-28 | 2025-12-20 | 2025-12-22 | V Contribute Co., Ltd | N/A | Closed | 2025-12-22 09:42:38 | Yes | Yes | 2025-12-22 09:42:38 |  | 2025-12-20 | 2025-12-20 | Chonradee Suwapan | Approved | Closed | 2026-01-06 15:54:30 | Yes | Yes | 2026-01-15 11:50:50 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 14:24:45 |  | 2025-12-20 | 2025-12-20 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:15:07 | Yes | Yes | 2026-01-15 21:11:00 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-15 16:37:52 | No | No |  | 15-Dec-2025 Add RRU5818 Sector A Add RRU3962 sector A Remove AAU3940 Add Ant 12port No Ret Add g3a g2 Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B222A_2025 Capacity Expansion Ph5_EXP_BKK | SOI ATTASIT (TOT POLE) | 2025-12-04 |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 16:36:35 | No | No |  |  |  | 2025-12-28 | 2025-12-27 | 2026-01-07 | V Contribute Co., Ltd | N/A | Closed | 2026-01-07 15:02:31 | Yes | Yes | 2026-01-07 15:02:32 |  | 2026-01-07 | 2026-01-07 | Chonradee Suwapan | Approved | Closed | 2026-03-16 17:56:27 | Yes | Yes | 2026-02-24 15:08:20 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-03-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:40:29 |  | 2026-01-07 | 2026-01-07 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:02:00 | Yes | Yes | 2026-01-07 22:35:10 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-04 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-12-04 19:05:46 | No | No |  | 6-Jan-2026 Add GPS 2025-12-04_Replace to BBU5900 by UMPTg2#， Add UBBPg3#， UBBPg2#， Add RRU5818 Sector B co sith Sector A#， Replace Ant to 12 port Sector A(No RET) ***Waiting GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B271A_2025 Capacity Expansion Ph5_EXP_BKK | TOT Pole Moo Ban Bang plee Noi | [5 empty] | 2025-12-07 | 2025-12-07 | Teloneer Company Limited | N/A | Closed | 2025-12-12 10:30:00 | No | No |  |  |  | 2025-11-20 | 2025-12-08 | 2025-12-09 | Teloneer Company Limited | N/A | Closed | 2025-12-09 15:34:56 | Yes | Yes | 2025-12-09 15:37:43 |  |  | 2025-12-09 | Apichart Kampuang | Approved | Closed | 2025-12-18 09:25:15 | Yes | Yes | 2025-12-09 15:36:04 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:32 | Yes | Yes | 2026-01-09 14:25:58 |  | 2025-12-05 | 2025-12-05 | Khathahat Sitthihong(Teloneer Company Limited) | Approved | Closed | 2026-03-12 10:17:02 | Yes | Yes | 2026-03-04 15:43:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-04 15:40:12 | No | No |  | 4-Dec-2025 Add RRU5818 Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B283A_2025 Capacity Expansion Ph6_EXP_BKK | Thepharak Rd. Small Cell 1 |  |  |  |  | 2025-12-24 | 2025-12-24 | 2025-12-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-24 16:05:44 | No | No |  |  |  | 2025-12-31 | 2025-12-25 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 19:55:50 | Yes | Yes | 2025-12-26 19:55:51 |  | 2026-01-19 | 2026-01-19 | Chonradee Suwapan | Approved | Closed | 2026-01-26 09:12:24 | Yes | Yes | 2026-01-19 22:21:38 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:41:11 |  |  | 2026-01-19 | Chonradee Suwapan | Approved | Closed | 2026-01-29 17:09:02 | Yes | Yes | 2026-01-19 22:26:38 |  |  | 2025-12-31 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  |  | 2025-12-24 | Supatong Juntorn WX1461874 | N/A | Closed | 2025-12-24 17:36:54 | No | No |  | 24-Dec-2025 ADD RRU 5516 SECTOR B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B335A_2025 Capacity Expansion Ph3_EXP_BKK | Uea Arthon Suvarnabhumi1_12 | 2025-09-24 |  |  |  | 2025-11-24 | 2025-11-24 | 2025-11-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:45:54 | No | No |  |  |  | 2025-09-30 | 2025-10-21 | 2025-11-27 | V Contribute Co., Ltd | N/A | Closed | 2025-11-27 18:01:49 | Yes | Yes | 2025-11-27 18:01:50 |  | 2025-11-24 | 2025-11-24 | Chonradee Suwapan | Approved | Closed | 2025-12-04 09:31:09 | Yes | Yes | 2026-01-05 10:26:43 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 10:58:17 |  | 2025-11-24 | 2025-11-24 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-11-24 22:17:29 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-18 17:50:30 | No | No |  | 18-11-2025. Add RRU5818 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-21 |  | N/A | Not assigned |  | No | No
B349A_2025 Capacity Expansion Ph5_EXP_BKK | BANG CHALONG MARKET (TOT POLE) |  |  |  | 2025-12-01 | 2025-12-08 | 2025-12-06 | 2025-12-06 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-12-12 10:30:00 | No | No |  |  |  | 2025-11-20 | 2025-12-04 | 2025-12-05 | Teloneer Company Limited | N/A | Closed | 2025-12-05 11:53:28 | Yes | Yes | 2025-12-08 10:15:28 |  |  | 2025-12-08 | Apichart Kampuang | Approved | Closed | 2025-12-15 09:24:38 | Yes | Yes | 2026-01-13 15:56:32 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 14:29:40 |  | 2025-11-30 | 2025-11-30 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:24:43 | Yes | Yes | 2025-11-30 23:42:28 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-02 16:21:00 | No | No |  | 2-Dec-2025 Add RRU5818 *1 Sector AB Replace Ant 12port No Ret Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B461A_2025 Capacity Expansion Ph2_EXP_BKK | Observation Juvenile Protection | [5 empty] | 2025-10-18 | 2025-10-18 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-09-22 | 2025-10-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-08 17:13:56 | Yes | Yes | 2025-10-08 17:13:57 |  | 2025-10-20 | 2025-10-20 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-27 16:54:48 | Yes | Yes | 2026-01-05 10:50:58 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:28 | Yes | Yes | 2025-10-29 15:26:15 |  | 2025-10-20 | 2025-10-20 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-28 14:33:42 | No | Yes | 2025-10-20 10:20:29 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-22 17:31:04 | No | No |  | 22-09-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， AIRU5636w Sec.A#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-17 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
B472A_2025 Capacity Expansion Ph3_EXP_BKK | Soi Thetsaban Bang Pu 69 Small Cell | 2025-09-29 |  |  |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-04 11:05:56 | No | No |  |  |  | 2025-10-09 | 2025-10-17 | 2025-10-17 | V Contribute Co., Ltd | N/A | Closed | 2025-10-17 17:45:53 | Yes | Yes | 2025-10-17 17:45:54 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-17 17:04:36 | Yes | Yes | 2025-11-08 17:53:49 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Krittee Chamboot 00319410 | Approved | Closed | 2026-04-09 20:35:22 | Yes | Yes | 2025-12-01 15:05:25 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-11-08 16:43:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-04 10:34:53 | No | No |  | 4-Nov-2025 Add RRU5818 Sector A 29-09-2025. ***Need RRU5818 Sec.A //Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-11-03 |  | N/A | Not assigned |  | No | No
B482A_2025 Capacity Expansion Ph5_EXP_BKK | THEPHARAK ROAD STATION 4 |  |  |  | 2025-12-09 | 2025-12-16 | 2025-12-19 | 2025-12-19 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-12-19 13:10:27 | No | No |  |  |  | 2025-11-20 | 2025-12-22 | 2025-12-23 | Teloneer Company Limited | N/A | Closed | 2025-12-23 20:51:17 | Yes | Yes | 2025-12-23 20:57:13 |  |  | 2026-02-11 | Apichart Kampuang | Approved | Closed | 2026-03-12 11:38:11 | Yes | Yes | 2026-02-11 13:29:11 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:42:20 |  | 2025-12-08 | 2025-12-08 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:23:08 | Yes | Yes | 2025-12-09 09:29:10 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-12 18:10:59 | No | No |  | 12-Dec-2025 Clear Alarm VSWR 11-Dec-2025 ***Pending VSWR ///Add RRU5818 sector B Add g2 remove d5 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B527A_2025 Capacity Expansion Ph3_EXP_BKK | KINGKAEW ROAD MICRO CELL STATION 1 | 2025-09-10 |  | Install & Integrate | 2026-01-28 | 2026-01-28 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  |  | 2025-09-30 | 2025-11-19 | 2025-11-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-11-19 19:34:10 | Yes | Yes | 2026-04-20 13:41:31 |  | 2026-05-07 | 2026-05-07 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-05-27 16:31:59 | Yes | Yes | 2026-05-15 10:59:50 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-05-28 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:05 | Yes | Yes | 2026-07-14 22:39:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-03-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-11 17:32:23 | No | No |  | 11-Mar-2026 Add RRU5516 Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Install 100% wait core fiber |  | 2026-01-27 |  | N/A | Not assigned |  | No | No
B540A_2025 Capacity Expansion Ph5_EXP_BKK | SMALL CELL KHLONG BANGPLI NOI STATION 2 |  |  |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-09 17:08:37 | No | No |  |  |  | 2025-12-28 | 2025-12-18 | 2025-12-19 | V Contribute Co., Ltd | N/A | Closed | 2025-12-19 09:46:12 | Yes | Yes | 2025-12-19 09:46:12 |  | 2025-12-11 | 2025-12-11 | Chonradee Suwapan | Approved | Closed | 2026-04-08 16:59:37 | Yes | Yes | 2026-04-02 15:59:56 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-04-12 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2025-12-11 | 2025-12-11 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-11 15:30:22 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-02 16:20:41 | No | No |  | 2-Dec-2025 Add RRU5818 Sector A Add RRU3962 Sector A Remove AAU5942 Add Ant 12port No Ret Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B564A_2025 Capacity Expansion Ph3_EXP_BKK | SMALL CELL KEHA BANG PLI 3 SOI 9 | [5 empty] | 2025-10-13 | 2025-10-13 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-15 | 2025-10-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-15 14:13:14 | Yes | Yes | 2025-10-29 10:57:38 |  | 2025-10-22 | 2025-11-03 | Kontira Kowapradit | Approved | Closed | 2025-11-17 17:05:33 | Yes | Yes | 2025-11-03 09:29:50 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:22 | Yes | Yes | 2025-12-01 15:06:44 |  | 2025-11-15 | 2025-11-15 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:25:38 | No | Yes | 2025-11-15 11:41:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-14 16:07:45 | No | No |  | 14-Oct-2025 Add RRU5818 SB Add g3a Remove d5 (เป็น BBU5900 แล้ว) 5/0 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
B582A_2025 Capacity Expansion Ph2_EXP_BKK | SMALL CELL CITY PARK BANG PHLI - 2 |  |  |  |  | 2025-09-11 | 2025-09-11 | 2025-09-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-11 16:50:09 | No | No |  |  |  | 2025-09-30 | 2025-09-23 | 2025-09-23 | V Contribute Co., Ltd | N/A | Closed | 2025-09-23 21:28:31 | Yes | Yes | 2025-09-23 21:28:32 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:44:55 | Yes | Yes | 2025-09-18 20:00:48 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:57 | Yes | Yes | 2025-10-06 14:52:47 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 21:27:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-11 18:53:44 | No | No |  | 2025-09-11_Replace to BBU5900 by UMPTg2#， Add GPS#， UBBPg3a#， RRU5818 Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-10 |  | N/A | Not assigned |  | No | No
B586A_2025 Capacity Expansion Ph3_EXP_BKK | SMALL CELL CITY PARK BANG PHLI 5 |  |  |  |  | 2025-11-18 | 2025-11-18 | 2025-11-18 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-21 12:25:28 | No | No |  |  |  | 2025-10-17 | 2025-10-24 | 2025-10-27 | V Contribute Co., Ltd | N/A | Closed | 2025-10-27 17:37:13 | Yes | Yes | 2025-10-27 17:37:14 |  | 2025-11-24 | 2025-11-24 | Chonradee Suwapan | Approved | Closed | 2025-12-23 09:40:52 | Yes | Yes | 2026-01-05 11:48:34 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:00 | Yes | Yes | 2026-03-19 14:42:51 |  | 2025-11-24 | 2025-11-24 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-11-24 22:18:03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-18 17:50:30 | No | No |  | 18-11-2025. Add AIRU5246 Sec.B //03-10-2025. Add UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 80% ยังไม่่มี core OSP ตามแผน |  | 2025-11-17 |  | N/A | Not assigned |  | No | No
B593A_2025 Capacity Expansion Ph6_EXP_BKK | HOR PAK URAIRAT | 2025-12-04 |  |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-04 18:19:04 | No | No |  |  |  | 2025-12-31 | 2025-12-19 | 2025-12-20 | V Contribute Co., Ltd | N/A | Closed | 2025-12-20 13:58:45 | Yes | Yes | 2025-12-20 13:58:46 |  | 2025-12-10 | 2025-12-10 | Chonradee Suwapan | Approved | Closed | 2025-12-19 17:39:21 | Yes | Yes | 2025-12-10 20:08:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-15 10:28:47 |  | 2025-12-10 | 2025-12-10 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-10 20:37:01 |  |  | 2025-12-31 | 2025-12-04 | V Contribute Co., Ltd | N/A | Closed | 2025-12-04 14:53:18 | No | No |  |  |  |  | 2025-12-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-04 15:40:51 | No | No |  | 4-Dec-2025 Add RRU5256 (1800-2100) Sector B Remove RRU5507 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B636A_2025 Capacity Expansion Ph2_EXP_BKK | SAMUT PRAKAN PAO. |  |  |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-17 16:18:56 | No | No |  |  |  | 2025-09-30 | 2025-09-26 | 2025-09-30 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 17:08:11 | Yes | Yes | 2025-09-30 17:08:12 |  | 2025-11-20 | 2025-11-20 | Chonradee Suwapan | Approved | Closed | 2025-12-03 09:56:01 | Yes | Yes | 2025-11-20 22:30:13 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:00:45 |  | 2025-11-20 | 2025-11-20 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-20 22:45:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-17 14:39:24 | No | No |  | 17-Nov-2025 Add RRU5516 (18002100) SB Add Ant 12 port No Ret (87) 2/1 13-Sep-2025 ***Pending Add RRU5516 (18002100) SB (82) Add Ant 12 port // Add RRU5516 (18002100) SA Replace RRU3962 (81) Replace Ant 4 port No RET Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-11-14 |  | N/A | Not assigned |  | No | No
B654A_2025 Capacity Expansion Ph3_EXP_BKK | BAN UEA ATHON MUEANG MAI BANG PHLI BUILDING 38 | [5 empty] | 2025-09-21 | 2025-09-21 | Akhom Srinara | N/A | Closed | 2025-09-25 13:58:15 | No | No |  |  |  |  | 2025-09-18 | 2025-09-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-21 19:36:05 | Yes | Yes | 2025-09-23 10:50:09 |  | 2025-09-23 | 2025-09-23 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-20 16:38:49 | Yes | Yes | 2025-09-23 16:33:34 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:14:45 |  | 2025-09-23 | 2025-09-23 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-23 15:09:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-19 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-19 17:39:44 | No | No |  | 19-09-2025. Add RRU3953#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-21 | Jia Rui 80023782 | N/A | Closed | 2025-10-20 17:44:05 | No | No
B658A_2025 Capacity Expansion Ph3_EXP_BKK | BAN UEA ATHON MUEANG MAI BANG PHLI BUILDING 59 | [5 empty] | 2025-09-22 | 2025-09-22 | Akhom Srinara | N/A | Closed | 2025-09-25 13:58:15 | No | No |  |  |  |  | 2025-09-19 | 2025-09-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-21 18:44:31 | Yes | Yes | 2025-09-23 10:21:03 |  | 2025-09-24 | 2025-09-24 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-21 23:21:03 | Yes | Yes | 2025-09-24 16:36:39 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-27 16:18:12 |  | 2025-09-24 | 2025-09-24 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-24 16:38:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-19 18:05:51 | No | No |  | 19-Sep-2025 Add RRU3953 SA Add Ant 12port No RET 18-Sep-2025 ***Pending Add RRU3953 SA ///Add g3a Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-22 | Jia Rui 80023782 | N/A | Closed | 2025-10-21 18:28:30 | No | No
B663A_2025 Capacity Expansion Ph7_EXP_BKK | Siriphand Stationery Suksawat |  |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-11 10:38:08 | No | No |  |  |  | 2026-01-31 | 2026-02-10 | 2026-02-10 | V Contribute Co., Ltd | N/A | Closed | 2026-02-10 19:52:09 | Yes | Yes | 2026-02-10 19:52:09 |  | 2026-02-10 | 2026-02-10 | Chonradee Suwapan | Approved | Closed | 2026-06-09 09:10:49 | Yes | Yes | 2026-05-29 01:49:40 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-01 | 2026-06-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-10 | 2026-02-10 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:36 | Yes | Yes | 2026-02-10 20:58:26 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-28 14:38:04 | No | No |  | 28-Jan-2026 Add RRU5818 SA Co SB Add g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B743M_2025 Capacity Expansion Ph6_EXP_BKK | BAN PRUKSA 74/3 | [5 empty] | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:42:22 | No | No |  |  |  | 2025-12-12 | 2025-12-13 | 2025-12-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-15 16:11:37 | Yes | Yes | 2025-12-22 15:10:46 |  | 2026-01-05 | 2026-01-08 | Aomchun Jittreemit | Approved | Closed | 2026-01-21 09:26:16 | Yes | Yes | 2026-01-08 10:30:42 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:43:50 |  | 2025-12-22 | 2025-12-22 | Aomchun Jittreemit | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2025-12-22 11:39:25 |  |  | 2025-12-31 | 2025-12-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-12 14:27:40 | No | No |  |  |  |  | 2025-12-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-12 18:11:48 | No | No |  | 12-Dec-2025 Add RRU5526 (1800-2100) S1 S2 S3 Remove RRU5507*3 Replace Ant 8port S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B743M_2025 Coverage Expansion Ph2_EXP_BKK | BAN PRUKSA 74/3 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-09 | 2025-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-10 10:51:33 | Yes | Yes | 2025-08-14 08:40:25 |  | 2025-08-18 | 2025-08-18 | Aomchun Jittreemit | Approved | Closed | 2025-08-22 13:14:50 | Yes | Yes | 2025-08-28 09:54:05 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:14 | Yes | Yes | 2025-08-26 17:45:56 |  | 2025-09-04 | 2025-09-04 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 11:34:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-09 18:06:38 | No | No |  | 09-08-2025. Add RRU3953#， Replace Ant.8 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
B77AB_2025 Coverage Expansion Ph1_EXP_BKK | THE BASE SUKHUMVIT 77 | 2025-09-04 |  |  |  | 2025-09-04 | 2025-09-19 | 2025-09-19 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-26 | 2025-09-18 | 2025-09-18 | V Contribute Co., Ltd | N/A | Closed | 2025-09-18 20:08:18 | Yes | Yes | 2025-09-18 20:08:18 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-10-10 14:08:42 | Yes | Yes | 2025-09-20 20:08:56 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:27 | Yes | Yes | 2025-11-06 12:20:56 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:06:10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-04 17:21:51 | No | No |  | 4-Sep-2025 Replace Ant to Ant 4x4H Small Cell Vertical Dual Beam Sector A No Config RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-18 |  | N/A | Not assigned |  | No | No
BAIMM_2025 Capacity Expansion NW Modernization_EXP_BKK | BEL-AIRE BANGKOK HOTEL (MACRO) |  |  |  | 2026-02-06 | 2026-02-14 | 2026-02-23 | 2026-02-23 | Akhom Srinara | N/A | Closed | 2026-02-23 17:44:36 | No | No |  |  | 2026-02-06 | 2026-02-14 | 2026-02-16 | 2026-02-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-02-18 15:12:17 | Yes | Yes | 2026-03-11 15:13:26 |  | 2026-03-22 | 2026-03-22 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-09-04 20:28:41 | Yes | Yes | 2026-03-22 19:48:35 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-04-08 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-06-21 | 2026-06-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-22 20:47:07 | Yes | Yes | 2026-06-21 03:40:30 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-07 18:27:14 | No | No |  | 7-Feb-2026 Add Add AAU5768 S2 S3 S2 Remove RRU5516 *1 Remove RRU5507*2 S3 Remove RRU5507*3 Add g3a 1 Remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BBDBM_2025 Capacity Expansion NW Modernization_EXP_BKK | BBD BUILDING ( RAMA 4 )_3G2100 |  |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-07 07:32:17 | No | No |  |  |  | 2026-02-19 | 2026-02-23 | 2026-02-23 | V Contribute Co., Ltd | N/A | Closed | 2026-02-23 17:16:09 | Yes | Yes | 2026-02-23 17:16:10 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-13 15:43:05 | Yes | Yes | 2026-02-26 15:08:16 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:56:40 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-05 22:23:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-21 19:27:06 | No | No |  | 30-01-2026 Add card g2 Done 21-01-2026 AAU 5768 DMM sector 1#，2#，3 Done 20-Jan-2026 ***Pending Add Add g3a Remove d5 Add AAU5768 S1 S2 S3 Remove RRU5507 S1 *4 S2 *2 S3 *4 // Replace Ant 12 port No RET Sector G Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BBK2M_2025 Coverage Expansion Ph2_EXP_BKK | BANGBO-KLONGDAN ROAD STATION 2 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-09 | 2025-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-10 12:37:38 | Yes | Yes | 2025-08-13 14:48:38 |  | 2025-08-18 | 2025-08-18 | Muhamadnase Chesamae | Approved | Closed | 2025-08-22 13:14:50 | Yes | Yes | 2025-08-18 11:33:13 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:14 | Yes | Yes | 2025-08-26 17:48:42 |  | 2025-09-04 | 2025-09-04 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 14:49:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-09 16:49:53 | No | No |  | 9-Aug-2025 Add RRU3953 S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
BCCPM_2025 Capacity Expansion NW Modernization_EXP_BKK | THE BANGKOK CHRISTIAN HOSPITAL CAR PARK MACRO |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 16:26:40 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-28 | 2026-01-29 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-29 17:50:02 | Yes | Yes | 2026-02-03 09:27:49 | SQC Close | 2026-02-05 | 2026-02-05 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-26 17:54:56 | Yes | Yes | 2026-02-26 15:51:25 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:56:59 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:55:44 | Yes | Yes | 2026-08-01 21:16:38 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-14 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-14 16:43:26 | No | No |  | 14 Jan 2026 swop rru 3962 to 5526 sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BCD2M_2025 Coverage Expansion Ph2_EXP_BKK | Soi Baen Chado 2 | [5 empty] | 2025-08-19 | 2025-08-19 | Palagon Prommueangma | N/A | Closed | 2025-08-19 16:38:33 | No | No |  |  | 2025-08-14 | 2025-08-16 | 2025-08-23 | 2025-08-23 | Teloneer Company Limited | N/A | Closed | 2025-08-23 17:56:53 | Yes | Yes | 2025-08-25 15:42:03 |  | 2025-08-21 | 2025-08-29 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2025-09-02 17:20:53 | Yes | Yes | 2025-10-14 09:51:34 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:12 | Yes | Yes | 2025-09-04 09:55:28 |  |  | 2025-08-12 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:08 | No | Yes | 2025-08-12 14:00:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-15 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-15 17:34:49 | No | No |  | 2025-08-15_Add RRU3953#， Replace to Ant 4 port Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-18 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 06:02:16 | No | No
BCD3M_2025 Coverage Expansion Ph2_EXP_BKK | Soi Baen Chado 3 | [5 empty] | 2025-08-19 | 2025-08-19 | Palagon Prommueangma | N/A | Closed | 2025-08-19 16:38:33 | No | No |  |  | 2025-08-13 | 2025-08-16 | 2025-08-23 | 2025-08-23 | Teloneer Company Limited | N/A | Closed | 2025-08-23 13:55:19 | Yes | Yes | 2025-08-25 15:42:49 |  | 2025-08-20 | 2025-08-29 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2025-09-02 17:20:53 | Yes | Yes | 2025-10-14 09:52:39 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:12 | Yes | Yes | 2025-09-04 09:56:48 |  |  | 2025-08-12 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:08 | No | Yes | 2025-08-12 14:01:20 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-13 19:10:33 | No | No |  | 13-Aug-2025 Add RRU3953 S3 Replace Ant. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-18 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 06:02:16 | No | No
BCHFG_2025 Capacity Expansion Ph7_EXP_SR | Ban Chiao Fueang |  |  |  |  | 2025-12-25 | 2026-01-05 | 2026-01-05 | Teloneer Company Limited | N/A | Closed | 2026-01-05 15:49:42 | No | No |  |  |  | 2025-12-08 | 2026-01-05 | 2026-01-05 | Teloneer Company Limited | N/A | Closed | 2026-01-05 16:59:33 | Yes | Yes | 2026-01-06 19:13:23 |  | 2026-01-06 | 2026-01-06 | Nattawoot Suwan | Approved | Closed | 2026-01-26 10:02:05 | Yes | Yes | 2026-01-07 15:39:42 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-14 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:32 | Yes | Yes | 2026-01-15 10:38:47 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-07 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-05 | Suthee Khamhom WX1452991 | N/A | Closed | 2026-01-05 17:03:17 | No | No |  | 05 Jan 2026 Replace BBU5900#， ADD UBBPg3a slot 5#， Add AAU5636w Sector 3#， Add GPS. |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-24 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-24 16:49:10 | Yes | Yes | 2025-12-24 16:04:55 |  |  | 2026-03-31 | Boonchot Boriwut | N/A | Closed | 2026-03-31 11:34:14 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BCI1M_2025 Capacity Expansion Ph3_EXP_BKK | BANG CHALONG NAI 1 | 2025-08-29 |  |  |  | 2025-08-30 | 2025-08-30 | 2025-08-30 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-30 09:04:17 | No | No |  |  |  | 2025-09-05 | 2025-09-08 | 2025-09-09 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:12:16 | Yes | Yes | 2025-09-30 10:12:17 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-10-10 22:26:44 | Yes | Yes | 2025-09-12 21:12:55 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:22 | Yes | Yes | 2025-12-01 15:24:43 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-12 22:21:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-29 19:46:21 | No | No |  | 29-Aug-2025 Add RRU5516 (1800-2100) S6 Add Ant 8port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-28 |  | N/A | Not assigned |  | No | No
BCI1M_2025 Capacity Expansion Ph6_EXP_BKK | BANG CHALONG NAI 1 |  |  |  |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-18 11:47:42 | No | No |  |  |  | 2025-12-31 | 2025-12-23 | 2025-12-23 | V Contribute Co., Ltd | N/A | Closed | 2025-12-23 20:16:38 | Yes | Yes | 2025-12-23 20:16:38 |  | 2025-12-20 | 2025-12-20 | Chonradee Suwapan | Approved | Closed | 2026-03-23 16:15:41 | Yes | Yes | 2026-01-15 17:17:55 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-03-24 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2025-12-20 | 2025-12-20 | Chonradee Suwapan | Approved | Closed | 2026-01-07 15:01:03 | Yes | Yes | 2026-01-07 10:13:24 |  |  | 2025-12-31 | 2025-12-16 | V Contribute Co., Ltd | N/A | Closed | 2025-12-16 15:26:20 | No | No |  |  |  |  | 2025-12-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-16 18:22:59 | No | No |  | 16-Dec-2025 Add AAU5636w sector 6 Add g3a remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BFBSC_2025 Capacity Expansion Ph2_EXP_SR | Ban Bangfaeb School |  |  |  | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-26 09:55:35 | No | No |  |  |  | 2025-08-23 | 2025-08-23 | 2025-09-23 | Teloneer Company Limited | N/A | Closed | 2025-09-23 18:11:16 | Yes | Yes | 2025-09-25 13:38:17 |  | 2025-09-26 | 2025-09-26 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2025-10-08 07:27:58 | Yes | Yes | 2025-09-30 21:23:40 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:18:25 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-09-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-21 | 2025-09-23 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-09-23 17:42:01 | No | No |  | add g3 (plan g3a) slot 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-21 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
BGNRM_2025 Capacity Expansion Ph6_EXP_ER | Bueng Nam Rak Moo 11 | 2025-11-22 | THCP_Wachira.s | Clear Pending |  | 2025-11-30 | 2025-11-21 | 2025-11-21 | Teloneer Company Limited | N/A | Closed | 2025-11-21 17:54:20 | No | No |  |  |  | 2025-11-30 | 2025-11-28 | 2025-12-01 | Teloneer Company Limited | N/A | Closed | 2025-12-01 11:12:07 | Yes | Yes | 2025-12-03 19:55:05 |  | 2025-11-30 | 2025-12-03 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-04 15:50:52 | Yes | Yes | 2025-12-03 23:59:31 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:32 | Yes | Yes | 2026-01-09 14:49:21 |  | 2025-11-30 | 2025-11-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-25 18:20:01 | Yes | Yes | 2025-11-22 13:20:47 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-21 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-21 18:39:34 | No | No |  | "**waiting on-service LNR26 -- Add UBBPg2 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R L_3 New L26F5 + NR26 (New AAU5636w) N_3 --> subcon install 5639w" |  | 2025-12-01 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-01 17:57:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BGNUM_2025 Coverage Expansion Ph2_EXP_BKK | BANG PHO NUEA | 2025-08-12 |  | Install & Integrate | 2025-08-12 | 2025-08-31 | 2025-08-12 | 2025-08-12 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2025-08-13 11:59:22 | No | No |  |  | 2025-08-15 | 2025-08-15 | 2025-08-12 | 2025-08-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-08-12 15:42:37 | Yes | Yes | 2025-08-13 15:19:52 |  | 2025-08-16 | 2025-08-22 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-08-29 16:53:28 | Yes | Yes | 2025-10-27 14:58:40 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:56 | Yes | Yes | 2025-10-06 15:23:22 |  | 2025-08-09 | 2025-08-09 | Sattaya Parakij | Approved | Closed | 2025-09-03 22:41:31 | No | Yes | 2025-08-09 00:25:58 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-12 17:52:26 | No | No |  | 12-08-2025. Add RRU3953 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-12 | 2025-08-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
BHTAG_2025 Coverage Expansion Ph1_New_SR | Ban To Tang 1 |  |  |  | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | Teloneer Company Limited | N/A | Closed | 2026-03-16 10:30:04 | No | No |  |  | 2026-03-12 | 2026-03-15 | 2026-03-14 | 2026-03-15 | Teloneer Company Limited | N/A | Closed | 2026-03-15 11:23:17 | Yes | Yes | 2026-03-17 20:20:02 |  | 2026-03-17 | 2026-03-17 | Nattawoot Suwan | Approved | Closed | 2026-03-19 08:10:45 | Yes | Yes | 2026-03-19 11:50:36 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-04-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:03 | Yes | Yes | 2026-04-09 11:30:45 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-03-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-03-14 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-03-14 17:28:22 | No | No |  | BBU3910#， UBBPd5*3 S1 > 3839 > Ant 4 port S2 > 3839 > Ant 4 port S3 > 3839 > Ant 4 port Test Done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-22 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 21:09:58 | Yes | Yes | 2026-01-22 15:17:47 |  |  | 2026-06-08 | Nattawoot Suwan | N/A | Closed | 2026-06-08 18:40:05 | No | No |  |  |  |  | 2026-03-11 | 2026-03-12 | Teloneer Company Limited | N/A | Closed | 2026-03-31 19:14:08 | No | No
BHUYM_2025 Capacity Expansion Ph2_EXP_ER | Ban Huayaca | 2025-08-06 |  | Clear Pending |  | 2025-08-31 | 2025-08-06 | 2025-08-06 | Teloneer Company Limited | N/A | Closed | 2025-08-06 17:16:01 | No | No |  |  |  | 2025-08-31 | 2025-08-09 | 2025-08-16 | Teloneer Company Limited | N/A | Closed | 2025-08-16 09:57:26 | Yes | Yes | 2025-08-21 19:37:52 |  | 2025-08-31 | 2025-09-12 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-18 15:00:39 | Yes | Yes | 2025-09-12 15:57:03 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-12-31 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:18 | Yes | Yes | 2025-09-22 17:17:37 |  | 2025-08-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:16:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-18 |  | 2025-08-05 | Reungsak Junkong 00927496 | N/A | Closed | 2025-08-05 19:27:02 | No | No |  | Add UBBPg3a #，New L26F1F5 + NR26 (New AAU5636w)x2 S1#，7 |  | 2025-08-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-08 12:31:24 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIONM_2025 Coverage Expansion Ph2_EXP_BKK | RESEARCH (R BUILDING) MAHIDOL UNIVERSITY | 2025-08-21 |  |  |  | 2025-08-21 | 2025-08-21 | 2025-08-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-21 17:56:59 | No | No |  |  |  | 2025-08-30 | 2025-08-31 | 2025-09-01 | V Contribute Co., Ltd | N/A | Closed | 2025-09-01 09:49:19 | Yes | Yes | 2025-09-01 09:51:38 |  |  | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-09-12 10:23:52 | Yes | Yes | 2025-10-27 17:57:53 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:18 | Yes | Yes | 2025-09-22 17:18:56 |  | 2025-09-05 | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-05 20:37:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-21 18:03:52 | No | No |  | 21-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-20 |  | N/A | Not assigned |  | No | No
BK9BM_2025 Capacity Expansion Ph3_EXP_BKK | BAN KEID 9 BUILDING | [5 empty] | 2025-10-25 | 2025-10-25 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-10 | 2025-10-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-15 11:07:23 | Yes | Yes | 2025-10-15 11:07:23 |  | 2025-10-27 | 2025-10-27 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-05 16:33:10 | Yes | Yes | 2025-10-28 21:25:34 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:27 | Yes | Yes | 2025-11-06 12:32:56 |  | 2025-10-27 | 2025-10-27 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-28 14:33:42 | No | Yes | 2025-10-27 16:23:33 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-09 18:26:53 | No | No |  | 09-10-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， RRU3953#， RRU5818#， Sec.A#， C#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
BK9BM_2025 Capacity Expansion Ph5_EXP_BKK | BAN KEID 9 BUILDING | [5 empty] | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:39:59 | No | No |  |  |  | 2025-12-11 | 2025-12-11 | 2025-12-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-12 19:57:03 | Yes | Yes | 2025-12-24 18:59:48 |  | 2025-12-24 | 2025-12-24 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-06 15:54:30 | Yes | Yes | 2025-12-24 20:53:16 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-09 14:56:40 |  | 2025-12-19 | 2025-12-19 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2025-12-24 12:48:53 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-10 17:43:44 | No | No |  | 10-Dec-2025 Add RRU5818 Sector 2 Replace Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BKE3M_2025 Coverage Expansion Ph2_EXP_BKK | Soi Bang Khae 3 (Bunmi) |  |  |  |  | 2025-09-30 | 2025-09-10 | 2025-09-10 | Subpoa Limsaihua | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  |  | 2025-09-08 | 2025-09-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-16 11:12:57 | Yes | Yes | 2025-10-01 14:57:02 |  | 2025-10-02 | 2025-10-03 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-06 16:50:14 | Yes | Yes | 2025-10-03 15:03:29 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:03 | Yes | Yes | 2025-10-09 19:24:45 |  | 2025-10-03 | 2025-10-03 | Mattura Habayae | Approved | Closed | 2025-11-28 14:33:42 | No | Yes | 2025-10-03 15:04:20 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-08 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-08 17:10:12 | No | No |  | 08-09-2025. Add RRU3953#， Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-09 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 19:41:47 | No | No
BKN4M_2025 Capacity Expansion Ph3_EXP_BKK | BAN KLANG STATION 4 | 2025-08-25 |  |  |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-25 17:13:12 | No | No |  |  |  | 2025-08-31 | 2025-08-27 | 2025-08-28 | V Contribute Co., Ltd | N/A | Closed | 2025-08-28 13:54:25 | Yes | Yes | 2025-08-28 13:55:52 |  | 2025-09-09 | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-18 16:40:10 | Yes | Yes | 2025-09-16 22:07:11 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:18 | Yes | Yes | 2025-09-22 17:29:05 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-09 19:03:29 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-25 18:38:48 | No | No |  | 25-Aug-2025 Add RRU5516 (1800-2100) S2 Remove RRU3962 Reolace Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-22 |  | N/A | Not assigned |  | No | No
BKN4M_2025 Coverage Expansion Ph2_EXP_BKK | BAN KLANG STATION 4 |  |  |  |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-07 17:44:53 | No | No |  |  |  | 2025-08-22 | 2025-08-15 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 09:48:05 | Yes | Yes | 2025-08-15 09:52:14 |  | 2025-08-24 | 2025-08-24 | Chonradee Suwapan | Approved | Closed | 2025-08-26 09:26:48 | Yes | Yes | 2025-08-24 20:44:44 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-27 | 2025-08-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:14 | Yes | Yes | 2025-08-26 17:51:20 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:50:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-07 17:52:12 | No | No |  | 07-08-2025. Add RRU3953#， Ant.4 port Sec.1#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-06 |  | N/A | Not assigned |  | No | No
BKNMI_2025 Capacity Expansion Ph2_EXP_SR | BAAN KUAN NIMITR | [5 empty] | 2025-08-27 | 2025-08-27 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-28 14:34:49 | No | No |  |  |  | 2025-08-24 | 2025-08-25 | 2025-08-25 | Teloneer Company Limited | N/A | Closed | 2025-08-25 15:42:51 | Yes | Yes | 2025-08-26 19:46:45 |  | 2025-08-26 | 2025-09-18 | Supot Hoonyong(Teloneer Company Limited) | Approved | Closed | 2025-09-26 11:47:36 | Yes | Yes | 2025-09-05 10:53:24 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:18 | Yes | Yes | 2025-09-22 17:30:23 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-25 | 2025-08-25 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-08-25 18:37:37 | No | No |  | Onservice cell 1800 ----- Remove AntMB S1 *2 Rep S1 MB > RRU3962(1)#， RRU3826(2) to 5516*1 MB > new Ant Cell 121> 2T2R to 4T4R ***remaining create cell 1800 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-08-27 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-28 14:35:19 | No | No | [5 empty] | 2025-08-26 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
BKP2M_2025 Coverage Expansion Ph2_EXP_BKK | BUENG KHAM PHROI STATION 2 | 2025-08-01 |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-01 17:31:33 | No | No |  |  |  | 2025-08-22 | 2025-08-12 | 2025-08-14 | V Contribute Co., Ltd | N/A | Closed | 2025-08-14 17:50:52 | Yes | Yes | 2025-08-14 17:53:13 |  |  | 2025-08-17 | Chonradee Suwapan | Approved | Closed | 2025-09-30 15:29:15 | Yes | Yes | 2025-08-17 00:46:31 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:56 | Yes | Yes | 2025-10-06 15:33:13 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:50:58 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-01 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-01 17:11:01 | No | No |  | 1-Aug-2025 Add RRU3953 S1 Replace Ant. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
BKPYK_2025 Coverage Expansion Ph1_New_SR | BKPYK |  |  |  | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-17 | Teloneer Company Limited | N/A | Closed | 2025-09-30 19:20:02 | No | No |  |  |  | 2025-09-17 | 2025-09-16 | 2025-09-19 | Teloneer Company Limited | N/A | Closed | 2025-09-19 19:57:00 | Yes | Yes | 2025-09-30 15:57:03 |  | 2025-09-30 | 2025-09-30 | Teloneer Company Limited | Approved | Closed | 2025-10-08 07:27:13 | Yes | Yes | 2025-10-04 09:30:19 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:22:05 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-09-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-17 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-09-17 16:48:16 | No | No |  | 17 Sep 2025 New site add 8RRU3826 BBU3910 4UBBPd5 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-09-12 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-09-12 14:10:54 | Yes | Yes | 2025-09-12 13:07:00 |  |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-16 |  | N/A | Not assigned |  | No | No
BKWNM_2025 Capacity Expansion Ph8_EXP_ER | Ban Bangkhwan | 2026-01-24 |  |  |  | 2026-02-28 | 2026-01-24 | 2026-01-24 | Teloneer Company Limited | N/A | Closed | 2026-01-24 14:01:28 | No | No |  |  |  | 2026-02-28 | 2026-01-23 | 2026-01-25 | Teloneer Company Limited | N/A | Closed | 2026-01-25 16:56:38 | Yes | Yes | 2026-01-26 20:51:15 |  | 2026-02-28 | 2026-01-26 | Apichat fangsantthia(Teloneer Company Limited) | Approved | Closed | 2026-02-10 15:36:08 | Yes | Yes | 2026-01-26 21:57:50 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:58 | Yes | Yes | 2026-03-20 16:22:29 |  | 2026-01-31 | 2026-01-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:16:17 | Yes | Yes | 2026-01-23 15:22:43 |  | 2026-01-24 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-24 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-01-24 18:08:35 | No | No |  | Replace Antenna (Dualband) + ReDirection 90 to 80_BKWNM_H_2 Replace Antenna (Dualband) + ReDirection 160 to 8170_BKWNM_H_3+ 4T4R+ Add RRU5505 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_BKWNM_H_7 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_BKWNM_H_8 |  | 2026-01-24 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-10 10:55:20 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BLTHE_2025 Capacity Expansion Ph2_EXP_SR | Ban Leam Thaen |  |  |  |  | 2025-09-03 | 2025-09-09 | 2025-09-09 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-09 16:31:13 | No | No |  |  |  | 2025-08-23 | 2025-08-24 | 2025-09-03 | Teloneer Company Limited | N/A | Closed | 2025-09-03 18:11:55 | Yes | Yes | 2025-09-17 11:08:54 |  | 2025-09-17 | 2025-09-18 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2025-09-26 09:29:16 | Yes | Yes | 2025-09-23 10:07:00 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:56 | Yes | Yes | 2025-10-06 15:34:30 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-03 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-09-03 16:41:06 | No | No |  | 3 Sep 2025 Add AAU5636m sector1 replace BBU5900 add GPS Pre work |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-08-21 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-08-22 16:08:48 | Yes | Yes | 2025-08-21 17:43:04 |  |  | 2025-09-09 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-09 16:30:47 | No | No | [5 empty] | 2025-09-02 |  | N/A | Not assigned |  | No | No
BMEGM_2025 Coverage Expansion Ph2_EXP_BKK | BANG MAE NANG | 2025-07-31 |  |  |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-07-31 17:04:06 | No | No |  |  |  | 2025-08-22 | 2025-08-02 | 2025-08-03 | V Contribute Co., Ltd | N/A | Closed | 2025-08-03 16:08:32 | Yes | Yes | 2025-08-03 16:09:00 |  | 2025-08-12 | 2025-08-12 | Chonradee Suwapan | Approved | Closed | 2025-08-18 17:06:34 | Yes | Yes | 2025-08-12 20:59:33 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-22 | 2025-08-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:14 | Yes | Yes | 2025-08-26 17:55:19 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:51:13 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-07-31 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-07-31 17:43:19 | No | No |  | 31-07-2025. Add RRU3953 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-30 |  | N/A | Not assigned |  | No | No
BMYIM_2025 Capacity Expansion Ph2_EXP_ER | Ban Mabyai | 2025-07-11 |  | Install & Integrate |  | 2025-07-31 | 2025-07-11 | 2025-07-11 | Teloneer Company Limited | N/A | Closed | 2025-07-11 19:27:17 | No | No |  |  |  | 2025-07-31 | 2025-07-15 | 2025-07-20 | Teloneer Company Limited | N/A | Closed | 2025-07-20 10:52:54 | Yes | Yes | 2025-07-27 13:42:35 |  | 2025-07-31 | 2025-09-15 | Thanakit Chaleechai | Approved | Closed | 2025-09-26 13:58:41 | Yes | Yes | 2025-09-15 14:50:37 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:18 | Yes | Yes | 2025-09-22 17:45:36 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:17:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-29 |  | 2025-07-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-11 18:16:29 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R Sec.3 & Replace Antenna (MB) + 4T4R Sec.6 |  | 2025-07-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-11 18:16:29 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BNHUY_2025 Capacity Expansion Ph6_EXP_SR | Ban Huai Yai |  |  |  |  | 2025-12-25 | 2025-12-13 | 2025-12-13 | Teloneer Company Limited | N/A | Closed | 2025-12-13 14:58:45 | No | No |  |  |  | 2025-12-08 | 2025-12-13 | 2025-12-13 | Teloneer Company Limited | N/A | Closed | 2025-12-13 16:36:35 | Yes | Yes | 2025-12-15 19:47:11 |  | 2025-12-16 | 2025-12-16 | Nattawoot Suwan | Approved | Closed | 2026-01-09 15:44:16 | Yes | Yes | 2025-12-17 16:15:39 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:03 | Yes | Yes | 2026-01-15 10:45:13 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-15 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-13 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-12-13 16:15:00 | No | No |  | Rep BBU5900#，add g3a*1#，add gps Add AAU5636w Sector 2 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-04 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-04 19:12:41 | Yes | Yes | 2025-12-04 17:41:30 |  |  | 2026-03-31 | Boonchot Boriwut | N/A | Closed | 2026-03-31 11:34:14 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BNPHK_2025 Capacity Expansion Ph1_EXP_SR | BAN NAI PHUK HIN KAEO |  |  |  |  | 2025-08-31 | 2025-08-13 | 2025-08-13 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-13 11:45:10 | No | No |  |  |  | 2025-08-04 | 2025-08-09 | 2025-08-09 | Teloneer Company Limited | N/A | Closed | 2025-08-09 14:07:23 | Yes | Yes | 2025-08-12 14:32:59 |  | 2025-08-13 | 2025-09-18 | Supot Hoonyong | Approved | Closed | 2025-09-26 11:47:36 | Yes | Yes | 2025-09-05 10:46:35 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-19 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 17:57:06 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-08-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-09 | 2025-08-09 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-08-09 17:46:23 | No | No |  | Add UBBPd5*1 S4 replace RRU3826(2) to RRU5516 MB > existing Ant Re config cell 124 > 2T2R to 4T4R On -Service Cell 1800 > S4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-08-13 | Nattawoot Suwan | N/A | Closed | 2025-08-13 11:45:49 | No | No |  |  |  |  | 2025-08-13 | 2025-08-12 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
BNWGN_2025 Capacity Expansion Ph2_EXP_SR | BAN WANG NGA |  |  |  |  | 2025-08-28 | 2025-09-09 | 2025-09-09 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-09 16:31:13 | No | No |  |  |  | 2025-08-24 | 2025-08-28 | 2025-08-28 | Teloneer Company Limited | N/A | Closed | 2025-08-28 16:07:06 | Yes | Yes | 2025-08-29 10:25:26 |  | 2025-08-29 | 2025-09-18 | Supot Hoonyong(Teloneer Company Limited) | Approved | Closed | 2025-09-26 11:47:36 | Yes | Yes | 2025-08-29 10:59:41 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-19 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 17:58:21 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-28 | 2025-08-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-08-28 18:08:47 | No | No |  | Onservice cell 1800 ----- Rep S2 MB > RRU3826*2 to 5516*1 MB > existing Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-09-09 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-09 16:30:47 | No | No | [5 empty] | 2025-08-27 |  | N/A | Not assigned |  | No | No
BP23M_2025 Coverage Expansion Ph2_EXP_BKK | SOI BANGPLA 2 STATION 3 | [5 empty] | 2025-08-23 | 2025-08-23 | Palagon Prommueangma | N/A | Closed | 2025-08-25 11:40:23 | No | No |  |  | 2025-08-23 | 2025-08-30 | 2025-08-26 | 2025-08-26 | Teloneer Company Limited | N/A | Closed | 2025-08-26 16:59:42 | Yes | Yes | 2025-08-28 14:29:47 |  |  | 2025-09-02 | Apichart Kampuang | Approved | Closed | 2025-09-08 16:35:17 | Yes | Yes | 2025-10-14 09:53:19 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 17:59:39 |  |  | 2025-08-12 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:08 | No | Yes | 2025-08-12 14:02:44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-23 18:16:46 | No | No |  | 23-Aug-2025 Add RRU3953 S2 Replace Ant.4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-08-27 | Teloneer Company Limited | N/A | Closed | 2025-08-28 14:38:08 | No | No |  |  |  | 100% |  | 2025-08-22 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
BPM2M_2025 Capacity Expansion Ph8_EXP_BKK | BANG PLI MUANG MAI 2 |  |  |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-09 18:10:08 | No | No |  |  |  | 2026-02-28 | 2026-03-26 | 2026-06-15 | V Contribute Co., Ltd | N/A | Closed | 2026-06-15 13:57:07 | Yes | Yes | 2026-06-15 13:57:08 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-07-06 09:43:51 | Yes | Yes | 2026-03-07 19:37:58 | 1.Page 1#，Phase name wrong.(must be 2025 Capacity Expansion Ph8_EXP_BKK) 2.All page Phase name wrong. 3.Page 57#，AIS passport have 3pcs but team member have 2persons. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-22 | 2026-07-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:16:39 | Yes | Yes | 2026-03-07 19:50:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-14 17:32:31 | No | No |  | 14-Feb-2026 Add AAU5636w Sector 6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPM3M_2025 Capacity Expansion Ph7_EXP_BKK | BANG PLI MUANG MAI 3 | 2026-01-19 |  |  |  | 2026-01-19 | 2026-01-19 | 2026-01-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-19 17:59:44 | No | No |  |  |  | 2026-01-31 | 2026-01-22 | 2026-02-19 | V Contribute Co., Ltd | N/A | Closed | 2026-02-19 17:41:19 | Yes | Yes | 2026-02-19 17:42:21 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-02-11 09:26:18 | Yes | Yes | 2026-02-26 16:25:57 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:46:11 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-06 22:50:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-19 17:46:00 | No | No |  | 19-Jan-2026 Add RRU5516 (700900) Sector 2 Replace Ant 4port Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPM4M_2025 Capacity Expansion Ph8_EXP_BKK | BANG PLI MUANG MAI 4 |  |  |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-09 18:10:08 | No | No |  |  |  | 2026-02-28 | 2026-04-15 | 2026-04-19 | V Contribute Co., Ltd | N/A | Closed | 2026-04-19 17:53:22 | Yes | Yes | 2026-04-19 17:53:22 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-07-06 09:43:51 | Yes | Yes | 2026-03-07 19:38:28 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-22 | 2026-07-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:16:39 | Yes | Yes | 2026-03-07 19:51:43 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-14 17:45:28 | No | No |  | 14-02-2026. Add AAU5636w Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPWFM_2025 Capacity Expansion Ph3_EXP_SR | Bue Ri Pat Waterfall |  |  |  |  | 2025-09-01 | 2025-09-09 | 2025-09-09 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-09 16:31:13 | No | No |  |  |  | 2025-09-01 | 2025-09-01 | 2025-09-01 | Teloneer Company Limited | N/A | Closed | 2025-09-01 18:37:10 | Yes | Yes | 2025-09-17 11:07:37 |  | 2025-09-17 | 2025-09-18 | Teloneer Company Limited | Approved | Closed | 2025-09-26 09:29:38 | Yes | Yes | 2025-09-17 15:45:45 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:56 | Yes | Yes | 2025-10-06 15:41:59 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-09-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-01 | 2025-09-01 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-09-01 20:13:20 | No | No |  | On service cell 1800 S3 Rep RRU*3#，Ant*2 S3 MB > RRU3826*2#，RRU3839*1 to 5516*1 MB > New Ant 4 port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-09-09 | Teloneer Company Limited | N/A | Closed | 2025-09-09 16:30:47 | No | No | [5 empty] | 2025-08-29 |  | N/A | Not assigned |  | No | No
BRHPA_2025 Capacity Expansion NW Modernization_EXP_BKK | BANG RAK HOSPITAL |  |  |  |  | 2026-01-19 | 2026-01-19 | 2026-01-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-19 09:12:28 | No | No |  |  |  | 2026-01-31 | 2026-01-30 | 2026-01-30 | V Contribute Co., Ltd | N/A | Closed | 2026-01-30 18:02:01 | Yes | Yes | 2026-01-30 18:02:01 |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-02-17 16:38:08 | Yes | Yes | 2026-02-26 16:33:27 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:59:48 |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-09 21:27:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-17 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-17 20:00:30 | No | No |  | 17 Jan 2026 Replace rru3962 to 5526 sector 1#， replace ant 12 port and no ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRMWM_2025 Coverage Expansion Ph2_EXP_BKK | BANRAKAD-MOTOR WAY | [5 empty] | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-21 | 2025-08-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-21 20:21:36 | Yes | Yes | 2025-08-23 18:09:29 |  | 2025-08-25 | 2025-08-25 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-02 18:23:31 | Yes | Yes | 2025-08-29 10:22:23 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-03-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:46:36 |  | 2025-09-02 | 2025-09-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-02 20:31:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-21 18:02:17 | No | No |  | 21-Aug-2025 Add RRU3953 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Hold เบิกของ 6/8/25 solution เปลี่ยน 14/8/25 แจ้งเบิกของใหม่ |  |  | Jia Rui 80023782 | N/A | Not assigned |  | No | No
BS02B_2025 Capacity Expansion NW Modernization_EXP_BKK | Baan Suan Plu Soi Phatthanasin Nang Linchee 2 Road |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-22 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:19:59 | Yes | Yes | 2026-04-01 10:37:24 |  | 2026-04-17 | 2026-04-17 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 17:39:55 | Yes | Yes | 2026-04-17 14:50:04 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 21:17:08 |  |  | 2026-02-28 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-25 20:32:59 | No | No |  | 25-Feb-2026 Add RRU5526 Sector A B Remove RRU3962 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSCWB_2025 Capacity Expansion Ph5_EXP_BKK | BAAN SUAN CHAENGWATTANA | [5 empty] | 2026-03-24 | 2026-03-24 | Akhom Srinara | N/A | Closed | 2026-04-21 20:48:32 | No | No |  |  |  | 2026-03-27 | 2026-03-22 | 2026-03-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-03-26 19:58:40 | Yes | Yes | 2026-05-06 10:04:49 |  | 2026-05-08 | 2026-05-08 | Aomchun Jittreemit | Approved | Closed | 2026-05-21 16:16:39 | Yes | Yes | 2026-05-15 10:27:58 | 1.Page 8#，In INV upload Board After activity & page 52 upload bbu#，bbp#，fan UMPT #，UPEU model & SN mismatch. 2.Page 8#，In RRU INV coulour fill for Remove UBBP card must be 2pcs. 3.Page 26#，Uploaded BBU left#，Right photo & in QC BBU left#，Right photo mismatch. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-21 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-06-20 | 2026-06-20 | Aomchun Jittreemit | Approved | Closed | 2026-07-20 10:31:34 | Yes | Yes | 2026-06-20 18:29:32 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-17 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-03-17 19:31:56 | No | No |  | 2026-03-17_Replace to BBU5900 by UMPTg2#， Add UBBPg2#， UBBPg3a#， GPS#， RRU5818 Sector A //13-Mar-26 //Pending Replace BBU5900 Add RRU5818 S1 /// Replace Ant S1 12 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSN2M_2025 Coverage Expansion Ph2_EXP_BKK | BANGLEN - SAI NOI (STATION 2) |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  | 2025-08-11 | 2025-08-12 | 2025-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-13 12:29:50 | Yes | Yes | 2025-08-20 11:51:52 | SQC closed. | 2025-08-19 | 2025-08-19 | Aomchun Jittreemit | Approved | Closed | 2025-08-25 17:33:55 | Yes | Yes | 2026-01-04 10:57:29 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 11:06:18 |  | 2025-09-04 | 2025-09-04 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 11:34:57 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-12 17:52:26 | No | No |  | 12-08-2025. Add RRU3953 Sec.1#， 2#， 3#， Replace Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
BSNTM_2025 Capacity Expansion Ph6_EXP_ER | Ban Suan Namtok | 2025-11-27 |  | Install & Integrate |  | 2025-11-30 | 2025-11-27 | 2025-11-27 | Teloneer Company Limited | N/A | Closed | 2025-11-27 13:26:57 | No | No |  |  |  | 2025-11-30 | 2025-11-27 | 2025-11-27 | Teloneer Company Limited | N/A | Closed | 2025-11-27 18:15:59 | Yes | Yes | 2025-12-01 16:15:52 |  | 2025-12-15 | 2025-12-01 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-02 14:49:44 | Yes | Yes | 2025-12-01 19:38:25 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 15:44:11 |  | 2025-11-30 | 2025-11-27 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-28 10:17:28 | Yes | Yes | 2025-11-27 16:10:30 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-27 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-27 16:39:09 | No | No |  | Add UBBPg2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_BSNTM_H_2 Replace RRU5508 to (RRU5516_900) + Co NR07 + 4T4R_BSNTM_L_2 Replace RRU3953 to (RRU5516_900) + Co L07 + Co NR07 + 4T4R_BSNTM_L_3 |  | 2025-12-01 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-01 17:57:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSPHS_2025 Coverage Expansion Ph1_New_SR | Ban Saphan Sai | [5 empty] | 2026-03-08 | 2026-03-09 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2026-03-16 10:32:02 | No | No |  |  |  | 2026-01-05 | 2026-01-05 | 2026-03-15 | Teloneer Company Limited | N/A | Closed | 2026-03-15 12:04:46 | Yes | Yes | 2026-03-17 14:15:49 |  | 2026-03-17 | 2026-03-17 | Teloneer Company Limited | Approved | Closed | 2026-03-19 08:10:48 | Yes | Yes | 2026-03-20 17:42:57 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-04-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:03 | Yes | Yes | 2026-04-09 11:31:03 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-03-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-03-09 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-03-09 14:52:28 | No | No |  | 09 Mar 2026 Clear Alarm Board Hardware Fault //Rep Card UBBPd5#， Rep RRU3826 Sector 1.1 Test Done ------------------- ***Pending Rep card UBBPd5/test alarm BBU3910#，UBBPd5*4 S1 > RRU3826(2) > Ant 8 Port S2 > RRU3826(2) > Ant 8 Port S3 > RRU3826(2) > Ant 8 Port S4 > RRU3826(2) > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-17 14:08:43 | Yes | Yes | 2025-12-15 17:30:00 |  |  | 2026-06-08 | Nattawoot Suwan | N/A | Closed | 2026-06-08 18:40:06 | No | No | [5 empty] | 2026-03-08 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:57 | No | No
BSRCB_2025 Capacity Expansion Ph2_EXP_BKK | BAN SUAN RATCHATHANI |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-11-12 16:15:37 | No | No |  |  |  | 2025-10-29 | 2025-10-29 | 2025-10-29 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-10-29 20:55:26 | Yes | Yes | 2025-11-06 08:52:31 |  | 2025-11-30 | 2025-11-12 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-12-03 09:56:01 | Yes | Yes | 2025-11-12 16:16:46 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:08:04 |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:34 | Yes | Yes | 2026-07-14 22:40:34 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-29 17:04:49 | No | No |  | 29-Oct-2025 Add AAU5246 SB 5/3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | on going |  | 2025-11-10 |  | N/A | Not assigned |  | No | No
BSSAK_2025 Capacity Expansion Ph2_EXP_SR | BAN SAM SAK | [5 empty] | 2025-08-27 | 2025-08-27 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-28 14:34:49 | No | No |  |  |  | 2025-08-24 | 2025-08-26 | 2025-08-26 | Teloneer Company Limited | N/A | Closed | 2025-08-26 15:55:18 | Yes | Yes | 2025-08-26 19:46:41 |  | 2025-08-26 | 2025-09-18 | Supot Hoonyong(Teloneer Company Limited) | Approved | Closed | 2025-09-26 11:47:36 | Yes | Yes | 2025-09-05 10:56:40 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:22:55 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-26 | 2025-08-26 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-30 16:58:53 | No | No |  | Onservice cell 1800 ----- MIMO 18/21 S1 REP.2RRU3826 TO 1RRU5516 REP.ANT4P |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-08-27 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-28 14:35:19 | No | No | [5 empty] | 2025-08-26 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
BSTFM_2025 Capacity Expansion Ph1_EXP_ER | BST Factory | 2025-08-06 |  | Install & Integrate |  | 2025-06-30 | 2025-08-06 | 2025-08-06 | Teloneer Company Limited | N/A | Closed | 2025-08-06 17:17:31 | No | No |  |  |  | 2025-05-31 | 2025-08-20 | 2025-08-20 | Teloneer Company Limited | N/A | Closed | 2025-08-20 18:10:58 | Yes | Yes | 2025-08-21 19:29:51 |  | 2025-06-30 | 2025-09-15 | Thanakit Chaleechai | Approved | Closed | 2025-09-26 13:58:41 | Yes | Yes | 2025-09-01 16:06:20 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:24:13 |  | 2025-05-31 | 2025-06-29 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-07-04 15:24:58 | Yes | Yes | 2025-06-29 20:49:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-06 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-06 18:54:57 | No | No |  | **waiting on-service LNR26 -- Add L26F1F5 +NR26 (Coo RRU5258) Co Anttenna Sec.D |  | 2025-08-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-08 12:31:24 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-08-27 | Teloneer Company Limited | N/A | Closed | 2025-08-28 14:38:08 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BT32M_2025 Capacity Expansion Ph2_EXP_BKK | BANGBUA THONG 32 |  |  |  | 2025-08-19 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-20 | 2025-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-20 15:31:22 | Yes | Yes | 2026-03-18 18:27:26 |  | 2025-08-25 | 2025-08-25 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-17 13:07:46 | Yes | Yes | 2025-08-29 11:06:57 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:26:50 |  | 2025-09-02 | 2025-09-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 20:29:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-20 20:02:21 | No | No |  | 2025-08-20_Add AAU5636w Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
BT32M_2025 Capacity Expansion Ph3_EXP_BKK | BANGBUA THONG 32 | [5 empty] | 2025-09-01 | 2025-09-01 | Akhom Srinara | N/A | Closed | 2025-09-01 09:42:25 | No | No |  |  |  |  | 2025-08-29 | 2025-08-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-29 22:50:59 | Yes | Yes | 2025-09-01 17:34:46 |  | 2025-09-02 | 2025-09-02 | Muhamadnase Chesamae | Approved | Closed | 2025-09-30 15:29:58 | Yes | Yes | 2025-09-04 15:44:27 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:56 | Yes | Yes | 2025-10-06 15:46:57 |  | 2025-09-05 | 2025-09-05 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-09-06 14:32:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-29 19:51:10 | No | No |  | 29-Aug-2025 Add RRU5516 (700900) S2 Add Ant 4port . Add g2 Add RRU5516 (1800-2100) S2 S3 Remove RRU5507 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-31 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
BTPJM_2025 Capacity Expansion Ph3_EXP_BKK | BTS PU CHAO | [5 empty] | 2025-10-17 | 2025-10-17 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-11-04 | 2025-11-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-25 12:26:10 | Yes | Yes | 2025-11-25 12:27:24 |  | 2025-11-20 | 2025-11-26 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-01 16:23:29 | Yes | Yes | 2025-11-21 13:05:39 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:37 | Yes | Yes | 2026-01-09 15:47:54 |  | 2025-11-21 | 2025-11-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:25:38 | No | Yes | 2025-11-21 13:41:04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-16 18:20:46 | No | No |  | 16-Oct-2025 Add AAU5636w S1 Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
BTT1M_2025 Capacity Expansion NW Modernization_EXP_BKK | BANTHADTHONG 1 |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-02-21 | 2026-02-03 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:06:30 | Yes | Yes | 2026-03-23 15:06:30 |  | 2026-04-24 | 2026-04-24 | Chonradee Suwapan | Approved | Closed | 2026-06-26 09:39:44 | Yes | Yes | 2026-04-24 02:27:19 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-14 | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-24 | 2026-04-24 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-24 17:41:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-02 19:21:08 | No | No |  | 2026-02-02_Replace RRU5507(4) to AAU5768 Sector 1#， Replace RRU3962(4) to AAU5768 Sector 2#， Replace RRU3962(2) to RRU5526 Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTTRB_2025 Capacity Expansion NW Modernization_EXP_BKK | BANTHADTHONG RD. |  |  |  |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-18 14:00:21 | No | No |  |  |  | 2026-02-27 | 2026-02-08 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 10:02:47 | Yes | Yes | 2026-02-11 10:02:48 | SQC Close | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-03-19 10:27:35 | Yes | Yes | 2026-02-27 12:34:46 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-06 | 2026-03-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:00:07 |  | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-17 21:58:39 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-04 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-04 17:23:25 | No | No |  | 4 Feb 2025 Replace RRU5526 sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTTRM_2025 Capacity Expansion NW Modernization_EXP_BKK | BANTHADTHONG RD. |  |  |  |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-18 14:00:21 | No | No |  |  |  | 2026-02-27 | 2026-02-07 | 2026-02-09 | V Contribute Co., Ltd | N/A | Closed | 2026-02-09 12:16:11 | Yes | Yes | 2026-02-09 12:16:12 |  | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-09-04 20:28:41 | Yes | Yes | 2026-08-21 11:10:29 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-06 | 2026-03-16 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-06-16 17:04:34 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-04 19:16:00 | No | No |  | 4-Feb-2026 Add AAU5768 sector 1#，3 Remove RRU5502 *4 Add RRU5526 sector 2 Remove RRU3962 *2 Add g3a Remove eb Replace Ant 8port S2 Co 1800 900 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUAGM_2025 Capacity Expansion Ph3_EXP_BKK | MU BAN BANG LUANG | 2025-08-30 |  |  |  | 2025-08-30 | 2025-08-31 | 2025-08-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-31 12:17:45 | No | No |  |  |  | 2025-09-05 | 2025-09-09 | 2025-09-10 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:13:27 | Yes | Yes | 2025-09-30 10:13:27 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:46:13 | Yes | Yes | 2025-09-11 20:47:56 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:56 | Yes | Yes | 2025-10-06 15:48:12 |  | 2025-09-11 | 2025-09-11 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-11 21:15:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-30 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-30 19:00:25 | No | No |  | 30-08-2025. Add UBBPg2#， AIRU5636w Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-31 |  | N/A | Not assigned |  | No | No
BUKHM_2025 Capacity Expansion Ph3_EXP_BKK | BUENG KHO HAI |  |  |  | 2025-09-18 | 2025-09-25 | 2025-09-28 | 2025-09-30 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-20 10:22:44 | No | No |  |  | 2025-09-25 | 2025-09-27 | 2025-09-29 | 2025-10-01 | Teloneer Company Limited | N/A | Closed | 2025-10-01 15:42:28 | Yes | Yes | 2025-10-01 17:23:28 |  |  | 2025-10-02 | Apichart Kampuang | Approved | Closed | 2025-10-22 17:31:20 | Yes | Yes | 2025-10-14 09:53:52 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:56 | Yes | Yes | 2025-10-27 16:58:20 |  |  | 2025-09-02 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 23:27:56 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-22 17:31:04 | No | No |  | 22-09-2025. Replace Ant Sec.3 แก้ Alarm //20-Sep-2025 Add RRU5516 (1800-2100) S3 Remove RRU3962 Replace Ant 4port Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-24 |  | N/A | Not assigned |  | No | No
BUR2M_2025 Capacity Expansion Ph7_EXP_BKK | Bangkok University Rangsit Station 2 |  |  |  |  | 2026-01-26 | 2026-01-26 | 2026-01-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-07 | 2026-03-30 | 2026-03-31 | V Contribute Co., Ltd | N/A | Closed | 2026-03-31 09:42:47 | Yes | Yes | 2026-03-31 09:42:47 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-03-11 16:32:23 | Yes | Yes | 2026-04-26 14:58:43 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-27 | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:47:30 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:36 | Yes | Yes | 2026-02-06 22:54:20 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-26 17:44:22 | No | No |  | 26-01-2026. Add AAU5636w Sec.6#， UBBPg3a x2 #，Rmv UBBPd5#， UBBPeb |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUR4M_2025 Capacity Expansion Ph7_EXP_BKK | Bangkok University Rangsit Station 4 |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:11:05 | No | No |  |  |  | 2026-01-31 | 2026-03-26 | 2026-03-31 | V Contribute Co., Ltd | N/A | Closed | 2026-03-31 14:05:32 | Yes | Yes | 2026-03-31 14:05:32 |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-03-13 17:34:55 | Yes | Yes | 2026-05-15 11:16:24 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-16 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-10 22:16:52 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-03 17:59:14 | No | No |  | 2026-02-03_Add AAU5636w Sector 7//2026-02-02_Replace RRU3962 to RRU5526 Sector 1#， **Pending Add AAU5636w Sector 7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BWK2M_2025 Coverage Expansion Ph2_EXP_BKK | BANGWAK STATION 2 | [5 empty] | 2025-08-30 | 2025-08-30 | Teloneer Company Limited | N/A | Closed | 2025-08-31 16:23:46 | No | No |  |  | 2025-08-31 | 2025-09-02 | 2025-09-10 | 2025-09-11 | Teloneer Company Limited | N/A | Closed | 2025-09-12 10:50:08 | Yes | Yes | 2025-09-12 10:50:09 |  |  | 2025-09-12 | Apichart Kampuang | Approved | Closed | 2025-09-29 15:44:55 | Yes | Yes | 2025-10-14 09:55:13 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:56 | Yes | Yes | 2025-10-06 15:49:26 |  |  | 2025-08-14 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-14 17:26:45 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-30 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-30 19:00:25 | No | No |  | 30-08-2025. Add UBBPd6#， RRU3953#， Ant.4 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-29 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
C002A_2025 Capacity Expansion Ph5_EXP_BKK | Soi Mu Ban Thai Thani 17_1 | [5 empty] | 2025-12-25 | 2025-12-25 | Akhom Srinara | N/A | Closed | 2025-12-25 09:49:04 | No | No |  |  |  | 2025-12-23 | 2025-12-25 | 2025-12-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-25 16:17:37 | Yes | Yes | 2026-01-06 13:14:34 |  | 2026-01-10 | 2026-01-10 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-14 09:18:58 | Yes | Yes | 2026-01-10 19:18:56 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-14 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 10:50:16 |  | 2026-01-10 | 2026-01-10 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 10:15:38 | Yes | Yes | 2026-01-10 19:20:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-23 | Supatong Juntorn WX1461874 | N/A | Closed | 2025-12-23 17:35:21 | No | No |  | 23-12-2025. Add RRU5818#， Ant.12 port x2 SecA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C004A_2025 Capacity Expansion Ph5_EXP_BKK | Soi Mu Ban Thai Thani 21_1 | [5 empty] | 2025-12-25 | 2025-12-25 | Akhom Srinara | N/A | Closed | 2025-12-25 09:49:04 | No | No |  |  |  | 2025-12-23 | 2025-12-25 | 2025-12-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-26 18:20:23 | Yes | Yes | 2026-01-16 11:34:04 |  | 2026-01-16 | 2026-04-08 | Aomchun Jittreemit | Approved | Closed | 2026-04-16 09:25:08 | Yes | Yes | 2026-04-10 14:51:05 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-04-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-09 | 2026-01-09 | Aomchun Jittreemit | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-09 09:39:15 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-23 | Supatong Juntorn WX1461874 | N/A | Closed | 2025-12-23 17:35:21 | No | No |  | 23-12-2025. Add RRU5818 SecA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C017A_2025 Capacity Expansion Ph5_EXP_BKK | Soi Mu Ban Villa Nawa Nakhon_2 |  |  |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-23 17:47:19 | No | No |  |  |  | 2025-12-28 | 2025-12-26 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 15:58:45 | Yes | Yes | 2025-12-26 15:58:45 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-02-04 09:24:58 | Yes | Yes | 2026-01-13 02:35:23 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:47:56 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:02:00 | Yes | Yes | 2026-01-13 02:59:06 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-22 14:41:36 | No | No |  | "22-Dec-2205 Add RRU5818 sector A Add g2 Remove RRU3962 Add Ant12port No RET *2 Use bidi 25G " |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C020A_2025 Capacity Expansion Ph5_EXP_BKK | Soi Mu Ban Villa Nawa Nakhon_5 |  |  |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-23 17:47:19 | No | No |  |  |  | 2025-12-28 | 2025-12-26 | 2025-12-27 | V Contribute Co., Ltd | N/A | Closed | 2025-12-27 13:53:34 | Yes | Yes | 2025-12-27 13:53:35 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-01-26 09:07:05 | Yes | Yes | 2026-01-22 15:53:25 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:48:23 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:02:00 | Yes | Yes | 2026-01-13 02:59:46 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-22 17:46:41 | No | No |  | 22-12-2025. Add RRU5818 Sec.B co Sec.A#， Chain RRU5502 Sec.B to Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C026A_2025 Capacity Expansion Ph5_EXP_BKK | Soi Mu Ban Thai Thani_5 |  |  |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-23 17:47:19 | No | No |  |  |  | 2025-12-28 | 2025-12-23 | 2025-12-24 | V Contribute Co., Ltd | N/A | Closed | 2025-12-24 10:17:58 | Yes | Yes | 2025-12-24 10:17:59 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-04-29 16:29:17 | Yes | Yes | 2026-04-27 17:05:17 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:02:00 | Yes | Yes | 2026-01-13 03:00:15 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-22 15:37:50 | No | No |  | 2026-04-03_Change SFP RRU5818 Sector A//22-Dec-2205 Add RRU5818 sector A Add g2 Replace Ant smallcell 12port No RET Add 12 port No RET Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C030A_2025 Capacity Expansion Ph2_EXP_BKK | SMALLCELL Pornkrajang Apartment Klong6 |  |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-11 17:27:06 | No | No |  |  |  | 2025-09-30 | 2025-09-19 | 2025-09-20 | V Contribute Co., Ltd | N/A | Closed | 2025-09-20 10:30:29 | Yes | Yes | 2025-09-20 10:30:30 |  | 2025-11-14 | 2025-11-14 | Chonradee Suwapan | Approved | Closed | 2025-11-26 09:23:51 | Yes | Yes | 2026-01-05 13:05:14 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 16:23:02 |  | 2025-11-14 | 2025-11-14 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-14 20:24:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-06 18:09:13 | No | No |  | 06-11-2025. Add RRU5516 L900 Sec.A //19-09-2025. Add UBBPg2#， Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-10 |  | N/A | Not assigned |  | No | No
C035A_2025 Capacity Expansion Ph5_EXP_BKK | Ban Uea Athon Soi Kun Pra_2 | [5 empty] | 2025-12-16 | 2025-12-16 | Akhom Srinara | N/A | Closed | 2025-12-18 14:24:31 | No | No |  |  |  | 2025-12-03 | 2025-12-04 | 2025-12-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-08 21:20:16 | Yes | Yes | 2025-12-10 19:02:59 |  | 2025-12-18 | 2026-01-21 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-29 09:17:05 | Yes | Yes | 2026-01-21 22:23:32 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:48:50 |  | 2025-12-18 | 2025-12-18 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2025-12-18 13:41:21 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-02 13:51:42 | No | No |  | 2-Dec-2025 Add RRU5818 Sector A Replace Ant 12 port No Ret Add g2 g3a Remove d5 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C037A_2025 Capacity Expansion Ph2_EXP_BKK | SMALLCELL Soi Muban Thaithani 21 |  |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-11 17:27:06 | No | No |  |  |  | 2025-11-21 | 2025-11-06 | 2025-11-07 | V Contribute Co., Ltd | N/A | Closed | 2025-11-07 12:22:45 | Yes | Yes | 2025-11-07 12:22:45 |  | 2025-11-14 | 2025-11-14 | Chonradee Suwapan | Approved | Closed | 2025-12-01 16:23:29 | Yes | Yes | 2025-11-14 20:06:49 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-02 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:09:20 |  | 2025-11-14 | 2025-11-14 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-14 20:25:15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-06 15:42:58 | No | No |  | 6-Nov-2025 Add RRU5516 (700900) Sector A Add g2 Replace Ant.12port No Ret 0/0 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-10 |  | N/A | Not assigned |  | No | No
C047A_2025 Capacity Expansion Ph5_EXP_BKK | River Park Condotel_1 |  |  |  |  | 2026-01-17 | 2026-01-17 | 2026-01-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-17 06:53:30 | No | No |  |  | 2025-11-14 | 2026-01-31 | 2026-01-27 | 2026-01-27 | V Contribute Co., Ltd | N/A | Closed | 2026-01-27 11:59:15 | Yes | Yes | 2026-01-27 11:59:15 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-06 13:12:59 | Yes | Yes | 2026-02-04 19:06:41 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:49:15 |  | 2025-11-12 | 2025-11-12 | Thanita Pannorrasri | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-04 19:16:13 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-16 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-16 18:09:35 | No | No |  | 16 Jan 2026 Add AAU5246 sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C048A_2025 Capacity Expansion Ph2_EXP_BKK | River Park Condotel_2 | 2025-09-29 |  |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-23 17:47:19 | No | No |  |  |  | 2025-10-09 | 2025-10-27 | 2025-12-18 | V Contribute Co., Ltd | N/A | Closed | 2025-12-18 18:22:06 | Yes | Yes | 2025-12-18 18:22:06 |  | 2026-01-19 | 2026-01-19 | Chonradee Suwapan | Approved | Closed | 2026-01-22 09:30:54 | Yes | Yes | 2026-02-26 10:43:27 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:49:39 |  | 2026-01-19 | 2026-01-19 | Chonradee Suwapan | Approved | Closed | 2026-01-29 17:10:14 | Yes | Yes | 2026-01-19 22:27:18 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-23 09:45:31 | No | No |  | 23-Dec-2205 Add RRU5818 Sector A 29-09-2025. ***Need RRU5818 Sec.A //Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-12-22 |  | N/A | Not assigned |  | No | No
C093A_2025 Capacity Expansion Ph2_EXP_BKK | TALARD RANGSIT_1 | 2025-09-30 |  |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 10:49:05 | No | No |  |  |  | 2025-10-10 | 2025-10-01 | 2025-10-02 | V Contribute Co., Ltd | N/A | Closed | 2025-10-02 14:50:53 | Yes | Yes | 2025-10-02 14:50:53 |  | 2025-10-04 | 2025-10-04 | Chonradee Suwapan | Approved | Closed | 2025-10-20 17:17:30 | Yes | Yes | 2026-01-05 10:24:53 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:37:30 |  | 2025-10-04 | 2025-10-04 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-04 21:00:56 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-30 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-30 16:47:54 | No | No |  | 30-09-2025. Add UBBPg2#， RRU5516 L900#， Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK40 |  | 2025-09-30 |  | N/A | Not assigned |  | No | No
C098A_2025 Capacity Expansion Ph5_EXP_BKK | Soi Mu Ban Thai Thani_10 | [5 empty] | 2025-12-25 | 2025-12-25 | Akhom Srinara | N/A | Closed | 2025-12-25 09:49:04 | No | No |  |  |  | 2025-12-23 | 2025-12-25 | 2025-12-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-26 18:19:11 | Yes | Yes | 2026-01-06 13:42:47 |  | 2026-01-10 | 2026-01-10 | Muhamadnase Chesamae | Approved | Closed | 2026-01-14 09:18:58 | Yes | Yes | 2026-01-10 10:35:03 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-14 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-15 10:51:30 |  | 2026-01-10 | 2026-01-10 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-10 10:35:33 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-23 | Supatong Juntorn WX1461874 | N/A | Closed | 2025-12-23 17:35:21 | No | No |  | 23-12-2025. Add RRU5818#， Ant.12 port x2 SecA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C139A_2025 Capacity Expansion Ph5_EXP_BKK | Rangsit - Pathumthani Soi 6_1 |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-12-28 | 2025-12-12 | 2025-12-18 | V Contribute Co., Ltd | N/A | Closed | 2025-12-18 11:19:49 | Yes | Yes | 2025-12-18 11:19:49 |  | 2025-11-28 | 2025-11-28 | Chonradee Suwapan | Approved | Closed | 2025-12-12 11:16:21 | Yes | Yes | 2025-11-28 19:45:39 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-09 15:59:05 |  | 2025-11-28 | 2025-11-28 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-11-28 19:57:15 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-20 17:36:02 | No | No |  | 20-Nov-2025 AAU5246 SB Remove AAU 5942 Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C150A_2025 Capacity Expansion Ph5_EXP_BKK | Ban Uea Athon Lat Lum Kaeo_2 |  |  |  | 2025-11-20 | 2025-11-27 | 2025-11-23 | 2025-11-23 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-11-26 17:26:31 | No | No |  |  | 2025-11-27 | 2025-11-29 | 2025-11-21 | 2025-11-22 | Teloneer Company Limited | N/A | Closed | 2025-11-22 12:29:18 | Yes | Yes | 2025-11-24 14:29:26 |  |  | 2025-11-25 | Apichart Kampuang | Approved | Closed | 2025-12-19 17:44:18 | Yes | Yes | 2026-01-05 11:28:35 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-09 16:00:20 |  | 2025-11-19 | 2025-11-19 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:25:38 | Yes | Yes | 2025-11-20 09:11:33 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-20 17:27:08 | No | No |  | 20-11-2025. Add UBBPg2#， Replace AIRU5246 Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C159A_2025 Capacity Expansion Ph6_EXP_BKK | THAI TECHNO PLATE CO., LTD. |  |  |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-15 18:16:03 | No | No |  |  |  | 2025-12-31 | 2025-12-18 | 2025-12-19 | V Contribute Co., Ltd | N/A | Closed | 2025-12-19 16:08:52 | Yes | Yes | 2025-12-19 16:08:53 |  | 2025-12-20 | 2025-12-20 | Chonradee Suwapan | Approved | Closed | 2026-01-06 15:54:30 | Yes | Yes | 2026-01-15 11:55:49 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 16:02:59 |  | 2025-12-20 | 2025-12-20 | Chonradee Suwapan | Approved | Closed | 2026-01-07 15:01:03 | Yes | Yes | 2026-01-07 10:15:11 |  |  | 2025-12-31 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  |  | 2025-12-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-15 16:38:43 | No | No |  | 15-Dec-2025 Replace BBU5900 UMPTg2 GPS Add g2 Add RRU5526 (1800-2100) sector A Remove RRU3962 Replace Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-25 06:10:09 | Yes | Yes | 2025-12-12 10:11:11 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C255A_2025 Capacity Expansion Ph2_EXP_BKK | SMALLCELL Soi Khlong Luang 27/1 | 2025-09-29 |  |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 10:49:05 | No | No |  |  |  | 2025-10-09 | 2025-10-20 | 2025-10-21 | V Contribute Co., Ltd | N/A | Closed | 2025-10-21 11:38:32 | Yes | Yes | 2025-10-21 11:38:32 |  | 2025-10-03 | 2025-10-03 | Chonradee Suwapan | Approved | Closed | 2025-10-21 17:18:31 | Yes | Yes | 2025-10-03 20:21:39 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:56 | Yes | Yes | 2025-10-27 17:00:50 |  | 2025-10-03 | 2025-10-03 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-03 21:17:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-29 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-29 17:23:14 | No | No |  | 2025-09-29_Replace to BBU5900 by UMPTg2#， Add UBBPg3a#， UBBPd5#， GPS#，RRU5518#， Replace to Ant 12 port (No RET) Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-09-30 |  | N/A | Not assigned |  | No | No
C263A_2025 Capacity Expansion Ph2_EXP_BKK | SOI KHLONG LUANG 7_4 SMALLCELL | 2025-09-30 |  |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 10:49:05 | No | No |  |  |  | 2025-10-10 | 2025-10-24 | 2025-10-29 | V Contribute Co., Ltd | N/A | Closed | 2025-10-29 12:30:17 | Yes | Yes | 2025-10-29 12:30:17 |  | 2025-10-03 | 2025-10-03 | Chonradee Suwapan | Approved | Closed | 2025-10-21 17:18:31 | Yes | Yes | 2025-10-03 20:22:36 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:56 | Yes | Yes | 2025-10-27 17:02:05 |  | 2025-10-03 | 2025-10-03 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-03 21:20:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-30 17:14:47 | No | No |  | 30-Sep-2025 Add RRU5516 (700900) S1 Add g2 Add Ant 12 port No Ret 0/3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK40 |  | 2025-09-30 |  | N/A | Not assigned |  | No | No
C268A_2025 Capacity Expansion Ph2_EXP_BKK | TOT COSY COZY RESIDENCE |  |  |  | 2025-11-11 | 2025-11-18 | 2025-11-22 | 2025-11-22 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-11-25 17:50:53 | No | No |  |  | 2025-11-18 | 2025-11-20 | 2025-11-15 | 2025-11-21 | Teloneer Company Limited | N/A | Closed | 2025-11-21 16:47:16 | Yes | Yes | 2025-11-21 16:48:16 |  |  | 2025-12-12 | Apichart Kampuang | Approved | Closed | 2026-01-23 09:27:42 | Yes | Yes | 2025-12-12 16:01:06 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:51:53 |  | 2025-11-10 | 2025-11-10 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:26:46 | No | Yes | 2025-11-10 17:30:15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-14 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-11-14 18:08:18 | No | No |  | 2025-11-14_Add RRU5516(LB)#， Replace Ant to 12 port Sector A#， Add UBBPg2#， re-config RRU sector B chain with Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-11-17 |  | N/A | Not assigned |  | No | No
C268A_2025 Capacity Expansion Ph7_EXP_BKK | TOT COSY COZY RESIDENCE |  |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2026-04-23 14:25:10 | No | No |  |  |  | 2026-02-28 | 2026-05-06 | 2026-05-07 | V Contribute Co., Ltd | N/A | Closed | 2026-05-07 11:30:06 | Yes | Yes | 2026-05-07 11:30:07 |  | 2026-03-25 | 2026-03-25 | Chonradee Suwapan | Approved | Closed | 2026-04-20 09:37:25 | Yes | Yes | 2026-03-25 21:51:18 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-15 | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-25 | 2026-03-25 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-25 21:56:12 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-20 18:47:26 | No | No |  | 2026-02-20_Add RRU5818 combine Sector A#，B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C276A_2025 Capacity Expansion Ph2_EXP_BKK | TOT SOI TEPKUNCHON 13/1 | 2025-09-13 |  |  |  | 2025-09-13 | 2025-09-13 | 2025-09-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-13 18:36:57 | No | No |  |  |  | 2025-09-30 | 2025-09-15 | 2025-09-18 | V Contribute Co., Ltd | N/A | Closed | 2025-09-18 21:29:02 | Yes | Yes | 2025-09-18 21:29:03 |  | 2025-09-23 | 2025-09-23 | Chonradee Suwapan | Approved | Closed | 2025-10-10 16:47:37 | Yes | Yes | 2026-01-04 15:09:30 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 16:25:29 |  | 2025-09-23 | 2025-09-23 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:20:11 | No | Yes | 2025-09-23 20:33:31 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-13 18:37:20 | No | No |  | 13-09-2025. Add UBBPg2#， RRU5516 L900#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-12 |  | N/A | Not assigned |  | No | No
C277A_2025 Capacity Expansion Ph2_EXP_BKK | THANYABURI CITY HALL SMALLCELL (TOT) |  |  |  | 2025-10-08 | 2025-10-15 | 2025-10-11 | 2025-10-11 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-28 10:43:04 | No | No |  |  | 2025-10-15 | 2025-10-17 | 2025-10-22 | 2025-10-28 | Teloneer Company Limited | N/A | Closed | 2025-10-28 18:14:28 | Yes | Yes | 2025-10-28 18:17:21 |  |  | 2025-10-28 | Apichart Kampuang | Approved | Closed | 2025-10-31 13:29:05 | Yes | Yes | 2026-01-05 14:40:38 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 16:26:43 |  | 2025-10-06 | 2025-10-06 | Teloneer Company Limited | Approved | Closed | 2025-11-28 14:34:00 | No | Yes | 2025-10-09 15:34:26 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-10 16:53:49 | No | No |  | 10-10-2025. Add UBBPd5 //09-10-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg2#， RRU5516#， Ant.12 port#， Sec.A#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
C296A_2025 Capacity Expansion Ph5_EXP_BKK | PATHUMTHANI TECHNICAL CALLAGE |  |  |  | 2025-12-22 | 2025-12-29 | 2025-12-24 | 2025-12-24 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-12-25 09:55:57 | No | No |  |  |  | 2025-11-20 | 2025-12-25 | 2025-12-26 | Teloneer Company Limited | N/A | Closed | 2025-12-26 14:10:28 | Yes | Yes | 2025-12-26 14:38:57 |  |  | 2025-12-29 | Apichart Kampuang | Approved | Closed | 2026-01-08 09:13:18 | Yes | Yes | 2025-12-30 12:00:58 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-09 16:04:13 |  | 2025-12-21 | 2025-12-21 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2025-12-21 13:51:46 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-24 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-12-24 19:55:08 | No | No |  | 2025-12-24_Add RRU5818 Sector B combine Sector A//23-12-2025. ***Need RRU5818 Sec.B co SecA //Replace BBU5900#， UMPTg2 10G#， Add UBBPg2#， UBBPg3a#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C7Y9M_2025 Capacity Expansion Ph2_EXP_BKK | Charoen Rat 7 Yeak 9 | [5 empty] | 2025-12-13 | 2025-12-13 | Akhom Srinara | N/A | Closed | 2025-12-18 11:53:12 | No | No |  |  |  |  | 2025-11-25 | 2025-12-03 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-03 21:38:13 | Yes | Yes | 2026-03-18 18:23:17 |  | 2025-12-15 | 2025-12-15 | Aomchun Jittreemit | Approved | Closed | 2025-12-18 15:19:48 | Yes | Yes | 2025-12-17 15:24:02 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:37 | Yes | Yes | 2026-01-09 16:05:26 |  | 2025-12-15 | 2025-12-15 | Aomchun Jittreemit | Approved | Closed | 2026-03-12 09:22:43 | No | Yes | 2025-12-15 13:14:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-14 17:22:56 | No | No |  | 14-11-2025. Add AIRU5636w Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-12-12 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
C940M_2025 Coverage Expansion Ph2_EXP_BKK | CHALERMPRAKIAT RAMA 9 SOI 40 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-13 | 2025-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-13 16:38:54 | Yes | Yes | 2025-08-17 10:08:36 | SQC closed. | 2025-08-20 | 2025-08-20 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 11:38:11 | Yes | Yes | 2026-01-16 19:57:55 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2026-01-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:52:19 |  | 2025-09-04 | 2025-09-04 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 14:52:12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-13 19:11:06 | No | No |  | 13-Aug-2025 Add RRU3953 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | No | No
CBTKM_2025 Capacity Expansion Ph2_EXP_ER | Chum Chon Ban Klong Ta Kao | 2025-07-25 |  | Install & Integrate |  | 2025-08-31 | 2025-07-25 | 2025-07-25 | Teloneer Company Limited | N/A | Closed | 2025-07-25 15:13:11 | No | No |  |  |  | 2025-07-31 | 2025-07-25 | 2025-07-25 | Teloneer Company Limited | N/A | Closed | 2025-07-25 16:08:48 | Yes | Yes | 2025-07-31 23:49:02 |  | 2025-07-31 | 2025-07-29 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-08-15 14:38:04 | Yes | Yes | 2025-07-29 22:02:40 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:16 | Yes | Yes | 2025-08-18 15:16:11 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | No | Yes | 2025-08-29 17:18:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-29 |  | 2025-07-25 | Reungsak Junkong 00927496 | N/A | Closed | 2025-07-25 19:30:10 | No | No |  | *** Waiting on-service -- Add UBBPg2 #， Replace RRU3953- to (RRU5516_900) + Co L07 + NR07 + 4T4R |  | 2025-08-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-13 18:45:29 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-07-26 | 2025-07-22 |  | N/A | Closed | 2025-07-22 16:00:05 | No | No
CCCBM_2025 Capacity Expansion Ph6_EXP_ER | Chonburi Concrete Product Public Company Limited (Ban Bung) | 2025-11-21 | thcp_Adirek.k | Clear Pending |  | 2025-11-30 | 2025-11-21 | 2025-11-21 | Teloneer Company Limited | N/A | Closed | 2025-11-21 11:58:19 | No | No |  |  |  | 2025-11-30 | 2025-11-22 | 2025-11-26 | Teloneer Company Limited | N/A | Closed | 2025-11-26 14:38:05 | Yes | Yes | 2025-12-03 19:42:22 |  | 2025-11-30 | 2025-12-03 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-04 15:50:52 | Yes | Yes | 2025-12-03 22:42:43 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 16:10:20 |  | 2025-11-30 | 2025-11-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-19 13:28:23 | Yes | Yes | 2025-11-18 14:16:03 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-19 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-19 18:11:25 | No | No |  | **waiting on-service LNR26 -- Replace Antenna (Dualband Dualbeam) H_3 Replace Antenna (Co Antenna) L_3 Replace Antenna (Co Antenna) N_3 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna H_8 New L26F5 + NR26 (New RRU5818) + Co Antenna N_2 New L26F5 + NR26 (Co RRU5818) + Co Antenna N_8 |  | 2025-11-21 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-21 16:48:25 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CCKGM_2025 Coverage Expansion CO-NT Tower_EXP_ER | Chumchon ChakKlang | 2025-08-18 |  | Install & Integrate |  | 2025-08-31 | 2025-08-18 | 2025-08-18 | Teloneer Company Limited | N/A | Closed | 2025-08-18 16:10:55 | No | No |  |  |  | 2025-08-31 | 2025-08-18 | 2025-08-19 | Teloneer Company Limited | N/A | Closed | 2025-08-19 17:10:49 | Yes | Yes | 2025-08-21 19:07:35 |  | 2025-08-31 | 2025-09-12 | Thanakit Chaleechai | Approved | Closed | 2025-09-18 15:00:39 | Yes | Yes | 2025-09-12 17:10:23 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:38:10 |  | 2025-08-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:19:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-19 |  | 2025-08-18 | Reungsak Junkong 00927496 | N/A | Closed | 2025-08-18 18:58:07 | No | No |  | Add act replace ANT LB Sec.1 #，New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB) S3#，Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R S1 |  | 2025-08-18 | Reungsak Junkong 00927496 | N/A | Closed | 2025-08-18 18:58:07 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CDTEM_2025 Capacity Expansion Ph6_EXP_BKK | CHINDA THANEE VILLAGE | [5 empty] | 2025-12-23 | 2025-12-23 | Akhom Srinara | N/A | Closed | 2025-12-23 19:02:27 | No | No |  |  |  | 2025-12-18 | 2025-12-22 | 2025-12-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-26 18:22:33 | Yes | Yes | 2026-01-06 13:23:39 |  | 2026-01-06 | 2026-01-06 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-16 16:02:54 | Yes | Yes | 2026-01-07 16:10:43 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:52:49 |  | 2026-01-06 | 2026-01-06 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-06 15:23:57 |  |  | 2025-12-31 | 2025-12-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-22 13:38:37 | No | No |  |  |  |  | 2025-12-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-22 12:20:47 | No | No |  | 22-Dec-2205 Add RRU3962 Sector 8.2 Replace Ant 8port co S3#，S8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CEKMB_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI EKKAMAI 30 (FOR C EKKAMAI) |  |  |  |  | 2026-02-20 | 2026-02-27 | 2026-02-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-18 16:37:14 | No | No |  |  |  | 2026-02-28 | 2026-02-23 | 2026-02-27 | V Contribute Co., Ltd | N/A | Closed | 2026-02-27 10:39:24 | Yes | Yes | 2026-02-27 10:39:25 |  | 2026-03-31 | 2026-03-31 | Chonradee Suwapan | Approved | Closed | 2026-09-04 17:39:55 | Yes | Yes | 2026-04-20 11:06:57 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-18 | 2026-09-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-31 | 2026-03-31 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-31 00:17:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-20 18:20:36 | No | No |  | 20-02-2026. Replace BBU5900#， UMPTg2#， RRU3962 to 5507 x2 Sec.A#， Add UBBPg2 x2#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CFSMB_2025 Capacity Expansion Ph2_EXP_BKK | Small cell BIG C Samrong for Ideo Sukhumvit 115 |  |  |  |  | 2025-10-03 | 2025-10-03 | 2025-10-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-03 10:03:34 | No | No |  |  |  | 2025-10-06 | 2025-10-24 | 2025-10-24 | V Contribute Co., Ltd | N/A | Closed | 2025-10-24 19:47:14 | Yes | Yes | 2025-10-24 19:47:15 |  | 2025-10-10 | 2025-10-10 | Chonradee Suwapan | Approved | Closed | 2025-10-24 17:41:33 | Yes | Yes | 2026-01-05 16:26:10 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:56 | Yes | Yes | 2025-10-27 17:04:34 |  | 2025-10-10 | 2025-10-10 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-10 19:39:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-01 17:50:57 | No | No |  | 10-01-2025. Add RRU5818#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-02 |  | N/A | Not assigned |  | No | No
CH16M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAN 16 YAEK 10-12 |  |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-28 16:44:27 | No | No |  |  |  | 2026-02-14 | 2026-01-24 | 2026-01-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-25 19:10:47 | Yes | Yes | 2026-01-27 10:20:55 | SQC Close | 2026-01-28 | 2026-01-28 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-11 09:40:40 | Yes | Yes | 2026-01-28 16:47:17 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:02:01 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 21:17:37 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-23 18:39:29 | No | No |  | 23-Jan-2026 Add AAU5768 S1 S2 S3 Remove RRU3962 *4 S1 S2*4 S3 *2 Add g3a =2 Remove eb |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHBNM_2025 Coverage Expansion Ph2_EXP_BKK | MUBAN CHUANCHUEN BANGNA |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-09 | 2025-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-10 10:47:00 | Yes | Yes | 2025-08-10 10:48:59 |  | 2025-08-19 | 2025-08-19 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:35:50 | Yes | Yes | 2025-08-19 20:10:07 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 11:25:16 |  | 2025-08-30 | 2025-08-30 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-08-30 23:38:36 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-09 18:08:41 | No | No |  | 9-Aug-2025 Add RRU3953 S1 Replace Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
CHGNM_2025 Capacity Expansion Ph2_EXP_ER | Choeng Noen Moo 3 | 2025-07-13 |  | Install & Integrate |  | 2025-07-31 | 2025-07-13 | 2025-07-14 | Teloneer Company Limited | N/A | Closed | 2025-07-14 17:37:01 | No | No |  |  |  | 2025-07-31 | 2025-07-14 | 2025-07-21 | Teloneer Company Limited | N/A | Closed | 2025-07-21 09:33:02 | Yes | Yes | 2025-07-27 13:41:17 |  | 2025-07-31 | 2025-08-06 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-08-15 14:36:02 | Yes | Yes | 2025-09-15 16:06:35 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:40:44 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:20:02 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-29 |  | 2025-07-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-13 16:45:51 | No | No |  | revise add 1ug3a to 1ug2#，Replace Antenna (Dualband) 18/21 S3 #，New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna) S3 |  | 2025-07-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-13 16:48:59 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHLCA_2025 Capacity Expansion Ph2_EXP_BKK | Chewathai Hallmark Ladprao - Chokchai 4 | [5 empty] | 2025-12-10 | 2025-12-10 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  | ต้องเข้า survey#，มีเดินท่อ#， CPRI ใช้คอร์ที่ตู้เดียวกัน และคอร์ที่ได้มาแล้วเพียง 2 core เท่านั้นยังขาดอีก 2 คอร์#，sector 2 เป็น Ant split |  | 2025-12-03 | 2025-12-05 | 2025-12-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-11 09:47:29 | Yes | Yes | 2025-12-11 19:33:30 |  | 2025-12-12 | 2025-12-12 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-20 13:32:47 | Yes | Yes | 2025-12-12 01:36:32 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:53:18 |  | 2025-12-12 | 2025-12-12 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:23:08 | No | Yes | 2025-12-12 15:13:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-03 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-03 17:11:00 | No | No |  | 03-12-2025. Add RRU5818 Sec.A#， B#， Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | ต้องเข้า survey,มีเดินท่อ, CPRI ใช้คอร์ที่ตู้เดียวกัน และคอร์ที่ได้มาแล้วเพียง 2 core เท่านั้นยังขาดอีก 2 คอร์,sector 2 เป็น Ant split |  |  |  | N/A | Not assigned |  | No | No
CHLRB_2025 Capacity Expansion NW Modernization_EXP_BKK | Chidlom Road small cell | [5 empty] | 2026-04-04 | 2026-04-04 | Akhom Srinara | N/A | Closed | 2026-04-21 20:40:15 | No | No |  |  |  | 2026-02-13 | 2026-03-24 | 2026-03-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-03-24 17:28:16 | Yes | Yes | 2026-04-02 11:59:10 |  | 2026-04-03 | 2026-04-06 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-24 16:51:02 | Yes | Yes | 2026-04-03 14:01:26 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-21 | 2026-04-21 | Charuwan Limsaihua | Approved | Closed | 2026-06-19 15:27:18 | Yes | Yes | 2026-04-21 14:01:18 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-14 16:09:00 | No | No |  | 14-Mar-2026 Add RRU5507 *2 sector A Remove RRU3962*2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHLRM_2025 Capacity Expansion NW Modernization_EXP_BKK | Chidlom Road | [5 empty] | 2026-03-30 | 2026-03-30 | Akhom Srinara | N/A | Closed | 2026-04-21 20:48:32 | No | No |  |  |  | 2026-02-13 | 2026-03-24 | 2026-04-01 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-04-01 17:19:06 | Yes | Yes | 2026-04-09 11:17:05 |  | 2026-04-23 | 2026-04-23 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-08 09:35:32 | Yes | Yes | 2026-06-30 15:51:46 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-15 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  |  | 2026-04-29 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-19 15:27:18 | Yes | Yes | 2026-04-29 09:05:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-14 17:12:11 | No | No |  | 14-Mar-2026 Add RRU5507 *2 Sector 2 Remove RRU3962*2 Add RRU5526 Sector 3 Remove RRU3962*2 Add RRU5516 S1 S2 S3 Remove RRU3953 S1 S2 S3 Replace Ant 8port S1 S2 S3 Co 18002100 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHU1M_2025 Capacity Expansion NW Modernization_EXP_BKK | CHULALONGKORN 1 |  |  |  | 2026-02-04 | 2026-02-04 | 2026-02-18 | 2026-02-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-08 22:48:26 | No | No |  |  |  | 2026-02-07 | 2026-01-30 | 2026-02-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-19 09:51:02 | Yes | Yes | 2026-02-19 09:52:12 |  | 2026-02-05 | 2026-02-19 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-23 15:57:48 | Yes | Yes | 2026-02-19 16:10:28 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:02:38 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 21:17:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-04 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-02-04 10:35:59 | No | No |  | 27-Jan-2026 Add AAU5768 sector2 Remove RRURRU5507*1 RRU3962*3 Add RRU5507 *2 sector 1 Remove RRU3962 *2 Add RRU5516 S1 S2 S3 Remove RRU3953 *3 Replace Ant Sector 1 Add g3a g2 Remove d6 d5 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHWGM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAROEN WIANG MACRO SITE |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-28 | 2026-03-23 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:15:58 | Yes | Yes | 2026-03-23 15:15:59 |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-05-12 16:26:02 | Yes | Yes | 2026-05-08 13:50:15 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-04 | 2026-05-15 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-18 22:55:09 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-30 17:42:31 | No | No |  | 30-01-2026 Site CHWGM -Replace ant sector 2#，3 18/21 -Remove sector 18/21 8 rru5507 -Add card g3a 2 card Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CHYPM_2025 Capacity Expansion Ph3_EXP_BKK | CHAIYAPRUK VILLAGE | 2025-08-23 |  |  |  | 2025-08-23 | 2025-08-23 | 2025-08-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-23 17:52:43 | No | No |  |  |  | 2025-08-31 | 2025-09-02 | 2025-09-03 | V Contribute Co., Ltd | N/A | Closed | 2025-09-03 16:15:25 | Yes | Yes | 2025-09-03 16:16:42 |  | 2025-09-09 | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-20 12:27:00 | Yes | Yes | 2025-09-16 21:25:46 | PAt pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:45:55 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-09 19:04:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-23 18:45:46 | No | No |  | 23-08-2025. Replace RRU5516 L900#， Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-21 |  | N/A | Not assigned |  | No | No
CIL1B_2025 Capacity Expansion NW Modernization_EXP_BKK | CEIL by Sansiri (Right) |  |  |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-05 08:14:22 | No | No |  |  |  | 2026-02-27 | 2026-03-17 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:05:46 | Yes | Yes | 2026-03-23 15:05:46 |  | 2026-03-02 | 2026-03-02 | Chonradee Suwapan | Approved | Closed | 2026-06-09 16:34:26 | Yes | Yes | 2026-05-29 01:50:15 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-06-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-02 | 2026-03-02 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:17:02 | Yes | Yes | 2026-03-02 20:54:22 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-06 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-06 19:00:44 | No | No |  | 6 Feb 2026 Replace RRU5507 s1#，add 5507 s1 rReplace BBU5900 // GPS ติดตั้งไม่ได้ |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CIL1B_2025 Coverage Expansion Ph1_EXP_BKK | CEIL by Sansiri (Right) | 2025-08-20 |  |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-20 16:21:33 | No | No |  |  |  | 2025-08-31 | 2025-09-03 | 2025-09-03 | V Contribute Co., Ltd | N/A | Closed | 2025-09-03 17:41:53 | Yes | Yes | 2025-09-03 17:41:59 |  |  | 2025-09-08 | Chonradee Suwapan | Approved | Closed | 2025-09-18 17:11:26 | Yes | Yes | 2025-10-31 18:35:14 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:47:12 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-15 15:50:40 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-20 20:02:21 | No | No |  | 2025-08-20_Replace to Ant Vertical dual Beam |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-19 |  | N/A | Not assigned |  | No | No
CIL2B_2025 Capacity Expansion NW Modernization_EXP_BKK | CEIL by Sansiri (Left) |  |  |  |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-06 18:17:38 | No | No |  |  |  | 2026-02-27 | 2026-03-19 | 2026-03-25 | V Contribute Co., Ltd | N/A | Closed | 2026-03-25 09:43:13 | Yes | Yes | 2026-03-25 09:43:14 |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-06-09 16:34:26 | Yes | Yes | 2026-05-29 16:03:23 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-21 | 2026-06-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:17:02 | Yes | Yes | 2026-03-05 20:59:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-06 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-06 19:00:44 | No | No |  | 6 Feb 2026 Replace RRU5507 s1#，add 5507 s1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CIL2B_2025 Coverage Expansion Ph1_EXP_BKK | CEIL by Sansiri (Left) | 2025-08-20 |  |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-20 16:21:33 | No | No |  |  |  | 2025-08-31 | 2025-09-03 | 2025-09-03 | V Contribute Co., Ltd | N/A | Closed | 2025-09-03 19:53:56 | Yes | Yes | 2025-09-03 19:54:08 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-18 17:11:26 | Yes | Yes | 2025-09-15 15:55:46 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:48:27 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 15:51:12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-20 17:10:26 | No | No |  | 20-Aug-2025 Replace Ant.to Ant.Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-19 |  | N/A | Not assigned |  | No | No
CINTN_2025 Capacity Expansion Ph2_EXP_SR | CHONG INTHANIN | [5 empty] | 2025-08-27 | 2025-08-27 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-28 14:34:49 | No | No |  |  |  | 2025-08-24 | 2025-08-27 | 2025-08-27 | Teloneer Company Limited | N/A | Closed | 2025-08-27 15:28:18 | Yes | Yes | 2025-08-28 12:48:01 |  | 2025-08-28 | 2025-09-18 | Supot Hoonyong(Teloneer Company Limited) | Approved | Closed | 2025-09-26 11:47:36 | Yes | Yes | 2025-08-28 13:57:53 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:49:42 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-27 | 2025-08-27 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-08-27 18:40:29 | No | No |  | Onservice cell 1800 ----- S2 MB >RRU3826*2 to RRU5516MB> existing Ant Cell 122 > 2T2R to 4T4R |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-08-27 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-28 14:35:19 | No | No | [5 empty] | 2025-08-26 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
CK39M_2025 Capacity Expansion NW Modernization_EXP_BKK | CHAROENKRUNG SOI 39 |  |  |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-10 15:43:46 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-30 | 2026-01-30 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-30 20:37:59 | Yes | Yes | 2026-02-03 09:34:10 |  | 2026-02-10 | 2026-02-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-02-24 10:43:20 | Yes | Yes | 2026-02-19 16:36:16 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:03:16 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 21:18:09 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-16 18:33:21 | No | No |  | 16-01-2026. Replace RRU3962 to RRU5526#， Ant.8 port Sec.1#， 2#， 3#， Add RRU5526 Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CK53M_2025 Coverage Expansion Ph2_EXP_BKK | SOI CHALONG KRUNG 53/1 YAK 9 |  |  |  | 2025-08-14 |  | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 19:08:41 | No | No |  |  |  |  | 2025-08-14 | 2025-08-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-14 12:32:02 | Yes | Yes | 2025-08-15 15:27:17 |  | 2025-08-15 | 2025-08-15 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-22 13:14:50 | Yes | Yes | 2025-08-15 22:32:03 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:14 | Yes | Yes | 2025-08-26 18:04:36 |  | 2025-09-03 | 2025-09-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-03 10:31:26 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-14 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-14 18:39:44 | No | No |  | 2025-08-14_Add RRU3953#， Ant 4 port Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
CK91M_2025 Capacity Expansion Ph2_EXP_BKK | SOI CHAROEN KRUNG 91 |  |  |  | 2025-08-20 | 2025-09-30 | 2025-10-05 | 2025-10-05 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-09-12 | 2025-10-03 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-03 15:28:01 | Yes | Yes | 2025-10-06 15:56:40 |  | 2025-10-07 | 2025-10-07 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-17 10:29:21 | Yes | Yes | 2025-10-07 14:18:57 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:46:10 |  | 2025-10-07 | 2025-10-07 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-28 14:33:42 | No | Yes | 2025-10-07 15:40:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-12 18:07:29 | No | No |  | 12-09-2025. Add UBBPg2#， RRU5516 L900#， Ant.12 port S.1#， 2#， Replace RRU5516 L18#， Ant.12 port S.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | รอสรุป Solution ant |  | 2025-09-29 |  | N/A | Not assigned |  | No | No
CKHMM_2025 Capacity Expansion Ph7_EXP_ER | Tha Kham Moo 6 | 2025-12-24 |  | Install & Integrate |  | 2025-12-31 | 2025-12-12 | 2025-12-12 | Teloneer Company Limited | N/A | Closed | 2025-12-12 13:20:38 | No | No |  |  |  | 2025-12-31 | 2025-12-12 | 2025-12-12 | Teloneer Company Limited | N/A | Closed | 2025-12-12 19:13:46 | Yes | Yes | 2025-12-13 18:17:06 |  | 2025-12-31 | 2025-12-16 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:28:48 | Yes | Yes | 2025-12-16 12:18:56 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:29 | Yes | Yes | 2026-03-20 16:34:22 |  | 2025-12-31 | 2025-12-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-13 21:12:48 | Yes | Yes | 2025-12-12 08:37:33 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-24 17:23:49 | No | No |  | Add UBBPg2 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_CKHMM_L_3 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_CKHMM_L_4 |  | 2025-12-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-24 17:23:49 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CKPOM_2025 Capacity Expansion Ph7_EXP_BKK | CHRISTIAN CHURCH KHLONG PHRA OI RD. |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-06 11:50:20 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-02-01 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-01 19:22:07 | Yes | Yes | 2026-02-06 09:05:11 |  | 2026-02-06 | 2026-02-06 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-09 16:38:58 | Yes | Yes | 2026-02-06 11:52:08 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:54:26 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 21:44:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-15 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-15 18:20:12 | No | No |  | 15 Jan 2026 Add AAU5636w sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CLDBM_2025 Capacity Expansion Ph3_EXP_BKK | Chonlada Bang Buathong Village |  |  |  | 2025-09-10 | 2025-09-17 | 2025-09-20 | 2025-09-20 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-26 14:02:11 | No | No |  |  | 2025-09-17 | 2025-09-19 | 2025-09-18 | 2025-09-19 | Teloneer Company Limited | N/A | Closed | 2025-09-19 10:01:14 | Yes | Yes | 2025-09-22 09:42:13 |  |  | 2025-09-23 | Apichart Kampuang | Approved | Closed | 2025-10-15 14:27:54 | Yes | Yes | 2025-10-14 09:55:53 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:51:03 |  |  | 2025-09-02 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 23:28:15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-10 17:46:37 | No | No |  | 10-09-2025. Add UBBPg2#， Replace RRU5516 L900#， Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-19 |  | N/A | Not assigned |  | No | No
CLMMM_2025 Coverage Expansion Ph2_EXP_BKK | CHALOEM PHRAKIAT YOUNG BUDDHIST MEDITATION CENTER | 2025-08-01 |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-01 17:31:33 | No | No |  |  |  | 2025-08-22 | 2025-08-13 | 2025-08-14 | V Contribute Co., Ltd | N/A | Closed | 2025-08-14 21:30:05 | Yes | Yes | 2025-08-14 21:31:22 |  | 2025-08-14 | 2025-08-14 | Chonradee Suwapan | Approved | Closed | 2025-08-22 17:57:48 | Yes | Yes | 2025-08-20 14:28:14 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:14 | Yes | Yes | 2025-08-26 18:07:22 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:51:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-01 16:26:43 | No | No |  | 01-08-2025. Add RRU3953 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
CLP7M_2025 Coverage Expansion Ph2_EXP_BKK | CHALOEM PHRAKIAT RAMA 9 SOI 7 YAEK 6 |  |  |  | 2025-08-15 | 2025-08-31 | 2025-08-18 | 2025-08-18 | Akhom Srinara | N/A | Closed | 2025-08-18 13:04:03 | No | No |  |  |  |  | 2025-08-15 | 2025-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-15 21:04:15 | Yes | Yes | 2025-08-19 22:25:22 |  | 2025-08-21 | 2025-08-21 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-02 18:23:31 | Yes | Yes | 2025-08-21 16:46:22 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:55:27 |  | 2025-09-02 | 2025-09-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-02 20:25:04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-15 15:31:34 | No | No |  | 15-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | Jia Rui 80023782 | N/A | Not assigned |  | No | No
CMKOM_2025 Capacity Expansion Ph1_EXP_SR | Ban Chum Ko |  |  |  |  | 2025-08-31 | 2025-08-13 | 2025-08-13 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-13 11:45:10 | No | No |  |  |  | 2025-08-04 | 2025-08-06 | 2025-08-06 | Teloneer Company Limited | N/A | Closed | 2025-08-06 17:00:17 | Yes | Yes | 2025-08-07 09:50:08 |  | 2025-08-07 | 2025-08-07 | Supot Hoonyong | Approved | Closed | 2025-09-01 11:12:03 | Yes | Yes | 2025-08-13 12:39:24 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 18:54:51 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-08-07 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-06 | 2025-08-06 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-08-06 15:59:35 | No | No |  | Add UBBPg3a*1 Add new HB S4 S4 > AAU5636w |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-08-13 | Nattawoot Suwan | N/A | Closed | 2025-08-13 11:45:49 | No | No |  |  |  |  | 2025-08-13 | 2025-08-12 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
CMSPM_2025 Coverage Expansion Ph2_EXP_BKK | S. CHAI MONG KOL SAMUT PRAKAN | 2025-08-16 |  |  |  | 2025-08-16 | 2025-08-16 | 2025-08-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-16 15:37:02 | No | No |  |  |  | 2025-08-31 | 2025-08-21 | 2025-08-22 | V Contribute Co., Ltd | N/A | Closed | 2025-08-22 10:49:12 | Yes | Yes | 2025-08-22 10:50:05 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-09-01 13:12:38 | Yes | Yes | 2025-08-27 14:16:10 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 11:32:12 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:40:47 | No | Yes | 2025-08-05 09:05:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-16 17:11:35 | No | No |  | 16-08-2025. Add RRU3953#， Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-14 |  | N/A | Not assigned |  | No | No
CN18M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAN18 |  |  |  |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-10 16:18:21 | No | No |  |  |  | 2026-02-28 | 2026-02-20 | 2026-02-26 | V Contribute Co., Ltd | N/A | Closed | 2026-02-26 09:34:13 | Yes | Yes | 2026-02-26 09:34:14 |  | 2026-02-07 | 2026-02-07 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:38:32 | Yes | Yes | 2026-02-07 22:05:30 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:04:32 |  | 2026-02-07 | 2026-02-07 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-07 22:13:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-23 18:25:08 | No | No |  | 23-01-2026. Replace RRU3962 to AAU5768 Sec.1#， RRU3962 to RRU5507#， Ant.8 port Sec.2#， 3#， UBBPd6 to UBBPg3a#， Remove Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN45M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAN45 |  |  |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-04 20:54:54 | No | No |  |  |  | 2026-02-07 | 2026-02-02 | 2026-02-04 | V Contribute Co., Ltd | N/A | Closed | 2026-02-04 16:52:46 | Yes | Yes | 2026-02-04 16:52:47 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-06 13:32:23 | Yes | Yes | 2026-02-04 19:07:15 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:05:10 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-04 19:17:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-21 18:17:00 | No | No |  | 21-01-2026. Add RRU3953 Sec.2#， UBBPg3a x2#， Rmv UBBPd5 *2 Replace RRU3962 to AAU5768 Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN47M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAN47 |  |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-07 07:32:17 | No | No |  |  |  | 2026-02-28 | 2026-02-19 | 2026-02-20 | V Contribute Co., Ltd | N/A | Closed | 2026-02-20 15:47:49 | Yes | Yes | 2026-02-20 15:47:49 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-11 09:40:40 | Yes | Yes | 2026-03-09 17:08:17 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:05:29 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-05 22:24:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-23 | Suthee Khamhom WX1452991 | N/A | Closed | 2026-01-23 16:25:38 | No | No |  | 23 Jan 2026 Add 2AAU5768 DMM S2#，S3 2Beam and RMV 4RRU5507#， 2RRU3962 18/21 S2#， S3#， S8. Add 3RRU5516 and RMV LB 3RRU3953 LB S1#， S2#， S3. Config LB S3 4T4R. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN47M_2025 Capacity Expansion Ph7_EXP_BKK | SOI CHAN47 | [5 empty] | 2026-02-23 | 2026-02-23 | Akhom Srinara | N/A | Closed | 2026-02-23 17:44:36 | No | No |  |  | 2026-01-17 | 2026-01-23 | 2026-02-03 | 2026-02-06 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-02-06 10:15:33 | Yes | Yes | 2026-02-28 10:14:57 | SQC Close | 2026-03-04 | 2026-03-04 | Muhamadnase Chesamae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-09 09:30:25 | Yes | Yes | 2026-03-04 10:26:44 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 11:58:00 |  | 2026-05-21 | 2026-05-21 | Muhamadnase Chesamae | Approved | Closed | 2026-06-19 15:23:48 | Yes | Yes | 2026-05-21 18:13:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-17 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-17 20:00:45 | No | No |  | 17 Jan 2026 Replace rru3962 to 5526 sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CNNWM_2025 Capacity Expansion NW Modernization_EXP_BKK | Yak Chan - Naradhiwas |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-02-26 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:18:59 | Yes | Yes | 2026-03-23 15:27:17 |  | 2026-04-20 | 2026-04-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-23 09:23:17 | Yes | Yes | 2026-04-24 11:20:48 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 21:18:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-09 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-09 18:25:38 | No | No |  | 09-02-26 Add RRU516 S1 S2 700/900 #， Replace 3962 To RRU5507 S2 7-Feb-2026 ***Pending Add RRU5516 S1 S2 Remove RRU3953 S1 S2 Add RRU5507 *2 S2 Remove RRU3962 *2 Replace Ant 8port *2 Remove Ant *4 ////Add RRU5516 S3 Remove RRU3953 Add RRU5507 S3 *2 Remove RRU3962 *2 Replace Ant 8port *1 Remove Ant *1 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
COA1B_2025 Coverage Expansion Ph1_EXP_BKK | Chapter One Modern Dutch RatBurana 33 Tower A 1 | [5 empty] | 2025-09-30 | 2025-09-30 | Akhom Srinara | N/A | Closed | 2025-09-30 14:03:02 | No | No |  |  |  |  | 2025-09-15 | 2025-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-24 20:05:05 | Yes | Yes | 2025-09-29 11:35:22 |  | 2025-10-01 | 2025-10-01 | Muhamadnase Chesamae | Approved | Closed | 2025-10-20 16:38:16 | Yes | Yes | 2025-10-01 11:29:30 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:53:28 |  | 2025-10-04 | 2025-10-04 | Muhamadnase Chesamae | Approved | Closed | 2025-11-28 14:33:42 | No | Yes | 2025-10-04 10:11:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-16 17:45:29 | No | No |  | 16-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector B Subrack 84 ( RRU*1 Ant 2) No Config RET 2025-09-15_*** Cancel Replace to Ant Vertical Dual Beam Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-28 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
COC1B_2025 Coverage Expansion Ph1_EXP_BKK | Chapter One Modern Dutch RatBurana 33 Tower C 1 | [5 empty] | 2025-09-17 | 2025-09-17 | Akhom Srinara | N/A | Closed | 2025-09-25 13:54:36 | No | No |  |  |  |  | 2025-09-16 | 2025-09-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-17 14:47:38 | Yes | Yes | 2025-09-19 13:38:28 |  | 2025-09-19 | 2025-09-19 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-07 16:22:25 | Yes | Yes | 2025-09-19 21:52:46 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:03 | Yes | Yes | 2025-10-09 19:48:58 |  | 2025-09-23 | 2025-09-23 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-23 15:04:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-15 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-15 19:06:55 | No | No |  | 2025-09-15_Replace to Ant Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-15 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
COSDM_2025 Capacity Expansion Ph3_EXP_BKK | COSMIC SOUND | [5 empty] | 2025-09-30 | 2025-09-30 | Akhom Srinara | N/A | Closed | 2025-09-30 14:03:02 | No | No |  |  |  |  | 2025-09-23 | 2025-09-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-28 10:41:42 | Yes | Yes | 2025-09-29 14:16:21 |  | 2025-09-29 | 2025-10-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-15 09:43:11 | Yes | Yes | 2025-10-03 16:37:33 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 15:55:55 |  | 2025-10-07 | 2025-10-07 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-28 14:33:42 | No | Yes | 2025-10-07 15:57:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-23 18:24:50 | No | No |  | 23-09-2025. Add AIRU5636w Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-28 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
CP24M_2025 Capacity Expansion Ph1_EXP_BKK | CHAENGWATTANA-PAKKRET SOI 24 | 2025-05-23 |  |  |  | 2025-05-23 | 2025-05-23 | 2025-05-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-05-23 18:17:22 | No | No |  |  |  | 2025-05-30 | 2025-05-26 | 2025-05-27 | V Contribute Co., Ltd | N/A | Closed | 2025-05-27 18:33:32 | Yes | Yes | 2025-05-27 18:35:03 |  |  | 2025-05-30 | Chonradee Suwapan | Approved | Closed | 2025-06-13 10:53:24 | Yes | Yes | 2025-05-30 21:24:03 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-17 | 2025-06-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:18:03 | Yes | Yes | 2025-08-05 13:04:58 |  | 2025-05-15 | 2025-05-15 | Annop Auyto | Approved | Closed | 2025-06-09 15:03:36 | No | Yes | 2025-05-15 17:48:18 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-05-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-05-23 17:34:24 | No | No |  | 23-May-2025 AAU5636w S7 add g3a Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed D1: 100% |  | 2025-05-22 |  | N/A | Not assigned |  | No | No
CPCEM_2025 Capacity Expansion Ph8_EXP_ER | ChuadPakChee | 2026-01-17 |  |  |  | 2026-02-28 | 2026-01-17 | 2026-01-17 | Teloneer Company Limited | N/A | Closed | 2026-01-17 14:38:18 | No | No |  |  |  | 2026-02-28 | 2026-01-17 | 2026-01-17 | Teloneer Company Limited | N/A | Closed | 2026-01-17 16:31:38 | Yes | Yes | 2026-01-17 22:56:19 | SQC Close | 2026-02-28 | 2026-01-21 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:19:34 | Yes | Yes | 2026-01-21 12:32:59 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:29 | Yes | Yes | 2026-03-20 16:37:49 |  | 2026-01-31 | 2026-01-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:16:17 | Yes | Yes | 2026-01-17 11:07:56 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-17 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-17 19:18:45 | No | No |  | New L26F5 + NR26 (New AAU5636w)_CPCEM_N_3 New L26F5 + NR26 (New AAU5636w)_CPCEM_N_4 |  | 2026-01-21 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-22 18:31:58 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CPRGM_2025 Capacity Expansion Ph2_EXP_ER | CP Rayong | 2025-07-23 |  | Take Photo & Clear Pending |  | 2025-07-31 | 2025-07-16 | 2025-07-17 | Teloneer Company Limited | N/A | Closed | 2025-07-17 11:20:07 | No | No |  |  |  | 2025-07-31 | 2025-07-21 | 2025-07-22 | Teloneer Company Limited | N/A | Closed | 2025-07-22 20:50:47 | Yes | Yes | 2025-07-27 13:42:39 |  | 2025-07-31 | 2025-08-07 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-08-15 14:36:02 | Yes | Yes | 2025-11-07 13:35:35 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:17 | Yes | Yes | 2025-09-22 19:01:15 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:23:06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-23 |  | 2025-07-16 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-16 19:16:01 | No | No |  | **waiting on-service -- Replace UBBPg2#，Co NR07 + Replace 1RRU5508 to (RRU5516_900) + 4T4R S2 #，New L26F4F5 + NR26 (New 1RRU5818) + Co Antenna S2#，6 #，Co NR07 S1#，3 |  | 2025-07-17 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-17 16:30:05 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CPT2A_2025 Capacity Expansion Ph5_EXP_BKK | CARPARK IMPACT MUANGTHONG THANI 1 | [8 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-31 | 2026-05-31 |  |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-07-14 22:41:48 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CPTCM_2025 Capacity Expansion Ph8_EXP_ER | Chulaporn Technical College | 2026-01-24 |  |  |  | 2026-02-28 | 2026-01-24 | 2026-01-24 | Teloneer Company Limited | N/A | Closed | 2026-01-24 15:30:55 | No | No |  |  |  | 2026-02-28 | 2026-01-24 | 2026-02-03 | Teloneer Company Limited | N/A | Closed | 2026-02-03 18:21:20 | Yes | Yes | 2026-02-03 18:22:18 |  | 2026-02-28 | 2026-02-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-10 19:23:03 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:29 | Yes | Yes | 2026-03-20 16:38:27 |  | 2026-01-31 | 2026-01-24 | Adisak Chanmao(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:16:17 | Yes | Yes | 2026-01-24 17:51:49 |  | 2026-01-24 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-24 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-01-24 18:08:35 | No | No |  | Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 120 + Remove RRU x 2_CPTCM_H_2 (Co AAU5768) + Main Dir = 120 + Remove RRU x 2_CPTCM_H_7 New Antenna (LB)_CPTCM_L_2 New Sector J (Co AAU5768) + Main Dir = 120_CPTCM_H_J New Sector K (Co AAU5768) + Main Dir = 120_CPTCM_H_K |  | 2026-01-24 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-10 10:55:20 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CPTHB_2025 Capacity Expansion NW Modernization_EXP_BKK | CHAPTER THONGLOR 25 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-03-15 | 2026-03-15 | 2026-03-15 | 2026-03-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-15 16:34:11 | Yes | Yes | 2026-03-18 09:43:09 |  | 2026-04-03 | 2026-04-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:30:59 | Yes | Yes | 2026-04-03 12:00:40 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 19:52:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-21 11:16:04 | No | No |  | 21-Feb-2026 Add RRU5526 sector A Remove RRU3962 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CS39M_2025 Capacity Expansion Ph7_EXP_BKK | CHARANSANITWONG SOI 39 | [5 empty] | 2026-02-23 | 2026-02-23 | Akhom Srinara | N/A | Closed | 2026-02-23 17:44:36 | No | No |  |  |  | 2026-01-15 | 2026-01-15 | 2026-02-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-02-05 09:53:08 | Yes | Yes | 2026-02-25 22:26:50 |  | 2026-02-26 | 2026-02-25 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-04 09:27:40 | Yes | Yes | 2026-02-26 00:19:44 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 12:01:29 |  | 2026-06-20 | 2026-06-20 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-22 20:47:07 | Yes | Yes | 2026-06-21 00:28:07 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-15 14:02:26 | No | No |  | 15-Jan-2026 AddAAU5636w sector 6 Add g3a Remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CSR2M_2025 Capacity Expansion Ph3_EXP_BKK | PRACHA SAMRAN ROAD STATION 2 | 2025-09-03 |  |  |  | 2025-09-03 | 2025-09-11 | 2025-09-11 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-30 | 2025-09-11 | 2025-09-16 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:13:43 | Yes | Yes | 2025-09-30 10:13:43 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-10-03 12:01:59 | Yes | Yes | 2025-10-01 15:03:22 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:56 | Yes | Yes | 2025-10-06 16:10:34 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-12 22:22:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-03 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-03 19:44:30 | No | No |  | 2025-09-03_Add AAU5636w Sector 1#，2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-10 |  | N/A | Not assigned |  | No | No
CVSLM_2025 Capacity Expansion NW Modernization_EXP_BKK | CONVAN SILOM |  |  |  |  | 2026-03-24 | 2026-03-06 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-20 | 2026-03-19 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:32:31 | Yes | Yes | 2026-03-23 15:32:31 |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-12 16:26:02 | Yes | Yes | 2026-04-29 22:06:16 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-05-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-29 22:22:03 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-06 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-06 19:15:56 | No | No |  | 06-Mar-26 Replace RRU5507 to AAU5768 DMM S1 S2 S3 Add RRU3953 S3 05-03-2026. Replace UBBPeb x3#， UBBPg2 to UBBPg3a x2#， UBBPg3#， UBBPd6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CVSLM_2025 Capacity Expansion Ph8_EXP_BKK | CONVAN SILOM |  |  |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | V Contribute Co., Ltd | N/A | Closed | 2026-03-06 14:50:10 | No | No |  |  |  | 2026-03-20 | 2026-03-19 | 2026-04-21 | V Contribute Co., Ltd | N/A | Closed | 2026-04-21 14:49:08 | Yes | Yes | 2026-04-21 14:49:09 |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-06-02 09:34:19 | Yes | Yes | 2026-05-04 11:37:25 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-24 | 2026-03-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-29 22:25:21 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-06 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-06 19:15:56 | No | No |  | 06-Mar-26 Add AAU5636w S8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CW15M_2025 Capacity Expansion Ph5_EXP_BKK | BAN TULAWARN | [5 empty] | 2025-11-17 | 2025-11-17 | Narongsak wanichachiwa | N/A | Closed | 2025-11-27 10:57:47 | No | No |  |  |  | 2025-11-12 | 2025-11-14 | 2025-11-15 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-11-15 13:35:49 | Yes | Yes | 2025-11-17 14:26:41 |  |  | 2025-11-19 | OATTAPAN AUTTAHON | Approved | Closed | 2025-12-15 14:40:35 | Yes | Yes | 2025-11-21 15:22:32 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 16:27:26 |  | 2025-12-25 |  | Turnkey Communication Services Public Company Limited. | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-14 16:22:50 | No | No |  | 14-Nov-2025 AAU5636w S8 Add g3a 5/5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CWMSM_2025 Coverage Expansion Ph2_EXP_BKK | CHUMCHON WAT NA MAI SCHOOL | 2025-07-31 |  |  |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-07-31 17:45:00 | No | No |  |  |  | 2025-08-22 | 2025-08-10 | 2025-08-11 | V Contribute Co., Ltd | N/A | Closed | 2025-08-11 12:17:55 | Yes | Yes | 2025-08-11 12:19:24 |  | 2025-08-11 | 2025-08-11 | Chonradee Suwapan | Approved | Closed | 2025-08-14 17:18:45 | Yes | Yes | 2025-08-11 17:59:56 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:15 | Yes | Yes | 2025-08-18 15:22:22 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:51:44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-07-31 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-07-31 17:43:19 | No | No |  | 31-07-2025. Add RRU3953 Sec.2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-30 |  | N/A | Not assigned |  | No | No
CWT2M_2025 Capacity Expansion Ph6_EXP_BKK | CHAENG WATTANA(10) 2 | [5 empty] | 2025-12-23 | 2025-12-23 | Akhom Srinara | N/A | Closed | 2025-12-23 19:02:27 | No | No |  |  |  | 2025-12-22 | 2025-12-24 | 2025-12-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-25 10:22:21 | Yes | Yes | 2025-12-26 13:18:21 |  | 2025-12-27 | 2025-12-27 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-06 15:54:30 | Yes | Yes | 2025-12-27 22:16:02 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:03 | Yes | Yes | 2026-01-09 16:29:55 |  | 2026-01-08 | 2026-01-08 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-08 09:40:06 |  |  | 2025-12-31 | 2025-12-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-23 11:52:23 | No | No |  |  |  |  | 2025-12-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-22 17:26:38 | No | No |  | 22-Dec-2205 Add RRU5526 (1800-2100) sector 7 Replace Ant 12port co 700900 18002100 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CYP1M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAIYAPRUK_3G2100 |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:26:23 | No | No |  |  |  | 2026-04-30 | 2026-04-07 | 2026-04-07 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-07 15:36:30 | Yes | Yes | 2026-04-17 09:17:31 |  | 2026-06-12 | 2026-06-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approving | Assigned |  | Yes | Yes | 2026-06-12 14:20:49 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 21:19:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-04 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-04-04 19:20:29 | No | No |  | 04-04-2026. Add UBBPg2#， Replace RRU3962 to 5507 x2#， RRU3953 to 5516#， Ant.8 port Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D020A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Phra Nakharet Small Cell |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-03-22 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 12:06:19 | Yes | Yes | 2026-04-01 09:34:28 |  | 2026-04-08 | 2026-04-08 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-30 12:45:05 | Yes | Yes | 2026-04-08 10:49:04 | all page: project name wrong pg no 4: wrong watermark DUID in photo ( Not update ) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-12-29 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 21:20:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-19 17:02:39 | No | No |  | 19-Jan-2026 Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D028A_2025 Capacity Expansion NW Modernization_EXP_BKK | Rama 1 Road Small Cell 1 |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-28 | 2026-03-24 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 14:46:06 | Yes | Yes | 2026-03-24 14:46:07 |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-09-04 20:30:59 | Yes | Yes | 2026-04-29 22:07:39 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-14 | 2026-06-29 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-29 22:22:38 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-19 19:22:52 | No | No |  | 19-Feb-2026 Add RRU5507 *4 Sector 1 #，2 Remove RRU3962 *2 Replace Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D094A_2025 Capacity Expansion Ph3_EXP_BKK | SOI CHUEAM SAMPHAN 15_3 | [5 empty] | 2026-01-29 | 2026-01-29 | Akhom Srinara | N/A | Closed | 2026-01-29 00:27:55 | No | No |  |  |  |  | 2025-11-07 | 2026-01-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-01-27 11:18:21 | Yes | Yes | 2026-02-04 22:56:47 |  | 2026-02-05 | 2026-02-08 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-02-11 09:26:18 | Yes | Yes | 2026-02-08 02:44:42 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-02-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 12:04:43 |  | 2026-05-21 | 2026-05-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-19 15:33:22 | Yes | Yes | 2026-04-09 15:49:48 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-26 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-26 18:23:01 | No | No |  | 26-01-2026 ADD 5518 SECTOR 1 L26 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
D201A_2025 Capacity Expansion Ph2_EXP_BKK | SATHU PRADIT 15_3 | [5 empty] | 2025-10-23 | 2025-10-23 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-11-01 | 2025-11-03 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-03 12:45:42 | Yes | Yes | 2025-11-11 15:01:42 |  | 2025-11-13 | 2025-11-13 | Aomchun Jittreemit | Approved | Closed | 2025-11-24 09:53:54 | Yes | Yes | 2025-11-13 14:51:56 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 17:01:06 |  | 2025-11-28 | 2025-11-28 | Aomchun Jittreemit | Approved | Closed | 2026-03-12 09:24:43 | No | Yes | 2025-11-28 08:25:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-22 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-22 18:17:06 | No | No |  | 2025-10-22_Add RRU5818#， Replace to Ant 12 port(No RET) Sector B#， Add UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
D230A_2025 Capacity Expansion Ph6_EXP_BKK | Yek HUAY KWANG_TOT | [5 empty] | 2026-01-29 | 2026-01-29 | Akhom Srinara | N/A | Closed | 2026-01-29 00:27:55 | No | No |  |  |  | 2026-01-22 | 2026-01-22 | 2026-01-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-01-23 10:25:54 | Yes | Yes | 2026-01-27 14:35:00 | SQC Close | 2026-01-29 | 2026-02-14 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-02-17 16:38:08 | Yes | Yes | 2026-02-14 16:25:47 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 12:05:49 |  | 2026-02-18 | 2026-02-18 | Mattura Habayae | Approved | Closed | 2026-03-12 10:03:32 | Yes | Yes | 2026-02-18 17:13:40 |  |  | 2025-12-31 | 2026-01-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-01-22 17:04:04 | No | No |  |  |  |  | 2026-01-22 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-22 18:54:30 | No | No |  | 2026-01-22_Add RRU5516(LB) Sector A#， Replace UBBPd5 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D232A_2025 Capacity Expansion NW Modernization_EXP_BKK | Suanplu 3_1 |  |  |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-24 11:00:29 | No | No |  |  |  | 2026-02-28 | 2026-02-22 | 2026-02-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-25 10:22:25 | Yes | Yes | 2026-02-25 10:24:55 |  | 2026-02-24 | 2026-02-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-06 09:05:06 | Yes | Yes | 2026-03-09 17:57:02 | 1.Page 24#，/ need AIS passport for 2 people (not yet update) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-14 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-07-14 22:42:10 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-11 18:06:02 | No | No |  | 11-Feb-2026 Replace BBU5900 UMPTg2 Add GPS Add g2 g3a=2 Remove d5=2 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-24 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-27 06:07:20 | Yes | Yes | 2026-01-22 11:58:01 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D243A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI ASOKE_1 |  |  |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-05 08:14:49 | No | No |  |  |  | 2026-02-27 | 2026-03-17 | 2026-03-19 | V Contribute Co., Ltd | N/A | Closed | 2026-03-19 18:09:43 | Yes | Yes | 2026-03-19 18:09:43 |  | 2026-03-02 | 2026-03-02 | Chonradee Suwapan | Approved | Closed | 2026-03-16 09:29:19 | Yes | Yes | 2026-04-02 10:37:15 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-03-16 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-02 | 2026-03-02 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:17:02 | Yes | Yes | 2026-03-02 20:55:01 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-06 17:06:17 | No | No |  | 6-Feb-2026 Replace BBU5900 UMPTg2 Add g3a d5 g2 Add RRU5526 sector 1 Remove RRU3962 Replace Ant 12port No RET ติด GPS ไม่ได้ |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D305A_2025 Capacity Expansion Ph3_EXP_BKK | Pheecharam1 village |  |  |  | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-11-20 15:27:43 | No | No |  |  |  | 2025-10-30 | 2025-10-09 | 2025-11-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2025-11-20 10:27:42 | Yes | Yes | 2025-11-20 10:30:25 |  | 2025-12-31 | 2025-12-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-05-18 17:16:39 | Yes | Yes | 2026-05-14 15:09:23 | Need to upload INV file | Not Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-05-19 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:59 | Yes | Yes | 2026-07-14 22:43:03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-18 17:50:30 | No | No |  | 18-11-2025. Add RRU5818 Sec.B //09-10-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | wait OSP |  |  |  | N/A | Not assigned |  | No | No
D354A_2025 Capacity Expansion Ph5_EXP_BKK | Soi Phet Kasem 70 |  |  |  | 2025-12-05 | 2025-12-12 | 2025-12-16 | 2025-12-16 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-12-18 11:53:14 | No | No |  |  |  | 2025-11-20 | 2025-12-16 | 2025-12-17 | Teloneer Company Limited | N/A | Closed | 2025-12-17 14:05:13 | Yes | Yes | 2025-12-17 14:08:04 |  |  | 2025-12-17 | Apichart Kampuang | Approved | Closed | 2025-12-19 17:39:21 | Yes | Yes | 2025-12-17 16:14:29 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:03 | Yes | Yes | 2026-01-15 11:10:57 |  | 2025-12-04 | 2025-12-05 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:23:57 | Yes | Yes | 2025-12-05 09:02:11 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-08 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-08 17:40:06 | No | No |  | 08-12-2025. Add UBBPg2#， UBBPg3a#， RRU5818 Sec.C//Change SFP to Bidi //5-Dec-2025 Add Ant 12port No Ret Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D410A_2025 Capacity Expansion Ph3_EXP_BKK | Ban Uea Athon Lat LATKABANG 1_5 |  |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-28 | V Contribute Co., Ltd | N/A | Closed | 2025-10-28 20:08:32 | Yes | Yes | 2025-10-28 20:08:33 |  | 2025-10-21 | 2025-10-21 | Chonradee Suwapan | Approved | Closed | 2025-10-28 16:01:31 | Yes | Yes | 2025-10-21 20:02:46 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-28 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:28 | Yes | Yes | 2025-10-29 15:28:41 |  | 2025-10-21 | 2025-10-21 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-21 20:19:51 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-09 18:26:53 | No | No |  | 09-10-2025. Replace AIRU5246 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
D412A_2025 Capacity Expansion Ph3_EXP_BKK | Ban Uea Athon Lat LATKABANG 1_7 |  |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-28 | V Contribute Co., Ltd | N/A | Closed | 2025-10-28 16:05:56 | Yes | Yes | 2025-10-28 16:05:56 |  | 2025-10-22 | 2025-10-22 | Chonradee Suwapan | Approved | Closed | 2025-11-14 09:44:58 | Yes | Yes | 2025-10-22 20:24:44 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 17:02:20 |  | 2025-10-22 | 2025-10-22 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-22 20:35:41 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-09 18:26:53 | No | No |  | 09-10-2025. Add UBBPg3a#， Replace AIRU5246 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
D565A_2025 Capacity Expansion Ph2_EXP_BKK | SOI PHITSANULOK 3 Small Cell |  |  |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-09-22 11:24:57 | No | No |  |  |  | 2025-10-04 | 2025-10-03 | 2025-10-17 | V Contribute Co., Ltd | N/A | Closed | 2025-10-17 18:00:37 | Yes | Yes | 2025-10-17 18:00:37 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2026-04-08 09:35:02 | Yes | Yes | 2026-04-02 14:50:04 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-12-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:37 | Yes | Yes | 2026-01-09 16:34:47 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-09-29 12:41:30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-18 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-18 17:34:21 | No | No |  | 2025-09-18_Add UBBPg2#， Add RRU5516(LB)#， Replace to Ant 12 port Co 18-21-26 (No RET) Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install completed |  | 2025-09-22 |  | N/A | Not assigned |  | No | No
D676A_2025 Capacity Expansion Ph3_EXP_BKK | Bang Waek Rd. |  |  |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-15 15:44:53 | No | No |  |  |  | 2025-09-30 | 2025-09-23 | 2026-06-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-18 10:57:47 | Yes | Yes | 2026-06-18 11:04:30 |  | 2026-06-15 | 2026-06-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-18 09:41:28 | Yes | Yes | 2026-06-15 15:44:18 | Page no.6#，43#， need to fill install BBP card activity. | Not Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-08-18 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:36 | Yes | Yes | 2026-07-14 22:44:31 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-06-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-06-11 18:13:38 | No | No |  | 2026-06-11_Add RRU5818 Sector C 2025-10-27_Replace to BBU5900 by UMPTg2#， Add UBBPg3a#， **Pending GPS#， RRU5818//2025-09-22_Replace to Ant 12 port (No RET) Sector A#， *** Pending Replace to BBU5900 by UMPTg2#， Add RRU5818#， |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | wait OSP |  |  |  | N/A | Not assigned |  | No | No
D685A_2025 Capacity Expansion Ph2_EXP_BKK | SATHU PRADIT 42_1 | [5 empty] | 2025-09-18 | 2025-09-18 | Akhom Srinara | N/A | Closed | 2025-11-26 16:34:53 | No | No |  |  |  |  | 2025-09-20 | 2025-09-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-20 17:19:47 | Yes | Yes | 2025-09-22 10:05:05 |  | 2025-09-24 | 2025-09-24 | Kontira Kowapradit | Approved | Closed | 2025-11-11 11:05:21 | Yes | Yes | 2025-09-24 15:01:29 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 17:03:33 |  | 2025-09-25 | 2025-09-25 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-25 11:03:30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-25 17:31:00 | No | No |  | 25-Nov-2025 AAU5246 Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
D711A_2025 Capacity Expansion Ph5_EXP_BKK | SOI NAWAMIN74_2 | [5 empty] | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:42:22 | No | No |  |  |  | 2025-12-11 | 2025-12-12 | 2025-12-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-16 17:31:47 | Yes | Yes | 2025-12-17 19:58:22 |  | 2025-12-19 | 2026-01-20 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-22 15:33:02 | Yes | Yes | 2026-01-20 19:53:56 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 12:06:24 |  | 2025-12-17 | 2025-12-17 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:22:43 | Yes | Yes | 2025-12-17 23:31:42 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-11 18:39:32 | No | No |  | 11-Dec-2025 Add RRU5818 Sector A Add Ant 12port No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D801A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI.EKAMAI 6 |  |  |  |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-18 14:00:21 | No | No |  |  |  | 2026-02-21 | 2026-03-17 | 2026-03-18 | V Contribute Co., Ltd | N/A | Closed | 2026-03-18 11:14:36 | Yes | Yes | 2026-03-18 11:14:36 |  | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-02-27 16:26:01 | Yes | Yes | 2026-02-17 21:39:44 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:11:07 |  | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:03:32 | Yes | Yes | 2026-02-17 22:00:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-03 18:22:54 | No | No |  | 03-02-2026. Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D834A_2025 Capacity Expansion NW Modernization_EXP_BKK | SATHON 2_1 |  |  |  |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:44:49 | No | No |  |  |  | 2026-02-28 | 2026-01-31 | 2026-02-01 | V Contribute Co., Ltd | N/A | Closed | 2026-02-01 11:33:37 | Yes | Yes | 2026-02-01 11:33:38 | SQC Close | 2026-04-24 | 2026-04-24 | Chonradee Suwapan | Approved | Closed | 2026-06-02 09:35:21 | Yes | Yes | 2026-05-04 11:50:47 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-05 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-24 | 2026-04-24 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-24 17:41:56 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-23 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-03-20 10:54:12 | No | No |  | 23 Jan 2026 Replace 2RRU3962 to 2RRU5526 config 18/21 4T4R sector A and B cell on-service. ***Pending add 1UBBPg2. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D845A_2025 Capacity Expansion Ph2_EXP_BKK | SOI ChanMueang |  |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-11 17:27:06 | No | No |  |  |  | 2025-09-30 | 2025-09-29 | 2025-09-30 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 14:54:17 | Yes | Yes | 2025-09-30 14:54:17 |  | 2025-11-17 | 2025-11-17 | Chonradee Suwapan | Approved | Closed | 2026-04-08 09:35:02 | Yes | Yes | 2026-04-02 15:10:02 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-04-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:11:45 |  | 2025-11-17 | 2025-11-17 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-17 21:45:25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-11 17:26:09 | No | No |  | 11-Nov-2025 Add AAU5246 Sector A 5/3 13-Sep-2025 Prework ***Waiting core |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
D878A_2025 Capacity Expansion Ph3_EXP_BKK | SOI RAM INTHRA 117_1 |  |  |  | 2025-10-06 | 2025-10-13 | 2025-10-24 | 2025-10-24 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-28 10:43:04 | No | No |  |  | 2025-10-13 | 2025-10-15 | 2025-10-22 | 2025-10-25 | Teloneer Company Limited | N/A | Closed | 2025-10-25 15:02:10 | Yes | Yes | 2025-10-27 10:17:19 |  |  | 2025-10-28 | Apichart Kampuang | Approved | Closed | 2025-10-31 13:29:05 | Yes | Yes | 2026-01-05 14:41:24 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 14:24:18 |  | 2025-10-03 | 2025-10-03 | Teloneer Company Limited | Approved | Closed | 2025-11-28 14:34:00 | No | Yes | 2025-10-06 16:26:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-11 17:36:17 | No | No |  | 11-10-2025. Add UBBPg2#， UBBPg3a#， RRU5516 L900 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
D894A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI EKKAMAI 19 (TOT POLE) |  |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-13 10:47:09 | No | No |  |  |  | 2026-02-07 | 2026-02-06 | 2026-02-06 | V Contribute Co., Ltd | N/A | Closed | 2026-02-06 10:55:54 | Yes | Yes | 2026-02-06 10:55:55 | SQC Close | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-02-24 10:33:37 | Yes | Yes | 2026-02-12 21:55:29 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:12:03 |  | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-12 22:35:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-02-11 09:49:00 | No | No |  | 30-01-2026 Add card g2 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D933A_2025 Capacity Expansion Ph7_EXP_BKK | Soi Lat Phrao 87 Yek 4 |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-13 14:45:49 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-02-01 | 2026-02-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-02 15:04:36 | Yes | Yes | 2026-02-11 13:13:12 | SQC Close | 2026-02-13 | 2026-02-13 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-18 10:24:26 | Yes | Yes | 2026-02-13 14:47:43 |  | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-07-23 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-23 12:57:26 | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 12:07:32 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:45:15 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-12 17:47:45 | No | No |  | 12-Feb-26 Add RRU5818 SA SB 17-01-2025. ***Need RRU5818 Sec.A co Sec.B //Replace Ant.4 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D941A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PRIDI PHANOMYONG 3 (CHAO PHRAYA) |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-13 13:27:00 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-02-04 | 2026-02-05 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-05 21:42:10 | Yes | Yes | 2026-02-11 09:27:29 |  | 2026-02-13 | 2026-02-13 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-03-21 00:25:39 | Yes | Yes | 2026-03-07 10:43:35 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-03 | 2026-03-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:12:22 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:21:29 |  |  | 2026-03-31 | 2026-04-09 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-09 20:47:10 | No | No |  |  |  |  | 2026-01-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-26 17:44:22 | No | No |  | 26-01-2026. Add UBBPg3a#， Replace RRU3962 to RRU5526#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D973A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Suan Phlu 5 Small Cell 1 |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-05 14:29:41 | No | No |  |  |  | 2026-02-28 | 2026-02-23 | 2026-02-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-24 10:01:38 | Yes | Yes | 2026-02-24 10:16:40 |  | 2026-03-05 | 2026-03-16 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-02 09:35:21 | Yes | Yes | 2026-03-16 16:04:31 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-23 | 2026-06-05 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:21:59 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 16-Feb-26 Replace RRU3962 To RRU5526 SA ///Pending Add RRU5526 4T4R SB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DAVTM_2025 Capacity Expansion NW Modernization_EXP_BKK | DEPARTMENT OF AVIATION |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-03-21 | 2026-03-24 | 2026-03-25 | V Contribute Co., Ltd | N/A | Closed | 2026-03-25 09:30:13 | Yes | Yes | 2026-03-25 09:31:44 |  | 2026-04-30 | 2026-04-29 | Chonradee Suwapan | Approving | Assigned |  | Yes | Yes | 2026-04-29 23:57:30 | หน้างานพบ alarm GPS ให้ตรวจสอบ ภาพขันแน่น ตำแหน่งติด GPS และตรวจสอบน้ำเข้า GPS Ant หรือไม่ | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-30 00:06:47 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-05 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-05 18:04:46 | No | No |  | 05-03-26 Relace RRU3953 To RRU5516 S1 S2 S3#， Replace RRU5507 To RRU5502 S1 #，Replace RRU3962 To Replace RRU5526 S3#，Add UBBPg2 Remove RRU S6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DHASA_2025 Capacity Expansion NW Modernization_EXP_BKK | DHA Siamwalla co., lte |  |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-29 09:34:01 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-27 | 2026-01-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-27 21:02:54 | Yes | Yes | 2026-01-28 11:26:39 | SQC Close | 2026-01-29 | 2026-01-29 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-04-16 17:08:40 | Yes | Yes | 2026-04-09 15:57:18 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-30 | 2026-04-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:22:12 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-12 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-12 16:18:36 | No | No |  | 12 Jan 2026 RRU5526 Replace 2t2r to 2t4r sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DHYSM_2025 Coverage Expansion Ph2_EXP_BKK | DARUN HIDAYA SCHOOL | 2025-08-01 |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-01 17:31:33 | No | No |  |  |  | 2025-08-22 | 2025-08-13 | 2025-08-14 | V Contribute Co., Ltd | N/A | Closed | 2025-08-14 11:24:59 | Yes | Yes | 2025-08-14 11:26:18 |  | 2025-08-19 | 2025-08-19 | Chonradee Suwapan | Approved | Closed | 2025-08-22 17:57:48 | Yes | Yes | 2025-08-19 23:10:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:10:10 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:51:56 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-01 16:26:43 | No | No |  | 01-08-2025. Add RRU3953 Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
DINCA_2025 Capacity Expansion Ph2_EXP_BKK | DIANA COURT |  |  |  |  | 2025-11-24 | 2025-11-24 | 2025-11-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:45:54 | No | No |  |  |  | 2025-09-30 | 2025-10-01 | 2025-10-01 | V Contribute Co., Ltd | N/A | Closed | 2025-10-01 17:45:43 | Yes | Yes | 2025-10-01 17:45:43 |  | 2025-12-01 | 2025-12-01 | Chonradee Suwapan | Approved | Closed | 2025-12-03 09:56:01 | Yes | Yes | 2025-12-01 18:15:44 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:10:33 |  | 2025-12-01 | 2025-12-01 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-12-01 18:21:20 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-24 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-11-24 17:00:28 | No | No |  | 2025-11-24_Add AAU5246 Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-21 |  | N/A | Not assigned |  | No | No
DLTCM_2025 Capacity Expansion Ph1_EXP_BKK | DEPARTMENT OF LAND TRANSPORT CHATUCHAK BUILDING 6 | 2025-06-17 |  |  |  | 2025-06-17 | 2025-06-17 | 2025-06-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-06-17 16:58:57 | No | No |  |  |  | 2025-06-27 | 2025-06-23 | 2025-06-24 | V Contribute Co., Ltd | N/A | Closed | 2025-06-24 09:56:33 | Yes | Yes | 2025-06-24 09:57:58 |  | 2025-06-20 | 2025-06-20 | Chonradee Suwapan | Approved | Closed | 2025-06-27 16:09:12 | Yes | Yes | 2025-06-20 19:04:29 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-02 | 2025-07-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:18:03 | Yes | Yes | 2025-08-05 13:10:01 |  | 2025-06-05 | 2025-06-05 | Annop Auyto | Approved | Closed | 2025-06-09 15:04:09 | No | Yes | 2025-06-05 18:00:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-06-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-06-17 17:24:02 | No | No |  | 17-Jun-2025 Add RRU5516 (700#，900 )S3 Rep.Ant 8port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-06-16 |  | N/A | Not assigned |  | No | No
DLTCM_2025 Capacity Expansion Ph6_EXP_BKK | DEPARTMENT OF LAND TRANSPORT CHATUCHAK BUILDING 6 |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 16:39:36 | No | No |  |  |  | 2025-12-31 | 2026-01-05 | 2026-01-05 | V Contribute Co., Ltd | N/A | Closed | 2026-01-05 12:10:23 | Yes | Yes | 2026-01-05 12:10:23 |  | 2026-01-22 | 2026-01-22 | Chonradee Suwapan | Approved | Closed | 2026-02-09 16:38:58 | Yes | Yes | 2026-02-06 12:27:09 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 12:08:05 |  | 2026-01-22 | 2026-01-22 | Chonradee Suwapan | Approved | Closed | 2026-01-29 17:09:02 | Yes | Yes | 2026-01-22 18:28:18 |  |  | 2025-12-31 | 2025-12-25 | V Contribute Co., Ltd | N/A | Closed | 2025-12-25 13:32:45 | No | No |  |  |  |  | 2025-12-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-25 17:22:28 | No | No |  | 25-Dec-2025 Add AAU5636w sector 6 Add g3a Remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DNSOM_2025 Capacity Expansion Ph7_EXP_ER | Denso Wellgrow |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  | 2025-12-31 |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-31 |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-12-31 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DSK1B_2025 Coverage Expansion Ph1_EXP_BKK | DIAMOND SUKHUMVIT (LEFT) |  |  |  |  | 2025-10-21 | 2025-10-21 | 2025-10-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-21 17:43:19 | No | No |  |  |  | 2025-10-18 | 2025-10-29 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 16:08:56 | Yes | Yes | 2025-10-30 16:08:57 |  | 2025-10-24 | 2025-10-24 | Chonradee Suwapan | Approved | Closed | 2025-11-03 20:59:11 | Yes | Yes | 2025-10-24 19:43:17 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-02 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 14:29:12 |  | 2025-10-24 | 2025-10-24 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-10-24 19:58:36 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-10 16:53:49 | No | No |  | 10-10-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Complted |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
DWOGM_2025 Capacity Expansion Ph1_EXP_SR | Don Pong Wong |  |  |  |  | 2025-08-31 | 2025-08-13 | 2025-08-13 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-13 11:45:10 | No | No |  |  |  | 2025-08-04 | 2025-08-08 | 2025-08-08 | Teloneer Company Limited | N/A | Closed | 2025-08-08 21:32:03 | Yes | Yes | 2025-08-12 14:35:57 |  | 2025-08-13 | 2025-08-13 | Supot Hoonyong | Approved | Closed | 2025-09-01 11:12:03 | Yes | Yes | 2025-08-13 12:37:51 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:16 | Yes | Yes | 2025-09-22 19:27:34 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-08-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-08 | 2025-08-08 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-08-08 18:44:18 | No | No |  | Add UBBPg3a*1 Add new HB S1 & S3 S1 > AAU5636w S2 > AAU5636w |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-08-13 | Nattawoot Suwan | N/A | Closed | 2025-08-13 11:45:49 | No | No |  |  |  |  | 2025-08-13 | 2025-08-12 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
E048A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PRIDI BANOMYONG 7 (TOT POLE) |  |  |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-02 16:43:53 | No | No |  |  |  | 2026-01-26 | 2026-01-30 | 2026-02-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-27 11:51:50 | Yes | Yes | 2026-02-27 11:54:28 |  | 2026-03-02 | 2026-03-02 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-04-16 16:58:38 | Yes | Yes | 2026-04-07 10:33:27 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-20 | 2026-04-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:22:46 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-26 18:26:07 | No | No |  | 2026-01-26_Replace RRU3962 to RRU5526 Sector B#， Add UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E069A_2025 Capacity Expansion Ph5_EXP_BKK | Soi Pracha U-Thit 81 Small Cell 1 | 2025-12-04 |  |  |  | 2026-01-08 | 2026-01-08 | 2026-01-08 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-08 17:10:04 | No | No |  |  |  | 2025-12-28 | 2025-12-11 | 2026-01-08 | V Contribute Co., Ltd | N/A | Closed | 2026-01-08 11:37:01 | Yes | Yes | 2026-01-08 11:37:01 |  | 2026-01-08 | 2026-01-08 | Chonradee Suwapan | Approved | Closed | 2026-02-06 13:32:23 | Yes | Yes | 2026-01-20 15:33:40 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 12:09:12 |  | 2026-01-08 | 2026-01-08 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:02:00 | Yes | Yes | 2026-01-08 22:08:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-08 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-08 17:30:16 | No | No |  | 5-Dec-2025 ***Pending split GPS /// Replace BBU5900 UMPTg2 Add g2 g3a Add RRU3962 Sector C Remove AAU3940 Add RRU5818 Sector C Add Ant 12port No RET Done 8-Jan-2026 Add GPS done and No alarm |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E074A_2025 Capacity Expansion Ph2_EXP_BKK | Surao Khlong Nueng Rd1_1 |  |  |  |  | 2025-09-25 | 2025-09-25 | 2025-09-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-25 09:53:30 | No | No |  |  |  | 2025-09-30 | 2025-09-25 | 2025-09-29 | V Contribute Co., Ltd | N/A | Closed | 2025-09-29 21:29:16 | Yes | Yes | 2025-09-29 21:29:17 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2025-10-16 16:35:33 | Yes | Yes | 2025-11-24 17:45:17 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 16:10:29 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-09-29 12:42:48 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-24 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-24 18:16:38 | No | No |  | 24-Sep-2025 Add RRU5516 (700900) SA Replace Ant 12port No Ret Add g2 Remove d5 0/3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-09-24 |  | N/A | Not assigned |  | No | No
E076A_2025 Capacity Expansion Ph2_EXP_BKK | TOT PoleSOI VIPHAVADI RANGSIT 19 (ON ANUSON) | [5 empty] | 2025-10-18 | 2025-10-18 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  | ติดตั้งวันที่ 29-30/9/2025 |  |  | 2025-09-30 | 2025-10-01 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-01 17:47:48 | Yes | Yes | 2025-10-01 17:47:48 |  | 2025-10-20 | 2025-10-20 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-22 15:01:43 | Yes | Yes | 2026-01-05 16:04:24 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:00 | Yes | Yes | 2025-10-21 16:11:53 |  | 2025-10-08 | 2025-10-08 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-28 14:33:42 | No | Yes | 2025-10-08 09:51:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-29 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-29 17:23:14 | No | No |  | 15-Oct-2025 Clear Pending work 2025-09-29_Replace to BBU5900 by UMPTg2#， Add UBBPg3a#， UBBPd5#， Split GSP#， RRU5518#， Replace to Ant 12 port (No RET) Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-17 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
E082A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI NANG LYCHEE_SMALL CELL 2 |  |  |  | 2026-01-26 | 2026-01-26 | 2026-02-25 | 2026-02-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-02-25 15:21:36 | No | No |  |  | 2026-01-25 | 2026-01-25 | 2026-01-26 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:20:27 | Yes | Yes | 2026-03-23 15:53:22 |  | 2026-02-25 | 2026-04-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-30 12:34:52 | Yes | Yes | 2026-04-03 10:54:56 | Page no.1#， site name wrong. Page no.7#， Install BBP SN wrong in INV. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-15 | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:23:06 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-20 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-03-20 10:57:21 | No | No |  | 20-1-2026 Replace rru5962 to rru5526 sector 1 Done#， pending add card ubbp G2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-01-26 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E099A_2025 Capacity Expansion Ph2_EXP_BKK | Soi Surao Khlong Nueng 9_1 |  |  |  |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-01 09:34:25 | No | No |  |  |  | 2025-12-12 | 2025-12-10 | 2025-12-10 | V Contribute Co., Ltd | N/A | Closed | 2025-12-10 15:18:18 | Yes | Yes | 2025-12-10 15:18:19 |  | 2025-12-02 | 2025-12-02 | Chonradee Suwapan | Approved | Closed | 2025-12-04 09:31:09 | Yes | Yes | 2026-01-13 19:45:43 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:14:11 |  | 2025-12-02 | 2025-12-02 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-12-02 20:40:00 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-27 15:07:30 | No | No |  | 27-Nov-2025 Add RRU5818 Sector A Replace Ant 12 port No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-28 |  | N/A | Not assigned |  | No | No
E100A_2025 Capacity Expansion Ph2_EXP_BKK | Soi Surao Khlong Nueng 7_1 | 2025-11-10 |  |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-10 17:58:20 | No | No |  |  |  | 2025-11-14 | 2025-11-17 | 2025-11-19 | V Contribute Co., Ltd | N/A | Closed | 2025-11-19 15:49:56 | Yes | Yes | 2025-11-19 15:49:57 |  | 2025-11-13 | 2025-11-13 | Chonradee Suwapan | Approved | Closed | 2025-12-08 09:18:18 | Yes | Yes | 2025-11-13 20:31:06 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:37 | Yes | Yes | 2026-01-09 16:46:05 |  | 2025-11-13 | 2025-11-13 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-11-13 20:56:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-01 17:59:37 | No | No |  | 11-01-2025. Combine RRU5818 with Sec.A#， Ant.12 port Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-07 |  | N/A | Not assigned |  | No | No
E100A_2025 Capacity Expansion Ph3_EXP_BKK | Soi Surao Khlong Nueng 7_1 | 2025-11-10 |  |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-10 17:58:32 | No | No |  |  |  | 2025-11-14 | 2025-11-25 | 2025-11-25 | V Contribute Co., Ltd | N/A | Closed | 2025-11-25 20:28:49 | Yes | Yes | 2025-11-25 20:28:49 |  | 2025-11-13 | 2025-11-13 | Chonradee Suwapan | Approved | Closed | 2025-11-20 09:23:35 | Yes | Yes | 2025-11-13 20:31:57 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 17:14:32 |  | 2025-11-13 | 2025-11-13 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-11-13 20:57:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-01 17:59:37 | No | No |  | 11-01-2025. Add RRU5818 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-07 |  | N/A | Not assigned |  | No | No
E131A_2025 Capacity Expansion Ph2_EXP_BKK | SOI LATPROA 122_1 |  |  |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-20 17:28:39 | No | No |  |  | 2025-09-30 | 2025-09-30 | 2025-09-24 | 2025-09-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-09-25 10:04:36 | Yes | Yes | 2025-11-10 09:10:05 |  | 2026-01-24 | 2026-01-21 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-01-27 15:29:52 | Yes | Yes | 2026-02-26 11:47:13 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-27 12:09:47 |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:59 | Yes | Yes | 2026-07-14 22:44:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-06 17:15:26 | No | No |  | 06-01-2026. Add RRU5516 L900 Sec.A#， RRU5818 Sec.C //23-09-2025. Add UBBPg2#， Replace RRU5516 L18 Sec.B#， RRU5818 Sec.B#， Ant.12 port Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | wait OSP |  | 2026-01-19 |  | N/A | Not assigned |  | No | No
E136A_2025 Capacity Expansion Ph2_EXP_BKK | RAM KAMHAENG 53 soi 3 | 2025-11-10 |  |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-10 17:58:32 | No | No |  |  |  | 2025-10-31 | 2025-11-06 | 2025-11-10 | V Contribute Co., Ltd | N/A | Closed | 2025-11-10 11:04:34 | Yes | Yes | 2025-11-10 11:04:35 |  | 2025-11-13 | 2025-11-13 | Chonradee Suwapan | Approved | Closed | 2026-04-08 16:59:37 | Yes | Yes | 2026-04-02 15:21:15 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-04-12 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-11-13 | 2025-11-13 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-13 21:00:02 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-31 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-31 17:06:16 | No | No |  | 31-10-2025. Add UBBPg3a x2#， RRU5818 Sec.B#， RRU5516 L900 Sec.C#， Replace Ant.12 port Sec.B#， C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
E142A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SRI BAMPHEN SMALL CELL 1 |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-06 13:47:58 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-30 | 2026-01-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-31 11:32:21 | Yes | Yes | 2026-02-04 10:21:42 | SQC Close | 2026-02-06 | 2026-02-06 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-23 15:57:48 | Yes | Yes | 2026-02-20 09:03:00 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:14:52 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:23:21 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-17 19:45:03 | No | No |  | 17-01-2025. Replace RRU3962 to RRU5526 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E178A_2025 Capacity Expansion NW Modernization_EXP_BKK | Surasak Rd. Small Cell (TOT) | 2026-01-14 |  |  |  | 2026-01-14 | 2026-02-10 | 2026-02-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-08 22:22:15 | No | No |  |  |  | 2026-01-31 | 2026-01-16 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 14:24:10 | Yes | Yes | 2026-02-11 14:24:10 | SQC Close | 2026-02-11 | 2026-02-11 | Chonradee Suwapan | Approved | Closed | 2026-02-13 15:36:20 | Yes | Yes | 2026-02-11 19:04:15 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:15:30 |  | 2026-02-11 | 2026-02-11 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-11 19:08:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-14 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-14 16:43:26 | No | No |  | 14 Jan 2026 Replace add card g3a 1#， remove g2 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E178A_2025 Capacity Expansion Ph1_EXP_BKK | Surasak Rd. Small Cell (TOT) |  |  |  |  | 2025-06-30 | 2025-06-30 | 2025-06-30 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-06-30 12:33:44 | No | No |  |  |  | 2025-06-27 | 2025-07-01 | 2025-07-02 | V Contribute Co., Ltd | N/A | Closed | 2025-07-02 10:21:15 | Yes | Yes | 2025-07-02 10:22:22 |  | 2025-07-03 | 2025-07-03 | Chonradee Suwapan | Approved | Closed | 2025-11-27 16:07:40 | Yes | Yes | 2025-11-14 15:45:21 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2026-01-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 11:17:30 |  | 2025-05-15 | 2025-05-15 | Annop Auyto | Approved | Closed | 2025-06-09 15:03:36 | No | Yes | 2025-05-15 17:48:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-06-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-06-27 16:52:38 | No | No |  | 27-06-2025. Replace BBU5900 UMPTg2 Add RRU5818 SA Add g3a Remove d6=1 เนื่องจาก D6 card เสีย เลยใช้ d5 Replace Ant.12 port Sec.A 20-06-2025. Replace Ant.12 port Sec.A#， Rollback BBU |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
E186A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Phet Ploi Small Cell 1 (TOT) |  |  |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-20 17:28:39 | No | No |  |  |  | 2026-01-31 | 2026-01-17 | 2026-01-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-23 13:39:49 | Yes | Yes | 2026-01-23 13:42:15 |  | 2026-01-23 | 2026-01-23 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-02 09:33:47 | Yes | Yes | 2026-01-23 14:13:27 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:15:49 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:23:38 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-12 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-12 16:18:36 | No | No |  | 12 Jan 2026 RRU5526 Replace 2t2r to 2t4r sector A . There is VSWR sector 1 port 1#，2 1.93 wait fix |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E189A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SUKHUMVIT 41 SMALL CELL 1 (TOT) | [5 empty] | 2026-04-09 | 2026-04-09 | Akhom Srinara | N/A | Closed | 2026-04-21 20:48:32 | No | No |  |  |  | 2026-02-13 | 2026-02-19 | 2026-04-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-04-11 10:31:04 | Yes | Yes | 2026-04-20 14:27:22 |  | 2026-04-28 | 2026-04-29 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-09-04 20:33:00 | Yes | Yes | 2026-04-29 00:21:43 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-06-21 | 2026-06-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-22 20:50:24 | Yes | Yes | 2026-06-21 07:32:15 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-18 18:21:19 | No | No |  | 18-Feb-26 Replace BBU3900 To BBU5900 GPS Replace RRU3962 to RRU5526 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E202A_2025 Capacity Expansion Ph3_EXP_BKK | SOI RAMKAMHAENG 166 YAK 3 |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-10-18 | 2025-12-10 | 2025-12-11 | V Contribute Co., Ltd | N/A | Closed | 2025-12-11 18:18:18 | Yes | Yes | 2025-12-11 18:18:18 |  | 2025-11-24 | 2025-11-24 | Chonradee Suwapan | Approved | Closed | 2025-12-04 09:31:09 | Yes | Yes | 2025-11-24 21:54:59 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:15:24 |  | 2025-11-24 | 2025-11-24 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-11-24 22:19:09 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-20 17:35:28 | No | No |  | 20-Nov-2025 Add RRU5818 SA SB 16-Oct-2025 ***Pending Add RRU5818 SA SB 5/2 SA 132 5/5 SB 135 //Replace BBU5900 UMPTg2 Add g3a Split GPS Replace Ant.12port No Ret SB Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-24 |  | N/A | Not assigned |  | No | No
E220A_2025 Capacity Expansion Ph5_EXP_BKK | B.Care Medical Center Hospital | [5 empty] | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:42:22 | No | No |  |  |  | 2025-12-17 | 2025-12-18 | 2025-12-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-21 11:50:18 | Yes | Yes | 2025-12-26 20:40:54 |  | 2026-01-06 | 2026-01-06 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-08 16:06:24 | Yes | Yes | 2026-01-06 13:36:57 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 16:48:32 |  | 2026-01-05 | 2026-01-05 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-05 11:51:39 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-17 12:43:43 | No | No |  | 17-Dec-2025 Add RRU5818 sector A Replace Ant 12port No Ret Add g2 Remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E276A_2025 Capacity Expansion Ph2_EXP_BKK | Soi Silom 21 Small Cell (TOT) |  |  |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-15 18:16:03 | No | No |  |  |  | 2025-09-30 | 2025-09-23 | 2025-09-25 | V Contribute Co., Ltd | N/A | Closed | 2025-09-25 17:09:26 | Yes | Yes | 2025-09-25 17:09:27 |  | 2025-12-20 | 2025-12-20 | Chonradee Suwapan | Approved | Closed | 2026-01-13 14:55:31 | Yes | Yes | 2026-01-15 12:03:55 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 16:49:44 |  | 2025-12-20 | 2025-12-20 | Chonradee Suwapan | Approved | Closed | 2026-01-07 15:01:54 | Yes | Yes | 2026-01-07 10:12:09 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-15 16:40:19 | No | No |  | 15-Dec-2025 Add RRU5516 (700900)S2 Add Ant 12 Port No Ret 11-Sep-2025 ***Pending Add RRU5516 (700900)S2 Add Ant 12 Port ///Add g2 Remove d2 =2 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-12-12 |  | N/A | Not assigned |  | No | No
E388A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SUKHUMVIT 13 SMALL CELL 1 (TOT) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:13:29 | Yes | Yes | 2026-03-23 15:19:10 |  | 2026-03-27 | 2026-03-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-04 20:33:00 | Yes | Yes | 2026-05-15 16:36:02 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:24:10 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-17 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-17 16:59:58 | No | No |  | 17-Feb-26 Replace RRU3962 to RRU5526 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E504A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Sukhumvit 49/6 Micro Cell Station 1 (TOT POLE) |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-17 | 2026-02-17 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-08 23:00:59 | No | No |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-18 11:41:26 | Yes | Yes | 2026-02-18 11:43:46 |  | 2026-02-13 | 2026-02-13 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-04-23 10:52:27 | Yes | Yes | 2026-02-20 09:49:17 | Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-07 | 2026-04-23 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 21:24:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-05 19:48:28 | No | No |  | 5 Feb 2025 add 1UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E506A_2025 Capacity Expansion Ph2_EXP_BKK | TOT Pole Soi Nqam Wong Wan 44 | [5 empty] | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:39:59 | No | No |  | solution Ant spit เสนอส่งเมล์แล้วครับ |  | 2025-12-09 | 2025-12-09 | 2025-12-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-10 15:46:41 | Yes | Yes | 2025-12-18 21:54:45 |  | 2025-12-19 | 2025-12-18 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-08-18 09:41:28 | Yes | Yes | 2025-12-19 01:34:52 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-08-18 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-12-19 | 2025-12-18 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:22:14 | No | Yes | 2025-12-19 01:57:23 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-09 19:29:49 | No | No |  | 9-Dec-2025 Replace BBU5900 UMPTg2 Add GPS add g3a Add RRU5818 Sector A replace Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
E520A_2025 Capacity Expansion NW Modernization_EXP_BKK | Surawong Rd. 1 Small Cell |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-06 15:06:04 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-31 19:48:22 | Yes | Yes | 2026-02-04 11:14:03 |  | 2026-02-06 | 2026-02-06 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-03-09 09:23:58 | Yes | Yes | 2026-02-20 10:00:58 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-27 | 2026-03-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:18:19 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 21:24:56 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-15 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-15 18:20:12 | No | No |  | 15 Jan 2026 Replace ant 4 port to 12 secor 1#，2#， swop card g2 to g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E521A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SUKHUMVIT 31 (SAWATDEE) |  |  |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-28 15:56:53 | No | No |  |  | 2026-03-09 | 2026-03-13 | 2026-03-13 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 17:22:47 | Yes | Yes | 2026-03-25 14:15:41 |  | 2026-04-28 | 2026-04-28 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-04-28 09:20:15 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 21:25:12 |  |  | 2026-03-02 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-02 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-03-02 17:22:39 | No | No |  | 2026-03-02_Replace to BBU5900 by UMPTg2#， Add UBBPg2#， UBBPg3a#， No GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-02-27 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E611A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI EKKAMAI 10 YEAK 2 | 2026-01-29 |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-02-07 | 2026-03-20 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:18:36 | Yes | Yes | 2026-03-23 15:18:37 |  | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-02-24 10:33:37 | Yes | Yes | 2026-02-12 21:58:28 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:19:16 |  | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-12 22:37:10 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-29 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-29 18:33:39 | No | No |  | 2026-01-29_Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E625A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Ekamai 22 (Soi Prasoet Di) Small Cell (Pipe) |  |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-13 10:47:09 | No | No |  |  |  | 2026-02-06 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 20:20:09 | Yes | Yes | 2026-02-11 20:20:10 |  | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-02-27 16:26:01 | Yes | Yes | 2026-02-12 22:01:23 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:19:34 |  | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-12 22:38:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-02 19:21:08 | No | No |  | 2026-02-02_Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E639A_2025 Capacity Expansion Ph2_EXP_BKK | SOI LATPROA 122_02 |  |  |  | 2025-12-14 | 2025-12-14 | 2025-12-14 | 2025-12-14 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-12-15 11:17:14 | No | No |  |  | 2025-11-30 | 2025-11-30 | 2025-11-27 | 2025-11-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-11-27 20:27:32 | Yes | Yes | 2025-12-15 10:03:53 |  | 2025-12-31 | 2025-12-15 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-12-19 17:59:27 | Yes | Yes | 2025-12-15 11:19:22 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 16:54:38 |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:59 | Yes | Yes | 2026-07-14 22:47:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-24 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-24 15:01:07 | No | No |  | 24-Nov-2025 Add RRU5516 (700900) Sector B Replace Ant 12 port No RET Use sfp BiDi 0/5 port A VSWR 140 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | LL แจ้งว่า AIS คุยเรื่องสัญญาและค่าเช่าก่อน ส่งเมลแล้ว wait AQM H/O |  | 2025-12-11 |  | N/A | Not assigned |  | No | No
E682A_2025 Capacity Expansion Ph2_EXP_BKK | Chumchon Ramkhamhaeng 53 Soi 2 | 2025-09-23 |  |  |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-04 11:05:56 | No | No |  |  |  | 2025-09-30 | 2025-10-09 | 2025-10-16 | V Contribute Co., Ltd | N/A | Closed | 2025-10-16 16:12:40 | Yes | Yes | 2025-10-16 16:12:40 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-18 16:04:59 | Yes | Yes | 2025-11-08 17:54:23 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Krittee Chamboot 00319410 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 17:19:34 |  | 2025-11-07 | 2025-11-07 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-11-07 12:44:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-04 10:34:53 | No | No |  | 4-Nov-2025 Add RRU5818 Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-11-03 |  | N/A | Not assigned |  | No | No
E715A_2025 Capacity Expansion Ph2_EXP_BKK | Rama 2 Road Small Cell TOT | 2025-11-10 |  |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-10 17:58:32 | No | No |  |  |  | 2025-11-15 | 2025-11-25 | 2025-11-26 | V Contribute Co., Ltd | N/A | Closed | 2025-11-26 19:14:31 | Yes | Yes | 2025-11-26 19:14:31 |  | 2025-11-13 | 2025-11-13 | Chonradee Suwapan | Approved | Closed | 2025-12-01 16:22:32 | Yes | Yes | 2025-11-13 20:33:16 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 16:55:53 |  | 2025-11-13 | 2025-11-13 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-13 21:01:02 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-03 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-03 17:06:34 | No | No |  | 03-11-2025. Combine RRU5258 Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-07 |  | N/A | Not assigned |  | No | No
E717A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Naradhiwas Rajanagarindra 10. Small Cell - TOT |  |  |  |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-10 16:17:32 | No | No |  |  |  | 2026-02-07 | 2026-02-16 | 2026-02-23 | V Contribute Co., Ltd | N/A | Closed | 2026-02-23 13:30:50 | Yes | Yes | 2026-02-23 13:30:50 |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-02-17 16:38:08 | Yes | Yes | 2026-02-09 21:18:23 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:19:53 |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-09 21:28:14 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-21 18:17:00 | No | No |  | 21-01-2026. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a x2#， UBBPg2#， GPS |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-20 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 05:53:28 | Yes | Yes | 2026-01-20 16:51:49 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E858A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Chan 41/1 |  |  |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-04 20:54:54 | No | No |  |  |  | 2026-02-07 | 2026-02-13 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:10:46 | Yes | Yes | 2026-03-23 15:10:46 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-13 15:36:20 | Yes | Yes | 2026-02-04 19:07:45 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:20:30 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-04 19:16:48 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-22 15:40:39 | No | No |  | 22-Jan-2026 Replace BBU5900 UMPTg2 g3a g2 split GPS 21-Jan-2026 ***Pending Replace BBU5900 UMPTg2 g3a g2 split GPS /// Replace Ant to Ant 12port No Ret Sector A Done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-20 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 05:53:28 | Yes | Yes | 2026-01-20 16:52:07 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E88BB_2025 Capacity Expansion NW Modernization_EXP_BKK | E88 BANGKOK BUILDING | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  | 2026-02-17 | 2026-02-28 | 2026-02-19 | 2026-02-19 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-19 15:31:49 | Yes | Yes | 2026-02-20 10:22:25 |  | 2026-02-13 | 2026-02-20 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-05-12 16:26:02 | Yes | Yes | 2026-05-17 10:02:57 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-05-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-02 | 2026-03-02 | Pariyakorn Jearwarakul | Approved | Closed | 2026-07-20 10:32:17 | Yes | Yes | 2026-03-25 12:39:04 |  | 2026-02-17 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-17 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-17 16:59:58 | No | No |  | 17-Feb-26 Replace RRU3962 to RRU5526 S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E910A_2025 Capacity Expansion Ph2_EXP_BKK | Small Cell Evergreen Mansion |  |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-11 17:27:06 | No | No |  |  |  | 2025-09-30 | 2025-09-22 | 2025-09-23 | V Contribute Co., Ltd | N/A | Closed | 2025-09-23 10:37:09 | Yes | Yes | 2025-09-23 10:37:09 |  | 2025-11-17 | 2025-11-17 | Chonradee Suwapan | Approved | Closed | 2026-02-12 14:35:31 | Yes | Yes | 2026-02-03 11:32:15 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-02-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 12:12:45 |  | 2025-11-17 | 2025-11-17 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-17 21:47:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-07 16:04:03 | No | No |  | 7-Nov-2025 Add RRU5516 (700900) SB 0/3 Replace Ant 12port No RET 20-Sep-2025 ***Pending wait core Add RRU5516 (700900) SB 0/3 ///Add g3a g2 Remove d5 Replace Ant 12port No RET Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-10 |  | N/A | Not assigned |  | No | No
E935A_2025 Capacity Expansion Ph2_EXP_BKK | Small Cell Soi Sri Rung | 2025-09-23 |  |  |  | 2025-11-14 | 2025-11-14 | 2025-11-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-21 12:25:28 | No | No |  |  |  | 2025-09-30 | 2025-09-24 | 2025-09-25 | V Contribute Co., Ltd | N/A | Closed | 2025-09-25 10:00:22 | Yes | Yes | 2025-09-25 10:00:23 |  | 2025-11-22 | 2025-11-22 | Chonradee Suwapan | Approved | Closed | 2026-01-13 14:55:31 | Yes | Yes | 2025-11-28 12:45:55 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 17:02:05 |  | 2025-11-22 | 2025-11-22 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-22 20:13:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-14 15:00:36 | No | No |  | 14-Nov-2025 Add RRU5516 (700900) SA Ant.12 port No ret Sec.A (0/0 #， 101) 23-09-2025. ***Need RRU5516 L900#， Ant.12 port Sec.A //Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Install 90% / ยังไม่มี Core ตามแผน |  | 2025-11-13 |  | N/A | Not assigned |  | No | No
E942A_2025 Capacity Expansion Ph2_EXP_BKK | SMALL CELL SOI PATTANAKARN 37 | 2025-09-30 |  |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 10:49:05 | No | No |  |  |  | 2025-10-10 | 2025-10-21 | 2025-10-24 | V Contribute Co., Ltd | N/A | Closed | 2025-10-24 11:00:23 | Yes | Yes | 2025-10-24 11:00:24 |  | 2025-10-07 | 2025-10-07 | Chonradee Suwapan | Approved | Closed | 2025-10-20 15:40:02 | Yes | Yes | 2025-10-25 09:41:00 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 16:18:02 |  | 2025-10-07 | 2025-10-07 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-07 19:38:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-30 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-30 16:47:54 | No | No |  | 30-09-2025. Add UBBPg2#， UBBPg3a#， RRU5516 L900#， Ant.12 port Sec.A#， RRU5818 Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK40 |  | 2025-09-30 |  | N/A | Not assigned |  | No | No
E961A_2025 Capacity Expansion Ph2_EXP_BKK | SMALL CELL SOI PRACHA RAT BAMPHEN 5 YAK 6-1 | [5 empty] | 2025-12-09 | 2025-12-09 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  | ตู้ไฟ AC เต็ม #，ต้อง Add single wall mount =1 set |  | 2025-12-03 | 2025-12-04 | 2025-12-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-04 16:12:56 | Yes | Yes | 2025-12-09 08:58:22 |  | 2025-12-11 | 2026-01-16 | Muhamadnase Chesamae | Approved | Closed | 2026-01-22 09:30:54 | Yes | Yes | 2026-01-20 14:36:57 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 12:13:21 |  | 2025-12-13 | 2025-12-13 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:22:43 | No | Yes | 2025-12-13 12:14:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-01 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-12-01 17:32:50 | No | No |  | 2025-12-01_Add RRU5516(LB)#， Ant Sector B#， Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
E964A_2025 Capacity Expansion Ph2_EXP_BKK | Small Cell Phahon Yothin SOI 49/1 |  |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-09 | 2025-10-16 | V Contribute Co., Ltd | N/A | Closed | 2025-10-16 15:56:48 | Yes | Yes | 2025-10-16 15:56:48 |  | 2025-10-20 | 2025-10-20 | Chonradee Suwapan | Approved | Closed | 2025-10-22 17:31:20 | Yes | Yes | 2025-10-20 17:18:12 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:56 | Yes | Yes | 2025-10-27 17:16:59 |  | 2025-10-20 | 2025-10-20 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-20 17:21:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-08 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-08 17:50:27 | No | No |  | 8-Oct-2025 Add RRU5516 (700900) SA 0/0 Add g2 Add Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
E968A_2025 Capacity Expansion Ph3_EXP_BKK | IN FRONT OF NOPPARAT RAJATHANEE HOSPITAL (RAMINTHRA ROAD) SMALLCELL TOT |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-31 | 2025-10-17 | 2025-10-18 | V Contribute Co., Ltd | N/A | Closed | 2025-10-18 15:28:32 | Yes | Yes | 2025-10-18 15:28:32 |  | 2025-10-28 | 2025-10-28 | Chonradee Suwapan | Approved | Closed | 2025-10-31 16:22:46 | Yes | Yes | 2025-10-30 21:44:57 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 17:21:59 |  | 2025-10-28 | 2025-10-28 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-28 19:26:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-14 17:38:55 | No | No |  | 14-10-2025. Add RRU5516#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
E989A_2025 Capacity Expansion Ph2_EXP_BKK | SMALLCELL Soi Ladphrao 122 Yak 15 | 2025-09-25 |  |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 10:49:05 | No | No |  |  |  | 2025-09-30 | 2025-10-15 | 2025-10-17 | V Contribute Co., Ltd | N/A | Closed | 2025-10-17 12:03:31 | Yes | Yes | 2025-10-17 12:03:31 |  | 2025-09-30 | 2025-09-30 | Chonradee Suwapan | Approved | Closed | 2025-10-16 16:35:33 | Yes | Yes | 2025-11-24 11:06:45 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:21 | Yes | Yes | 2025-12-01 17:23:14 |  | 2025-09-30 | 2025-09-30 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-09-30 20:23:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-25 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-25 18:25:38 | No | No |  | 2025-09-25_Add UBBPg2#， Add RRU5516(LB)#， Replace to Ant 12 port (No RET) Sector C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-09-30 |  | N/A | Not assigned |  | No | No
EBRUT_2025 Capacity Expansion Ph7_EXP_SR | ENGINEERING BUILDING RAJAMANGALA UNIVERSITY OF TECHNOLOGY SRIVIJAYA. |  |  |  | 2025-12-27 | 2025-12-27 | 2026-01-06 | 2026-01-06 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-01-06 16:54:23 | No | No |  |  |  | 2025-12-28 | 2026-01-06 | 2026-01-06 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-01-06 19:56:50 | Yes | Yes | 2026-01-09 11:28:27 |  | 2026-01-13 | 2026-01-13 | Rosak soko | Approved | Closed | 2026-01-27 11:44:19 | Yes | Yes | 2026-01-13 12:23:34 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:00 | Yes | Yes | 2026-03-19 18:19:19 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-07 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-06 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-01-06 17:23:34 | No | No |  | Rep BBU 5900/add g3a*1/add gps Add AAU5636w Sector 3 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-24 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-24 16:49:10 | Yes | Yes | 2025-12-24 16:05:26 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EDKLM_2025 Coverage Expansion Ph2_EXP_BKK | FACULTY OF ENGINEERING DEANS OFFICE BUILDING, KMITL | 2025-08-19 |  |  |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-19 18:17:20 | No | No |  |  |  | 2025-08-29 | 2025-08-26 | 2025-08-26 | V Contribute Co., Ltd | N/A | Closed | 2025-08-26 21:01:10 | Yes | Yes | 2025-08-26 21:02:06 |  |  | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2026-06-29 16:19:56 | Yes | Yes | 2025-09-01 00:08:29 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-06-24 | wangxing 84250914 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 01:48:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-19 17:52:35 | No | No |  | 2025-08-19_Add RRU3953#， Ant 4 port Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
EKBRM_2025 Capacity Expansion Ph6_EXP_BKK | EKBURAPA ROAD | 2025-12-11 |  |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-15 18:16:03 | No | No |  |  |  | 2025-12-31 | 2025-12-18 | 2025-12-20 | V Contribute Co., Ltd | N/A | Closed | 2025-12-20 11:47:28 | Yes | Yes | 2025-12-20 11:47:28 |  | 2025-12-16 | 2025-12-16 | Chonradee Suwapan | Approved | Closed | 2026-01-12 16:05:53 | Yes | Yes | 2026-01-15 10:57:36 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 12:14:38 |  | 2025-12-16 | 2025-12-16 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-16 21:24:11 |  |  | 2025-12-31 | 2025-12-11 | V Contribute Co., Ltd | N/A | Closed | 2025-12-11 17:29:18 | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 11-12-2025. Add AIRU5614 Sec.1#， RRU3962 Sec.6#， Replace UBBPd5 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EKBRM_2025 Coverage Expansion Ph2_EXP_BKK | EKBURAPA ROAD | 2025-07-31 |  |  |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-07-31 17:04:06 | No | No |  |  |  | 2025-08-22 | 2025-08-08 | 2025-09-09 | V Contribute Co., Ltd | N/A | Closed | 2025-09-09 18:30:38 | Yes | Yes | 2025-09-09 18:31:38 |  | 2025-08-11 | 2025-08-11 | Chonradee Suwapan | Approved | Closed | 2025-08-14 15:00:11 | Yes | Yes | 2025-08-11 18:34:19 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-15 | 2025-08-14 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:15 | Yes | Yes | 2025-08-18 15:27:18 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:52:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-07-31 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-07-31 17:43:19 | No | No |  | 31-07-2025. Add RRU3953 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-30 |  | N/A | Not assigned |  | No | No
EKTNM_2025 Capacity Expansion Ph3_EXP_BKK | EKKACHAI THANI | [5 empty] | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-23 | 2025-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-23 17:56:35 | Yes | Yes | 2025-08-25 23:22:16 |  | 2025-08-28 | 2025-09-02 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-22 15:50:32 | Yes | Yes | 2025-09-02 18:25:20 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:56 | Yes | Yes | 2025-10-06 16:25:41 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 21:43:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-23 18:45:46 | No | No |  | 23-08-2025. Add AIRU5636w Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
EKTSM_2025 Coverage Expansion Ph2_EXP_BKK | EAKTUKSIN ROAD |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-17 | 2025-10-30 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 17:00:56 | Yes | Yes | 2025-10-30 17:00:57 |  | 2025-10-28 | 2025-10-28 | Chonradee Suwapan | Approved | Closed | 2025-10-30 16:53:04 | Yes | Yes | 2026-01-05 15:29:30 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 14:39:13 |  | 2025-10-28 | 2025-10-28 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-28 19:29:32 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-14 17:38:55 | No | No |  | 14-10-2025. Add RRU3953#， Ant.8 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
EM21M_2025 Capacity Expansion NW Modernization_EXP_BKK | EKAMAI SOI 21 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-14 | 2026-03-14 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-14 15:29:23 | Yes | Yes | 2026-03-18 09:33:46 |  | 2026-03-23 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:33:00 | Yes | Yes | 2026-04-01 16:16:12 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 19:54:18 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-19 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-19 17:09:54 | No | No |  | 19-Feb-26 Replace RRU3962 To RRU5077*2 S3 Add RRU3953 S3 // Replace 3962 To RRU5526 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EM30M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI EKKAMAI 30 | 2026-01-29 |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-11 19:07:38 | No | No |  |  |  | 2026-02-07 | 2026-01-30 | 2026-01-31 | V Contribute Co., Ltd | N/A | Closed | 2026-01-31 15:39:54 | Yes | Yes | 2026-01-31 15:39:54 | SQC Close | 2026-02-11 | 2026-02-11 | Chonradee Suwapan | Approved | Closed | 2026-05-11 16:12:29 | Yes | Yes | 2026-02-11 19:04:40 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-01 | 2026-05-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-11 | 2026-02-11 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-11 19:09:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-29 21:41:29 | No | No |  | 29-Jan-2026 Add AAU5768 S1 S2 Remove RRU5507*7 Add RRU3953 Sector 3 Add g3a Remove d6 Replace Ant 8port 18002100 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ES23B_2025 Capacity Expansion NW Modernization_EXP_BKK | THE EDGE SUKHUMVIT 23 |  |  |  |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:09:22 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:21:57 | Yes | Yes | 2026-03-23 15:21:58 |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-05-11 16:12:29 | Yes | Yes | 2026-05-06 10:06:50 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-16 | 2026-05-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-14 22:23:56 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-17 15:34:46 | No | No |  | 17-Feb-26 Replace BBU5900 UMPTg2 Add GPS Add g2=2 Add RRU5526 setor A Remove RRU3826 Replace Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-02-13 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-06-25 04:38:41 | Yes | Yes | 2026-02-17 10:18:32 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ETEBM_2025 Capacity Expansion Ph5_EXP_ER | E-Tech Building | 2025-10-28 | thcp_phet.s | Clear Pending |  | 2025-10-31 | 2025-10-25 | 2025-10-25 | Teloneer Company Limited | N/A | Closed | 2025-10-25 16:17:12 | No | No |  |  |  | 2025-10-31 | 2025-10-25 | 2025-10-28 | Teloneer Company Limited | N/A | Closed | 2025-10-28 10:23:12 | Yes | Yes | 2025-10-28 10:34:02 |  | 2025-10-31 | 2025-10-28 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-29 15:47:04 | Yes | Yes | 2025-11-07 13:36:06 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-11-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 14:40:26 |  | 2025-10-15 | 2025-10-02 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-10-07 11:30:55 | Yes | Yes | 2025-10-02 12:11:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-25 |  | 2025-10-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-24 18:01:30 | No | No |  | **waiting on-service LNR26 -- Co L26 F5 S4#， Co L26 F5 NR26 S7#， New L26F5 + NR26 (New 1RRU5818) + Co Antenna S3 #，New L26F5 + NR26 (New 1RRU5818) + Co Antenna S6 |  | 2025-10-27 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-27 15:07:13 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ETETM_2025 Capacity Expansion Ph5_EXP_ER | Eastern College of Technology (E.TECH) , Electrician Department Building | 2025-10-28 | thcp_phet.s | Clear Pending |  | 2025-10-31 | 2025-10-20 | 2025-10-20 | Teloneer Company Limited | N/A | Closed | 2025-10-20 16:59:54 | No | No |  |  |  | 2025-10-31 | 2025-10-21 | 2025-10-24 | Teloneer Company Limited | N/A | Closed | 2025-10-24 14:37:19 | Yes | Yes | 2025-10-24 20:46:27 |  | 2025-10-31 | 2025-10-28 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-29 15:47:04 | Yes | Yes | 2025-11-07 13:37:04 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-11-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 14:41:40 |  | 2025-10-15 | 2025-10-02 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-10-07 11:30:55 | Yes | Yes | 2025-10-02 12:11:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-20 |  | 2025-10-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-20 17:25:30 | No | No |  | **waiting on-service LNR26 -- Add UBBPg3a #，New L26F5 + NR26 (New RRU5818) + Co Antenna S.A#，B | 2025-10-22 | 2025-10-22 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-22 17:26:19 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EXHLM_2025 Capacity Expansion NW Modernization_EXP_BKK | EXPRESS HAULAMPHONG REPEATER |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-11 10:40:21 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-02-02 | 2026-02-03 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-03 20:43:21 | Yes | Yes | 2026-02-10 16:01:11 |  | 2026-02-11 | 2026-02-12 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-03-09 09:23:58 | Yes | Yes | 2026-03-07 10:06:26 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-01 | 2026-03-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:22:41 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 21:26:25 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-24 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-24 14:05:53 | No | No |  | 24-Jan-2026 Add RRU3953 *2 Sector3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FBKIM_2025 Capacity Expansion NW Modernization_EXP_BKK | FLAT BONKAI |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  |  | 2026-02-28 | 2026-02-27 | 2026-02-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-27 15:12:02 | Yes | Yes | 2026-03-05 10:18:04 |  | 2026-03-30 | 2026-03-30 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-20 14:38:47 | Yes | Yes | 2026-03-30 14:27:59 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 19:54:51 |  |  | 2026-02-26 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-26 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-26 17:47:08 | No | No |  | 26-Feb-26 Replace RRU5507 To AAU5768 DMM S2 25-Feb-2026 ***Pending Add AAU5768 Sector 2 Remove RRU3962 *2 Add g3a ///Add AAU5768 Sector 3 Remove RRU3962 *2 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FLK7M_2025 Coverage Expansion Ph1_New_BKK | FACTORY LAMLUKKA KHLONG 7 | [5 empty] | 2025-12-25 | 2025-12-25 | Akhom Srinara | N/A | Closed | 2025-12-25 10:07:39 | No | No |  |  |  | 2025-12-19 | 2025-12-26 | 2026-01-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-01-05 11:28:13 | Yes | Yes | 2026-01-06 15:30:20 |  | 2026-01-09 | 2026-01-09 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-01-13 15:20:09 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-14 | 2026-01-14 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-14 11:21:32 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-20 18:44:14 | No | No |  | 20-12-2025. New Site Macro Add RRU5507#， RRU3962#， Ant.4 port Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
FS4VM_2025 Coverage Expansion Ph2_EXP_BKK | Fueang Suk 4 Village | 2025-07-31 |  |  |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-07-31 17:04:06 | No | No |  |  |  | 2025-08-22 | 2025-08-11 | 2025-08-11 | V Contribute Co., Ltd | N/A | Closed | 2025-08-11 20:04:36 | Yes | Yes | 2025-08-11 20:06:57 |  | 2025-08-12 | 2025-08-12 | Chonradee Suwapan | Approved | Closed | 2025-08-14 17:18:45 | Yes | Yes | 2025-08-12 21:01:23 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:15 | Yes | Yes | 2025-08-18 15:28:34 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:52:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-07-31 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-07-31 16:39:13 | No | No |  | 31-Jul-2025 Add RRU3953 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-30 |  | N/A | Not assigned |  | No | No
FURMM_2025 Capacity Expansion NW Modernization_EXP_BKK | FURAMA HOTEL SILOM |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:45:18 | No | No |  |  | 2026-01-24 | 2026-01-31 | 2026-05-27 | 2026-06-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-02 15:11:47 | Yes | Yes | 2026-06-02 15:15:54 |  | 2026-06-02 | 2026-06-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-05 09:28:56 | Yes | Yes | 2026-06-02 14:52:53 | AAM Ant #， DCDU ที่เข้าพร้อมงานให้แนบมาด้วย เพื่อตรวจสอบว่าคีย์ทรัพย์สินมาจริง | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 21:26:39 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-16 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-16 20:08:05 | No | No |  | 16-01-2026 Replace RRU3962 to AAU5768 sector 1#，2#，3 on air DMM done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G009A_2025 Capacity Expansion Ph2_EXP_BKK | Small Cell Soi San Prasoet |  |  |  |  | 2025-09-10 | 2025-09-18 | 2025-09-18 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-30 | 2025-09-11 | 2025-09-11 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:14:08 | Yes | Yes | 2025-09-30 10:14:09 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-10-10 22:26:44 | Yes | Yes | 2025-11-24 16:39:41 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 14:42:53 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-19 20:36:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-10 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-10 22:29:01 | No | No |  | 2025-09-10_Add UBBPg2#， Add RRU5516(LB)#， Replace to Ant 12 port (No RET) Sector A#，C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-17 |  | N/A | Not assigned |  | No | No
G016A_2025 Capacity Expansion NW Modernization_EXP_BKK | Small Cell Soi Nuan Chit 1 |  |  |  |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-21 | 2026-03-25 | 2026-03-25 | V Contribute Co., Ltd | N/A | Closed | 2026-03-25 15:52:22 | Yes | Yes | 2026-03-25 15:52:23 |  | 2026-02-19 | 2026-02-19 | Chonradee Suwapan | Approved | Closed | 2026-02-27 16:26:01 | Yes | Yes | 2026-02-19 22:03:13 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:23:19 |  | 2026-02-19 | 2026-02-19 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:03:32 | Yes | Yes | 2026-02-19 22:07:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-03 17:59:14 | No | No |  | 2026-02-03_Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G016A_2025 Capacity Expansion Ph8_EXP_BKK | Small Cell Soi Nuan Chit 1 |  |  |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | V Contribute Co., Ltd | N/A | Closed | 2026-03-06 16:22:54 | No | No |  |  |  | 2026-03-27 | 2026-03-12 | 2026-03-14 | V Contribute Co., Ltd | N/A | Closed | 2026-03-14 10:02:52 | Yes | Yes | 2026-03-14 10:02:52 |  | 2026-04-27 | 2026-04-27 | Chonradee Suwapan | Approved | Closed | 2026-07-16 16:54:20 | Yes | Yes | 2026-05-04 15:52:45 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-24 | 2026-07-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-27 | 2026-04-27 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-27 02:08:22 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-03-06 18:29:12 | No | No |  | 06-03-2026. Co RRU5258 Sec.A with Sec.B#， Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G050A_2025 Capacity Expansion Ph3_EXP_BKK | TRIAM UDOM SUKSA PATTANAKARN SCHOOL | [5 empty] | 2025-11-03 | 2025-11-03 | Akhom Srinara | N/A | Closed | 2025-11-07 15:20:45 | No | No |  |  |  |  | 2025-10-07 | 2025-11-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-04 11:46:53 | Yes | Yes | 2025-11-05 19:29:01 |  |  | 2025-11-13 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-17 17:04:36 | Yes | Yes | 2026-01-05 15:50:35 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 17:29:24 |  | 2025-11-06 | 2025-11-06 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:27:01 | No | Yes | 2025-11-06 10:26:46 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-07 17:18:36 | No | No |  | 07-10-2025. Add RRUU3953#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-02 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
G097A_2025 Capacity Expansion Ph5_EXP_BKK | Madee Apartment Srinakarin Road |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 16:37:47 | No | No |  |  |  | 2025-12-28 | 2025-12-26 | 2025-12-27 | V Contribute Co., Ltd | N/A | Closed | 2025-12-27 18:23:42 | Yes | Yes | 2025-12-27 18:23:42 |  | 2026-01-22 | 2026-01-22 | Chonradee Suwapan | Approved | Closed | 2026-04-08 17:10:34 | Yes | Yes | 2026-04-02 14:35:47 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-04-12 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-22 | 2026-01-22 | Chonradee Suwapan | Approved | Closed | 2026-01-29 17:09:02 | Yes | Yes | 2026-01-22 18:29:01 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-06 17:15:26 | No | No |  | 06-01-2026. Add GPS //23-Dec-2025 Replace BBU5900 UMPTg2 add g3a g2 Add RRU3962 Sector A Remove AAU3940 *2 Add RRU5818 sector A Add Ant small cell 12port No Ret |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-22 | Supatong Juntorn WX1461874 | Approved | Closed | 2025-12-25 06:10:09 | Yes | Yes | 2025-12-22 16:48:46 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G117A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI YEN AR KARD 1 |  |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-07 | 2026-02-07 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 09:33:23 | Yes | Yes | 2026-02-11 09:33:23 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 12:50:41 | Yes | Yes | 2026-03-09 11:16:55 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-01 | 2026-03-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:23:37 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:16:39 | Yes | Yes | 2026-03-07 19:54:06 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-03 17:59:14 | No | No |  | 12-May-2026 Clear Pending work Replace UBBPg2 Remove d5 2026-02-03_Replace to Ant 12 port (No ret)#， Add UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G157A_2025 Capacity Expansion Ph2_EXP_BKK | SOI LATPROA 134 |  |  |  | 2025-08-20 | 2025-09-30 | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:39:59 | No | No |  |  |  | 2025-11-14 | 2025-11-14 | 2025-12-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-17 15:40:34 | Yes | Yes | 2025-12-22 15:10:42 |  | 2026-01-16 | 2026-01-16 | Aomchun Jittreemit | Approved | Closed | 2026-01-26 09:12:24 | Yes | Yes | 2026-01-16 11:28:08 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 12:17:35 |  | 2025-12-22 | 2025-12-22 | Aomchun Jittreemit | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2026-01-09 09:40:15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-11 18:37:27 | No | No |  | 11-Dec-2025 Add RRU5516 (700900)SB Add g2 14-Nov-2025 ***Pending Add RRU5516 (700900)SB Add g2 /// Replace Ant 12port No RET SB Replace OPM Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-29 |  | N/A | Not assigned |  | No | No
G236A_2025 Capacity Expansion Ph2_EXP_BKK | S.R.T. APARTMENT SUKHUMVIT64 |  |  |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-17 16:18:56 | No | No |  |  |  | 2025-10-06 | 2025-11-25 | 2025-11-27 | V Contribute Co., Ltd | N/A | Closed | 2025-11-27 19:20:03 | Yes | Yes | 2025-11-27 19:20:03 |  | 2025-11-20 | 2025-11-20 | Chonradee Suwapan | Approved | Closed | 2025-12-03 09:56:01 | Yes | Yes | 2025-11-20 19:44:42 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:17:49 |  | 2025-11-20 | 2025-11-20 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-20 22:47:10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-14 17:22:56 | No | No |  | 14-11-2025. Add RRU5516 L900 Sec.A //1-Oct-2025 Replace ant 12 port No RET (combile MB LB) Add g2 Remove d6 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-14 |  | N/A | Not assigned |  | No | No
G252A_2025 Capacity Expansion Ph2_EXP_BKK | SMALL CELL SOI SUTTHIPHONG 3 |  |  |  |  | 2025-09-10 | 2025-09-17 | 2025-09-17 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-30 | 2025-09-22 | 2025-09-22 | V Contribute Co., Ltd | N/A | Closed | 2025-09-22 16:25:20 | Yes | Yes | 2025-09-22 16:25:20 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-10-07 20:34:19 | Yes | Yes | 2025-09-18 20:01:33 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:03 | Yes | Yes | 2025-10-09 19:56:33 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 21:28:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-10 17:46:37 | No | No |  | 10-09-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， RRU5818#， Ant.12 port Sec.A#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-16 |  | N/A | Not assigned |  | No | No
G289A_2025 Capacity Expansion NW Modernization_EXP_BKK | WATTANA_6 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-12 | 2026-03-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-12 09:27:26 | Yes | Yes | 2026-03-17 08:48:32 |  | 2026-03-24 | 2026-03-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-28 22:13:51 | Yes | Yes | 2026-03-24 16:20:03 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-08-29 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 19:56:18 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-16 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-16 16:47:08 | No | No |  | 16 Feb 2026 Add 1UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-02-25 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G321A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAN 18/7 SMALL CELL |  |  |  |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:47:30 | No | No |  |  |  | 2026-02-28 | 2026-02-25 | 2026-02-25 | V Contribute Co., Ltd | N/A | Closed | 2026-02-25 17:43:04 | Yes | Yes | 2026-02-25 17:43:05 |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-06-26 09:39:44 | Yes | Yes | 2026-04-01 11:35:44 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-16 | 2026-06-29 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-17 20:40:16 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 23-Jan-2026 ***Pending GPS ///Replace BBU5900 UMPTg2 Add g2 Done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-20 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 05:53:28 | Yes | Yes | 2026-01-20 16:52:39 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G325A_2025 Capacity Expansion Ph2_EXP_BKK | SOI SABAIJAI YAK 5 |  |  |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-10 18:33:54 | No | No |  |  |  | 2025-10-17 | 2025-10-06 | 2025-10-07 | V Contribute Co., Ltd | N/A | Closed | 2025-10-07 18:43:06 | Yes | Yes | 2025-10-07 18:43:07 |  | 2025-10-10 | 2025-10-10 | Chonradee Suwapan | Approved | Closed | 2025-10-27 09:33:43 | Yes | Yes | 2025-10-10 16:11:27 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:56 | Yes | Yes | 2025-10-27 17:22:05 |  | 2025-10-10 | 2025-10-10 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-10 19:39:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-03 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-03 17:39:03 | No | No |  | 03-10-2025. Add UBBPg2#， RRU5516 L900#， Ant.12 port Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-09 |  | N/A | Not assigned |  | No | No
G334A_2025 Capacity Expansion Ph2_EXP_BKK | SMALL CELL NOPPAWAN MANSION |  |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-11 17:27:06 | No | No |  |  |  | 2025-09-30 | 2025-11-13 | 2025-11-27 | V Contribute Co., Ltd | N/A | Closed | 2025-11-27 13:43:38 | Yes | Yes | 2025-11-27 13:43:38 |  | 2025-11-17 | 2025-11-17 | Chonradee Suwapan | Approved | Closed | 2026-01-29 09:17:05 | Yes | Yes | 2026-01-05 21:28:52 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 12:18:19 |  | 2025-11-17 | 2025-11-17 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-17 21:49:25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-07 17:28:33 | No | No |  | 07-11-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， RRU3962#， RRU5818#， Ant.4 port S.A#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-10 |  | N/A | Not assigned |  | No | No
G346A_2025 Capacity Expansion Ph5_EXP_BKK | SOI LAT PHRAO 48 YEAK 8 TOT | [5 empty] | 2026-01-22 | 2026-01-22 | Narongsak wanichachiwa | N/A | Closed | 2026-01-27 10:38:21 | No | No |  |  |  | 2025-11-18 | 2026-01-08 | 2026-01-09 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-01-09 13:39:33 | Yes | Yes | 2026-01-11 14:22:50 | SQC Close |  | 2026-01-11 | Sukhum Parintawong | Approved | Closed | 2026-04-07 13:12:18 | Yes | Yes | 2026-04-07 20:21:27 | PAT Pass | Pass | 2026-06-11 | 2026-06-11 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-06-13 13:33:21 | No | Yes | 2026-06-13 13:33:10 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 12:19:08 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-08 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-08 11:29:08 | No | No |  | 8-Jan-2026 Add split GPS 26-Dec-2025 ***Pending GPS //// Add RRU5818*1 Sector BA 25-12-2025. ***Need RRU5818#， GPS //Replace BBU5900#， UMPTg2 10G#， Add UBBPg2#， UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G355A_2025 Capacity Expansion NW Modernization_EXP_BKK | TOT SOI WAT MAHA PHRUTTHARAM SMALL CELL |  |  |  |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-20 16:16:18 | No | No |  |  |  | 2026-02-07 | 2026-01-20 | 2026-01-22 | V Contribute Co., Ltd | N/A | Closed | 2026-01-22 10:26:27 | Yes | Yes | 2026-01-22 10:26:27 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-06 13:12:59 | Yes | Yes | 2026-02-26 10:47:12 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:26:07 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-04 19:17:44 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 20-01-2026. Replace BBU5900#， UMPTg2 10G#， Add UBBPg2#， RRU5507 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-19 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 05:53:28 | Yes | Yes | 2026-01-19 16:42:23 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G357A_2025 Capacity Expansion NW Modernization_EXP_BKK | POLO_4 |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:11:05 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:37:38 | Yes | Yes | 2026-03-23 15:37:39 |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-04-10 11:05:10 | Yes | Yes | 2026-03-24 17:37:29 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-04-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-10 22:20:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-12 20:34:17 | No | No |  | 12-Feb-2026 Replace BBU5900 UMPTg2 Add GPS Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G386A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI RUAMJAI |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-17 | 2026-02-17 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-08 23:00:59 | No | No |  |  | 2026-02-05 | 2026-02-05 | 2026-02-05 | 2026-02-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-18 11:38:51 | Yes | Yes | 2026-02-18 11:49:16 |  | 2026-02-13 | 2026-02-13 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-04-17 09:36:07 | Yes | Yes | 2026-02-20 11:20:26 | Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-07 | 2026-04-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 21:27:38 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-05 15:01:08 | No | No |  | 5-Feb-2026 Add UBBPg3a Remove UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G388A_2025 Capacity Expansion NW Modernization_EXP_BKK | SANGTHIP MARKET |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-12 15:51:41 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-02-04 | 2026-02-05 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-05 10:46:03 | Yes | Yes | 2026-02-11 09:24:56 |  | 2026-02-12 | 2026-02-13 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-03-21 00:25:39 | Yes | Yes | 2026-02-20 11:31:35 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-02 | 2026-03-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:27:03 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:27:53 |  |  | 2026-03-31 | 2026-04-09 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-09 21:23:00 | No | No |  |  |  |  | 2026-01-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-26 17:44:22 | No | No |  | 26-01-2026. Add UBBPg3a#， Replace RRU3962 to RRU5526 Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G402A_2025 Capacity Expansion Ph2_EXP_BKK | PHRAYA SUREN 19 |  |  |  | 2025-10-08 | 2025-10-15 | 2025-10-22 | 2025-10-22 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-28 10:43:04 | No | No |  |  | 2025-10-15 | 2025-10-17 | 2025-10-22 | 2025-10-23 | Teloneer Company Limited | N/A | Closed | 2025-10-23 14:36:26 | Yes | Yes | 2025-10-29 09:58:39 |  |  | 2025-10-29 | Apichart Kampuang | Approved | Closed | 2025-11-14 09:37:39 | Yes | Yes | 2026-01-05 12:30:54 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Krittee Chamboot 00319410 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 17:31:52 |  | 2025-10-06 | 2025-10-06 | Teloneer Company Limited | Approved | Closed | 2025-11-28 14:34:00 | No | Yes | 2025-10-09 15:57:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-09 16:44:06 | No | No |  | 9-Oct-2025 Replace BBU59000 UMPTg2 Add g2 Add RRU5516 (700900)SB 0/1 Replace Ant (Combile MB+LB) 12port No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-21 |  | N/A | Not assigned |  | No | No
G450A_2025 Capacity Expansion Ph8_EXP_BKK | SMALL CELL TOT SOI RAJAVITHI 15 |  |  |  |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-06 18:17:38 | No | No |  |  |  | 2026-02-28 | 2026-03-08 | 2026-03-09 | V Contribute Co., Ltd | N/A | Closed | 2026-03-09 09:49:59 | Yes | Yes | 2026-03-09 09:50:00 |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-03-12 11:43:46 | Yes | Yes | 2026-03-13 16:44:48 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-21 | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:27:21 |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:17:02 | Yes | Yes | 2026-03-05 21:01:29 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-13 18:58:33 | No | No |  | 13-Feb-26 Replace BBU3900 To RRU900 Add UBBPg3a Add AAU5246 SB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G473A_2025 Capacity Expansion Ph3_EXP_BKK | SOI LATPRAO 111/1 SMALL CELL TOT |  |  |  | 2025-10-11 | 2025-10-18 | 2025-10-24 | 2025-10-24 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-28 10:43:04 | No | No |  |  |  | 2025-10-23 | 2025-10-23 | 2025-10-25 | Teloneer Company Limited | N/A | Closed | 2025-10-25 11:49:45 | Yes | Yes | 2025-10-27 10:15:50 |  |  | 2025-10-29 | Apichart Kampuang | Approved | Closed | 2025-11-13 08:59:30 | Yes | Yes | 2026-05-17 12:10:21 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 17:33:05 |  | 2025-10-08 | 2025-10-10 | Teloneer Company Limited | Approved | Closed | 2025-11-28 14:34:00 | No | Yes | 2025-10-11 11:01:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-15 16:39:50 | No | No |  | 15-Oct-2025 Replace BBU5900 UMPTg2 Add g3a Add RRU5818 * 1 Sector BC 5/1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-16 |  | N/A | Not assigned |  | No | No
G505A_2025 Capacity Expansion Ph2_EXP_BKK | SMALL SOI PHARMACARE RATCHADAPHISEK 3 |  |  |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-09-22 11:24:57 | No | No |  |  |  | 2025-10-04 | 2025-10-03 | 2025-10-09 | V Contribute Co., Ltd | N/A | Closed | 2025-10-09 15:58:01 | Yes | Yes | 2025-10-09 15:58:01 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2025-10-14 17:07:34 | Yes | Yes | 2025-09-29 12:30:31 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 16:39:35 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-09-29 12:43:57 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-19 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-19 17:39:44 | No | No |  | 19-09-2025. Add RRU5818 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-21 |  | N/A | Not assigned |  | No | No
G511A_2025 Capacity Expansion NW Modernization_EXP_BKK | TOT TROK KLUEA SMALL CELL |  |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-29 09:34:01 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-27 | 2026-01-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-28 10:13:02 | Yes | Yes | 2026-01-28 11:21:05 |  | 2026-01-29 | 2026-01-30 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-11 09:40:40 | Yes | Yes | 2026-01-30 12:02:55 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:28:17 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:28:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-12 17:18:01 | No | No |  | 12-Jan-2026 Add RRU5526 Sector A #， B Remove RRU3962 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G527B_2025 Coverage Expansion Ph1_EXP_BKK | PLUM CONDO LADPRAO 101 |  |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-09 | 2025-10-10 | V Contribute Co., Ltd | N/A | Closed | 2025-10-10 15:21:28 | Yes | Yes | 2025-10-10 15:21:29 |  | 2025-10-21 | 2025-10-21 | Chonradee Suwapan | Approved | Closed | 2025-10-24 17:42:42 | Yes | Yes | 2026-01-05 13:46:47 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 14:52:33 |  | 2025-10-21 | 2025-10-21 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-10-21 20:20:23 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-10 16:37:04 | No | No |  | 10-Oct-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam SA SB E-tilt -200 82 83 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
G545A_2025 Capacity Expansion Ph2_EXP_BKK | SMALL CELL SOI PHATTANAKARN 38 |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-10-16 | 2025-12-04 | 2025-12-23 | V Contribute Co., Ltd | N/A | Closed | 2025-12-23 17:22:46 | Yes | Yes | 2025-12-23 17:22:46 |  | 2025-11-27 | 2025-11-27 | Chonradee Suwapan | Approved | Closed | 2025-12-08 16:16:01 | Yes | Yes | 2026-03-13 15:31:27 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 17:15:44 |  | 2025-11-27 | 2025-11-27 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-27 20:21:44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-21 18:38:38 | No | No |  | 21-Nov-2025 Add Add RRU5818 Sector B 2025-10-02_Replace to Ant 12 port(No RET) Sector B#， ***Waiting core Add RRU5818 Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-24 |  | N/A | Not assigned |  | No | No
G546A_2025 Capacity Expansion NW Modernization_EXP_BKK | U SATHORN BANGKOK |  |  |  |  | 2026-02-10 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-08 23:00:59 | No | No |  |  |  | 2026-02-07 | 2026-02-09 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 10:06:51 | Yes | Yes | 2026-02-12 10:06:51 |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-09 21:20:13 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:28:55 |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:36 | Yes | Yes | 2026-02-09 21:27:06 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-27 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-01-27 18:27:08 | No | No |  | 27 Jan 2026 Replace RRU5526 sector A#，B#，C add 1UBPPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G551A_2025 Capacity Expansion Ph5_EXP_BKK | SOI ASSUMPTION 23 SMALL CELL | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-11-20 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Site Cancle | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G558A_2025 Capacity Expansion Ph2_EXP_BKK | SMALL CELL SATHON SOI 3 (SUANPLU) |  |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-11 17:27:06 | No | No |  |  |  | 2025-09-30 | 2025-10-06 | 2025-10-15 | V Contribute Co., Ltd | N/A | Closed | 2025-10-15 16:11:00 | Yes | Yes | 2025-10-15 16:11:01 |  | 2025-11-18 | 2025-11-18 | Chonradee Suwapan | Approved | Closed | 2026-01-23 16:11:22 | Yes | Yes | 2025-11-28 12:46:35 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 12:22:12 |  | 2025-11-18 | 2025-11-18 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-11-18 17:41:57 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-10 17:59:57 | No | No |  | 11-10-2025. Add RRU5516 L900#， Ant.12 port Sec.B //2025-09-18_Add RRU5516(LB)#， Add Ant 4 port Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-10 |  | N/A | Not assigned |  | No | No
G559A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SUKHUMVIT 13 SMALL CELL 2 (TOT) |  |  |  | 2026-02-10 | 2026-02-10 | 2026-02-17 | 2026-02-17 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-08 23:00:59 | No | No |  |  | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-18 11:42:32 | Yes | Yes | 2026-02-18 11:46:19 |  | 2026-02-10 | 2026-02-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-04-17 09:39:16 | Yes | Yes | 2026-03-06 15:49:41 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-07 | 2026-04-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:28:52 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-02 17:52:51 | No | No |  | 2 Feb 2026 Replace RRU5526 sector1#，2#，3 RRU5526 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G563A_DPU40_OPM30_Replacement_BKK | CONCRETE POLE SUPALAI LOFT YAEK FAI CHAI SMALL CELL |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-26 | 2026-01-07 | V Contribute Co., Ltd | N/A | Closed | 2026-01-07 12:14:47 | Yes | Yes | 2026-01-07 12:14:48 |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-01-20 15:48:07 | Yes | Yes | 2026-01-18 19:48:32 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 12:23:00 |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-18 20:15:26 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-26 | Supatong Juntorn WX1461874 | N/A | Closed | 2025-12-26 16:34:13 | No | No |  | 26-Dec-2025 Replace DPU40 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
G565A_2025 Capacity Expansion Ph2_EXP_BKK | MAHIDOL UNIVERSITY FACULTY OF DENTISTRY |  |  |  |  | 2025-10-22 | 2025-10-22 | 2025-10-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-10-31 | 2025-10-30 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 14:42:57 | Yes | Yes | 2025-10-30 14:42:57 |  | 2025-10-31 | 2025-10-31 | Chonradee Suwapan | Approved | Closed | 2025-11-14 09:37:39 | Yes | Yes | 2026-01-05 13:55:11 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Krittee Chamboot 00319410 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 17:36:43 |  | 2025-10-31 | 2025-10-31 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-31 20:44:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-21 17:29:57 | No | No |  | 21-10-2025. Add UBBPg2#， RRU5516 L900 Ant.12 port Sec.A#， C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-21 |  | N/A | Not assigned |  | No | No
G576A_DPU40_OPM30_Replacement_BKK | BAAN KLANG MUANG MENGJAI-LADPRAO |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-25 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 14:48:56 | Yes | Yes | 2025-12-26 14:48:57 |  | 2026-01-14 | 2026-01-14 | Chonradee Suwapan | Approved | Closed | 2026-01-19 15:45:52 | Yes | Yes | 2026-01-16 10:30:44 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-19 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 12:23:49 |  | 2026-01-14 | 2026-01-14 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-14 20:42:09 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-25 17:24:32 | No | No |  | 25-Dec-2025 Replace DPU40 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
G591A_2025 Capacity Expansion NW Modernization_EXP_BKK | SUKHUMVIT 15 (SMALL CELL) |  |  |  | 2026-01-23 | 2026-01-23 | 2026-02-18 | 2026-02-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-02-18 10:36:35 | No | No |  |  | 2026-01-24 | 2026-01-24 | 2026-01-24 | 2026-02-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-24 15:38:06 | Yes | Yes | 2026-02-24 15:40:58 |  | 2026-02-18 | 2026-02-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-23 15:57:48 | Yes | Yes | 2026-02-20 15:50:37 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:29:33 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:29:07 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-23 16:06:19 | No | No |  | 23-Jan-2026 Add RRU5526 Remove RRU5507*2 Sector A#， B Add g2 Replace ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-01-23 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G602A_DPU40_OPM30_Replacement_BKK | BAAN KLANG MUANG GRAND DE PARIS RATCHADA |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-25 | 2025-12-25 | V Contribute Co., Ltd | N/A | Closed | 2025-12-25 14:47:26 | Yes | Yes | 2025-12-25 14:47:26 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-01-19 15:45:52 | Yes | Yes | 2026-03-13 16:46:06 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 14:51:49 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-13 21:07:32 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-25 17:24:33 | No | No |  | 25-Dec-2025 Replace DPU40 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
G603A_DPU40_OPM30_Replacement_BKK | BAAN KLANG MUANG GRAND DE PARIS RATCHADA 2 |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-25 | 2025-12-25 | V Contribute Co., Ltd | N/A | Closed | 2025-12-25 15:57:24 | Yes | Yes | 2025-12-25 15:57:24 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-01-19 15:45:52 | Yes | Yes | 2026-01-13 21:03:05 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 14:52:08 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-13 21:07:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-25 17:24:32 | No | No |  | 25-Dec-2025 Replace DPU40 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
G604A_DPU40_OPM30_Replacement_BKK | BAAN KLANG MUANG GRAND DE PARIS RATCHADA 3 |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-25 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 12:00:02 | Yes | Yes | 2025-12-26 12:00:03 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-01-19 15:45:52 | Yes | Yes | 2026-01-13 21:01:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-19 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 14:52:26 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-13 21:08:22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-25 17:24:32 | No | No |  | 25-Dec-2025 Replace DPU40 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
G611A_2025 Capacity Expansion Ph2_EXP_BKK | MAMA HOUSE NARADHIWAS SMALL CELL | 2025-09-15 |  |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-15 18:10:01 | No | No |  |  |  | 2025-09-30 | 2025-09-25 | 2025-09-30 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 15:27:01 | Yes | Yes | 2025-09-30 15:27:02 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-10-07 20:34:19 | Yes | Yes | 2025-09-24 18:17:41 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:03 | Yes | Yes | 2025-10-09 20:00:25 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:20:11 | No | Yes | 2025-09-24 21:33:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-15 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-15 17:35:06 | No | No |  | 15-09-2025. Add UBBPg2#， RRU5516 L900#， Ant.12 port Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-14 |  | N/A | Not assigned |  | No | No
G613A_2025 Capacity Expansion Ph2_EXP_BKK | Soi Sathu Pradit 49 |  |  |  |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-29 08:38:16 | No | No |  |  |  | 2025-09-30 | 2025-09-30 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 14:59:55 | Yes | Yes | 2025-10-30 14:59:55 |  | 2025-10-04 | 2025-10-04 | Chonradee Suwapan | Approved | Closed | 2025-10-15 22:31:52 | Yes | Yes | 2025-10-04 20:15:58 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 16:40:48 |  | 2025-10-04 | 2025-10-04 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-04 21:03:00 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-19 18:08:57 | No | No |  | 27-Sep-2025 Clear Alarm VSWR Replace Ant 12 port No RET 19-Sep-2025 Add RRU5516 (700900) SC 17-Sep-2025 ***Pending Add RRU5516 (700900) SC ////Add g2 Remove d5 Add Ant 4port No RET (0/4) Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Antenna ไม่ support ต้องเปลี่ยน type antenna |  | 2025-09-28 |  | N/A | Not assigned |  | No | No
G620A_2025 Capacity Expansion Ph3_EXP_BKK | SUAN SIAM 16 ALLEY, LANE 3 |  |  |  | 2025-10-24 | 2025-10-31 | 2025-10-26 | 2025-10-26 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-28 10:43:04 | No | No |  |  | 2025-10-30 | 2025-11-03 | 2025-10-29 | 2025-10-30 | Teloneer Company Limited | N/A | Closed | 2025-10-30 18:06:39 | Yes | Yes | 2025-10-31 09:38:42 |  |  | 2025-10-31 | Apichart Kampuang | Approved | Closed | 2025-12-18 09:25:15 | Yes | Yes | 2026-03-13 17:34:19 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 17:19:24 |  | 2025-10-22 | 2025-10-24 | Teloneer Company Limited | Approved | Closed | 2025-11-28 14:34:00 | No | Yes | 2025-10-24 11:06:48 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-25 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-25 17:06:11 | No | No |  | 25-10-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， RRU5818 Sec.A#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-30 |  | N/A | Not assigned |  | No | No
G625A_2025 Capacity Expansion Ph5_EXP_BKK | ELECTRICITY POLE OF KHLONG CHAN HOUSING BUILDING 21 |  |  |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-15 18:16:03 | No | No |  |  |  | 2025-12-28 | 2025-12-20 | 2025-12-21 | V Contribute Co., Ltd | N/A | Closed | 2025-12-21 15:28:04 | Yes | Yes | 2025-12-21 15:28:05 |  | 2025-12-17 | 2025-12-17 | Chonradee Suwapan | Approved | Closed | 2026-01-23 16:11:22 | Yes | Yes | 2026-01-21 18:07:18 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 14:53:03 |  | 2025-12-17 | 2025-12-17 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-17 18:27:27 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-15 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-15 17:11:18 | No | No |  | 15-12-2025. Add RRU5818 Sec.A#， Replace UBBPd5 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G625A_DPU40_OPM30_Replacement_BKK | ELECTRICITY POLE OF KHLONG CHAN HOUSING BUILDING 21 |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-25 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 14:18:03 | Yes | Yes | 2025-12-26 14:18:04 |  | 2026-01-14 | 2026-01-14 | Chonradee Suwapan | Approved | Closed | 2026-01-19 15:45:52 | Yes | Yes | 2026-01-16 10:57:09 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-19 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 14:53:23 |  | 2026-01-14 | 2026-01-14 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-14 20:42:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-25 17:24:06 | No | No |  | 25-Dec-2025 Replace DPU30 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
G627A_2025 Capacity Expansion NW Modernization_EXP_BKK | ELECTRIC POLE OF SUKHUMVIT 23 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:54:42 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-04-19 | 2026-04-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-24 09:22:53 | Yes | Yes | 2026-04-24 09:55:28 |  | 2026-05-06 | 2026-05-06 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-07 09:36:42 | Yes | Yes | 2026-05-06 11:18:31 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:29:22 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-21 17:31:11 | No | No |  | 21-Jan-2026 Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G627A_2025 Capacity Expansion Ph7_EXP_BKK | ELECTRIC POLE OF SUKHUMVIT 23 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:54:42 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-04-19 | 2026-05-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-06 15:40:25 | Yes | Yes | 2026-05-06 15:43:01 |  | 2026-05-06 | 2026-05-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-16 16:54:20 | Yes | Yes | 2026-05-20 11:09:30 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-25 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:45:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-04-06 18:18:13 | No | No |  | 6-Apr-2026 Add RRU5526 Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G633A_2025 Capacity Expansion Ph3_EXP_BKK | AEKBURI VILLAGE 1 (MEA) | 2025-09-29 |  |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 10:49:05 | No | No |  |  |  | 2025-10-09 | 2025-10-01 | 2025-10-02 | V Contribute Co., Ltd | N/A | Closed | 2025-10-02 12:07:45 | Yes | Yes | 2025-10-02 12:07:45 |  | 2025-10-03 | 2025-10-03 | Chonradee Suwapan | Approved | Closed | 2025-10-31 16:25:21 | Yes | Yes | 2026-01-05 14:40:58 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 17:41:38 |  | 2025-10-03 | 2025-10-03 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-03 21:22:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-29 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-29 16:44:17 | No | No |  | 29-09-2025. Add UBBPg3#， UBBPg2#， RRU5818#， Replace RRU5516#， Ant.12 port S.A Combine S.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-01 |  | N/A | Not assigned |  | No | No
G635A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAN 18/7 |  |  |  |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-29 08:07:45 | No | No |  |  |  | 2026-02-07 | 2026-01-26 | 2026-01-28 | V Contribute Co., Ltd | N/A | Closed | 2026-01-28 09:57:09 | Yes | Yes | 2026-01-28 09:57:10 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-11 09:40:40 | Yes | Yes | 2026-02-26 17:51:31 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:29:53 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-05 22:24:58 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-22 15:09:42 | No | No |  | 22-Jan-2026 Replace BBU5900 UMPTg2 Add g3a=2 g2 remove d6 add GPS Add RRU5526 Sector A#，B Remove RRU3962 *2 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-20 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 05:53:28 | Yes | Yes | 2026-01-20 16:52:56 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G652A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL 21 Saladaeng TOT pole |  |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-13 10:47:09 | No | No |  |  |  | 2026-02-07 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 19:04:25 | Yes | Yes | 2026-02-11 19:04:25 |  | 2026-02-10 | 2026-02-10 | Chonradee Suwapan | Approved | Closed | 2026-02-17 17:18:26 | Yes | Yes | 2026-02-10 20:53:42 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:30:11 |  | 2026-02-10 | 2026-02-10 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-10 21:00:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-26 18:26:07 | No | No |  | 2026-01-26_Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G658A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Phet Ploi |  |  |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-25 11:54:42 | No | No |  |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | 2026-02-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-25 16:14:37 | Yes | Yes | 2026-02-25 16:17:49 |  | 2026-02-25 | 2026-02-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:34:46 | Yes | Yes | 2026-03-09 20:46:33 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:29:37 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-13 17:42:48 | No | No |  | 13-Jan-2026 Replace BBU5900 UMPTg2 Add g2 GPS Add RRU5526 Sector A Remove RRU3962 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-13 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-13 16:07:27 | Yes | Yes | 2026-01-13 10:25:44 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GEPCM_2025 Capacity Expansion Ph2_EXP_ER | Glow Energy Public Company Limited | 2025-09-16 |  | Install & Integrate |  | 2025-09-30 | 2025-09-16 | 2025-09-16 | Teloneer Company Limited | N/A | Closed | 2025-09-16 15:48:59 | No | No |  |  |  | 2025-07-31 | 2025-09-16 | 2025-09-16 | Teloneer Company Limited | N/A | Closed | 2025-09-16 16:40:40 | Yes | Yes | 2025-09-22 12:45:43 |  | 2025-07-31 | 2025-09-22 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-10 10:16:30 | Yes | Yes | 2025-09-22 16:32:54 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 14:58:50 |  | 2025-07-31 | 2025-10-09 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-12-18 21:29:47 | Yes | Yes | 2025-12-18 18:16:37 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-16 |  | 2025-09-16 | Reungsak Junkong 00927496 | N/A | Closed | 2025-09-16 18:23:31 | No | No |  | "** Waiting On-service LNR26 #， Add UBBPg3a #，New L26F5 + NR26 (New AAU5636w) S.B#，C Replace Antenna (MB) + Replace RRU (RRU5516_1800) + 4T4R S2" |  | 2025-09-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-18 18:21:12 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GOCPM_2025 Coverage Expansion Ph2_EXP_BKK | Government Office Car Park |  |  |  | 2025-10-28 | 2025-11-04 | 2025-11-03 | 2025-11-03 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-11-21 15:53:01 | No | No |  |  | 2025-11-04 | 2025-11-06 | 2025-10-31 | 2025-11-06 | Teloneer Company Limited | N/A | Closed | 2025-11-06 16:28:48 | Yes | Yes | 2025-11-06 16:31:59 |  |  | 2025-11-05 | Apichart Kampuang | Approved | Closed | 2025-12-03 09:56:01 | Yes | Yes | 2026-05-17 15:17:34 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:22:41 |  | 2025-09-02 | 2025-10-27 | Palagon Prommueangma(Teloneer Company Limited) | Approved | Closed | 2025-11-28 14:34:00 | No | Yes | 2025-10-28 09:05:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-29 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-29 17:19:30 | No | No |  | 29-10-2025. Add RRU3953#， Replace SFP BIDI Sec.1 //28-Oct-2025 Replace Ant 8port Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-11-03 |  | N/A | Not assigned |  | No | No
GSP2P_2025 Capacity Expansion NW Modernization_EXP_BKK | LAMPSITE GAYSORN PLAZA 2 | [5 empty] | 2026-03-24 | 2026-03-24 | Akhom Srinara | N/A | Closed | 2026-03-24 11:11:26 | No | No |  |  |  | 2026-02-13 | 2026-03-08 | 2026-03-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-03-08 16:22:34 | Yes | Yes | 2026-03-21 15:16:12 |  | 2026-06-02 | 2026-06-02 | Aomchun Jittreemit | Approved | Closed | 2026-09-16 16:45:53 | Yes | Yes | 2026-06-02 09:54:25 | page.1 need to fill site name | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-12-29 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-06-20 | 2026-06-20 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-06-20 20:36:02 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-06 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-03-06 01:22:21 | No | No |  | 11-Mar-2026 GSP2P_L2 Replace BBU5900 UMPTg2 Add GPS Add g2 g3a 6 Mar 2026 Replace BBU5900 add GPS |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-02-13 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-06-25 04:38:41 | Yes | Yes | 2026-02-17 10:19:13 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GSPZM_2025 Capacity Expansion NW Modernization_EXP_BKK | GAYSORN PLAZA_3G2100 | [5 empty] | 2026-03-24 | 2026-03-24 | Akhom Srinara | N/A | Closed | 2026-04-21 20:49:36 | No | No |  |  |  | 2026-04-11 | 2026-03-16 | 2026-03-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-03-26 10:06:01 | Yes | Yes | 2026-06-09 17:18:56 |  | 2026-06-05 | 2026-06-11 | Aomchun Jittreemit | Approved | Closed | 2026-08-05 09:28:56 | Yes | Yes | 2026-06-12 18:37:19 | ขอรายการ tower laod area เสา Sector1 เกินมาตรฐานหรือไม่ | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-06-11 | 2026-06-11 | Aomchun Jittreemit | Approved | Closed | 2026-06-19 15:27:18 | Yes | Yes | 2026-06-11 10:17:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-07 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-07 16:45:45 | No | No |  | 07-Mar-26 Replace RRU5502 To DMM S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GSPZP_2025 Capacity Expansion NW Modernization_EXP_BKK | GAYSORN PLAZA | [5 empty] | 2026-03-17 | 2026-03-17 | Akhom Srinara | N/A | Closed | 2026-03-24 11:11:26 | No | No |  |  | 2026-03-13 | 2026-04-11 | 2026-03-14 | 2026-03-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-03-14 10:05:03 | Yes | Yes | 2026-03-18 20:46:03 |  | 2026-03-18 | 2026-03-19 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-09-18 18:28:50 | Yes | Yes | 2026-03-19 17:06:59 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-17 | 2026-04-17 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-04-17 12:57:56 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-06 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-03-06 01:22:21 | No | No |  | 6 Mar 2026 Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GSTPM_2025 Capacity Expansion Ph2_EXP_ER | G Steel Plant (G Steel Public Company Limited | 2025-07-18 |  | Install & Integrate |  | 2025-07-31 | 2025-07-19 | 2025-07-19 | Teloneer Company Limited | N/A | Closed | 2025-07-19 16:31:39 | No | No |  |  |  | 2025-07-31 | 2025-07-20 | 2025-07-20 | Teloneer Company Limited | N/A | Closed | 2025-07-20 14:44:28 | Yes | Yes | 2025-07-27 13:42:23 |  | 2025-07-31 | 2025-09-24 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-26 13:58:41 | Yes | Yes | 2025-09-24 15:12:30 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:16 | Yes | Yes | 2025-09-22 19:40:01 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:23:48 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-19 |  | 2025-07-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-18 20:07:23 | No | No |  | Add UBBPg2 #，Replace Antenna (Dualband) 18/21 co HB + Replace RRU5505 (RRU5516_1800) + 4T4R S1#，2 #，New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna) S1#，2 |  | 2025-07-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-18 20:15:34 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GTICB_2025 Capacity Expansion NW Modernization_EXP_BKK | GRAND TOWER INN COMPANY |  |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-16 17:56:33 | No | No |  |  |  | 2026-02-06 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 20:07:48 | Yes | Yes | 2026-02-11 20:07:49 |  | 2026-02-13 | 2026-02-13 | Chonradee Suwapan | Approved | Closed | 2026-02-23 15:57:48 | Yes | Yes | 2026-02-13 22:55:30 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:30:49 |  | 2026-02-13 | 2026-02-13 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-13 23:10:26 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-02 18:27:48 | No | No |  | 02-02-2026. Replace UBBPd6#， UBBPeb to UBBPg3a x2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GTICM_2025 Capacity Expansion NW Modernization_EXP_BKK | GRAND TOWER INN COMPANY |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-17 16:22:25 | No | No |  |  |  | 2026-02-06 | 2026-03-25 | 2026-03-26 | V Contribute Co., Ltd | N/A | Closed | 2026-03-26 08:33:26 | Yes | Yes | 2026-03-26 08:33:27 |  | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-05-11 16:12:29 | Yes | Yes | 2026-05-05 17:34:51 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-07 | 2026-03-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-16 22:23:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-02 17:52:51 | No | No |  | 2 Feb 2026 Add AAY5726 sector1#，3 replace RRU5526 sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GVEMB_2025 Capacity Expansion NW Modernization_EXP_BKK | GREEN VIEW EKKAMAI 10 | 2026-01-29 |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:46:20 | No | No |  |  |  | 2026-02-07 | 2026-03-20 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:22:39 | Yes | Yes | 2026-03-23 15:22:40 |  | 2026-03-20 | 2026-03-20 | Chonradee Suwapan | Approved | Closed | 2026-06-09 16:36:07 | Yes | Yes | 2026-05-29 01:51:26 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-20 | 2026-03-20 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-20 21:38:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-29 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-29 18:33:39 | No | No |  | 2026-01-29_Replace RRU3962 to RRU5526 Sector A#，B#，C#， Existing Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAAWM_2025 Coverage Expansion Ph2_EXP_BKK | HAT AMMARA AKSARALAK WITTHAYA SCHOOL | 2025-08-06 |  | Install & Integrate | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-08-07 08:29:49 | No | No |  |  | 2025-08-06 | 2025-08-08 | 2025-08-09 | 2025-08-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-08-19 10:18:16 | Yes | Yes | 2025-08-19 10:20:46 |  | 2025-08-10 | 2025-09-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-09-09 09:04:09 | Yes | Yes | 2025-11-25 09:42:11 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:16 | Yes | Yes | 2025-09-22 19:42:29 |  | 2025-08-20 | 2025-08-20 | Sattaya Parakij | Approved | Closed | 2025-09-03 22:43:51 | No | Yes | 2025-08-20 23:45:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-06 16:58:00 | No | No |  | 06-08-2025. Add RRU3953 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-05 |  | N/A | Not assigned |  | No | No
HCU2M_2025 Coverage Expansion Ph2_EXP_BKK | HUACHIEW CHALERMPRAKIET 2 UNIVERSITY |  |  |  | 2026-02-08 | 2026-02-21 | 2026-02-10 | 2026-02-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-02-10 17:46:30 | No | No |  |  | 2026-02-08 | 2026-02-21 | 2026-02-12 | 2026-02-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-02-12 17:48:48 | Yes | Yes | 2026-03-12 20:38:30 |  | 2026-03-13 | 2026-03-12 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-05-27 16:31:59 | Yes | Yes | 2026-03-13 00:28:10 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-06-08 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-04-09 | 2026-04-09 | Charuwan Limsaihua | Approved | Closed | 2026-06-19 15:35:14 | Yes | Yes | 2026-04-09 15:02:00 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-09 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-09 18:25:38 | No | No |  | 09-02-26 Replace RRU5507 To RRU5502 S1 S6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | เป้น Wall ploe ส่งเมล์เสนอ solution แล้ว |  |  |  | N/A | Not assigned |  | No | No
HK72M_2025 Capacity Expansion Ph3_EXP_BKK | HIN KLUK ROAD SOI CHALOEM PHRAKIAT 72 PHANSA |  |  |  | 2025-09-05 | 2025-09-12 | 2025-09-16 | 2025-09-16 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-16 13:23:17 | No | No |  |  | 2025-09-12 | 2025-09-15 | 2025-09-15 | 2025-09-15 | Teloneer Company Limited | N/A | Closed | 2025-09-16 11:05:33 | Yes | Yes | 2025-09-16 11:05:34 |  |  | 2025-09-16 | Apichart Kampuang | Approved | Closed | 2025-10-14 17:07:34 | Yes | Yes | 2025-10-14 11:42:56 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 16:49:29 |  |  | 2025-09-02 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 23:28:37 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-05 19:42:01 | No | No |  | 5-Sep-2025 Add RRU5516 (1800-2100)S3 Remove RRU5507 Replace Ant.4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-15 |  | N/A | Not assigned |  | No | No
HKG2M_2025 Capacity Expansion Ph1_EXP_BKK | HUAY KWANG 2_3G2100 | 2025-05-26 |  |  |  | 2025-05-26 | 2025-05-26 | 2025-05-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-05-26 15:47:22 | No | No |  |  |  | 2025-05-29 | 2025-06-12 | 2025-06-13 | V Contribute Co., Ltd | N/A | Closed | 2025-06-13 17:49:36 | Yes | Yes | 2025-06-13 17:51:05 |  |  | 2025-05-31 | Chonradee Suwapan | Approved | Closed | 2025-06-27 16:08:39 | Yes | Yes | 2025-06-27 15:03:31 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-02 | 2025-07-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:18:03 | Yes | Yes | 2025-08-05 13:33:19 |  | 2025-05-15 | 2025-05-15 | Annop Auyto | Approved | Closed | 2025-06-09 15:03:36 | No | Yes | 2025-05-15 17:48:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-05-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-05-26 16:35:41 | No | No |  | 26-05-2025. Add UBBPg3a#， AIRU5636w Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-05-23 |  | N/A | Not assigned |  | No | No
HLEKM_2025 Capacity Expansion Ph6_EXP_ER | Ban Huay Lek | 2025-11-08 | THCP_Phet.S | Install & Integrate |  | 2025-11-30 | 2025-11-08 | 2025-11-08 | Teloneer Company Limited | N/A | Closed | 2025-11-08 11:27:37 | No | No |  |  |  | 2025-11-30 | 2025-11-10 | 2025-11-10 | Teloneer Company Limited | N/A | Closed | 2025-11-10 20:41:10 | Yes | Yes | 2025-11-12 13:46:15 |  | 2025-11-30 | 2025-11-12 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-14 16:35:18 | Yes | Yes | 2025-11-12 16:09:17 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 17:30:31 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:54 | Yes | Yes | 2025-11-04 08:55:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-08 | Reungsak Junkong 00927496 | N/A | Closed | 2025-11-08 18:07:29 | No | No |  | **waiting on-service L7/L9 -- Add UBBPg2 #，Replace Antenna (Dualband) Sec.3 &New L0709 + 4T4R + (RRU5516_900) + (Co Antenna) Sec.3 |  | 2025-11-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-10 17:55:28 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HLP1M_2025 Capacity Expansion NW Modernization_EXP_BKK | HUA LAM PHONG 1 |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-24 14:48:20 | No | No |  |  |  | 2026-02-21 | 2026-03-10 | 2026-03-15 | V Contribute Co., Ltd | N/A | Closed | 2026-03-15 16:54:02 | Yes | Yes | 2026-03-15 16:54:02 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-02-26 10:52:14 | Yes | Yes | 2026-02-23 21:18:41 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:31:27 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-23 22:51:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-05 19:06:37 | No | No |  | 5-Feb-2026 Add AAU5768 Sector 2 Remove RRU5502 *2 Add RRU5526 S1 Remove RRU3962 *2 Add RRU5526 S3 Remove RRU3962 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HLP2M_2025 Capacity Expansion NW Modernization_EXP_BKK | HUA LAM PHONG 2 |  |  |  | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-20 11:27:26 | No | No |  |  | 2026-02-03 | 2026-02-28 | 2026-02-03 | 2026-05-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-11 18:09:20 | Yes | Yes | 2026-05-11 18:11:45 |  | 2026-04-20 | 2026-04-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-20 20:30:26 | Yes | Yes | 2026-05-17 15:51:13 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-20 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:29:53 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-27 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-01-27 18:27:08 | No | No |  | 27 Jan 2026 Replace RRU5513 sector1 RRU5526 sector3 AAU5768 sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HNDAN_2025 Coverage Expansion Ph2_New_SR | Hin Dan |  |  |  | 2025-12-25 |  | 2025-12-26 | 2025-12-26 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2026-01-20 14:04:11 | No | No |  |  |  | 2025-12-25 | 2025-12-25 | 2025-12-26 | Teloneer Company Limited | N/A | Closed | 2025-12-26 14:42:29 | Yes | Yes | 2026-02-20 19:33:56 |  | 2026-02-20 | 2026-02-20 | Nattawoot Suwan | Approved | Closed | 2026-02-25 11:14:20 | Yes | Yes | 2026-02-20 21:46:11 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-04-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:03 | Yes | Yes | 2026-04-09 11:31:22 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-06-08 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-06-08 18:40:27 | No | No |  | 16 Jan 2026 on service pending alarm RRU S2.2 26 Dec 2025 New site add 6RRU3826 3UBBPd5 BBU3910 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-17 14:08:58 | Yes | Yes | 2025-12-15 17:30:43 |  |  | 2026-02-05 | Nattawoot Suwan | N/A | Closed | 2026-02-05 11:17:05 | No | No | [7 empty] | N/A | Not assigned |  | No | No
HUSRM_2025 Capacity Expansion Ph7_EXP_ER | Hua Samrong | 2025-12-24 | Thcp_adirek.kh | Install & Integrate |  | 2025-12-31 | 2025-12-13 | 2025-12-13 | Teloneer Company Limited | N/A | Closed | 2025-12-13 15:31:41 | No | No |  |  |  | 2025-12-31 | 2025-12-13 | 2025-12-16 | Teloneer Company Limited | N/A | Closed | 2025-12-16 14:57:45 | Yes | Yes | 2025-12-18 10:12:24 |  | 2025-12-31 | 2025-12-18 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-01-06 16:29:46 | Yes | Yes | 2025-12-18 18:56:28 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:28 | Yes | Yes | 2026-03-20 16:48:14 |  | 2025-12-31 | 2025-12-15 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:26:56 | Yes | Yes | 2025-12-15 09:12:22 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-13 15:49:13 | No | No |  | Add UBBPg3a_HUSRM_H_1 Remove Antenna + (New AAU5768) + Main Dir = 220 + Remove RRU5505 x 2_HUSRM_H_3 Remove Antenna + (Co AAU5768) + Main Dir = 220 + Remove RRU5505 x 2_HUSRM_H_8 New Antenna (L) + Replace RRU5508 to (RRU5516_900) + 4T4R_HUSRM_L_8 New Sector M (Co AAU5768) + Main Dir = 220_HUSRM_H_M New Sector N (Co AAU5768) + Main Dir = 220_HUSRM_H_N | 2025-12-13 | 2025-12-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-13 17:16:52 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HYIPM_2025 Capacity Expansion Ph2_EXP_SR | Hadyai Park | [5 empty] | 2025-08-27 | 2025-08-27 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-28 14:34:49 | No | No |  |  |  | 2025-08-30 | 2025-08-27 | 2025-08-27 | Teloneer Company Limited | N/A | Closed | 2025-08-27 17:34:08 | Yes | Yes | 2025-09-05 16:18:02 |  | 2025-09-06 | 2025-09-18 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2025-09-26 11:47:36 | Yes | Yes | 2025-09-06 11:26:03 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:55 | Yes | Yes | 2025-10-06 16:40:04 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-27 | 2026-06-05 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-06-05 10:34:57 | No | No |  | ***Pending Clear Alarm RET Antenna Motor Fault Remove Cell NR700 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-08-27 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-08-28 14:35:19 | No | No | [5 empty] | 2025-08-26 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
HYMUM_2025 Capacity Expansion Ph2_EXP_SR | HAT YAI MUNICIPALITY | [5 empty] | 2026-03-27 | 2026-03-27 | Teloneer Company Limited | N/A | Closed | 2026-03-27 16:23:49 | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA
IBNGM_2025 Capacity Expansion Ph4_EXP_ER | Ban Intarat Bangnang | 2025-09-05 |  | Install & Integrate |  | 2025-09-30 | 2025-09-05 | 2025-09-05 | Teloneer Company Limited | N/A | Closed | 2025-09-05 15:50:49 | No | No |  |  |  | 2025-09-30 | 2025-09-06 | 2025-09-06 | Teloneer Company Limited | N/A | Closed | 2025-09-07 21:29:46 | Yes | Yes | 2025-09-07 21:29:47 |  | 2025-09-30 | 2025-09-08 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-10 10:16:30 | Yes | Yes | 2025-11-07 13:37:40 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 15:20:56 |  | 2025-09-30 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2026-03-02 15:29:20 | Yes | Yes | 2025-10-08 09:35:44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-09 |  | 2025-09-05 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-05 18:40:56 | No | No |  | **waiting on-service NR7 -- Replace 1RRU5508 to (RRU5516_900) + Co NR07 + 4T4R S2 |  | 2025-09-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-10 16:23:32 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IDBSB_2025 Capacity Expansion Ph3_EXP_BKK | IDEO BLUECOVE SUKHUMVIT | [5 empty] | 2025-12-09 | 2025-12-09 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  |  |  | 2025-10-06 | 2025-10-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-31 17:28:50 | Yes | Yes | 2025-12-08 23:22:27 |  | 2025-12-11 | 2026-03-23 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-04-07 21:28:50 | Yes | Yes | 2026-03-23 19:34:57 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-04-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:32:42 |  | 2025-12-18 | 2025-12-18 | Charuwan Limsaihua | Approved | Closed | 2026-03-12 09:22:14 | No | Yes | 2025-12-18 15:28:06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-04 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-12-04 19:06:56 | No | No |  | 2025-12-04_Add RRU5818 sector D co-with sector E//02-12-2025. ***Pending Add Add RRU5818 SD Co RRU2600 SE 5/5 //Add GPS //6-Oct-2025 Replace BBU5900 UMPTg2 Add g3a remove d5 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
IDCIB_2025 Coverage Expansion Ph1_EXP_BKK | IDEO MOBI CHARAN INTERCHANGE | [5 empty] | 2025-09-13 | 2025-09-13 | Akhom Srinara | N/A | Closed | 2025-09-25 13:54:36 | No | No |  |  |  |  | 2025-09-12 | 2025-09-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-15 10:46:43 | Yes | Yes | 2025-09-15 10:46:43 |  | 2025-09-15 | 2025-09-15 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-07 16:22:25 | Yes | Yes | 2025-09-15 13:36:10 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:02 | Yes | Yes | 2025-10-09 20:11:11 |  | 2025-09-15 | 2025-09-18 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:28:19 | No | Yes | 2025-09-18 14:57:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-12 16:59:41 | No | No |  | 12-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของเพิ่มเติมขาด Spliter 2way |  | 2025-09-12 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
IS71B_2025 Capacity Expansion NW Modernization_EXP_BKK | I STORE SELF STORAGE AT SUKHUMVIT 71 FOR NIA BY SANSIRI |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:29:00 | No | No |  |  | 2026-05-31 | 2026-05-31 | 2026-05-13 | 2026-05-14 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-14 09:48:20 | Yes | Yes | 2026-05-19 13:54:28 |  | 2026-06-25 | 2026-06-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-10 16:45:22 | Yes | Yes | 2026-06-25 15:39:30 | 1.Page 7#，39#，In SOW & EQ install RRU must be 2pcs. 2.Page 22#，RRU must be 2pcs. 3.Page 25#，Need to upload RRU 2pcs activity. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-07-14 22:50:47 |  |  | 2026-05-31 | 2026-05-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-02 15:04:10 | No | No |  |  |  |  | 2026-05-02 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-05-02 17:19:56 | No | No |  | 02-05-2026. Add RRU5507 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ITICB_2025 Coverage Expansion Ph1_EXP_BKK | IDEO THAPHRA INTERCHANGE |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:10 | No | No |  |  |  | 2025-11-28 | 2025-11-04 | 2025-11-26 | V Contribute Co., Ltd | N/A | Closed | 2025-11-26 19:36:16 | Yes | Yes | 2025-11-26 19:36:16 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-11 16:14:42 | Yes | Yes | 2025-11-08 17:54:56 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 18:07:18 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-08 16:44:09 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-28 16:18:05 | No | No |  | 28-Oct-2025 Replace to Ant Vertical Dual Beam Sector A B C #，82 83 84 E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
ITLSM_2025 Capacity Expansion Ph2_EXP_BKK | IT SQUARE LAK SI DEPARTMENT STORE |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:10 | No | No |  |  |  | 2025-11-28 | 2025-11-09 | 2025-11-10 | V Contribute Co., Ltd | N/A | Closed | 2025-11-10 10:26:35 | Yes | Yes | 2025-11-10 10:26:35 |  | 2025-11-10 | 2025-11-10 | Chonradee Suwapan | Approved | Closed | 2025-11-20 09:23:35 | Yes | Yes | 2025-11-10 17:38:03 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 18:08:32 |  | 2025-11-10 | 2025-11-10 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-10 17:43:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-28 16:16:39 | No | No |  | 28-Oct-2025 Add RRU5516 (1800-2100) S1 Remove RRU5507 Replace Ant 12port S1 Add RRU5516 (1800-2100) S6 Co-Ant With S1 Remove Ant 900 4/3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
IVA1B_2025 Capacity Expansion Ph7_EXP_BKK | IVY AMPIO (Front) |  |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2026-04-23 14:25:09 | No | No |  |  |  | 2026-04-10 | 2026-04-24 | 2026-05-18 | V Contribute Co., Ltd | N/A | Closed | 2026-05-18 15:07:48 | Yes | Yes | 2026-05-18 15:07:48 |  | 2026-04-27 | 2026-04-27 | Chonradee Suwapan | Approved | Closed | 2026-05-11 09:29:24 | Yes | Yes | 2026-04-27 02:04:33 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-27 | 2026-04-27 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-27 02:10:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-26 17:44:22 | No | No |  | 26-01-2026. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， RRU5818 Sec.A //ติด GPS ไม่ได้ |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IVA1B_2025 Coverage Expansion Ph1_EXP_BKK | IVY AMPIO (Front) | 2025-09-03 |  |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-03 18:12:42 | No | No |  |  |  | 2025-09-30 | 2025-09-11 | 2025-09-15 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:14:29 | Yes | Yes | 2025-09-30 10:14:30 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:45:39 | Yes | Yes | 2025-11-25 12:34:01 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:55 | Yes | Yes | 2025-10-06 16:45:03 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-19 20:34:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-05 09:49:06 | No | No |  | 2025-09-03_Replace to Ant Vertical Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | ขาด UBBPD6=1 |  | 2025-09-02 |  | N/A | Not assigned |  | No | No
JAV1A_2025 Capacity Expansion NW Modernization_EXP_BKK | J AVENUE THONGLOR |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-03-05 | 2026-03-05 | 2026-03-20 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:45:21 | Yes | Yes | 2026-03-25 14:15:03 |  | 2026-04-24 | 2026-04-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-04 17:39:55 | Yes | Yes | 2026-04-24 16:53:15 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 21:30:08 |  |  | 2026-03-02 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-02 19:25:49 | No | No |  | 2026-06-19_Replace to BBU5900 by UMPTg2#， Add UBBPg2#， No GPS 2-Mar-2026 Add RRU5526 SA SB Remove RRU3962 *2 Replace Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JAVNP_2025 Capacity Expansion NW Modernization_EXP_BKK | J-Avenue |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 18:22:45 | Yes | Yes | 2026-03-24 14:18:57 |  | 2026-04-20 | 2026-04-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-30 20:16:37 | Yes | Yes | 2026-04-24 14:45:29 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-01 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 21:30:24 |  |  | 2026-03-05 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-13 16:06:17 | No | No |  | 13-Feb-2026 Replace BBU5900 UMPTg2 Add g2 ติด GPS ไม่ได้ เป็นห้อง |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JJS05_2025 Capacity Expansion Ph5_EXP_BKK | JATUJAK MARKET (SMALL CELL) No.5 |  |  |  |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-22 09:18:28 | No | No |  |  |  | 2025-12-28 | 2025-12-24 | 2025-12-24 | V Contribute Co., Ltd | N/A | Closed | 2025-12-24 21:11:03 | Yes | Yes | 2025-12-24 21:11:03 |  | 2026-01-08 | 2026-01-08 | Chonradee Suwapan | Approved | Closed | 2026-02-17 17:18:26 | Yes | Yes | 2026-02-12 16:36:49 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 14:56:36 |  | 2026-01-08 | 2026-01-08 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:02:00 | Yes | Yes | 2026-01-08 22:09:49 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-19 19:04:14 | No | No |  | 19-Dec-2205 Add RRU5818 sector A Add g2 5/1 (Remark slot 0 Fail) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JNTWB_2025 Coverage Expansion Ph1_EXP_BKK | JOHNNY TOWER | 2025-09-15 |  |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-15 18:10:01 | No | No |  |  |  | 2025-09-30 | 2025-09-15 | 2025-09-15 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:14:44 | Yes | Yes | 2025-09-30 10:14:45 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-10-06 16:26:47 | Yes | Yes | 2025-09-22 19:42:42 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:02 | Yes | Yes | 2025-10-09 20:12:27 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-22 19:56:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-15 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-15 17:35:06 | No | No |  | 15-09-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-14 |  | N/A | Not assigned |  | No | No
JTDOM_2025 Capacity Expansion Ph2_EXP_BKK | Jom Thong District Office | 2025-08-22 |  |  |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-22 17:15:25 | No | No |  |  |  | 2025-08-31 | 2025-08-26 | 2025-08-27 | V Contribute Co., Ltd | N/A | Closed | 2025-08-27 10:23:11 | Yes | Yes | 2025-08-27 10:26:46 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-17 13:07:46 | Yes | Yes | 2025-09-06 19:15:40 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:16 | Yes | Yes | 2025-09-22 19:56:14 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-06 19:22:56 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-22 16:59:10 | No | No |  | 22-Aug-2025 Add RRU5516 (1800-2100) S6 Add Ant 8 port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-21 |  | N/A | Not assigned |  | No | No
K100M_2025 Capacity Expansion Ph2_EXP_BKK | Khun yay 100 Year market | 2025-09-02 |  |  |  | 2025-09-02 | 2025-09-02 | 2025-09-02 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-02 15:53:01 | No | No |  |  |  | 2025-09-30 | 2025-09-02 | 2025-09-11 | V Contribute Co., Ltd | N/A | Closed | 2025-09-11 18:07:09 | Yes | Yes | 2025-09-11 18:08:09 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-09-18 17:11:26 | Yes | Yes | 2025-09-12 21:14:24 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:16 | Yes | Yes | 2025-09-22 19:57:29 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-12 22:24:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-02 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-02 17:59:46 | No | No |  | 11-Sep-2025 Clear Alarm VSWR 900 Subrack 101 2025-09-02_Add UBBPg2#， Add RRU5516#， Ant 4 port Sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-01 |  | N/A | Not assigned |  | No | No
K100M_2025 Capacity Expansion Ph7_EXP_BKK | KHUN YAY 100 YEAR MARKET | 2026-01-14 |  |  |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-14 16:19:24 | No | No |  |  |  | 2026-01-31 | 2026-01-16 | 2026-02-13 | V Contribute Co., Ltd | N/A | Closed | 2026-02-13 11:44:09 | Yes | Yes | 2026-02-13 11:44:10 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-06 13:32:23 | Yes | Yes | 2026-02-26 11:01:24 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 14:56:55 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-04 19:15:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-14 12:10:53 | No | No |  | 14-Jan-2025 AAU5636w Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
K100M_2025 Coverage Expansion Ph2_EXP_BKK | KHUN YAY 100 YEAR MARKET | 2025-08-18 |  |  |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-18 18:56:06 | No | No |  |  |  | 2025-08-29 | 2025-08-25 | 2025-08-25 | V Contribute Co., Ltd | N/A | Closed | 2025-08-25 17:37:00 | Yes | Yes | 2025-08-25 17:41:09 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-05 17:11:19 | Yes | Yes | 2025-09-02 18:09:15 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:16 | Yes | Yes | 2025-09-22 19:58:42 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 01:54:03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-18 16:42:17 | No | No |  | 18-Aug-2025 Add RRU3953 S3 Add Ant. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-15 |  | N/A | Not assigned |  | No | No
K107M_2025 Capacity Expansion Ph2_EXP_BKK | Soi Charoen Krung 107 Yaek 15/1-1 |  |  |  | 2025-08-20 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-21 | 2025-08-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-21 20:30:24 | Yes | Yes | 2025-08-26 14:32:41 |  | 2025-08-28 | 2025-08-28 | Muhamadnase Chesamae | Approved | Closed | 2025-10-27 09:33:43 | Yes | Yes | 2025-09-02 18:50:30 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-10-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:56 | Yes | Yes | 2025-10-27 17:29:53 |  | 2025-09-04 | 2025-09-04 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 15:02:20 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-21 18:34:48 | No | No |  | 21-08-2025. Add UBBPg2#， RRU5516 L900 Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
K122M_2025 Coverage Expansion Ph2_EXP_BKK | RANGSIT KHLONG 12 STATION2 | 2025-08-06 |  | Install & Integrate | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-08-07 08:29:49 | No | No |  |  | 2025-08-31 | 2025-08-31 | 2025-08-06 | 2025-08-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-08-06 18:27:04 | Yes | Yes | 2025-08-13 14:40:14 |  | 2025-08-10 | 2025-09-01 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-09-03 14:47:58 | Yes | Yes | 2025-09-01 11:56:00 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:14:03 |  | 2025-08-20 | 2025-08-20 | Sattaya Parakij | Approved | Closed | 2025-09-03 22:43:51 | No | Yes | 2025-08-20 23:45:44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-06 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-06 18:52:51 | No | No |  | 2025-08-06_Add RRU3953 Sector 3#， No act Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-05 |  | N/A | Not assigned |  | No | No
K546M_2025 Capacity Expansion Ph2_EXP_BKK | SOI KLONG 5 TAWANTOK 46 |  |  |  | 2025-08-19 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-19 | 2025-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-19 17:36:27 | Yes | Yes | 2025-08-21 12:13:44 |  | 2025-08-21 | 2025-08-31 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-15 09:18:52 | Yes | Yes | 2025-11-03 13:25:44 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:16 | Yes | Yes | 2025-09-22 19:59:54 |  | 2025-09-03 | 2025-09-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 10:33:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-19 17:52:35 | No | No |  | 23-10-2025. Add UBBPg2 //2025-08-19_Replace RRU3953 to RRU5516#， Replace to Ant 4 port Sector 1#，2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
KAN2M_2025 Capacity Expansion Ph3_EXP_BKK | SOI KAO NA 2 | [5 empty] | 2025-10-06 | 2025-10-06 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-03 | 2025-10-07 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-07 22:27:15 | Yes | Yes | 2025-10-27 09:49:19 |  | 2025-10-30 | 2025-10-30 | Muhamadnase Chesamae | Approved | Closed | 2025-11-11 09:20:58 | Yes | Yes | 2025-10-30 09:36:55 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 18:09:46 |  | 2025-10-30 | 2025-10-30 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-30 09:38:12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-06 14:48:44 | No | No |  | 6-Oct-2025 Add AAU5636w Sec.3 04-10-2025. ***Need AIRU5636w Sec.3 //Add RRU5516 L900 Sec.2#， AIRU5636w Sec.1#， Replace RRU5516 L18 Sec.1#， 3 //03-10-2025. Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
KB11M_2025 Capacity Expansion Ph3_EXP_BKK | NIKOM BANG PU 11 |  |  |  | 2025-09-12 | 2025-09-19 | 2025-09-23 | 2025-09-23 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-26 14:02:11 | No | No |  |  | 2025-09-19 | 2025-09-23 | 2025-09-22 | 2025-09-23 | Teloneer Company Limited | N/A | Closed | 2025-09-23 11:37:05 | Yes | Yes | 2025-09-26 17:31:25 |  |  | 2025-09-25 | Apichart Kampuang | Approved | Closed | 2025-10-19 21:27:05 | Yes | Yes | 2025-10-14 11:30:48 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 16:56:56 |  |  | 2025-09-02 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 23:29:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-15 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-15 19:06:55 | No | No |  | 2025-09-15_Replace AAU5768 to RRU5516 Sector 2#，7#，J#，3#，8#，M (Reconfig 32T32R to 4T4R)#， Add UBBPg2#， Add Ant TRI Beam//13-Sep-2025 Prework |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-22 |  | N/A | Not assigned |  | No | No
KBGYM_2025 Coverage Expansion Ph2_New_BKK | Khlong Bang Kaew Yai |  |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | V Contribute Co., Ltd | N/A | Closed | 2026-04-23 15:25:35 | No | No |  |  |  | 2026-04-30 | 2026-05-13 | 2026-05-14 | V Contribute Co., Ltd | N/A | Closed | 2026-05-14 18:22:04 | Yes | Yes | 2026-05-14 18:22:04 |  | 2026-05-15 | 2026-05-15 | Chonradee Suwapan | Approving | Assigned |  | Yes | Yes | 2026-05-15 02:35:33 | Page no.8#， 67#， 68 #， 90#， UBBPd5 - 1pc#， UPEU #， BBU fan SN wrong in INV. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-05-15 | 2026-05-15 | Chonradee Suwapan | Approved | Closed | 2026-05-21 14:12:58 | Yes | Yes | 2026-05-15 12:43:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-04-24 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-04-24 17:29:46 | No | No |  | 18 Jun 2026 Add GPS clear pending PAT 24-04-2026. Replace BBU แก้ slot card เสีย //23-Apr-2026 New site Add RRU3962 S1 S2 S3 Add d5 =3 Add Ant 8port S1 S2 S3 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
KBL1M_2025 Coverage Expansion Ph2_EXP_BKK | KHUBANGLUANG 1 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-11 | 2025-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-11 20:36:51 | Yes | Yes | 2025-08-15 15:28:47 |  | 2025-08-15 | 2025-08-15 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:33:55 | Yes | Yes | 2025-08-15 17:40:38 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:24:36 |  | 2025-09-03 | 2025-09-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-03 10:29:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-11 18:15:26 | No | No |  | 2025-08-11_Add RRU3953#， No act Ant Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
KBW3B_2025 Coverage Expansion Ph1_EXP_BKK | The Key BTS-Wutthakat (Back) |  |  |  |  | 2025-10-21 | 2025-10-21 | 2025-10-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-10-31 | 2025-10-29 | 2025-10-31 | V Contribute Co., Ltd | N/A | Closed | 2025-10-31 12:05:54 | Yes | Yes | 2025-10-31 12:05:54 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-19 16:03:47 | Yes | Yes | 2025-11-21 17:27:30 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 18:13:25 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-30 20:48:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-20 17:45:00 | No | No |  | 20-10-2025. Replace Ant.12 port Condo Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
KCDPO_2025 Capacity Expansion Ph4_EXP_SR | KANCHANADIT POST OFFICE |  |  |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | Nattawoot Suwan | N/A | Closed | 2025-11-13 08:47:46 | No | No |  |  |  | 2025-09-26 | 2025-11-11 | 2025-11-11 | Teloneer Company Limited | N/A | Closed | 2025-11-11 15:13:18 | Yes | Yes | 2025-11-12 11:18:06 |  | 2025-11-13 | 2025-11-13 | Nattawoot Suwan | Approved | Closed | 2025-12-11 10:27:05 | Yes | Yes | 2025-11-13 09:31:24 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-18 | 2025-11-18 | Chayanat mangmool WX1323423 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 18:14:37 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-11-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-11 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-11-11 16:33:22 | No | No |  | 11 Nov 2025 Add AAU5626w sector3 add 1UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-11 |  | N/A | Not assigned |  | No | No
KCT1B_2025 Coverage Expansion Ph1_EXP_BKK | The Key Chaengwattana (left) |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-24 | 2025-10-30 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 15:44:07 | Yes | Yes | 2025-10-30 15:44:08 |  | 2025-10-31 | 2025-10-31 | Chonradee Suwapan | Approved | Closed | 2025-11-05 16:33:10 | Yes | Yes | 2025-10-31 20:11:44 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 15:31:25 |  | 2025-10-31 | 2025-10-31 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-31 20:51:37 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-17 17:35:25 | No | No |  | 17-10-2025. Replace Ant.12 port x4 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
KEKCB_2025 Capacity Expansion Ph2_EXP_BKK | KENSINGTON KASET CAMPUS |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-11-28 | 2025-12-04 | 2025-12-09 | V Contribute Co., Ltd | N/A | Closed | 2025-12-09 12:28:28 | Yes | Yes | 2025-12-09 12:28:29 |  | 2025-11-28 | 2025-11-28 | Chonradee Suwapan | Approved | Closed | 2025-12-04 09:31:09 | Yes | Yes | 2025-11-28 19:46:12 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:27:31 |  | 2025-11-28 | 2025-11-28 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-28 19:58:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-17 16:58:25 | No | No |  | 17-11-2025. Add UBBPg3a#， RRU5818#， Ant.12 port Sec.C#， RRU5516 L18#， Ant.12 port Sec.E |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-24 |  | N/A | Not assigned |  | No | No
KEKCB_2025 Coverage Expansion Ph1_EXP_BKK | KENSINGTON KASET CAMPUS |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:10 | No | No |  |  |  | 2025-11-28 | 2025-10-30 | 2025-10-31 | V Contribute Co., Ltd | N/A | Closed | 2025-10-31 10:40:05 | Yes | Yes | 2025-10-31 10:40:05 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-12 09:16:41 | Yes | Yes | 2025-11-08 17:55:25 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 18:15:51 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-08 16:44:47 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-28 18:34:48 | No | No |  | 28-10-2025. Repalce Ant.12 port Condo Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
KFSNM_2025 Capacity Expansion Ph3_EXP_BKK | KLONG FARANG SAINOI |  |  |  |  | 2025-09-05 | 2025-09-14 | 2025-09-14 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-26 | 2025-09-17 | 2025-09-18 | V Contribute Co., Ltd | N/A | Closed | 2025-09-18 14:48:47 | Yes | Yes | 2025-09-18 14:48:48 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-10-07 16:22:25 | Yes | Yes | 2025-10-25 09:42:44 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:02 | Yes | Yes | 2025-10-09 20:20:08 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 17:34:30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-05 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-05 17:31:50 | No | No |  | 05-09-2025. Add UBBPg2#， AIRU5636w Sec.1#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-13 |  | N/A | Not assigned |  | No | No
KFSNM_2025 Coverage Expansion Ph2_EXP_BKK | KLONG FARANG SAINOI | 2025-07-31 |  |  |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-07-31 17:04:06 | No | No |  |  |  | 2025-08-22 | 2025-08-12 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 17:17:31 | Yes | Yes | 2025-08-15 17:18:58 |  | 2025-08-11 | 2025-08-11 | Chonradee Suwapan | Approved | Closed | 2025-08-18 17:06:03 | Yes | Yes | 2025-08-11 18:02:08 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-22 | 2025-08-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:17:57 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:52:40 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-07-31 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-07-31 17:43:19 | No | No |  | 31-07-2025. Add RRU3953 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-30 |  | N/A | Not assigned |  | No | No
KGSOM_2025 Capacity Expansion Ph3_EXP_BKK | KHLONG SONG |  |  |  | 2025-09-10 | 2025-09-17 | 2025-09-19 | 2025-09-19 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-22 17:57:16 | No | No |  |  | 2025-09-17 | 2025-09-19 | 2025-09-18 | 2025-09-18 | Teloneer Company Limited | N/A | Closed | 2025-09-18 16:17:10 | Yes | Yes | 2025-09-19 16:38:20 |  |  | 2025-09-22 | Apichart Kampuang | Approved | Closed | 2025-10-22 15:01:43 | Yes | Yes | 2025-11-26 17:23:50 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 16:59:28 |  |  | 2025-09-04 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-09-04 19:14:41 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-11 18:53:44 | No | No |  | 11-Sep-2025 Add RRU5516 (1800-2100) Sector J Replace Ant to Tri Beam J |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-18 |  | N/A | Not assigned |  | No | No
KGSRM_2025 Capacity Expansion Ph5_EXP_BKK | KHO SO LO. SAI BAN KHLONG SAMRONG RD. | 2025-12-23 |  |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-23 17:47:19 | No | No |  |  |  | 2025-12-31 | 2025-12-26 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 16:59:56 | Yes | Yes | 2025-12-26 16:59:57 |  | 2026-01-08 | 2026-01-08 | Chonradee Suwapan | Approved | Closed | 2026-01-16 16:09:55 | Yes | Yes | 2026-01-08 21:54:58 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 14:58:43 |  | 2025-12-22 | 2025-12-22 | Annop Auyto | Approved | Closed | 2026-01-07 10:01:43 | Yes | Yes | 2025-12-22 18:59:36 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-23 16:55:48 | No | No |  | 23-12-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBg3a#， UBBPd5 x2#， AAU5636 Sec.3#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KH74M_2025 Capacity Expansion Ph3_EXP_BKK | Soi Kheha Romklao 74 Yaek 6 | [5 empty] | 2025-09-15 | 2025-09-15 | Akhom Srinara | N/A | Closed | 2025-09-25 13:59:16 | No | No |  |  |  |  | 2025-09-09 | 2025-09-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-15 11:18:50 | Yes | Yes | 2025-09-15 11:18:51 |  | 2025-09-17 | 2025-09-17 | Muhamadnase Chesamae | Approved | Closed | 2025-10-10 16:48:15 | Yes | Yes | 2025-09-17 10:01:47 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 15:39:05 |  | 2025-09-16 | 2025-09-16 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:28:45 | No | Yes | 2025-09-16 12:00:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-10 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-10 22:29:01 | No | No |  | 2025-09-10_2025-09-10_Replace to BBU5900 by UMPTg2#， Add UBBPg3#， GPS#， Replace to RRU5516(18-21) Sector 1#，2#，3#， Add RRU5516#， Ant Sector 6#， Add AAU5636w Sector 1#，2#，3//9-Sep-2025 Rollback Site |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-14 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
KHDNM_2025 Capacity Expansion Ph5_EXP_ER | Ban Khao Din | 2025-10-08 | thcp_phet.s | Install & Integrate |  | 2025-10-31 | 2025-10-08 | 2025-10-09 | Teloneer Company Limited | N/A | Closed | 2025-10-09 09:23:25 | No | No |  |  |  | 2025-10-31 | 2025-10-08 | 2025-10-09 | Teloneer Company Limited | N/A | Closed | 2025-10-09 16:05:01 | Yes | Yes | 2025-10-11 21:30:22 |  | 2025-10-31 | 2025-10-15 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-28 10:27:10 | Yes | Yes | 2025-11-07 13:38:14 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-11-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 15:41:42 |  | 2025-10-15 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-10 14:39:00 | Yes | Yes | 2025-10-08 15:39:34 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-10 |  | 2025-10-08 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-08 16:46:27 | No | No |  | **waiting on-service LNR26 -- Add UBBPg3a #，New L26F5 + NR26 (New AAU5636w) S1#，3 |  | 2025-10-09 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-09 16:38:38 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KHHKM_2025 Capacity Expansion Ph2_EXP_BKK | Khlong Hua Kluea | 2025-08-09 |  |  |  | 2025-08-09 | 2025-08-09 | 2025-08-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-09 16:06:17 | No | No |  |  |  | 2025-08-31 | 2025-08-17 | 2025-08-18 | V Contribute Co., Ltd | N/A | Closed | 2025-08-18 10:52:49 | Yes | Yes | 2025-08-18 11:28:38 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-09-12 19:05:30 | Yes | Yes | 2025-09-03 21:06:14 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:16 | Yes | Yes | 2025-09-22 20:09:14 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:38 | No | Yes | 2025-09-03 20:53:45 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-09 18:06:38 | No | No |  | 09-08-2025. Add UBBPg2#， Replace RRU5516 L18#， Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-09 |  | N/A | Not assigned |  | No | No
KHHKM_2025 Capacity Expansion Ph3_EXP_BKK | KHLONG HUA KLUEA | 2025-08-28 |  |  |  | 2025-08-28 | 2025-08-28 | 2025-08-28 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-28 16:57:01 | No | No |  |  |  | 2025-09-05 | 2025-08-28 | 2025-08-30 | V Contribute Co., Ltd | N/A | Closed | 2025-08-30 11:08:41 | Yes | Yes | 2025-08-30 11:10:05 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2026-03-11 16:32:23 | Yes | Yes | 2025-09-11 20:49:08 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-12-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 18:06:50 |  | 2025-09-11 | 2025-09-11 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-11 21:22:33 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-28 17:47:31 | No | No |  | 28-Aug-2025 Add RRU5516 (1800-2100) S6 Replace Ant 8port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-27 |  | N/A | Not assigned |  | No | No
KHNWM_2025 Capacity Expansion Ph7_EXP_BKK | KEHA NAWANAKHON | 2026-01-14 |  |  |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-14 16:19:24 | No | No |  |  |  | 2026-01-31 | 2026-01-14 | 2026-01-15 | V Contribute Co., Ltd | N/A | Closed | 2026-01-15 10:48:57 | Yes | Yes | 2026-01-15 10:48:58 | SQC Close | 2026-01-31 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-04 09:24:58 | Yes | Yes | 2026-01-31 23:47:05 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 14:59:28 |  | 2026-02-01 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-01 00:01:39 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-14 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-14 16:43:26 | No | No |  | 14 Jan 2026 add aau5636w sector 8#， add g2 slot 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KHRHM_2025 Capacity Expansion Ph2_EXP_BKK | KHLONG RAHAENG |  |  |  | 2025-09-03 | 2025-09-10 | 2025-09-16 | 2025-09-16 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-16 13:23:17 | No | No |  |  | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-15 | Teloneer Company Limited | N/A | Closed | 2025-09-16 10:34:13 | Yes | Yes | 2025-09-16 10:34:14 |  |  | 2025-09-16 | Apichart Kampuang | Approved | Closed | 2025-09-30 15:29:15 | Yes | Yes | 2025-10-17 17:26:20 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:55 | Yes | Yes | 2025-10-06 17:01:14 |  | 2025-08-31 | 2025-08-31 | Teloneer Company Limited | Approved | Closed | 2025-10-10 17:28:56 | No | Yes | 2025-08-31 16:51:33 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-04 17:03:23 | No | No |  | 4-Sep-2025 Add RRU5516 (700900) S1 S3 Add Ant 4port S1 S3 add g2 2025-09-03_Pre work |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-15 |  | N/A | Not assigned |  | No | No
KHS4B_2025 Capacity Expansion Ph5_EXP_BKK | KEHASAMUT PRAKAN4(BANGPOO) BUILDING 18 25 |  |  |  |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-01 09:34:25 | No | No |  |  |  | 2025-12-28 | 2025-12-15 | 2025-12-16 | V Contribute Co., Ltd | N/A | Closed | 2025-12-16 11:00:05 | Yes | Yes | 2025-12-16 11:00:05 |  | 2025-12-04 | 2025-12-04 | Chonradee Suwapan | Approved | Closed | 2025-12-15 09:24:38 | Yes | Yes | 2026-01-13 16:41:43 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 18:10:29 |  | 2025-12-04 | 2025-12-04 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-12-04 21:35:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-28 17:37:50 | No | No |  | 28-11-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， RRU5818 Sec.A#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KHS4B_DPU40_OPM30_Replacement_BKK | KEHASAMUT PRAKAN4(BANGPOO) BUILDING 18 25 |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-25 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 17:21:46 | Yes | Yes | 2025-12-26 17:21:47 |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-01-26 16:02:01 | Yes | Yes | 2026-01-16 17:36:02 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-23 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-13 21:08:45 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-25 17:23:47 | No | No |  | 25-Dec-2025 Replace DPU40 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
KHTRM_2025 Capacity Expansion Ph7_EXP_BKK | Soi Muban Kan Keha Chumchon Thonburi 1 Soi 8 |  |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-07 07:32:17 | No | No |  |  |  | 2026-01-31 | 2026-01-26 | 2026-01-30 | V Contribute Co., Ltd | N/A | Closed | 2026-01-30 09:08:36 | Yes | Yes | 2026-01-30 09:08:37 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-02-17 15:01:31 | Yes | Yes | 2026-02-26 18:19:16 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:36:08 |  | 2026-02-05 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-05 22:29:26 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-23 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-23 18:01:39 | No | No |  | 23-01-2026 Add aau5636w sector 8 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KIMHB_2025 Capacity Expansion Ph5_EXP_BKK | KANCHANABHISHEK INSTITUTE OF MEDICAL AND PUBLIC HEALTH TECHNOLOGY |  |  |  | 2025-12-24 | 2025-12-26 | 2025-12-26 | 2025-12-27 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2026-01-20 17:18:00 | No | No |  |  |  | 2025-11-20 | 2025-12-26 | 2025-12-28 | Teloneer Company Limited | N/A | Closed | 2025-12-28 10:27:16 | Yes | Yes | 2025-12-28 19:18:51 |  |  | 2025-12-29 | Apichart Kampuang | Approved | Closed | 2026-01-07 16:05:42 | Yes | Yes | 2025-12-29 17:31:40 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 18:11:42 |  |  | 2025-12-24 | Teloneer Company Limited | Approved | Closed | 2026-03-12 10:15:38 | Yes | Yes | 2025-12-29 14:40:26 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-26 | Supatong Juntorn WX1461874 | N/A | Closed | 2025-12-26 16:33:33 | No | No |  | 26-Dec-2025 Replace BBU5900 UMPTg2 Add split GPS Add g3a g2 d5=3 Add RRU5818 *1sector DC Replace Ant smallcell 12port No Ret use sfp bidi |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KJP9M_2025 Capacity Expansion Ph7_EXP_BKK | SOI KANJANAPISAK 9/1 | [5 empty] | 2026-01-29 | 2026-01-29 | Akhom Srinara | N/A | Closed | 2026-01-29 00:27:55 | No | No |  |  |  | 2026-01-13 | 2026-01-13 | 2026-01-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-01-23 18:07:36 | Yes | Yes | 2026-07-27 10:13:36 | SQC Close | 2026-01-29 | 2026-01-29 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-02-05 16:24:47 | Yes | Yes | 2026-02-04 19:03:43 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:36:27 |  | 2026-06-20 | 2026-06-20 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-22 20:47:07 | Yes | Yes | 2026-06-20 23:34:28 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-13 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-13 17:56:34 | No | No |  | 13 Jan 2026 Add AAU5636w sector 2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KKIUM_2025 Capacity Expansion Ph4_EXP_ER | khlong kiu Moo 4 | 2025-09-12 |  | Install & Integrate |  | 2025-09-30 | 2025-09-12 | 2025-09-12 | Teloneer Company Limited | N/A | Closed | 2025-09-12 15:52:15 | No | No |  |  |  | 2025-09-30 | 2025-09-12 | 2025-09-16 | Teloneer Company Limited | N/A | Closed | 2025-09-29 15:32:48 | Yes | Yes | 2025-10-05 20:21:49 |  | 2025-09-30 | 2025-10-05 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-10 10:16:30 | Yes | Yes | 2025-11-07 13:38:48 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 15:47:20 |  | 2025-09-30 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2026-03-02 15:29:20 | Yes | Yes | 2025-10-08 09:37:41 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-12 |  | 2025-09-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-13 16:14:21 | No | No |  | "** waiting on service NR7 -- Replace UBBPg1 to UBBPg2 + Replace UBBPg1 to UBBPg3 #， Add RRU5505 x 1 + 4T4R S1#，2 #， Replace RRU5508 to (RRU5516_900) + Co NR07 + 4T4R S1#，2 #，Co NR07 S3" |  | 2025-09-15 | Reungsak Junkong 00927496 | N/A | Closed | 2025-09-15 16:46:25 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KL05M_2025 Capacity Expansion Ph5_EXP_BKK | KHLONG LHUANG SOI 5 |  |  |  | 2025-11-13 |  | 2025-11-16 | 2025-11-16 | Akhom Srinara | N/A | Closed | 2025-11-26 16:34:53 | No | No |  |  |  | 2025-11-14 | 2025-11-13 | 2025-11-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-14 10:12:48 | Yes | Yes | 2025-11-18 15:20:39 |  | 2025-11-19 | 2025-11-18 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-11 09:22:40 | Yes | Yes | 2025-11-23 11:15:49 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 18:15:23 |  | 2025-11-21 | 2025-11-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:24:43 | Yes | Yes | 2025-11-21 14:36:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-12 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-11-12 17:04:10 | No | No |  | 2025-11-12_Replace RRU5507 to RRU5526(18-21) Sector 1#， No act Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KL07M_2025 Capacity Expansion Ph5_EXP_BKK | KHLONG LHUANG SOI 7 |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-12-28 | 2025-12-08 | 2025-12-10 | V Contribute Co., Ltd | N/A | Closed | 2025-12-10 15:23:49 | Yes | Yes | 2025-12-10 15:23:50 |  | 2025-11-25 | 2025-11-25 | Chonradee Suwapan | Approved | Closed | 2025-12-04 09:36:04 | Yes | Yes | 2025-11-25 18:11:50 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2025-12-09 11:29:56 |  | 2025-11-25 | 2025-11-25 | Chonradee Suwapan | Approved | Closed | 2025-12-04 09:45:12 | Yes | Yes | 2025-11-25 19:08:01 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-18 17:50:30 | No | No |  | 18-11-2025. Replace RRU5526#， Ant.8 port Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-11-18 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KL6RM_2025 Coverage Expansion Ph2_EXP_BKK | KLONG6 ROAD | 2025-08-06 |  | Install & Integrate | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-08-07 08:29:49 | No | No |  |  | 2025-08-31 | 2025-08-31 | 2025-08-06 | 2025-08-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-08-06 15:54:19 | Yes | Yes | 2025-08-07 08:56:25 |  | 2025-08-10 | 2025-09-01 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-09-03 14:48:30 | Yes | Yes | 2025-11-27 09:50:42 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:27:07 |  | 2025-08-20 | 2025-08-20 | Sattaya Parakij | Approved | Closed | 2025-09-03 22:43:51 | No | Yes | 2025-08-20 23:46:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-06 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-06 18:52:51 | No | No |  | 2025-08-06_Add RRU3953#， Ant 4 port Sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-05 |  | N/A | Not assigned |  | No | No
KL85M_2025 Capacity Expansion Ph2_EXP_BKK | SOI KHLONGLUANG 8.5 | 2025-08-14 |  |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-14 18:26:57 | No | No |  |  |  | 2025-08-29 | 2025-08-15 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 13:41:46 | Yes | Yes | 2025-08-15 13:42:16 |  |  | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-09 16:45:53 | Yes | Yes | 2025-11-27 10:02:39 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:17:59 |  | 2025-09-04 | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-04 20:11:58 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-14 18:51:52 | No | No |  | 14-08-2025. Replace RRU5516 L18#， Ant.12 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-13 |  | N/A | Not assigned |  | No | No
KL85M_2025 Capacity Expansion Ph8_EXP_BKK | SOI KHLONGLUANG 8.5 |  |  |  |  | 2026-02-18 | 2026-02-18 | 2026-02-18 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-28 | 2026-02-17 | 2026-02-18 | V Contribute Co., Ltd | N/A | Closed | 2026-02-18 09:51:12 | Yes | Yes | 2026-02-18 09:51:13 |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-03-09 09:23:58 | Yes | Yes | 2026-03-11 16:58:43 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-08 | 2026-03-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:38:01 |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:16:39 | Yes | Yes | 2026-03-05 21:05:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-12 17:47:45 | No | No |  | 12-Feb-26 Add AAU5636w S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KL85M_2025 Coverage Expansion Ph2_EXP_BKK | SOI KHLONGLUANG 8.5 | 2025-08-14 |  |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-14 18:26:57 | No | No |  |  |  | 2025-08-29 | 2025-08-15 | 2025-08-20 | V Contribute Co., Ltd | N/A | Closed | 2025-08-20 19:34:42 | Yes | Yes | 2025-08-20 19:36:04 |  |  | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-04 09:25:37 | Yes | Yes | 2025-09-01 00:09:41 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:19:13 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 02:00:40 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-14 18:51:52 | No | No |  | 14-08-2025. Add RRU3953 Sec.1#， 2#， Ant.4 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-13 |  | N/A | Not assigned |  | No | No
KLKXM_2025 Capacity Expansion Ph7_EXP_BKK | Klong Lal Khon |  |  |  | 2026-01-10 | 2026-01-10 | 2026-01-20 | 2026-01-20 | Mahadee Japakiya(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-01-20 17:28:39 | No | No |  |  | 2026-01-12 | 2026-01-12 | 2026-01-17 | 2026-01-17 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-17 16:47:31 | Yes | Yes | 2026-01-21 10:35:28 |  | 2026-01-22 | 2026-01-22 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-18 17:05:56 | Yes | Yes | 2026-02-25 12:58:17 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:39:17 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 21:45:48 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-10 17:40:52 | No | No |  | 10-01-2026. Add UBBPg3a#， AIRU5636w Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KLWSM_2025 Capacity Expansion Ph3_EXP_BKK | SOI KHLONGKWANGBON SCHOOL | 2025-08-29 |  |  |  | 2025-08-30 | 2025-08-30 | 2025-08-30 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-30 09:04:17 | No | No |  |  |  | 2025-09-05 | 2025-09-01 | 2025-09-01 | V Contribute Co., Ltd | N/A | Closed | 2025-09-01 19:07:16 | Yes | Yes | 2025-09-01 19:08:30 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-10-03 12:01:59 | Yes | Yes | 2025-11-27 11:34:53 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:55 | Yes | Yes | 2025-10-06 17:07:26 |  | 2025-09-11 | 2025-09-11 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-11 21:28:56 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-29 18:39:45 | No | No |  | 29-08-2025. Replace RRU5516 L18#， Ant.8 port Sec.2#， 7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-28 |  | N/A | Not assigned |  | No | No
KMTAM_2025 Small DC Inb Cov Ex_Ph1 | Ban Klong Mai Tha Sa An |  |  |  | N/A | 2026-02-28 | N/A | 2026-01-05 | Teloneer Company Limited | N/A | Closed | 2026-01-05 15:47:35 | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNBPM_2025 Capacity Expansion Ph8_EXP_ER | KhueanThotNam Bangpakong | 2026-02-05 |  |  |  | 2026-02-28 | 2026-01-26 | 2026-01-26 | Teloneer Company Limited | N/A | Closed | 2026-01-26 14:29:06 | No | No |  |  |  | 2026-02-28 | 2026-01-28 | 2026-01-29 | Teloneer Company Limited | N/A | Closed | 2026-01-29 13:36:29 | Yes | Yes | 2026-01-29 21:35:10 | SQC Close | 2026-02-28 | 2026-02-04 | Apichat fangsantthia(Teloneer Company Limited) | Approved | Closed | 2026-02-13 10:42:51 | Yes | Yes | 2026-02-04 21:42:46 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:28 | Yes | Yes | 2026-03-24 12:08:40 |  | 2026-01-31 | 2026-01-29 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-01-29 10:48:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-05 16:59:22 | No | No |  | 20260205 Clear Alarm RET // Add UBBPg2 + Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KNBPM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KNBPM_H_3 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KNBPM_H_4 New L26F5 + NR26 (New AAU5636w)_KNBPM_N_1 |  | 2026-01-28 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-28 18:46:48 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNOEM_2025 Capacity Expansion Ph4_EXP_SR | Khanom Electricity |  |  |  | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-15 | Teloneer Company Limited | N/A | Closed | 2025-11-10 09:17:00 | No | No |  |  |  | 2025-09-26 | 2025-10-04 | 2025-10-15 | Teloneer Company Limited | N/A | Closed | 2025-10-15 16:07:41 | Yes | Yes | 2025-10-15 16:09:51 |  | 2025-10-10 | 2025-10-10 | Nattawoot Suwan | Approved | Closed | 2025-10-14 09:15:57 | Yes | Yes | 2025-10-28 10:25:12 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 18:21:30 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-10-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-04 | 2025-10-04 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-10-04 18:20:24 | No | No |  | add AAU5636w sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-02 |  | N/A | Not assigned |  | No | No
KOKEW_2025 Capacity Expansion Ph2_EXP_SR | Khao Kaew |  |  |  |  | 2025-09-15 | 2025-08-28 | 2025-08-28 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-22 11:40:33 | No | No |  |  |  | 2025-08-30 | 2025-08-28 | 2025-08-28 | Teloneer Company Limited | N/A | Closed | 2025-08-28 15:54:06 | Yes | Yes | 2025-11-06 09:49:14 |  | 2025-09-06 | 2025-09-18 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2025-09-26 11:47:36 | Yes | Yes | 2025-09-06 11:26:30 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:55 | Yes | Yes | 2025-10-06 17:14:58 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-08-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-28 | 2025-09-15 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-09-15 12:35:52 | No | No |  | Remove Cell NR700 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-12 |  | N/A | Not assigned |  | No | No
KOKEW_2025 Capacity Expansion Ph5_EXP_SR | Khao Kaew |  |  |  |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | Teloneer Company Limited | N/A | Closed | 2025-11-04 15:04:39 | No | No |  |  |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | Teloneer Company Limited | N/A | Closed | 2025-11-04 17:30:53 | Yes | Yes | 2025-11-18 10:12:19 |  | 2025-11-08 | 2025-11-08 | Teloneer Company Limited | Approved | Closed | 2025-12-11 10:27:05 | Yes | Yes | 2025-11-18 11:11:06 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 18:35:50 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-04 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-11-04 17:09:14 | No | No |  | 4 Nov 2025 Add AAU5636w sector3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-03 |  | N/A | Not assigned |  | No | No
KOMLM_2025 Capacity Expansion Ph5_EXP_ER | Ban KohMaiLaem | 2025-10-10 | thcp_phet.s | Clear Pending |  | 2025-10-31 | 2025-10-10 | 2025-10-10 | Teloneer Company Limited | N/A | Closed | 2025-10-10 15:24:49 | No | No |  |  |  | 2025-10-31 | 2025-10-11 | 2025-10-14 | Teloneer Company Limited | N/A | Closed | 2025-10-14 09:53:12 | Yes | Yes | 2025-10-14 12:07:10 |  | 2025-10-31 | 2025-10-20 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-28 10:26:39 | Yes | Yes | 2025-10-21 10:04:56 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-11-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 16:00:17 |  | 2025-10-15 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-10 14:39:00 | Yes | Yes | 2025-10-08 15:42:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-10 |  | 2025-10-09 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-09 18:15:15 | No | No |  | **waiting on-service LNR26 -- Add RRU5505 x 1 + 4T4R S2 #，Add RRU5508 x 1 + 4T4R S3#，1 #，New L26F5 + NR26 (New AAU5636w) S2 |  | 2025-10-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-10 15:53:57 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KPEAM_2025 Capacity Expansion Ph2_EXP_ER | Klaeng Provincial Electricity Authority | 2025-07-18 |  | Install & Integrate |  | 2025-07-31 | 2025-07-17 | 2025-07-19 | Teloneer Company Limited | N/A | Closed | 2025-07-19 09:30:50 | No | No |  |  |  | 2025-07-31 | 2025-07-17 | 2025-07-23 | Teloneer Company Limited | N/A | Closed | 2025-07-23 18:26:22 | Yes | Yes | 2025-07-27 13:13:42 |  | 2025-07-31 | 2025-09-24 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-26 13:58:41 | Yes | Yes | 2025-09-24 15:57:17 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:29:16 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:25:02 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-19 |  | 2025-07-10 | Reungsak Junkong 00927496 | N/A | Closed | 2025-07-17 18:28:21 | No | No |  | **waiting on-service LNR26 Sec.2 -- Replace Antenna (HB) + Add RRU5505 x 1 + 4T4R Sec.2#，3 & New L26F4F5 + NR26 (New AAU5636w) Sec.2 |  | 2025-07-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-18 20:30:49 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KPKUM_2025 Coverage Expansion Ph2_EXP_BKK | KHLONG PAD-KHLONG KU PHARA |  |  |  |  | 2025-08-06 | 2025-08-06 | 2025-08-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-06 17:03:49 | No | No |  |  |  | 2025-08-22 | 2025-08-15 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 09:53:02 | Yes | Yes | 2025-08-15 09:55:50 |  | 2025-08-22 | 2025-08-22 | Chonradee Suwapan | Approved | Closed | 2026-03-10 16:23:29 | Yes | Yes | 2025-08-22 07:52:15 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-03-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:39:54 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:52:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-06 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-06 18:52:51 | No | No |  | 2025-08-06_Add RRU3953 Sector 2#， Add RRU3953#， Replace to Ant 4 port Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
KPWTM_2025 Capacity Expansion Ph8_EXP_ER | Klong Prawet | 2026-02-04 |  |  |  | 2026-02-28 | 2026-01-26 | 2026-01-26 | Teloneer Company Limited | N/A | Closed | 2026-01-26 16:15:46 | No | No |  |  |  | 2026-02-28 | 2026-01-28 | 2026-02-04 | Teloneer Company Limited | N/A | Closed | 2026-02-04 15:34:13 | Yes | Yes | 2026-02-06 22:14:58 | SQC Close | 2026-02-28 | 2026-02-07 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-02-13 10:42:51 | Yes | Yes | 2026-02-11 10:50:30 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:28 | Yes | Yes | 2026-03-24 12:10:32 |  | 2026-01-31 | 2026-01-28 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-01-28 14:18:42 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-04 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-04 17:10:33 | No | No |  | Clear alarm RET sector 2 L18/21 /// Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KPWTM_H_2 |  | 2026-01-26 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-10 10:55:20 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRCGM_2025 Capacity Expansion Ph2_EXP_SR | KHAO RUP CHANG (SONGKHLA 3) |  |  |  | 2025-09-23 |  | 2025-09-23 | 2025-09-23 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-26 09:55:35 | No | No |  |  |  | 2025-08-23 | 2025-08-23 | 2025-09-23 | Teloneer Company Limited | N/A | Closed | 2025-09-23 16:06:08 | Yes | Yes | 2025-09-25 13:38:03 |  | 2025-09-26 | 2025-09-26 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2025-10-08 07:27:47 | Yes | Yes | 2025-10-04 09:30:42 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 17:11:53 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-09-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-23 | 2025-09-23 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-09-23 12:01:21 | No | No |  | remove d6 /add g3 (plan g3a) slot 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-21 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
KRGIB_2025 Capacity Expansion NW Modernization_EXP_BKK | King Royal Gardan Inn |  |  |  |  | 2026-02-06 | 2026-02-24 | 2026-02-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-08 23:00:59 | No | No |  |  |  | 2026-02-07 | 2026-02-18 | 2026-02-25 | V Contribute Co., Ltd | N/A | Closed | 2026-02-25 11:50:50 | Yes | Yes | 2026-02-25 11:50:50 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-03-09 09:30:25 | Yes | Yes | 2026-03-09 17:56:11 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:41:09 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-05 22:27:27 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-22 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-22 18:54:30 | No | No |  | 2026-01-22_Replace RRU3962 to RRU5526 Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRGIM_2025 Capacity Expansion NW Modernization_EXP_BKK | KING ROYAL GARDAN INN |  |  |  |  | 2026-01-19 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-17 22:10:55 | No | No |  |  |  | 2026-01-31 | 2026-02-09 | 2026-02-13 | V Contribute Co., Ltd | N/A | Closed | 2026-02-13 17:43:43 | Yes | Yes | 2026-02-13 17:43:44 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-05-11 09:29:24 | Yes | Yes | 2026-02-26 11:36:30 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-03 | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-04 19:18:15 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-16 21:32:24 | No | No |  | 16-Jan-2026 Add Add g3a Add RRU5516 (700900) S1 S2 S3 Remove RRU3953 S1 S2 S3 Remove RRU5508 S2 Add RRU5526 S2 Remove RRU3962 Add AAU5768 S3 Remove RRU5516 (1800-2100) *2 S3 S8 Replace Ant to 4x4L/4x4H Single Beam Multi Port S2 Replace Ant 12port No RET S3 (700900) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRNYM_2025 Coverage Expansion Ph2_EXP_BKK | KHLONG RAT NIYOM | 2025-07-31 |  |  |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-07-31 17:04:06 | No | No |  |  |  | 2025-08-22 | 2025-08-11 | 2025-08-11 | V Contribute Co., Ltd | N/A | Closed | 2025-08-11 13:00:25 | Yes | Yes | 2025-08-11 13:01:47 |  | 2025-08-11 | 2025-08-11 | Chonradee Suwapan | Approved | Closed | 2025-08-18 17:06:03 | Yes | Yes | 2025-08-11 18:04:31 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-22 | 2025-08-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:40:37 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:53:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-07-31 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-07-31 16:38:49 | No | No |  | 31-Jul-2025 Add RRU3953 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-30 |  | N/A | Not assigned |  | No | No
KRSPM_2025 Coverage Expansion Ph2_EXP_BKK | KET ARSA PATTANA ROAD | 2025-07-31 |  |  |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-07-31 17:04:06 | No | No |  |  |  | 2025-08-22 | 2025-08-02 | 2025-08-03 | V Contribute Co., Ltd | N/A | Closed | 2025-08-03 16:17:12 | Yes | Yes | 2025-08-03 16:17:42 |  | 2025-08-12 | 2025-08-12 | Chonradee Suwapan | Approved | Closed | 2025-08-18 17:06:03 | Yes | Yes | 2025-08-12 21:02:25 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-22 | 2025-08-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:41:56 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:53:25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-07-31 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-07-31 16:39:34 | No | No |  | 31-Jul-2025 Add RRU3953 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-30 |  | N/A | Not assigned |  | No | No
KS13M_2025 Capacity Expansion Ph6_EXP_BKK | MUBAN SUAN KASET SOI 13 |  |  |  |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-22 09:18:28 | No | No |  |  |  | 2025-12-31 | 2025-12-22 | 2025-12-22 | V Contribute Co., Ltd | N/A | Closed | 2025-12-22 19:45:56 | Yes | Yes | 2025-12-22 19:45:57 |  | 2026-01-07 | 2026-01-07 | Chonradee Suwapan | Approved | Closed | 2026-01-09 17:03:57 | Yes | Yes | 2026-01-08 17:41:35 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 11:42:40 |  | 2026-01-07 | 2026-01-07 | Chonradee Suwapan | Approved | Closed | 2026-01-15 21:02:00 | Yes | Yes | 2026-01-07 22:35:54 |  |  | 2025-12-31 | 2025-12-20 | V Contribute Co., Ltd | N/A | Closed | 2025-12-20 15:52:10 | No | No |  |  |  |  | 2025-12-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-20 18:44:14 | No | No |  | 20-12-2025. Add UBBPg2 AIRU5636w Sec.3#， AIRU5636m Sec.2#， Remove UBBPd5 x2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS13M_2025 Coverage Expansion Ph2_EXP_BKK | MUBAN SUAN KASET SOI 13 |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-17 | 2025-10-30 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 21:22:25 | Yes | Yes | 2025-10-30 21:22:26 |  | 2025-10-28 | 2025-10-28 | Chonradee Suwapan | Approved | Closed | 2025-10-30 16:53:04 | Yes | Yes | 2025-10-28 18:04:51 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 16:10:24 |  | 2025-10-28 | 2025-10-28 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-28 19:31:06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-14 16:08:06 | No | No |  | 14-Oct-2025 Add RRU3953 S3 Replace Ant 8 port 1/2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
KS42B_2025 Capacity Expansion Ph5_EXP_BKK | KEHASAMUT PRAKAN4(BANGPOO) BUILDING 2 8 |  |  |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-15 18:16:03 | No | No |  |  |  | 2025-12-28 | 2025-12-18 | 2025-12-21 | V Contribute Co., Ltd | N/A | Closed | 2025-12-21 17:36:18 | Yes | Yes | 2025-12-21 17:36:18 |  | 2025-12-16 | 2025-12-16 | Chonradee Suwapan | Approved | Closed | 2025-12-19 17:39:21 | Yes | Yes | 2026-01-15 15:02:44 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-15 11:43:53 |  | 2025-12-16 | 2025-12-16 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-16 21:23:14 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-12 18:10:31 | No | No |  | 12-Dec-2025 Add RRU5818 sector B Add g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KS42B_DPU40_OPM30_Replacement_BKK | KEHASAMUT PRAKAN4(BANGPOO) BUILDING 2 8 |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-25 | 2025-12-27 | V Contribute Co., Ltd | N/A | Closed | 2025-12-27 19:46:07 | Yes | Yes | 2025-12-27 19:46:07 |  | 2026-01-14 | 2026-01-14 | Chonradee Suwapan | Approved | Closed | 2026-01-26 16:02:01 | Yes | Yes | 2026-01-17 17:47:30 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-23 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-01-13 | 2026-01-13 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-13 21:10:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-25 17:23:47 | No | No |  | 25-Dec-2025 Replace DPU40 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
KSBBM_2025 Coverage Expansion Ph2_EXP_BKK | KARNCHANAPHISEK (BANGNA-BANGPRAIN) |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-13 | 2025-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-13 12:15:48 | Yes | Yes | 2025-08-16 01:08:31 |  | 2025-08-16 | 2025-08-16 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-22 13:14:50 | Yes | Yes | 2025-08-16 02:19:30 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:44:34 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 19:51:20 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-13 19:11:21 | No | No |  | 13-Aug-2025 Add RRU3953 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
KSOGC_2025 Capacity Expansion Ph7_EXP_SR | Khonsong Community |  |  |  | 2025-12-27 | 2025-12-27 | 2025-12-25 | 2025-12-25 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-12-25 14:56:41 | No | No |  |  |  | 2025-12-28 | 2025-12-25 | 2025-12-26 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-12-26 15:06:45 | Yes | Yes | 2026-01-09 11:32:50 |  | 2026-01-13 | 2026-01-13 | Rosak soko | Approved | Closed | 2026-01-27 11:46:59 | Yes | Yes | 2026-01-13 12:23:54 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:00 | Yes | Yes | 2026-03-19 18:20:15 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-26 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-25 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-12-25 18:53:53 | No | No |  | Add AAU5636w Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSSRM_2025 Capacity Expansion NW Modernization_EXP_BKK | KASEM SAMRAN SOI 8 | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  |  | 2026-02-11 | 2026-02-16 | 2026-02-20 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-20 15:48:29 | Yes | Yes | 2026-02-20 15:49:26 |  |  | 2026-02-20 | OATTAPAN AUTTAHON | Approved | Closed | 2026-03-17 17:20:16 | Yes | Yes | 2026-03-12 17:53:04 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:41:47 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-13 18:27:25 | No | No |  | 13-02-2026. Replace Ant.8 port Sec.1//12-Feb-26 Replace RRU3962 To RRU5526 S1 S2 //Pending Clear alarm RET S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTFPM_2025 Capacity Expansion Ph5_EXP_ER | Krungthai Farm Company , Nong Phai Kaew | 2025-11-18 | THCP_PHET.S | Install & Integrate |  | 2025-10-31 | 2025-10-16 | 2025-10-16 | Teloneer Company Limited | N/A | Closed | 2025-10-16 15:21:00 | No | No |  |  |  | 2025-10-31 | 2025-10-16 | 2025-10-20 | Teloneer Company Limited | N/A | Closed | 2025-10-20 11:47:40 | Yes | Yes | 2025-11-04 12:33:12 |  | 2025-10-31 | 2025-10-25 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-28 10:26:39 | Yes | Yes | 2025-11-07 13:39:16 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-11-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:26 | Yes | Yes | 2025-11-06 16:15:29 |  | 2025-10-15 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-10 14:39:00 | Yes | Yes | 2025-10-09 15:46:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-16 |  | 2025-10-18 | Reungsak Junkong 00927496 | N/A | Closed | 2025-10-18 11:02:47 | No | No |  | Add UBBPg3a #，MIMO 18/21 2RRU5505 REP.ANT S1(NOT FINISH) #，New L26F5 + NR26 (New AAU5636w) S1#，2#，3 (FINISH) |  | 2025-10-17 | Reungsak Junkong 00927496 | N/A | Closed | 2025-10-18 11:02:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTFPM_2025 Capacity Expansion Ph6_EXP_ER | Krungthai Farm Company , Nong Phai Kaew | 2025-11-20 | thcp_adirek.k | Install & Integrate |  | 2025-11-30 | 2025-11-20 | 2025-11-20 | Teloneer Company Limited | N/A | Closed | 2025-11-20 16:34:24 | No | No |  |  |  | 2025-11-30 | 2025-11-20 | 2025-11-24 | Teloneer Company Limited | N/A | Closed | 2025-11-24 13:19:03 | Yes | Yes | 2025-11-26 17:59:52 |  | 2025-11-30 | 2025-11-30 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-02 14:49:44 | Yes | Yes | 2025-11-30 19:50:43 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:32 | Yes | Yes | 2026-01-09 18:31:18 |  | 2025-11-30 | 2025-11-20 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-21 16:47:33 | Yes | Yes | 2025-11-20 09:32:21 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-20 17:16:43 | No | No |  | **waiting on-service LNR7/L9 -- Add UBBPg3a H_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB) L_1#，2#，3 |  | 2025-11-21 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-21 16:48:25 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTHNM_2025 Capacity Expansion Ph7_EXP_ER | Ban KhaoKraThin | 2025-12-12 |  | Install & Integrate |  | 2025-12-31 | 2025-12-12 | 2025-12-12 | Teloneer Company Limited | N/A | Closed | 2025-12-12 16:50:36 | No | No |  |  |  | 2025-12-31 | 2025-12-13 | 2025-12-13 | Teloneer Company Limited | N/A | Closed | 2025-12-13 11:03:25 | Yes | Yes | 2025-12-15 16:07:24 |  | 2025-12-31 | 2025-12-15 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:28:08 | Yes | Yes | 2025-12-15 21:29:20 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 12:13:06 |  | 2025-12-31 | 2025-12-13 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-13 21:12:48 | Yes | Yes | 2025-12-13 08:15:42 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-12 | Reungsak Junkong 00927496 | N/A | Closed | 2025-12-12 17:32:55 | No | No |  | Add UBBPg2 Replace Antenna (Dualband) + Add RRU5505 x 1 + 4T4R_KTHNM_H_3 Replace Antenna (Co Antenna)_KTHNM_N_3 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_KTHNM_L_3 |  | 2025-12-15 | Reungsak Junkong 00927496 | N/A | Closed | 2025-12-15 18:25:08 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTINM_2025 Capacity Expansion Ph2_EXP_ER | Khao Ta-in | 2025-07-22 |  | Take Photo & Clear Pending |  | 2025-08-31 | 2025-07-22 | 2025-07-23 | Teloneer Company Limited | N/A | Closed | 2025-07-23 17:56:50 | No | No |  |  |  | 2025-07-31 | 2025-07-17 | 2025-07-23 | Teloneer Company Limited | N/A | Closed | 2025-07-23 20:31:47 | Yes | Yes | 2025-07-30 23:30:24 |  | 2025-07-31 | 2025-09-24 | Thanakit Chaleechai | Approved | Closed | 2025-09-26 13:58:41 | Yes | Yes | 2025-09-24 16:11:40 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:33:05 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:25:46 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-23 |  | 2025-07-18 | Reungsak Junkong 00927496 | N/A | Closed | 2025-07-18 20:07:23 | No | No |  | on-service LNR26 Sec.2 -- ReSectorname (LB) S2 to S6 #， S3 to S2 #， S4 to S3 & New L26F4F5 + NR26 (New AAU5636w) Sec.2 |  | 2025-07-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-18 20:15:34 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTKIM_2025 Coverage Expansion Ph2_EXP_BKK | KLONG TA KHLAI |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-11 | 2025-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-12 15:25:58 | Yes | Yes | 2025-08-16 01:05:25 |  | 2025-08-17 | 2025-08-17 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:35:50 | Yes | Yes | 2025-08-17 05:15:31 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:47:11 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 18:40:48 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-11 18:15:26 | No | No |  | 2025-08-11_Add RRU3953#， Replace to Ant 4 port Sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
KTL2M_2025 Coverage Expansion Ph2_EXP_BKK | KHUM THONG-LAM TOITING RD. STATION2 | [5 empty] | 2025-08-21 | 2025-08-21 | Teloneer Company Limited | N/A | Closed | 2025-08-22 23:49:24 | No | No |  |  | 2025-08-20 | 2025-08-22 | 2025-08-26 | 2025-08-26 | Teloneer Company Limited | N/A | Closed | 2025-08-26 18:23:31 | Yes | Yes | 2025-08-28 14:29:50 |  |  | 2025-08-29 | Apichart Kampuang | Approved | Closed | 2025-09-02 17:20:53 | Yes | Yes | 2025-10-17 17:26:54 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:50:27 |  |  | 2025-08-12 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:08 | No | Yes | 2025-08-12 14:03:12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-20 17:12:06 | No | No |  | 20-Aug-2025 Add RRU3953 S1 S3 Replace Ant.4port S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-20 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 06:02:16 | No | No
KTLTM_2025 Coverage Expansion Ph2_EXP_BKK | KHUM THONG-LAM TOITING RD. |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-08 | 2025-08-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-08 22:34:14 | Yes | Yes | 2025-08-15 13:04:07 |  | 2025-08-17 | 2025-08-17 | Kontira Kowapradit | Approved | Closed | 2025-08-22 13:14:50 | Yes | Yes | 2025-08-17 16:14:20 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:48:29 |  | 2025-09-03 | 2025-09-03 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 18:12:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-08 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-08 19:12:47 | No | No |  | 8-Aug-2025 Add RRU3953 S3 Replace Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
KTN1M_2025 Capacity Expansion NW Modernization_EXP_BKK | KHLONGTON 1 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:54:42 | No | No |  |  |  | 2026-05-31 | 2026-05-06 | 2026-05-07 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-07 16:56:43 | Yes | Yes | 2026-05-08 14:03:06 |  | 2026-06-04 | 2026-06-04 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-03 09:43:26 | Yes | Yes | 2026-06-04 13:48:14 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-07-14 22:51:08 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-28 14:02:44 | No | No |  | 28-Mar-2026 Add g2 Add RRU5507*2 S1 Remove RRU3962 Add RRU5507*2 S2 Remove RRU3962 Add RRU5507*2 S3 Remove RRU3962 Add RRU5516 S1 S2 S3 Remove RRU3953*3 Replace Ant 8port S1 S2 S3 Co 1800900 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTNAM_2025 Coverage Expansion Ph2_EXP_BKK | KANTANA | [5 empty] | 2025-08-21 | 2025-08-21 | Teloneer Company Limited | N/A | Closed | 2025-08-22 23:49:24 | No | No |  |  | 2025-08-20 | 2025-08-22 | 2025-08-26 | 2025-08-26 | Teloneer Company Limited | N/A | Closed | 2025-08-26 17:26:40 | Yes | Yes | 2025-08-28 14:30:57 |  |  | 2025-09-02 | Apichart Kampuang | Approved | Closed | 2025-09-03 14:48:30 | Yes | Yes | 2025-09-02 14:53:16 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:51:46 |  |  | 2025-08-14 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-14 17:27:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-20 17:13:31 | No | No |  | 20-Aug-2025 Add RRU3953 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-20 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 06:02:16 | No | No
KV69M_2025 Capacity Expansion Ph3_EXP_BKK | KHWANTHIP VILLAGE PETCHKASEM 69 | 2025-09-01 |  |  |  | 2025-09-01 | 2025-09-01 | 2025-09-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-01 18:03:40 | No | No |  |  |  | 2025-09-06 | 2025-09-09 | 2025-09-10 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:15:01 | Yes | Yes | 2025-09-30 10:15:01 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-10-09 15:47:01 | Yes | Yes | 2025-09-13 20:03:19 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:25 | Yes | Yes | 2025-11-06 16:18:05 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-14 12:57:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-01 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-01 19:45:17 | No | No |  | 1-Sep-2025 ADD RRU5516 (18002100 ) S1 S2 S3 Remove RRU5507 *3 Replace Ant 4port S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-29 |  | N/A | Not assigned |  | No | No
KW12M_2025 Coverage Expansion Ph2_EXP_BKK | SOI KINGKAEW 12 |  |  |  | 2025-08-15 |  | 2025-08-18 | 2025-08-18 | Akhom Srinara | N/A | Closed | 2025-08-18 13:04:03 | No | No |  |  |  |  | 2025-08-15 | 2025-08-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-16 15:59:28 | Yes | Yes | 2025-08-21 12:59:53 |  | 2025-08-27 | 2025-09-03 | Kontira Kowapradit | Approved | Closed | 2025-09-15 17:01:13 | Yes | Yes | 2025-09-03 15:02:23 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:35:32 |  | 2025-09-04 | 2025-09-04 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 13:47:56 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-15 17:53:05 | No | No |  | 15-Aug-2025 Add RRU3953 S2 Replace Ant.4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-17 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 06:02:16 | No | No
KWAPM_2025 Capacity Expansion Ph2_EXP_BKK | KAIWAN APARTMENT | 2025-08-09 |  |  |  | 2025-08-09 | 2025-08-09 | 2025-08-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-09 16:06:17 | No | No |  |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | V Contribute Co., Ltd | N/A | Closed | 2025-08-20 19:22:14 | Yes | Yes | 2026-03-18 18:20:03 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-09-10 09:28:36 | Yes | Yes | 2025-09-03 21:07:21 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:36:47 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-03 20:51:46 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-09 16:44:15 | No | No |  | 9-Aug-2025 Add RRU5516 (1800-2100) Remove RRU3962 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-09 |  | N/A | Not assigned |  | No | No
KWAPM_2025 Coverage Expansion Ph2_EXP_BKK | KAIWAN APARTMENT | 2025-08-09 |  |  |  | 2025-08-09 | 2025-08-09 | 2025-08-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-09 16:06:17 | No | No |  |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | V Contribute Co., Ltd | N/A | Closed | 2025-08-20 19:45:42 | Yes | Yes | 2025-08-20 19:47:08 |  |  | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-09 09:04:09 | Yes | Yes | 2025-09-01 00:10:51 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:38:03 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 02:06:03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-09 16:51:24 | No | No |  | 9-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-08 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-09-16 16:57:05 | No | No
L133M_2025 Coverage Expansion Ph2_EXP_BKK | LEAB KHLONG 13 STATION 3 |  |  |  |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-07 17:44:53 | No | No |  |  |  | 2025-08-29 | 2025-08-16 | 2025-08-24 | V Contribute Co., Ltd | N/A | Closed | 2025-08-24 16:21:04 | Yes | Yes | 2025-08-24 16:22:05 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-08-28 16:37:42 | Yes | Yes | 2025-08-27 14:18:37 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:53:03 |  | 2025-08-13 | 2025-08-13 | Annop Auyto | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-13 13:12:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-07 17:52:12 | No | No |  | 07-08-2025. Add RRU3953 Sec.1#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-06 |  | N/A | Not assigned |  | No | No
L13EM_2025 Coverage Expansion Ph2_EXP_BKK | LEAB LAMLUKKAKHLONG 13 (EAST) |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-13 | 2025-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-13 21:02:15 | Yes | Yes | 2025-08-21 12:59:21 |  | 2025-08-25 | 2025-08-25 | Kontira Kowapradit | Approved | Closed | 2025-08-27 22:17:55 | Yes | Yes | 2025-08-25 15:25:34 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-08-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:55:46 |  | 2025-09-04 | 2025-09-04 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-04 10:05:15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-13 18:41:35 | No | No |  | 2025-08-13_Add RRU3953#， No act Ant Sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
LATWM_2025 Capacity Expansion Ph2_EXP_BKK | LATWAI ROAD |  |  |  | 2025-08-18 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-18 | 2025-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-18 14:21:21 | Yes | Yes | 2025-08-27 13:34:26 |  | 2025-08-27 | 2025-08-27 | Muhamadnase Chesamae | Approved | Closed | 2025-09-15 17:01:13 | Yes | Yes | 2025-09-02 18:22:57 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:41:46 |  | 2025-09-04 | 2025-09-04 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 15:04:06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-18 18:24:34 | No | No |  | 18-Aug-2025 Add RRU5516 (1800-2100) S2 Remove RRU5507 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
LB50M_2025 Capacity Expansion Ph2_EXP_BKK | SOI LATKABANG 50 |  |  |  | 2025-09-24 | 2025-10-01 | 2025-10-12 | 2025-10-14 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-20 10:22:44 | No | No |  |  |  | 2025-10-31 | 2025-10-06 | 2025-10-10 | Teloneer Company Limited | N/A | Closed | 2025-10-10 12:25:30 | Yes | Yes | 2025-10-14 09:41:34 |  |  | 2026-01-20 | Apichart Kampuang | Approved | Closed | 2026-06-24 09:33:40 | Yes | Yes | 2026-01-20 18:17:30 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 18:38:37 |  | 2025-08-31 | 2025-08-31 | Teloneer Company Limited | Approved | Closed | 2025-10-10 17:28:56 | No | Yes | 2025-08-31 16:52:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-25 19:06:15 | No | No |  | 2025-10-27_Add GPS//25-Sep-2025 Replace UMPTg2 Add g2 Add RRU5516 (700900) S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
LBP1B_2025 Coverage Expansion Ph1_EXP_BKK | Life At BTS Thapra (Corner) | [5 empty] | 2025-09-30 | 2025-09-30 | Akhom Srinara | N/A | Closed | 2025-09-30 14:03:02 | No | No |  |  |  |  | 2025-09-15 | 2025-09-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-19 15:47:56 | Yes | Yes | 2025-09-21 15:02:09 |  | 2025-09-26 | 2025-09-26 | Kontira Kowapradit | Approved | Closed | 2025-10-20 15:40:02 | Yes | Yes | 2025-10-07 11:30:39 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 17:18:05 |  | 2025-09-25 | 2025-09-25 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-25 13:19:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-15 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-15 17:35:06 | No | No |  | 15-09-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-29 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
LBP2B_2025 Coverage Expansion Ph1_EXP_BKK | Life At BTS Thapra (Back) | [5 empty] | 2025-09-30 | 2025-09-30 | Akhom Srinara | N/A | Closed | 2025-09-30 14:03:02 | No | No |  |  |  |  | 2025-09-15 | 2025-09-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-21 09:47:00 | Yes | Yes | 2025-09-25 13:30:36 |  | 2025-09-25 | 2025-09-25 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-20 15:40:02 | Yes | Yes | 2025-09-25 16:49:13 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 17:19:22 |  | 2025-09-23 | 2025-09-23 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-23 15:42:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-15 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-15 17:35:06 | No | No |  | 15-09-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-29 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
LBP3B_2025 Coverage Expansion Ph1_EXP_BKK | LIFE AT BTS THAPRA (SIDE) | [5 empty] | 2025-09-30 | 2025-09-30 | Akhom Srinara | N/A | Closed | 2025-09-30 14:03:02 | No | No |  |  |  |  | 2025-09-12 | 2025-09-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-15 19:16:49 | Yes | Yes | 2025-09-15 19:16:49 |  | 2025-09-25 | 2025-09-25 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-20 16:38:16 | Yes | Yes | 2025-09-25 15:06:55 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 17:20:35 |  | 2025-09-17 | 2025-09-17 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-23 15:35:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-12 18:07:29 | No | No |  | 12-09-2025. Replace Ant.12 port x2 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-29 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
LBRAB_2025 Coverage Expansion Ph1_EXP_BKK | LUMPINI CONDOTOWN BODINDECHA-RAMKHAMHAENG 43/1 (BUILDING A) | 2025-11-10 |  |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-10 17:58:32 | No | No |  |  |  | 2025-11-07 | 2025-11-10 | 2025-11-15 | V Contribute Co., Ltd | N/A | Closed | 2025-11-15 10:37:02 | Yes | Yes | 2025-11-15 10:37:02 |  | 2025-11-12 | 2025-11-12 | Chonradee Suwapan | Approved | Closed | 2025-11-26 09:23:51 | Yes | Yes | 2025-11-12 18:55:53 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 19:04:18 |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-11 19:32:50 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-31 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-31 16:37:20 | No | No |  | 31-Oct-2025 Replace to Ant Vertical Dual Beam Sector B#， subrack 82#， 83#， SC subrack 84 85 E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-07 |  | N/A | Not assigned |  | No | No
LBRBB_2025 Coverage Expansion Ph1_EXP_BKK | Lumpini Condotown Bodindecha-Ramkhamhaeng 43/1 (Building B) | 2025-11-10 |  |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-10 17:58:32 | No | No |  |  |  | 2025-11-07 | 2025-11-16 | 2025-12-01 | V Contribute Co., Ltd | N/A | Closed | 2025-12-01 09:56:15 | Yes | Yes | 2025-12-01 09:56:15 |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2025-12-01 16:23:29 | Yes | Yes | 2025-11-11 19:25:43 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:35:59 |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-11 19:33:18 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-31 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-31 17:06:16 | No | No |  | 31-10-2025. Replace Ant.12 port Condo x4 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-07 |  | N/A | Not assigned |  | No | No
LBRDB_2025 Capacity Expansion Ph2_EXP_BKK | LUMPINI CONDOTOWN BODINDECHA-RAMKHAMHAENG 43/1 (BUILDING C-D) |  |  |  |  | 2025-10-21 | 2025-10-21 | 2025-10-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-21 17:43:19 | No | No |  |  |  | 2025-10-17 | 2025-10-30 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 11:25:54 | Yes | Yes | 2025-10-30 11:25:55 |  | 2025-10-27 | 2025-10-27 | Chonradee Suwapan | Approved | Closed | 2025-11-03 20:57:07 | Yes | Yes | 2025-10-27 20:56:08 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:25 | Yes | Yes | 2025-11-06 16:19:21 |  | 2025-10-27 | 2025-10-27 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-10-27 21:10:04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-10 16:34:50 | No | No |  | 10-Oct-2025 Add AAU5246 SB 5/1 Change Solution SA >>SB 8-Oct-2025 ***Pending Add AAU5246 SB 5/1 ///Add g3a Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Complted |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
LET1B_2025 Coverage Expansion Ph1_EXP_BKK | Leticia Rama 9 (Right) |  |  |  |  | 2025-10-25 | 2025-10-25 | 2025-10-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-29 | V Contribute Co., Ltd | N/A | Closed | 2025-10-29 13:56:16 | Yes | Yes | 2025-10-29 13:56:16 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-06 08:51:11 | Yes | Yes | 2025-11-04 19:58:07 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 19:05:31 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-04 20:21:37 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-24 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-24 17:07:14 | No | No |  | 24-10-2025. Replace Ant.12 port Condo Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
LET3B_2025 Coverage Expansion Ph1_EXP_BKK | Leticia Rama 9 (Left) |  |  |  |  | 2025-10-25 | 2025-10-25 | 2025-10-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-29 | V Contribute Co., Ltd | N/A | Closed | 2025-10-29 20:09:25 | Yes | Yes | 2025-10-29 20:09:25 |  | 2025-11-03 | 2025-11-03 | Chonradee Suwapan | Approved | Closed | 2025-11-14 09:37:39 | Yes | Yes | 2026-01-06 11:12:39 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Krittee Chamboot 00319410 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 19:06:47 |  | 2025-11-03 | 2025-11-03 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-03 20:02:33 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-24 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-24 17:07:14 | No | No |  | 24-10-2025. Replace Ant.12 port Condo Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
LET4B_2025 Coverage Expansion Ph1_EXP_BKK | Leticia Rama 9 (Basement) |  |  |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-10 18:33:54 | No | No |  |  |  | 2025-10-17 | 2025-10-27 | 2025-10-27 | V Contribute Co., Ltd | N/A | Closed | 2025-10-27 17:48:39 | Yes | Yes | 2025-10-27 17:48:39 |  | 2025-10-10 | 2025-10-10 | Chonradee Suwapan | Approved | Closed | 2025-10-15 22:31:52 | Yes | Yes | 2026-01-06 16:59:32 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 17:21:49 |  | 2025-10-10 | 2025-10-10 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-10-10 19:37:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-03 18:08:20 | No | No |  | 3-Oct-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam SA E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-09 |  | N/A | Not assigned |  | No | No
LF18B_2025 Coverage Expansion Ph1_EXP_BKK | Life at Ladprao 18 | [5 empty] | 2025-09-22 | 2025-09-22 | Akhom Srinara | N/A | Closed | 2025-09-25 13:54:36 | No | No |  |  |  |  | 2025-09-12 | 2025-09-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-15 09:47:13 | Yes | Yes | 2025-09-15 09:47:14 |  | 2025-09-18 | 2025-09-24 | Kontira Kowapradit | Approved | Closed | 2025-10-16 16:35:33 | Yes | Yes | 2025-09-24 12:05:58 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:59 | Yes | Yes | 2025-10-21 17:23:01 |  | 2025-09-22 | 2025-09-22 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:28:19 | No | Yes | 2025-09-22 09:46:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-12 17:01:15 | No | No |  | 12-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector C E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-21 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
LK12M_2025 Coverage Expansion Ph2_EXP_BKK | LEAB KHLONG 12 |  |  |  |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-07 17:44:53 | No | No |  |  |  | 2025-08-29 | 2025-08-16 | 2025-08-17 | V Contribute Co., Ltd | N/A | Closed | 2025-08-17 11:04:57 | Yes | Yes | 2025-08-17 11:06:18 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-08-28 16:37:42 | Yes | Yes | 2025-08-27 14:20:38 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:57:05 |  | 2025-08-13 | 2025-08-13 | Annop Auyto | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-13 13:12:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-07 16:10:50 | No | No |  | 7-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-06 |  | N/A | Not assigned |  | No | No
LK13M_2025 Coverage Expansion Ph2_EXP_BKK | LEAB KHLONG 13 | 2025-08-09 |  | Install & Integrate | 2025-08-29 | 2025-08-30 | 2025-08-29 | 2025-08-30 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2025-10-09 18:23:19 | No | No |  |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-11-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-11-26 15:08:13 | Yes | Yes | 2025-11-26 15:09:30 |  | 2025-09-30 | 2025-09-09 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-09-12 19:05:01 | Yes | Yes | 2025-11-28 11:54:59 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:45:31 |  | 2025-08-20 | 2025-08-20 | Sattaya Parakij | Approved | Closed | 2025-09-03 22:43:51 | No | Yes | 2025-08-20 23:47:18 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-09 18:06:38 | No | No |  | 09-08-2025. Add RRU3953#， Replace Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-09 | 2025-08-29 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-10-10 15:00:11 | No | No
LK83M_2025 Capacity Expansion Ph3_EXP_BKK | LAMLUKKAKHLONG 8 STATION 3 |  |  |  |  | 2025-09-06 | 2025-09-14 | 2025-09-14 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-26 | 2025-09-06 | 2025-09-08 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:15:16 | Yes | Yes | 2025-09-30 10:15:17 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-10-06 16:27:34 | Yes | Yes | 2025-09-15 17:59:12 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:02 | Yes | Yes | 2025-10-09 20:34:23 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 17:36:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-06 15:57:29 | No | No |  | 6-Sep-2025 Add AAU5636w S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-13 |  | N/A | Not assigned |  | No | No
LK92M_2025 Coverage Expansion Ph2_EXP_BKK | LAMLUKKA KHLONG 9 STATION 2 |  |  |  |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-07 17:44:53 | No | No |  |  |  | 2025-08-22 | 2025-08-15 | 2025-08-16 | V Contribute Co., Ltd | N/A | Closed | 2025-08-16 10:41:29 | Yes | Yes | 2025-08-16 10:42:53 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-08-28 16:37:42 | Yes | Yes | 2025-08-27 14:21:26 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:58:23 |  | 2025-08-13 | 2025-08-13 | Annop Auyto | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-13 13:12:47 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-07 16:11:06 | No | No |  | 7-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-06 |  | N/A | Not assigned |  | No | No
LKBSM_2025 Capacity Expansion Ph3_EXP_BKK | LIAB KLONG BANG SHAI | [5 empty] | 2025-09-01 | 2025-09-01 | Akhom Srinara | N/A | Closed | 2025-09-01 09:42:25 | No | No |  |  |  |  | 2025-08-30 | 2025-08-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-30 13:14:57 | Yes | Yes | 2025-09-01 22:08:13 |  | 2025-09-01 | 2025-09-02 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-30 15:29:15 | Yes | Yes | 2025-09-02 18:08:58 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:54 | Yes | Yes | 2025-10-06 17:45:12 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 22:30:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-30 20:43:38 | No | No |  | 30-Aug-2025Add RRU5516 (18002100) S3 Remove RRU5507 Replace Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-31 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
LKG9M_2025 Coverage Expansion Ph2_EXP_BKK | LEAB KHLONG 9 | 2025-08-02 |  |  |  | 2025-08-02 | 2025-08-02 | 2025-08-02 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-02 17:51:49 | No | No |  |  |  | 2025-08-22 | 2025-08-14 | 2025-08-18 | V Contribute Co., Ltd | N/A | Closed | 2025-08-18 10:51:21 | Yes | Yes | 2025-08-18 11:21:53 |  | 2025-08-19 | 2025-08-19 | Chonradee Suwapan | Approved | Closed | 2025-08-22 17:57:48 | Yes | Yes | 2025-08-19 23:13:44 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:53:51 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:53:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-02 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-02 17:04:11 | No | No |  | 02-08-2025. Add RRU3953 Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
LKL6M_2025 Coverage Expansion Ph2_EXP_BKK | LAMLUKKA KHLONG HOK ROAD | 2025-08-23 |  |  |  | 2025-08-23 | 2025-08-23 | 2025-08-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-23 17:52:43 | No | No |  |  |  | 2025-08-31 | 2025-08-28 | 2025-09-02 | V Contribute Co., Ltd | N/A | Closed | 2025-09-02 11:09:19 | Yes | Yes | 2025-09-02 11:10:13 |  |  | 2025-09-08 | Chonradee Suwapan | Approved | Closed | 2025-09-19 16:33:12 | Yes | Yes | 2025-11-28 17:20:00 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:48:01 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:28 | No | Yes | 2025-09-06 19:29:20 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-23 18:17:22 | No | No |  | 23-Aug-2025 Add RRU3953 S1 S3 Add Ant 4port S1 S3 Act Cell 111 113 Run NB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-21 |  | N/A | Not assigned |  | No | No
LKRPM_2025 Coverage Expansion Ph2_EXP_BKK | LIAB KLONG RATPRASERT ROAD |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-11 | 2025-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-11 20:02:45 | Yes | Yes | 2025-08-11 20:03:00 |  | 2025-08-18 | 2025-08-18 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:33:55 | Yes | Yes | 2025-08-19 12:20:53 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 12:59:39 |  | 2025-08-30 | 2025-08-30 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-08-30 23:40:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-11 18:23:00 | No | No |  | 11-08-2025. Add RRU3953#， Replace Ant.4 port Sec.2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
LL12M_2025 Coverage Expansion Ph2_EXP_BKK | LAMLUKKAKHLONG 12 |  |  |  |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-07 17:44:53 | No | No |  |  |  | 2025-08-29 | 2025-08-16 | 2025-08-17 | V Contribute Co., Ltd | N/A | Closed | 2025-08-17 11:13:22 | Yes | Yes | 2025-08-17 11:14:41 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-04 09:25:37 | Yes | Yes | 2025-09-02 18:10:08 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:54:21 |  | 2025-08-13 | 2025-08-13 | Annop Auyto | Approved | Closed | 2025-09-03 22:42:08 | No | Yes | 2025-08-13 13:13:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-07 17:52:12 | No | No |  | 07-08-2025. Add RRU3953 Sec.1#， 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-06 |  | N/A | Not assigned |  | No | No
LL13M_2025 Coverage Expansion Ph2_EXP_BKK | LAMLUKKAKHLONG 13 |  |  |  |  | 2025-08-06 | 2025-08-06 | 2025-08-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-06 17:03:49 | No | No |  |  | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-07 | V Contribute Co., Ltd | N/A | Closed | 2025-08-07 16:02:19 | Yes | Yes | 2025-08-07 16:02:48 |  | 2025-08-24 | 2025-08-24 | Chonradee Suwapan | Approved | Closed | 2025-08-26 09:26:48 | Yes | Yes | 2025-08-24 20:49:00 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-27 | 2025-08-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:56:26 |  | 2025-08-13 | 2025-08-13 | Annop Auyto | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-13 13:13:25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-06 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-06 18:52:51 | No | No |  | 2025-08-06_Add RRU3953 Sector 1#， No act Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-05 |  | N/A | Not assigned |  | No | No
LLK2M_2025 Coverage Expansion Ph2_EXP_BKK | LAT LUM KAEW STATION 2 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-11 | 2025-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-11 15:23:58 | Yes | Yes | 2025-08-15 16:47:53 |  | 2025-08-19 | 2025-08-19 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:33:55 | Yes | Yes | 2025-08-19 21:53:01 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 13:02:13 |  | 2025-09-02 | 2025-09-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-02 20:19:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-11 18:15:26 | No | No |  | 2025-08-11_Add RRU3953#， No act Ant Sector 2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
LLK8M_2025 Coverage Expansion Ph2_EXP_BKK | LAMLUKKAKHLONG8 | 2025-08-02 |  |  |  | 2025-08-02 | 2025-08-02 | 2025-08-02 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-02 17:51:49 | No | No |  |  |  | 2025-08-22 | 2025-08-14 | 2025-08-14 | V Contribute Co., Ltd | N/A | Closed | 2025-08-14 20:26:16 | Yes | Yes | 2025-08-14 20:29:44 |  | 2025-08-19 | 2025-08-19 | Chonradee Suwapan | Approved | Closed | 2025-08-22 17:57:48 | Yes | Yes | 2025-08-19 23:15:20 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 13:03:31 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:53:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-02 17:50:24 | No | No |  | 2-Aug-2025 Add RRU3953 S2 Replace Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
LMA1B_2025 Capacity Expansion Ph5_EXP_BKK | Lumpini Megacity Bangna 1 Building A1 |  |  |  |  | 2026-01-27 | 2026-01-27 | 2026-01-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-07 | 2026-03-30 | 2026-03-30 | V Contribute Co., Ltd | N/A | Closed | 2026-03-30 16:47:19 | Yes | Yes | 2026-03-30 16:47:20 |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-03-16 17:56:27 | Yes | Yes | 2026-02-09 21:20:47 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-31 | 2026-03-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:10:11 | Yes | Yes | 2026-02-09 21:25:53 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-27 17:14:08 | No | No |  | 27-Jan-2026 Add RRU5818 sector D Replace Ant 12port No RET Add g3a g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LMN2M_2025 Coverage Expansion Ph2_EXP_BKK | SOI LIANG MUANG NONTHABURI 2 (SI PHON SAWAN) | 2025-08-20 |  |  |  | 2025-08-31 | 2025-08-20 | 2025-08-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-20 16:21:33 | No | No |  |  |  | 2025-08-31 | 2025-08-29 | 2025-09-05 | V Contribute Co., Ltd | N/A | Closed | 2025-09-05 13:15:10 | Yes | Yes | 2025-09-05 13:16:33 |  |  | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-12 19:05:01 | Yes | Yes | 2025-11-28 15:02:46 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 20:58:10 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:54:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-20 20:02:21 | No | No |  | 2025-08-20_Add RRU3953#， Replace Ant to 4 port Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-19 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 05:58:50 | No | No
LNS2B_2025 Capacity Expansion Ph2_EXP_BKK | LUMPINI CONDO TOWN NIDA-SERITHAI 2 |  |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-11-18 14:49:55 | No | No |  |  | 2025-11-30 | 2025-11-30 | 2025-11-15 | 2025-11-16 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2025-11-16 15:22:20 | Yes | Yes | 2025-11-17 13:07:15 |  | 2025-11-30 | 2025-11-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-12-12 11:16:21 | Yes | Yes | 2025-11-18 16:05:43 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 18:47:12 |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:33:06 | Yes | Yes | 2026-07-14 22:51:31 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-14 16:25:51 | No | No |  | 14-Nov-2025 Replace BBU5900 UMPTg2 GPS g3a Remove d5 Add RRU5818 SC Replace Ant 12port No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | wait OSP |  | 2025-11-14 |  | N/A | Not assigned |  | No | No
LP35M_2025 Capacity Expansion Ph6_EXP_BKK | LAT PHRAO SOI 35 | 2025-12-03 |  |  |  | 2025-12-31 | 2025-12-04 | 2025-12-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-04 18:19:04 | No | No |  |  |  | 2025-12-31 | 2025-12-10 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 10:50:54 | Yes | Yes | 2025-12-26 10:50:54 |  | 2025-12-09 | 2025-12-09 | Chonradee Suwapan | Approved | Closed | 2025-12-18 09:25:15 | Yes | Yes | 2026-01-14 16:48:05 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:03 | Yes | Yes | 2026-01-09 18:48:24 |  | 2025-12-09 | 2025-12-09 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-09 20:59:43 |  |  | 2025-12-31 | 2025-12-03 | V Contribute Co., Ltd | N/A | Closed | 2025-12-03 16:47:14 | No | No |  |  |  |  | 2025-12-03 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-03 17:11:00 | No | No |  | 03-12-2025. Add AIRU5636w Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LPG2M_2025 Capacity Expansion Ph3_EXP_BKK | LUANG PHAENG RD. STATION2 |  |  |  |  | 2025-09-06 | 2025-09-14 | 2025-09-14 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-26 | 2025-09-15 | 2025-09-15 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:15:31 | Yes | Yes | 2025-09-30 10:15:32 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-10-10 16:48:15 | Yes | Yes | 2025-09-15 18:02:33 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:25 | Yes | Yes | 2025-11-06 16:27:33 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 17:54:47 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-06 17:44:02 | No | No |  | 06-09-2025. Add AIRU5636w Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-13 |  | N/A | Not assigned |  | No | No
LPG3M_2025 Capacity Expansion Ph3_EXP_BKK | LUANG PHAENG RD. STATION 3 | 2025-08-25 |  |  |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-25 17:13:12 | No | No |  |  |  | 2025-08-31 | 2025-09-02 | 2025-09-03 | V Contribute Co., Ltd | N/A | Closed | 2025-09-03 16:55:59 | Yes | Yes | 2025-09-03 17:06:25 |  |  | 2025-09-08 | Chonradee Suwapan | Approved | Closed | 2025-09-19 20:13:57 | Yes | Yes | 2025-09-16 22:37:10 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 21:04:29 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-06 19:30:34 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-25 18:38:32 | No | No |  | 25-Aug-2025 Add RRU5516 (1800-2100) S2 Remove RRU3962 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-22 |  | N/A | Not assigned |  | No | No
LPG5M_2025 Capacity Expansion Ph3_EXP_BKK | LUANG PHAENG RD. STATION 5 |  |  |  | 2025-10-30 | 2025-11-06 | 2025-11-05 | 2025-11-05 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-11-21 15:53:01 | No | No |  |  | 2025-11-06 | 2025-11-08 | 2025-11-05 | 2025-11-06 | Teloneer Company Limited | N/A | Closed | 2025-11-06 15:12:17 | Yes | Yes | 2025-11-06 16:45:12 |  |  | 2025-11-07 | Apichart Kampuang | Approved | Closed | 2025-11-18 16:04:59 | Yes | Yes | 2025-11-07 15:57:07 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 19:11:43 |  |  | 2025-10-30 | Palagon Prommueangma(Teloneer Company Limited) | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-30 16:28:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-01 17:59:37 | No | No |  | 11-01-2025. Add RRU5516 L900 Sec.7#， Ant.8 port Sec.2#， 7#， Ant.12 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
LPNLB_2025 Capacity Expansion Ph5_EXP_BKK | LUMPINI CENTER LADPRAO 111 | [5 empty] | 2026-03-24 | 2026-03-24 | Akhom Srinara | N/A | Closed | 2026-03-24 11:11:26 | No | No |  |  |  | 2026-03-02 | 2026-03-02 | 2026-03-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-03-19 16:12:13 | Yes | Yes | 2026-03-24 10:37:45 |  | 2026-04-09 | 2026-05-18 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-05-19 17:05:30 | Yes | Yes | 2026-05-18 13:35:08 | Already upload New PAT DOC 18-05-2026 | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-07-22 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-22 16:17:02 | No | No |  |  |  | 2026-05-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-09 | 2026-04-09 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-19 15:26:19 | Yes | Yes | 2026-04-09 15:58:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-25 11:54:50 | No | No |  | 25-Feb-2026 Replace BBU5900 UMPTg2 Add GPS g3a g2 Remove d5 Add RRU5818 Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LR49M_2025 Coverage Expansion Ph2_EXP_BKK | SOI LEAB WAREE 49 |  |  |  |  | 2025-10-21 | 2025-10-21 | 2025-10-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-21 17:43:19 | No | No |  |  |  | 2025-10-17 | 2025-10-29 | 2025-10-29 | V Contribute Co., Ltd | N/A | Closed | 2025-10-29 21:11:02 | Yes | Yes | 2025-10-29 21:11:03 |  | 2025-10-29 | 2025-10-29 | Chonradee Suwapan | Approved | Closed | 2025-11-03 20:57:07 | Yes | Yes | 2026-01-06 16:23:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:25 | Yes | Yes | 2025-11-06 16:36:12 |  | 2025-10-29 | 2025-10-29 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-29 20:23:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-11 17:36:17 | No | No |  | 11-10-2025. Add RRU3953#， Ant.8 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Complted |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
LRS1B_2025 Coverage Expansion Ph1_EXP_BKK | LIFE RATCHADASUTHISAN (FRONT LEFT) | [5 empty] | 2025-10-17 | 2025-10-17 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-16 | 2025-10-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-31 11:51:44 | Yes | Yes | 2025-11-03 13:34:22 |  | 2025-11-03 | 2025-11-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 15:52:18 | Yes | Yes | 2025-11-10 18:13:45 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 11:57:34 |  | 2025-12-18 | 2025-12-18 | Charuwan Limsaihua | Approved | Closed | 2026-03-12 09:22:14 | No | Yes | 2025-12-18 15:28:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-16 18:21:16 | No | No |  | 16-Oct-2025 Replace Ant to Ant Vertical dual beam SA E-tilt -200 80 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของเพิ่มเติมขาด Spliter 2way , wait survey |  | 2025-10-16 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
LRS2B_2025 Coverage Expansion Ph1_EXP_BKK | Life RatchadaSuthisan (Front Right) | [5 empty] | 2025-10-17 | 2025-10-17 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-16 | 2025-10-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-31 11:41:35 | Yes | Yes | 2025-10-31 11:41:35 |  | 2025-11-05 | 2025-11-05 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-11 11:05:21 | Yes | Yes | 2025-11-05 16:17:44 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 19:27:32 |  | 2025-11-05 | 2025-11-05 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:27:01 | No | Yes | 2025-11-05 16:20:31 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-16 17:03:25 | No | No |  | 16-10-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของเพิ่มเติมขาด Spliter 2way, wait survey |  | 2025-10-16 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
LRS3B_2025 Coverage Expansion Ph1_EXP_BKK | LIFE RATCHADASUTHISAN (BACK) | [5 empty] | 2025-10-17 | 2025-10-17 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-16 | 2025-10-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-31 11:50:25 | Yes | Yes | 2025-11-08 10:02:08 |  | 2025-11-08 | 2025-11-08 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-11 16:13:53 | Yes | Yes | 2025-11-13 15:44:17 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 19:28:45 |  | 2025-11-08 | 2025-11-08 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:26:46 | No | Yes | 2025-11-08 16:09:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-16 18:21:31 | No | No |  | 16-Oct-2025 Replace Ant to Ant Vertical dual beam SA E-tilt -200 82 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของเพิ่มเติมขาด Spliter 4way, wait survey |  | 2025-10-16 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
LS67B_2025 Capacity Expansion NW Modernization_EXP_BKK | Life@Sukhumvit 67 Condominium |  |  |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-05 08:14:49 | No | No |  |  |  | 2026-02-14 | 2026-03-06 | 2026-03-08 | V Contribute Co., Ltd | N/A | Closed | 2026-03-08 12:52:20 | Yes | Yes | 2026-03-08 12:52:21 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-16 17:56:27 | Yes | Yes | 2026-05-17 18:12:11 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-03-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-27 | 2026-02-27 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-27 01:34:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-09 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-09 18:25:38 | No | No |  | 09-02-26 Replace BBU3900 To BBU5900 Replace RRU5502 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LSHPT_2025 Capacity Expansion Ph6_EXP_SR | Langsuan hospital |  |  |  |  | 2025-12-28 | 2025-12-26 | 2025-12-26 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2026-01-19 13:12:02 | No | No |  |  |  | 2025-12-08 | 2025-12-26 | 2026-02-04 | Teloneer Company Limited | N/A | Closed | 2026-02-04 11:32:03 | Yes | Yes | 2026-02-04 11:36:53 |  | 2026-01-14 | 2026-01-14 | Nattawoot Suwan | Approved | Closed | 2026-03-05 17:10:15 | Yes | Yes | 2026-02-11 08:25:57 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 12:17:10 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-25 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-24 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-12-24 18:24:35 | No | No |  | Rep d6*1 to g3a*1 Re MB S5>S2#，S6>S3 Re HB S6>S3 Add AAU5768 Sector 1 Add AAU5636w Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-02-05 | Nattawoot Suwan | N/A | Closed | 2026-02-05 11:17:05 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LSN1M_2025 Capacity Expansion Ph6_EXP_SR | หลังสวน 1 |  |  |  |  | 2025-12-25 | 2025-12-20 | 2025-12-20 | Teloneer Company Limited | N/A | Closed | 2025-12-20 10:03:14 | No | No |  |  |  | 2025-12-08 | 2025-12-19 | 2025-12-20 | Teloneer Company Limited | N/A | Closed | 2025-12-20 11:38:55 | Yes | Yes | 2025-12-22 14:48:56 |  | 2025-12-23 | 2025-12-23 | Nattawoot Suwan | Approved | Closed | 2026-01-26 10:02:39 | Yes | Yes | 2025-12-23 18:00:30 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-14 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:32 | Yes | Yes | 2026-01-15 11:58:47 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-22 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-12-19 17:02:01 | No | No |  | AAU5636w Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LTDBM_2025 Capacity Expansion Ph6_EXP_BKK | Tesco Lotus Distribution Center-Bangbuathong | [5 empty] | 2025-12-25 | 2025-12-25 | Akhom Srinara | N/A | Closed | 2025-12-25 09:52:09 | No | No |  |  |  | 2025-12-23 | 2025-12-23 | 2025-12-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-26 18:22:43 | Yes | Yes | 2026-01-09 11:24:57 |  | 2026-01-11 | 2026-01-11 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-16 16:09:55 | Yes | Yes | 2026-01-15 13:44:00 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:47:45 |  | 2026-01-11 | 2026-01-11 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-11 16:13:06 |  |  | 2025-12-31 | 2025-12-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-23 16:04:43 | No | No |  |  |  |  | 2025-12-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-23 16:55:48 | No | No |  | 23-12-2025. Add AAU5614 Sec.1#， Replace RRU3953 to RRU5516 L900#， Ant.8 port Sec.3#， UBBPd5 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LU10M_2025 Coverage Expansion Ph2_EXP_BKK | LUANG PHAENG 10 (SOI CHIT SON) |  |  |  | 2025-08-15 | 2025-08-31 | 2025-08-18 | 2025-08-18 | Akhom Srinara | N/A | Closed | 2025-08-18 13:04:03 | No | No |  |  |  |  | 2025-08-15 | 2025-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-15 17:13:06 | Yes | Yes | 2025-08-20 08:40:29 |  | 2025-08-29 | 2025-08-29 | Aomchun Jittreemit | Approved | Closed | 2025-09-08 16:35:17 | Yes | Yes | 2025-09-02 18:38:28 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:15 | Yes | Yes | 2025-09-22 21:09:29 |  | 2025-09-04 | 2025-09-04 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 15:51:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-15 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-15 17:34:49 | No | No |  | 2025-08-15_Add RRU3953#， Replace to Ant 4 port Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-17 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 05:58:50 | No | No
LWREM_2025 Coverage Expansion Ph2_EXP_BKK | LEABWAREE ROAD |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  | 2025-08-11 | 2025-08-12 | 2025-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-12 18:14:58 | Yes | Yes | 2025-08-16 14:59:39 |  | 2025-08-19 | 2025-08-19 | Aomchun Jittreemit | Approved | Closed | 2025-08-25 17:34:38 | Yes | Yes | 2025-08-19 15:03:32 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 13:07:24 |  | 2025-09-04 | 2025-09-04 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-04 11:35:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-12 17:52:26 | No | No |  | 12-08-2025. Add RRU3953#， Replace Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
M3Y2M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI MI SUWAN 3 YEAK 2 (SOI SAM SAKUN 1) |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-03-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-02 11:58:21 | Yes | Yes | 2026-03-04 10:55:34 |  | 2026-03-27 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-02 16:18:36 | Yes | Yes | 2026-04-01 15:49:01 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:06:34 | Yes | Yes | 2026-08-01 19:59:30 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-20 20:42:08 | No | No |  | 20-Feb-2026 Add RRU5526 Sector 1 Remove RRU3962 *2 Replace Ant 8port Co 1800900 11-Feb-26 Replace RRU3962 To RRU5516 S1 #， Relace RRU5507 To DMM S2 #，Remove RRU5507 S7 ///Pending Raplace RRU5526 S1 10-02-26 Add AAU5768 DMM S3 ***///Pending Add DMM S2 #，swap RRU3962 To 5526 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MA31M_2025 Capacity Expansion NW Modernization_EXP_BKK | MONTHIRA APARTMENT SOI SUKHUMVIT 31 |  |  |  | 2026-01-29 | 2026-01-29 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:24:51 | No | No |  |  | 2026-01-26 | 2026-01-26 | 2026-01-27 | 2026-02-03 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-03 17:32:27 | Yes | Yes | 2026-02-06 14:12:34 | SQC Close | 2026-04-22 | 2026-06-16 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-06-16 11:52:50 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-12-29 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:06:34 | Yes | Yes | 2026-08-01 21:32:17 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 27-Jan-2026 Add AAU5768 S1 S2 S3 Remove RRU5507*5 RRU3962 *2 RRU5507*5 *4 Add RRU3953 S1 S2 S3 Add g3a Remove d6 Now cell down due to Cell Unavailable as detail below *** Pending DMM sector 3 wrong sfp 10g wait change 25g |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-01-29 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MARCB_2025 Capacity Expansion NW Modernization_EXP_BKK | MARCHE THONGLOR SMALL CELL |  |  |  | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-08-04 19:33:03 | No | No |  |  | 2026-05-20 | 2026-05-20 | 2026-07-25 | 2026-08-01 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-08-01 19:44:54 | Yes | Yes | 2026-08-01 19:44:55 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:06:34 | Yes | Yes | 2026-08-01 21:32:32 |  |  | 2026-07-22 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-07-20 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-07-20 20:21:40 | No | No |  | 2026-07-20 alarm VSWR clear |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBCDM_2025 Capacity Expansion Ph3_EXP_BKK | MOO BAAN CHONLADA |  |  |  |  | 2025-09-05 | 2025-09-14 | 2025-09-14 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-26 | 2025-09-16 | 2025-09-16 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:15:45 | Yes | Yes | 2025-09-30 10:15:45 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-10-07 16:22:25 | Yes | Yes | 2025-11-29 12:22:52 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:02 | Yes | Yes | 2025-10-09 20:43:03 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 17:45:23 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-05 19:42:35 | No | No |  | 5-Sep-2025 Add RRU5516 (700900) S3 Remove RRU3953 Add g2 Replace Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-13 |  | N/A | Not assigned |  | No | No
MBHPM_2025 Coverage Expansion Ph2_EXP_BKK | MU BAN HOME PLACE |  |  |  | 2025-08-14 | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 19:08:41 | No | No |  |  |  |  | 2025-08-14 | 2025-08-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-14 20:24:46 | Yes | Yes | 2025-08-20 08:47:20 |  | 2025-08-26 | 2025-08-26 | Muhamadnase Chesamae | Approved | Closed | 2025-09-03 14:48:30 | Yes | Yes | 2025-08-26 10:02:25 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 13:09:56 |  | 2025-09-04 | 2025-09-04 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 14:59:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-14 18:51:52 | No | No |  | 14-08-2025. Add RRU3953#， Replace Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
MBK1P_2025 Capacity Expansion NW Modernization_EXP_BKK | MABOONKRONGH 1 |  |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-11 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 10:32:28 | Yes | Yes | 2026-02-12 10:32:28 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-04-10 11:05:10 | Yes | Yes | 2026-02-23 21:19:16 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-02 | 2026-04-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:45 | Yes | Yes | 2026-02-23 22:47:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Replace UBBPd6 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBK2P_2025 Capacity Expansion NW Modernization_EXP_BKK | MABOONKRONGH 2 |  |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 20:49:57 | Yes | Yes | 2026-02-11 20:49:57 | SQC Close | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-06 15:45:14 | Yes | Yes | 2026-02-25 21:57:45 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:48:22 |  | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:45 | Yes | Yes | 2026-02-25 22:33:33 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Replace UBBPd5(2) to UBBPg3a#， UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBLWM_2025 Capacity Expansion Ph3_EXP_BKK | MOO BAAN LAKEWOOD | [5 empty] | 2025-09-30 | 2025-09-30 | Akhom Srinara | N/A | Closed | 2025-09-30 14:03:02 | No | No |  |  |  |  | 2025-09-16 | 2025-09-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-21 16:17:26 | Yes | Yes | 2025-09-21 16:18:41 |  | 2025-09-26 | 2026-01-20 | Aomchun Jittreemit | Approved | Closed | 2026-01-27 09:26:03 | Yes | Yes | 2026-01-20 17:32:41 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-12-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 19:02:58 |  | 2025-09-26 | 2025-09-26 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-26 19:45:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-16 17:05:42 | No | No |  | 16-09-2025. Add AIRU5636w Sec.1#， 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-29 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
MBPLM_2025 Capacity Expansion Ph2_EXP_BKK | MUANG MAI BANG PLI |  |  |  | 2025-08-18 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-20 | 2025-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-20 17:24:39 | Yes | Yes | 2025-08-23 01:20:19 |  | 2025-08-25 | 2025-08-31 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-16 13:40:08 | Yes | Yes | 2025-08-31 16:53:27 | PAT pas | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:14 | Yes | Yes | 2025-09-22 21:25:55 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 20:08:06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-19 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-19 17:45:16 | No | No |  | 19-08-2025. Add UBBPg2#， AIRU5636w Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
MBTKD_2025 Coverage Expansion Ph1_New_SR | Mu Ban Takhian Dam |  |  |  | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28 | Nattawoot Suwan | N/A | Closed | 2026-03-13 18:40:38 | No | No |  |  |  | 2026-02-27 | 2026-02-27 | 2026-02-28 | Teloneer Company Limited | N/A | Closed | 2026-02-28 16:43:17 | Yes | Yes | 2026-03-04 14:52:33 |  | 2026-03-04 | 2026-03-04 | Nattawoot Suwan | Approved | Closed | 2026-03-05 09:51:27 | Yes | Yes | 2026-03-09 20:16:52 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-04-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:03 | Yes | Yes | 2026-04-09 11:32:18 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-02-28 18:15:32 | No | No |  | 28 Feb 2026 "RRU3953*4#，RRU3826*8 > Ant 8 port *4//test Alarm #，cell Done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-22 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 21:09:58 | Yes | Yes | 2026-01-22 15:18:20 |  |  | 2026-03-09 | Nattawoot Suwan | N/A | Closed | 2026-03-09 14:42:38 | No | No | [5 empty] | 2026-02-26 |  | N/A | Not assigned |  | No | No
MBYYM_2025 Capacity Expansion Ph2_EXP_BKK | Mu Ban Yang Yuen | [5 empty] | 2025-11-14 | 2025-11-14 | Narongsak wanichachiwa | N/A | Closed | 2025-11-21 16:38:32 | No | No |  |  |  | 2025-11-05 | 2025-11-13 | 2025-11-14 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-11-14 14:51:00 | Yes | Yes | 2025-11-14 18:54:39 |  |  | 2025-11-17 | OATTAPAN AUTTAHON | Approved | Closed | 2025-12-03 09:56:01 | Yes | Yes | 2025-11-17 14:14:15 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 19:04:10 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-10 17:59:57 | No | No |  | 11-10-2025. Add UBBPg2#， RRU5516 L900#， Ant.4 port Sec.2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
MEMGM_2025 Coverage Expansion Ph2_EXP_BKK | MUBAN THE EMERALD GARDEN |  |  |  |  | 2025-08-06 | 2025-08-06 | 2025-08-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-06 17:03:49 | No | No |  |  |  | 2025-08-22 | 2025-08-07 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 16:23:12 | Yes | Yes | 2025-08-15 16:24:32 |  | 2025-08-22 | 2025-08-22 | Chonradee Suwapan | Approved | Closed | 2025-08-25 17:34:38 | Yes | Yes | 2025-11-29 15:14:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 18:59:01 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:54:31 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-06 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-06 18:52:51 | No | No |  | 2025-08-06_Add RRU3953#， No act Ant Sector 1#， Add RRU3953#， Ant 4 port Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-05 |  | N/A | Not assigned |  | No | No
MEPHP_2025 Capacity Expansion Ph2_EXP_ER | MEP Hexa (Thailand) Ltd. | 2025-08-20 |  | Install & Integrate |  | 2025-08-31 | 2025-08-20 | 2025-08-20 | Teloneer Company Limited | N/A | Closed | 2025-08-20 17:52:58 | No | No |  |  |  | 2025-07-31 | 2025-08-21 | 2025-08-21 | Teloneer Company Limited | N/A | Closed | 2025-08-21 11:55:30 | Yes | Yes | 2025-08-22 16:13:30 |  | 2025-07-31 | 2025-09-16 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-18 15:00:39 | Yes | Yes | 2025-09-16 13:58:27 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-12-31 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:14 | Yes | Yes | 2025-09-22 21:32:08 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:26:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-21 |  | 2025-08-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-20 19:04:23 | No | No |  | Change Remote RRU to Remote BBU |  | 2025-08-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-20 19:04:23 | No | No |  |  |  | 2025-07-11 | Angsana Jituafua WX1434741 | Approved | Closed | 2025-07-22 13:37:41 | Yes | Yes | 2025-07-22 11:27:26 |  |  | 2025-08-27 | Teloneer Company Limited | N/A | Closed | 2025-08-28 14:38:08 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MI21M_2025 Coverage Expansion Ph2_EXP_BKK | SOI MIT PRACHA 21 |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-31 | 2025-10-17 | 2025-10-18 | V Contribute Co., Ltd | N/A | Closed | 2025-10-18 15:20:45 | Yes | Yes | 2025-10-18 15:20:45 |  | 2025-10-27 | 2025-10-27 | Chonradee Suwapan | Approved | Closed | 2025-10-30 12:49:26 | Yes | Yes | 2026-01-06 11:35:15 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:25 | Yes | Yes | 2025-11-06 17:00:10 |  | 2025-10-27 | 2025-10-27 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-27 21:10:41 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-16 17:03:25 | No | No |  | 16-10-2025. Add RRU3953 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
MKHRM_2025 Capacity Expansion Ph7_EXP_ER | Moo9 HuaSamrong | 2025-12-09 | THCP_Wachira.s | Install & Integrate |  | 2025-12-31 | 2025-12-07 | 2025-12-07 | Teloneer Company Limited | N/A | Closed | 2025-12-07 14:05:55 | No | No |  |  |  | 2025-12-31 | 2025-12-07 | 2025-12-07 | Teloneer Company Limited | N/A | Closed | 2025-12-07 15:38:29 | Yes | Yes | 2025-12-09 16:00:28 |  | 2025-12-31 | 2025-12-09 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-13 21:13:48 | Yes | Yes | 2025-12-09 19:57:06 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 12:21:12 |  | 2025-12-31 | 2025-12-07 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:33:47 | Yes | Yes | 2025-12-07 11:14:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-09 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-12-09 18:33:04 | No | No |  | ReDirection 240 to 220_MKHRM_N_3 New L26F5 + NR26 (New AAU5636w)_MKHRM_N_8 |  | 2025-12-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-11 18:18:21 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MKTNM_2025 Capacity Expansion NW Modernization_EXP_BKK | MUBAN KHLONGTON NIWET_3G2100 |  |  |  |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-03 | 2026-02-07 | V Contribute Co., Ltd | N/A | Closed | 2026-02-07 17:56:22 | Yes | Yes | 2026-05-12 17:35:54 | SQC Close | 2026-04-27 | 2026-04-27 | Chonradee Suwapan | Approved | Closed | 2026-07-06 09:43:51 | Yes | Yes | 2026-05-04 10:19:36 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-28 | 2026-09-11 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-27 | 2026-04-27 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-27 02:11:54 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-04 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-04 17:23:25 | No | No |  | 4 Feb 2026 Replace RRU5516 sector1#，2#，3 900/700 replace RRU5526 sector2#，3 18/21 2026-02-03_Pre work |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MKTNM_2025 Capacity Expansion Ph7_EXP_BKK | MUBAN KHLONGTON NIWET_3G2100 |  |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-23 14:25:10 | No | No |  |  |  | 2026-01-31 | 2026-06-03 | 2026-06-03 | V Contribute Co., Ltd | N/A | Closed | 2026-06-03 17:22:24 | Yes | Yes | 2026-06-03 17:25:18 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-09-10 16:45:22 | Yes | Yes | 2026-05-08 12:44:33 | Page no.50#， After DCDU C3 photo wrong. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-27 | 2026-09-11 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:36 | Yes | Yes | 2026-02-06 22:55:32 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-26 18:23:01 | No | No |  | 26-01-2026 Replace 3962 to AAU5768 On DMM sector 1 #，add card g2#，g3a Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MLLSM_2025 Coverage Expansion Ph2_EXP_BKK | Ma Lea Lai School | 2025-08-08 |  |  |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-08 18:25:52 | No | No |  |  |  | 2025-08-22 | 2025-08-18 | 2025-08-20 | V Contribute Co., Ltd | N/A | Closed | 2025-08-20 12:00:22 | Yes | Yes | 2025-08-20 12:01:41 |  | 2025-08-24 | 2025-08-24 | Chonradee Suwapan | Approved | Closed | 2026-03-11 16:32:23 | Yes | Yes | 2025-08-24 20:50:44 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:51:49 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:54:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-08 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-08 19:12:01 | No | No |  | 8-Aug-2025 Add RRU3953 S2 Add Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
MMCTM_2025 Capacity Expansion NW Modernization_EXP_BKK | M.M. COURT |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-02-07 | 2026-03-20 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:38:31 | Yes | Yes | 2026-03-23 15:38:32 |  | 2026-02-13 | 2026-02-13 | Chonradee Suwapan | Approved | Closed | 2026-05-12 16:26:02 | Yes | Yes | 2026-05-08 14:46:35 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-02 | 2026-05-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-13 | 2026-02-13 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-13 23:11:01 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-30 17:16:01 | No | No |  | 30-01-2026. Replace RRU3962 to AAU5768 Sec.1#， RRU5507 to AAU5768 Sec.2#， 3#， UBBPd5#， UBBPd6 to UBBPg3a x2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MNTLM_2025 Capacity Expansion Ph2_EXP_BKK | MINISTRY OF LABOUR | 2025-09-25 |  |  |  | 2025-12-02 | 2025-12-02 | 2025-12-02 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-02 18:45:42 | No | No |  |  |  | 2025-09-30 | 2025-09-29 | 2025-09-29 | V Contribute Co., Ltd | N/A | Closed | 2025-09-29 21:27:32 | Yes | Yes | 2025-09-29 21:27:32 |  | 2025-12-04 | 2025-12-04 | Chonradee Suwapan | Approved | Closed | 2025-12-12 09:47:05 | Yes | Yes | 2025-12-04 21:05:51 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 19:13:52 |  | 2025-12-04 | 2025-12-04 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-12-04 21:36:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-02 16:34:43 | No | No |  | 2-Dec-2025 Add RRU5516 (700900) S1 *** Pending SFP ต่ำ RX 850 26-Sep-2025 ***Pending Add RRU5516 (700900) S1 //// Add RRU5516 (700900) S3 Done sfp ต่ำ 26-Sep-2025 ***Pending Add RRU5516 (700900) S1 S3 //Add RRU5516 (700900) S2 Add g2 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-12-01 |  | N/A | Not assigned |  | No | No
MONTB_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL THE MONTIEN HOTEL BANGKOK |  |  |  | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-05 15:39:25 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-29 | 2026-01-30 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-30 16:06:59 | Yes | Yes | 2026-02-03 09:29:48 |  | 2026-02-05 | 2026-02-05 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-22 09:22:52 | Yes | Yes | 2026-06-18 12:00:16 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-25 | 2026-07-02 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:33:03 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-14 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-14 17:52:21 | No | No |  | 2026-01-14_replace UBBPd5 to UBBPg2#， Add AAU5636w Sector 8 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-13 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-13 16:07:27 | Yes | Yes | 2026-01-13 10:26:03 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MPBST_2025 Coverage Expansion Ph1_New_SR | Mo 8 Ban Sai Tok |  |  |  |  | 2026-01-12 | 2026-01-06 | 2026-01-06 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2026-01-19 13:12:02 | No | No |  |  |  | 2026-01-05 | 2026-01-06 | 2026-01-06 | Teloneer Company Limited | N/A | Closed | 2026-01-06 18:28:16 | Yes | Yes | 2026-01-14 20:24:39 |  | 2026-01-21 | 2026-01-21 | Nattawoot Suwan | Approved | Closed | 2026-01-23 09:44:16 | Yes | Yes | 2026-01-29 19:19:55 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-02-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 17:02:28 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-12 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-01-12 17:12:07 | No | No |  | BBU3910#，UBBPd5*4 S1 > RRU3826(2) > Ant 4 Port S2 > RRU3826(2) > Ant 4 Port S3 > RRU3826(2) > Ant 4 Port S4 > RRU3826(2) > Ant 4 Port Test Done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-17 14:08:58 | Yes | Yes | 2025-12-15 17:31:08 |  |  | 2026-06-08 | Nattawoot Suwan | N/A | Closed | 2026-06-08 18:40:06 | No | No | [5 empty] | 2026-01-09 |  | N/A | Not assigned |  | No | No
MPCHM_2025 Capacity Expansion Ph6_EXP_BKK | MUBAN MIT PRACHA | [5 empty] | 2025-12-11 | 2025-12-11 | Akhom Srinara | N/A | Closed | 2025-12-18 11:53:12 | No | No |  |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-09 21:14:09 | Yes | Yes | 2025-12-11 14:59:51 |  | 2025-12-13 | 2026-03-22 | Muhamadnase Chesamae | Approved | Closed | 2026-04-08 09:35:02 | Yes | Yes | 2026-03-22 17:45:14 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-04-08 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2025-12-13 | 2025-12-13 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:22:43 | Yes | Yes | 2025-12-13 11:47:00 |  |  | 2025-12-31 | 2025-12-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-09 14:27:34 | No | No |  |  |  |  | 2025-12-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-09 18:04:12 | No | No |  | 09-12-2025. Add AIRU5636w Sec.2#， Replace UBBPd5 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MPRUM_2025 Coverage Expansion Ph2_EXP_BKK | MU BAN PHET MANI RAT UTHIT |  |  |  |  | 2025-08-06 | 2025-08-06 | 2025-08-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-06 17:03:49 | No | No |  |  |  | 2025-08-22 | 2025-08-14 | 2025-08-16 | V Contribute Co., Ltd | N/A | Closed | 2025-08-16 10:53:17 | Yes | Yes | 2025-08-16 10:54:35 |  | 2025-08-22 | 2025-08-22 | Chonradee Suwapan | Approved | Closed | 2026-03-10 16:23:29 | Yes | Yes | 2025-08-22 07:53:58 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-03-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:52:09 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:55:04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-06 16:58:00 | No | No |  | 06-08-2025. Add RRU3953 Sec.1#， 3#， Replace Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
MPS5M_2025 Coverage Expansion Ph2_EXP_BKK | MUBAN PUSSORN5 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  | 2025-08-11 | 2025-08-12 | 2025-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-13 10:50:41 | Yes | Yes | 2025-08-17 10:26:44 |  | 2025-08-23 | 2025-08-23 | Muhamadnase Chesamae | Approved | Closed | 2025-09-01 13:12:07 | Yes | Yes | 2025-08-27 12:53:00 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:11 | Yes | Yes | 2025-09-04 13:13:52 |  | 2025-09-04 | 2025-09-04 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 14:54:40 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-12 17:52:26 | No | No |  | 12-08-2025. Add RRU3953 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:56 | No | No
MRTBM_2025 Capacity Expansion Ph1_EXP_BKK | MRTBM | 2025-06-18 |  |  |  | 2025-06-18 | 2025-06-18 | 2025-06-18 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-06-18 14:28:37 | No | No |  |  |  | 2025-06-27 | 2025-06-24 | 2025-06-24 | V Contribute Co., Ltd | N/A | Closed | 2025-06-24 16:06:14 | Yes | Yes | 2025-06-24 16:07:43 |  | 2025-06-20 | 2025-06-20 | Chonradee Suwapan | Approved | Closed | 2025-07-24 11:41:48 | Yes | Yes | 2025-06-20 19:06:04 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-04 | 2025-07-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:18:03 | Yes | Yes | 2025-08-05 14:54:01 |  |  | 2025-06-19 | Chonradee Suwapan | Approved | Closed | 2025-06-24 13:18:53 | No | Yes | 2025-06-19 12:55:04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-06-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-06-18 16:47:14 | No | No |  | 18-Jun-2025 Add AAU5636w S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-06-17 |  | N/A | Not assigned |  | No | No
MRTBM_2025 Capacity Expansion Ph3_EXP_BKK | SOI MUBAN | 2025-08-27 |  |  |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-27 18:39:50 | No | No |  |  |  | 2025-09-05 | 2025-09-02 | 2025-09-03 | V Contribute Co., Ltd | N/A | Closed | 2025-09-03 14:49:04 | Yes | Yes | 2025-09-03 14:50:45 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-25 14:38:34 | Yes | Yes | 2025-11-30 11:29:15 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:54 | Yes | Yes | 2025-10-06 18:40:10 |  | 2025-09-11 | 2025-09-11 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:04 | No | Yes | 2025-09-11 21:30:09 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-27 19:44:56 | No | No |  | 27-Aug-2025 Add RRU5516 (700900)S2 Remove RRU3953 Replace Ant 4port Add RRU5516 (700900)S3 Remove RRU3953 Replace Ant 4port Add RRU5516 (18002100)S3 Remove RRU3962 Add g2 Remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-26 |  | N/A | Not assigned |  | No | No
MSOTM_2025 Coverage Expansion Ph2_EXP_BKK | SOI SUMPATHONG | 2025-08-16 |  |  |  | 2025-08-16 | 2025-08-16 | 2025-08-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-16 15:37:02 | No | No |  |  |  | 2025-08-31 | 2025-08-23 | 2025-08-24 | V Contribute Co., Ltd | N/A | Closed | 2025-08-24 16:09:53 | Yes | Yes | 2025-08-24 16:11:21 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-09 09:04:09 | Yes | Yes | 2025-09-02 18:10:50 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:14 | Yes | Yes | 2025-09-22 22:01:30 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:55:18 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-16 17:11:35 | No | No |  | 16-08-2025. Add RRU3953#， Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-14 |  | N/A | Not assigned |  | No | No
MSPPM_2025 Capacity Expansion Ph4_EXP_ER | Moo2 Pimpa | 2025-09-30 | THCP_PHET.S | Install & Integrate |  | 2025-10-31 | 2025-09-30 | 2025-09-30 | Teloneer Company Limited | N/A | Closed | 2025-09-30 16:09:00 | No | No |  |  |  | 2025-09-30 | 2025-10-01 | 2025-10-02 | Teloneer Company Limited | N/A | Closed | 2025-10-02 09:31:09 | Yes | Yes | 2025-10-05 00:44:26 |  | 2025-09-30 | 2025-10-08 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-20 18:04:14 | Yes | Yes | 2025-10-08 20:58:09 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 17:40:11 |  | 2025-09-30 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2026-03-02 15:29:20 | Yes | Yes | 2025-10-08 10:45:02 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 |  | 2025-09-30 | Reungsak Junkong 00927496 | N/A | Closed | 2025-10-03 17:49:45 | No | No |  | ** Waiting on-service L700 Sec.1 #， Replace 1RRU3953 to 3RRU5508 config LB 4x4 Sec.1#，2 |  | 2025-10-03 | Reungsak Junkong 00927496 | N/A | Closed | 2025-10-03 17:49:45 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MSPPM_2025 Capacity Expansion Ph7_EXP_ER | Moo2 Pimpa | 2025-12-15 |  | Install & Integrate |  | 2025-12-31 | 2025-12-15 | 2025-12-15 | Teloneer Company Limited | N/A | Closed | 2025-12-15 14:07:19 | No | No |  |  |  | 2025-12-31 | 2025-12-15 | 2025-12-15 | Teloneer Company Limited | N/A | Closed | 2025-12-15 15:14:17 | Yes | Yes | 2025-12-16 19:23:57 |  | 2025-12-31 | 2026-02-21 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-02-23 15:37:40 | Yes | Yes | 2026-01-21 16:49:30 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 12:24:00 |  | 2025-12-31 | 2025-12-15 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:26:56 | Yes | Yes | 2025-12-15 13:09:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-15 18:25:08 | No | No |  | "Replace Antenna (Dualband Dualbeam)_MSPPM_H_2 Replace Antenna (Co Antenna)_MSPPM_L_2 New L18L21 + 4T4R+ Add RRU5526 x 1 + Co Antenna_MSPPM_H_7 " |  | 2025-12-15 | Reungsak Junkong 00927496 | N/A | Closed | 2025-12-15 18:25:08 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MTF1A_2025 Capacity Expansion Ph1_EXP_BKK | MTF1A | 2025-07-22 |  |  |  | 2025-07-22 | 2025-07-22 | 2025-07-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-07-22 16:45:41 | No | No |  |  |  | 2025-07-31 | 2025-07-24 | 2025-07-25 | V Contribute Co., Ltd | N/A | Closed | 2025-07-25 14:43:50 | Yes | Yes | 2025-07-25 14:45:36 |  | 2025-07-31 | 2025-07-31 | Chonradee Suwapan | Approved | Closed | 2025-08-06 15:25:26 | Yes | Yes | 2025-07-31 03:06:47 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-09 | 2025-08-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:15 | Yes | Yes | 2025-08-18 16:03:42 |  | 2025-07-02 | 2025-07-02 | Annop Auyto | Approved | Closed | 2025-10-10 17:21:38 | No | Yes | 2025-07-02 09:51:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-07-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-07-22 16:52:55 | No | No |  | 22-Jul-2025 Add AAU5636w Sector E Add RRU5502 Sector E Add Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-21 |  | N/A | Not assigned |  | No | No
MTF2A_2025 Capacity Expansion Ph2_EXP_BKK | MUANGTHONG UNITED STADIUM (2) |  |  |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-10-23 | 2025-10-31 | 2025-10-31 | V Contribute Co., Ltd | N/A | Closed | 2025-10-31 16:57:56 | Yes | Yes | 2026-05-29 09:17:53 | SQC Close | 2025-11-03 | 2025-11-03 | Chonradee Suwapan | Approved | Closed | 2025-11-10 16:08:56 | Yes | Yes | 2025-11-03 19:56:08 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 19:52:00 |  | 2025-11-03 | 2025-11-03 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-11-03 20:04:30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-22 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-22 18:17:06 | No | No |  | 2025-10-22_Add RRU5516(LB)#， Replace to Ant 12 port(No RET) Sector F#， Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-22 |  | N/A | Not assigned |  | No | No
MTKTM_2025 Capacity Expansion Ph6_EXP_BKK | MU BAN THIAN KASEM - THEPHARAK | [5 empty] | 2025-12-12 | 2025-12-12 | Akhom Srinara | N/A | Closed | 2025-12-18 11:53:12 | No | No |  |  |  | 2025-12-08 | 2025-12-08 | 2025-12-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-09 16:52:22 | Yes | Yes | 2025-12-12 13:59:28 |  | 2025-12-14 | 2025-12-14 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-23 16:15:41 | Yes | Yes | 2025-12-16 15:14:41 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-03-24 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  |  | 2025-12-14 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:22:43 | Yes | Yes | 2025-12-14 17:09:37 |  |  | 2025-12-31 | 2025-12-06 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-06 17:35:31 | No | No |  |  |  |  | 2025-12-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-06 17:47:47 | No | No |  | 06-12-2025. Add AIRU5636w Sec.1#， 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MTRNM_2025 Capacity Expansion Ph3_EXP_BKK | MUBAN THARAKON | 2025-09-01 |  |  |  | 2025-09-01 | 2025-09-01 | 2025-09-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-01 18:03:40 | No | No |  |  |  | 2025-09-06 | 2025-09-09 | 2025-09-09 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:16:00 | Yes | Yes | 2025-09-30 10:16:00 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:46:13 | Yes | Yes | 2025-09-12 21:15:12 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:54 | Yes | Yes | 2025-10-06 18:45:16 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-12 22:25:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-01 18:01:13 | No | No |  | 01-09-2025. Add RRU5516 L18 Sec.6#， Replace RRU5516 L18 Sec.2#， 7#， Ant.12 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-10-02 09:31:24 | No | No
MWRIB_2025 Coverage Expansion Ph1_EXP_BKK | MAGNOLIAS WATERFRONT RESIDENCES ICONSIAM |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:10 | No | No |  |  |  | 2025-11-28 | 2025-11-09 | 2025-11-09 | V Contribute Co., Ltd | N/A | Closed | 2025-11-09 14:37:45 | Yes | Yes | 2025-11-09 14:37:45 |  | 2025-11-10 | 2025-11-10 | Chonradee Suwapan | Approved | Closed | 2025-11-12 15:53:26 | Yes | Yes | 2025-11-10 17:38:45 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 19:58:09 |  | 2025-11-10 | 2025-11-10 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-10 17:44:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-29 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-29 17:19:30 | No | No |  | 29-10-2025. Replace Ant.12 port Condo Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-10-30 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
MWRPM_2025 Capacity Expansion Ph2_EXP_BKK | MOTORWAY-RATTANAKOSIN 200 PI |  |  |  | 2025-08-18 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-19 | 2025-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-20 10:10:15 | Yes | Yes | 2025-08-26 14:18:38 |  | 2025-08-27 | 2025-08-27 | Muhamadnase Chesamae | Approved | Closed | 2025-09-16 13:40:08 | Yes | Yes | 2025-09-03 17:13:21 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:14 | Yes | Yes | 2025-09-22 22:05:14 |  | 2025-09-04 | 2025-09-04 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 15:00:44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-18 16:38:59 | No | No |  | 18-Aug-2025 Add AAU5636w S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
MYGMM_2025 Capacity Expansion Ph1_EXP_ER | Map Yang Porn Moo 6 | 2025-06-16 |  | Clear Alarm |  | 2025-06-30 | 2025-06-12 | 2025-06-13 | Teloneer Company Limited | N/A | Closed | 2025-06-13 16:39:07 | No | No |  |  |  | 2025-06-30 | 2025-06-13 | 2025-06-20 | Teloneer Company Limited | N/A | Closed | 2025-06-20 20:53:23 | Yes | Yes | 2025-06-28 20:21:48 |  | 2025-06-30 | 2025-06-29 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-07-25 09:36:20 | Yes | Yes | 2025-06-29 12:09:22 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-07-25 | 2025-07-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:18:03 | Yes | Yes | 2025-08-05 14:56:42 |  | 2025-06-30 | 2025-06-29 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-07-04 15:24:58 | Yes | Yes | 2025-06-29 20:28:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-05-29 |  | 2025-06-11 | Angsana Jituafua 84362665 | N/A | Closed | 2025-06-12 09:16:19 | No | No |  | **waiting on-service -- rep.rru3953 to rru5508 S2 #，Replace UBBPg3a#， New L26F1F5 + NR26 (New RRU5818) + Co Antenna S1 #，New L26F1F5 + NR26 (New RRU5818) + Co Antenna S2#，New L26F1F5 + NR26 (Co RRU5818) + Co Antenna S3 |  | 2025-06-20 | Reungsak Junkong 00927496 | N/A | Closed | 2025-06-20 16:23:09 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-06-13 | 2025-06-13 | Boonchot Boriwut | N/A | Closed | 2025-06-24 09:45:19 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MYSPM_2025 Capacity Expansion Ph1_EXP_ER | Map Yang Phon Soi 18 | 2025-06-16 |  | Install & Integrate |  | 2025-06-30 | 2025-06-20 | 2025-06-21 | Suwit poomthaisong(Teloneer Company Limited) | N/A | Closed | 2025-06-21 10:24:59 | No | No |  | Replace ANT Dual Band(HB) Sec.1#，2#，3 #， add New 3RRU5505 Sec.6#，7#，8 #， On-service 3G L1821 Sec.6#，7#，8 |  | 2025-06-30 | 2025-06-20 | 2025-06-21 | Teloneer Company Limited | N/A | Closed | 2025-06-21 13:48:42 | Yes | Yes | 2025-06-28 18:20:09 |  | 2025-06-30 | 2025-07-27 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-08-18 16:28:21 | Yes | Yes | 2025-07-27 12:31:43 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-08-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:15 | Yes | Yes | 2025-08-18 16:07:29 |  | 2025-06-30 | 2025-06-29 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-07-04 15:24:58 | Yes | Yes | 2025-06-29 20:28:51 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-21 |  | 2025-06-16 | Reungsak Junkong 00927496 | N/A | Closed | 2025-06-16 16:21:06 | No | No |  |  |  | 2025-06-16 | Reungsak Junkong 00927496 | N/A | Closed | 2025-06-16 16:21:06 | No | No |  | Replace ANT Dual Band(HB) Sec.1#，2#，3 #， add New 3RRU5505 Sec.6#，7#，8 #， On-service 3G L1821 Sec.6#，7#，8 |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-06-21 | 2025-06-21 | Boonchot Boriwut | N/A | Closed | 2025-06-24 09:45:19 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAAHM_2025 Capacity Expansion Ph4_EXP_ER | Nikom Amata Nakorn H | 2025-09-10 |  | Install & Integrate |  | 2025-09-30 | 2025-09-10 | 2025-09-10 | Teloneer Company Limited | N/A | Closed | 2025-09-10 11:05:05 | No | No |  |  |  | 2025-09-30 | 2025-09-10 | 2025-09-11 | Teloneer Company Limited | N/A | Closed | 2025-09-11 21:27:47 | Yes | Yes | 2025-09-11 21:27:48 |  | 2025-09-30 | 2025-09-22 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-10 10:16:30 | Yes | Yes | 2025-09-22 17:07:15 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:25 | Yes | Yes | 2025-11-06 17:33:18 |  | 2025-09-30 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2026-03-02 15:29:20 | Yes | Yes | 2025-10-08 10:48:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-10 |  | 2025-09-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-10 18:51:39 | No | No |  | **waiting on-service NR7 -- Replace RRU5508 to (RRU5516_900) + 4T4R S2 |  | 2025-09-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-11 17:18:09 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NATWM_2025 Capacity Expansion Ph6_EXP_ER | Na Talad Worakit | 2025-11-10 | THCP_Phet.S | Install & Integrate |  | 2025-11-30 | 2025-11-10 | 2025-11-10 | Teloneer Company Limited | N/A | Closed | 2025-11-10 15:58:13 | No | No |  |  |  | 2025-11-30 | 2025-11-10 | 2025-11-11 | Teloneer Company Limited | N/A | Closed | 2025-11-11 16:28:51 | Yes | Yes | 2025-11-12 16:04:22 |  | 2025-11-30 | 2025-11-12 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-14 16:34:33 | Yes | Yes | 2025-11-12 19:19:39 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-09 19:27:12 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:54 | Yes | Yes | 2025-11-04 09:01:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-10 17:51:35 | No | No |  | **waiting on-service L9/L7 -- Add UBBPg3a >Remove Antenna + (New AAU5768)+ Remove RRU5505 x 2 S3 >(Co AAU5768) + Remove RRU5505 x 2 S8 >New Sector M#，N (Co AAU5768) >New L0709 + 4T4R + (RRU5516_900) + (New Antenna LB) S1#，3 **before ulocell 36 --> S8 (RRU85 -->S8) |  | 2025-11-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-12 16:15:41 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NBKUB_2025 Capacity Expansion Ph3_EXP_BKK | Knightsbridge Kaset Society | [5 empty] | 2025-10-25 | 2025-10-25 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-15 | 2025-10-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-16 20:13:00 | Yes | Yes | 2025-10-27 10:30:17 |  | 2025-10-27 | 2025-10-27 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-26 16:08:44 | Yes | Yes | 2026-08-13 18:45:27 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 20:05:43 |  | 2025-12-18 | 2025-12-18 | Charuwan Limsaihua | Approved | Closed | 2026-03-12 09:22:14 | No | Yes | 2025-12-18 15:52:25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-15 16:39:07 | No | No |  | 15-Oct-2025 Add RRU5818 *1 SAB Add RRU5818 SC Add g2 Remove eb (follow Plan from mail ) 3/2 3/4 137 138#， 139 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
NBPUM_2025 Capacity Expansion Ph2_EXP_BKK | NORTH NIKHOM BANGPU |  |  |  | 2025-09-08 | 2025-09-15 | 2025-09-20 | 2025-09-20 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-26 14:02:11 | No | No |  |  | 2025-09-15 | 2025-09-18 | 2025-09-18 | 2025-09-19 | Teloneer Company Limited | N/A | Closed | 2025-09-19 17:44:46 | Yes | Yes | 2025-09-22 09:37:34 |  |  | 2025-09-23 | Apichart Kampuang | Approved | Closed | 2025-10-10 17:28:56 | Yes | Yes | 2026-02-23 10:16:41 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 19:32:03 |  | 2025-08-16 | 2025-08-31 | Khathahat Sitthihong(Teloneer Company Limited) | Approved | Closed | 2025-10-10 17:28:56 | No | Yes | 2025-08-16 15:54:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-09 18:50:04 | No | No |  | 9-Sep-2025 Add RRU5516 (700900) S2 g2 Add Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-19 |  | N/A | Not assigned |  | No | No
NBPUM_2025 Capacity Expansion Ph6_EXP_BKK | NORTH NIKHOM BANGPU | [5 empty] | 2025-12-16 | 2025-12-16 | Narongsak wanichachiwa | N/A | Closed | 2025-12-23 09:27:43 | No | No |  |  |  | 2025-12-12 | 2025-12-09 | 2025-12-14 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-12-14 15:55:24 | Yes | Yes | 2025-12-14 15:56:17 |  |  | 2025-12-18 | OATTAPAN AUTTAHON | Approved | Closed | 2026-01-09 17:03:57 | Yes | Yes | 2026-02-21 08:54:57 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-15 12:14:32 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  |  | 2025-12-31 | 2025-12-09 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-12-09 16:39:09 | No | No |  |  |  |  | 2025-12-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-09 18:04:12 | No | No |  | 09-12-2025. Add AIRU5636w Sec.7#， 8#， Replace UBBPd6 to UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NBRCB_2025 Capacity Expansion NW Modernization_EXP_BKK | NOBLE RECOLE SUKHUMVIT 19 |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:29:00 | No | No |  |  | 2026-04-07 | 2026-04-21 | 2026-04-07 | 2026-04-21 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-21 18:30:52 | Yes | Yes | 2026-04-22 10:13:27 |  | 2026-06-12 | 2026-06-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-03 09:26:53 | Yes | Yes | 2026-06-12 15:11:22 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-07-14 22:53:08 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-04-06 14:49:55 | No | No |  | 6-Apr-2026 Add RRU3962 Sector A Remove RRU3826 Follow mail on 1T1R Follow before |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NBRPM_2025 Capacity Expansion Ph6_EXP_ER | Na Burapa University | 2025-11-26 | THCP_Phet.S | Install & Integrate |  | 2025-11-30 | 2025-11-26 | 2025-11-26 | Teloneer Company Limited | N/A | Closed | 2025-11-26 11:34:45 | No | No |  |  |  | 2025-11-30 | 2025-11-26 | 2025-11-27 | Teloneer Company Limited | N/A | Closed | 2025-11-27 14:33:31 | Yes | Yes | 2025-11-30 16:24:38 |  | 2025-12-15 | 2025-11-30 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-02 14:49:44 | Yes | Yes | 2025-11-30 21:12:04 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 19:33:16 |  | 2025-11-30 | 2025-11-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-25 18:20:01 | Yes | Yes | 2025-11-24 17:35:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-26 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-11-26 17:11:46 | No | No |  | 26-Nov-2025 Replace 1RRU5508 to 5516 sector 2 L09 #， Add 2RRU5505 sector 2&3 L1821 #， Add 1UBBPg2 |  | 2025-12-01 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-01 17:57:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NC21M_2025 Coverage Expansion Ph2_EXP_BKK | SOI NUAN CHAN 21 |  |  |  | 2025-09-18 | 2025-09-25 | 2025-09-30 | 2025-09-30 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-30 10:53:47 | No | No |  |  | 2025-09-25 | 2025-09-27 | 2025-09-26 | 2025-09-29 | Teloneer Company Limited | N/A | Closed | 2025-09-29 09:50:29 | Yes | Yes | 2025-09-29 10:16:25 |  |  | 2025-09-30 | Apichart Kampuang | Approved | Closed | 2025-10-10 14:08:42 | Yes | Yes | 2025-09-30 10:52:46 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:25 | Yes | Yes | 2025-11-06 17:39:29 |  |  | 2025-08-14 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-14 17:27:47 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-20 16:42:56 | No | No |  | 20-09-2025. Add RRU3953#， Replace Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-29 |  | N/A | Not assigned |  | No | No
NCFMM_2025 Capacity Expansion Ph3_EXP_BKK | NAM CHAI 999 FRESH MARKET | 2025-09-04 |  |  |  | 2025-09-04 | 2025-09-12 | 2025-09-12 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-26 | 2025-09-04 | 2025-09-05 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:16:15 | Yes | Yes | 2025-09-30 10:16:15 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2026-03-11 16:32:23 | Yes | Yes | 2025-09-13 20:06:47 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-12-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 19:34:28 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-14 12:59:57 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-04 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-04 18:31:27 | No | No |  | 04-09-2025. Add AIRU5636w Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
NDP1M_2025 Capacity Expansion NW Modernization_EXP_BKK | NGAMDUPLEE 1 |  |  |  | 2026-03-02 | 2026-03-09 | 2026-03-02 | 2026-03-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-02 16:43:53 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-19 | 2026-02-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-25 10:23:17 | Yes | Yes | 2026-02-25 13:12:53 |  | 2026-03-02 | 2026-03-02 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-03 09:27:15 | Yes | Yes | 2026-03-02 16:45:29 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-20 | 2026-08-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-03 09:29:42 | Yes | Yes | 2026-08-01 21:33:19 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-31 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-31 20:46:10 | No | No |  | 31-Jan-2026 Add RRU3953 S1 S2 S3 Add RRU5526 S2 S3 Remove RRU3962 *4 s7 RRU3962 *2 Replace Ant 8 port S2 Co 18002100 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NGETM_2025 Capacity Expansion Ph7_EXP_ER | Ban Nong E-Thone | 2025-12-09 |  | Install & Integrate |  | 2025-12-31 | 2025-12-09 | 2025-12-09 | Teloneer Company Limited | N/A | Closed | 2025-12-09 13:51:04 | No | No |  |  |  | 2025-12-31 | 2025-12-09 | 2025-12-10 | Teloneer Company Limited | N/A | Closed | 2025-12-10 12:14:52 | Yes | Yes | 2025-12-13 13:38:20 |  | 2025-12-31 | 2025-12-13 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:28:08 | Yes | Yes | 2025-12-13 16:44:30 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 14:20:53 |  | 2025-12-31 | 2025-12-09 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:36:07 | Yes | Yes | 2025-12-09 11:30:21 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-09 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-12-09 18:33:04 | No | No |  | Add UBBPg3a + Replace Antenna (Dualband)_NGETM_H_1 Replace Antenna (Dualband)_NGETM_H_2 Replace Antenna (Dualband)_NGETM_H_8 Replace Antenna (Co Antenna)_NGETM_L_1 Replace Antenna (Co Antenna)_NGETM_L_2 New L26F5 + NR26 (New AAU5636w)_NGETM_N_8 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_NGETM_L_8 |  | 2025-12-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-11 18:18:21 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NIBKA_2025 Capacity Expansion Ph5_EXP_BKK | NICHE ID BANGKHAE PHASE 1 |  |  |  |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-01 09:34:25 | No | No |  |  |  | 2025-12-28 | 2025-12-10 | 2025-12-12 | V Contribute Co., Ltd | N/A | Closed | 2025-12-12 11:23:24 | Yes | Yes | 2025-12-12 11:23:25 |  | 2025-12-07 | 2025-12-07 | Chonradee Suwapan | Approved | Closed | 2025-12-12 14:57:39 | Yes | Yes | 2026-01-13 22:35:34 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 19:48:31 |  | 2025-12-07 | 2025-12-07 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-12-07 23:28:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-26 17:33:26 | No | No |  | 26-11-2025. Add UBBPg3a#， RRU5818#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NIBKA_DPU40_OPM30_Replacement_BKK | NICHE ID BANGKHAE PHASE 1 |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-26 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 15:21:43 | Yes | Yes | 2025-12-26 15:21:43 |  | 2026-01-14 | 2026-01-14 | Chonradee Suwapan | Approved | Closed | 2026-01-19 15:45:52 | Yes | Yes | 2026-01-17 18:07:18 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-20 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-01-14 | 2026-01-14 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-14 20:43:33 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-26 | Supatong Juntorn WX1461874 | N/A | Closed | 2025-12-26 16:34:13 | No | No |  | 26-Dec-2025 Replace DPU40 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
NIMCB_2025 Coverage Expansion Ph1_EXP_BKK | NICHE MONO CHAENGWATTHANA |  |  |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-10-22 | 2025-10-24 | V Contribute Co., Ltd | N/A | Closed | 2025-10-24 10:01:17 | Yes | Yes | 2025-10-24 10:01:17 |  | 2025-11-01 | 2025-11-01 | Chonradee Suwapan | Approved | Closed | 2025-11-05 16:33:10 | Yes | Yes | 2025-11-01 19:59:54 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:25 | Yes | Yes | 2025-11-06 17:51:04 |  | 2025-11-01 | 2025-11-01 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-01 20:06:51 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-21 17:29:57 | No | No |  | 21-10-2025. Replace Ant.12 port Condo Sec.A#， B#， C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-22 |  | N/A | Not assigned |  | No | No
NISTA_2025 Capacity Expansion NW Modernization_EXP_BKK | NIST INTERNATIONAL SCHOOL_HUB BUILDING |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-14 | 2026-03-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-15 10:43:42 | Yes | Yes | 2026-03-18 09:50:29 |  | 2026-03-30 | 2026-03-30 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:35:56 | Yes | Yes | 2026-04-20 16:26:00 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 19:59:44 |  |  | 2026-02-28 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-21 16:37:44 | No | No |  | 21-Feb-2026 Add RRU5526 SA SB Remove RRU3962 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NISTA_2025 Capacity Expansion Ph5_EXP_BKK | NIST INTERNATIONAL SCHOOL_HUB BUILDING |  |  |  | 2025-12-13 | 2025-12-20 | 2025-12-19 | 2025-12-19 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-12-19 13:10:27 | No | No |  |  |  | 2025-11-20 | 2025-12-23 | 2025-12-23 | Teloneer Company Limited | N/A | Closed | 2025-12-23 18:20:36 | Yes | Yes | 2025-12-24 09:00:55 |  |  | 2025-12-24 | Apichart Kampuang | Approved | Closed | 2026-01-07 16:05:42 | Yes | Yes | 2025-12-24 17:37:40 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-09 19:49:45 |  | 2025-12-12 | 2025-12-12 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:22:43 | Yes | Yes | 2025-12-13 09:09:12 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-13 18:09:14 | No | No |  | 13-12-2025. Add RRU5818 Sec.A#， Replace UBBPd5 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NIVRB_2025 Coverage Expansion Ph2_New_BKK | Nivati Residence Thonglor 23 | [5 empty] | 2025-12-25 | 2025-12-25 | Akhom Srinara | N/A | Closed | 2025-12-25 10:07:39 | No | No |  |  |  | 2025-12-19 | 2025-12-25 | 2025-12-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-26 18:09:14 | Yes | Yes | 2026-01-06 13:33:07 |  | 2026-01-10 | 2026-01-13 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-01-13 15:52:32 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-10 | 2026-01-10 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-10 19:25:20 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-19 19:04:00 | No | No |  | 19-Dec-2205 New small cell Add RRU3962 S1 S2 d5=2 Add Ant 12 port No Ret *4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
NK12M_2025 Capacity Expansion NW Modernization_EXP_BKK | NARATHIWAT RATNAKARIN SOI 12_3G2100 | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  | 2026-02-09 | 2026-02-28 | 2026-02-11 | 2026-02-12 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-12 17:19:17 | Yes | Yes | 2026-02-12 17:20:23 |  | 2026-02-13 | 2026-02-13 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-03-10 16:56:42 | Yes | Yes | 2026-02-13 11:23:58 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:54:02 |  | 2026-02-06 | 2026-03-06 | Pariyakorn Jearwarakul | Approved | Closed | 2026-07-20 10:33:26 | Yes | Yes | 2026-03-24 08:21:19 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-10 15:45:07 | No | No |  | 10-Feb-2026 Add RRU5516 S1 S2 S3 Remove RRU3953 S1 S2 S3 Replace Ant 4 port S1 Replace Ant 8port S2 S3 Co 1800900 09-02-2026. Replace RRU5507 to AAU5768 Sec.1#， Add UBBPg2#， UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NK15M_2025 Capacity Expansion NW Modernization_EXP_BKK | NARATHIWAT RATNAKARIN SOI 15 |  |  |  |  | 2026-01-23 | 2026-01-23 | 2026-01-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-28 | 2026-02-25 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 14:46:40 | Yes | Yes | 2026-03-24 14:46:41 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:42:08 | Yes | Yes | 2026-04-02 11:58:09 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:54:21 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-05 22:28:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-23 18:46:48 | No | No |  | 23-Jan-2026 Add AAU5768 S1 S3 Remove RRU5502 *2 S1 RRU3962 *1 RRU5516 * S3 Add RRU5526 Remove RRU3962*2 sector 2 Replace Ant 8port S2 Add g3a=3 Remove g2 eb d6 ยังไม่มี Cell DMM |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NK15M_2025 Capacity Expansion Ph2_EXP_BKK | NARATHIWAT RATNAKARIN SOI 15 | 2025-08-14 |  |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-14 18:26:57 | No | No |  |  |  | 2025-08-29 | 2025-08-25 | 2025-08-26 | V Contribute Co., Ltd | N/A | Closed | 2025-08-26 11:02:56 | Yes | Yes | 2025-08-26 11:04:24 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-09-08 16:45:13 | Yes | Yes | 2025-09-03 21:08:14 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:53 | Yes | Yes | 2025-10-06 19:10:28 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-03 20:54:26 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No |  | 14-Aug-2025 ***Pending Add RRU3962 S8 1.2 //Add RRU5516 (18002100 )S3 Remove RRU3962 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-13 |  | N/A | Not assigned |  | No | No
NK15M_2025 Capacity Expansion Ph6_EXP_BKK | NARATHIWAT RATNAKARIN SOI 15 | 2025-12-04 |  |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-04 18:19:04 | No | No |  |  |  | 2025-12-31 | 2025-12-18 | 2025-12-18 | V Contribute Co., Ltd | N/A | Closed | 2025-12-18 19:50:57 | Yes | Yes | 2025-12-18 19:50:58 |  | 2025-12-10 | 2025-12-10 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:23:02 | Yes | Yes | 2026-02-03 09:56:57 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:54:40 |  | 2025-12-10 | 2025-12-10 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-10 20:37:51 |  |  | 2025-12-31 | 2025-12-04 | V Contribute Co., Ltd | N/A | Closed | 2025-12-04 14:31:44 | No | No |  |  |  |  | 2025-12-04 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-12-04 19:05:46 | No | No |  | 2025-12-04_Add AAU5636w Sector 6#， Replace UBBPd6 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKB3M_2025 Capacity Expansion Ph5_EXP_BKK | NIKOM LADKRABANG PHASE3 | 2025-12-11 |  |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-15 18:16:03 | No | No |  |  |  | 2025-12-28 | 2025-12-18 | 2025-12-19 | V Contribute Co., Ltd | N/A | Closed | 2025-12-19 12:06:58 | Yes | Yes | 2025-12-19 12:06:58 |  | 2025-12-17 | 2025-12-17 | Chonradee Suwapan | Approved | Closed | 2026-03-10 16:24:13 | Yes | Yes | 2026-01-15 16:55:27 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-03-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:54:59 |  | 2025-12-17 | 2025-12-17 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-17 18:28:10 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-11 17:30:08 | No | No |  | 11-12-2025. Replace UBBPeb to UBBPg3#， AIRU5614 to AIRU5826g Sec.2#， Add AIRU5636w Sec.6#， Ant.12 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKB3M_2025 Capacity Expansion Ph7_EXP_BKK | NIKOM LADKRABANG PHASE3 |  |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2026-04-23 14:25:10 | No | No |  |  |  | 2026-02-28 | 2026-05-10 | 2026-05-20 | V Contribute Co., Ltd | N/A | Closed | 2026-05-20 11:46:59 | Yes | Yes | 2026-05-20 11:47:00 |  | 2026-03-25 | 2026-03-25 | Chonradee Suwapan | Approved | Closed | 2026-04-23 10:52:27 | Yes | Yes | 2026-03-25 21:52:30 | 1.Page 7#，In SOW remove card must be UBBPg3. 2.Page 7#，In SOW need to fill reposition activity. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-28 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-25 | 2026-03-25 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-25 21:56:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-20 18:47:38 | No | No |  | 2026-02-20_Replace Blade AAU to AAU5636w#， Add Ant 4 port Sector 2#， Add AAU5636w Sector 7#， Replace AAU5614 to Balde AAU Sector 3#， Replace UBBPg3 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKLAM_2025 Capacity Expansion Ph6_EXP_ER | Nong Kla | 2025-11-12 | Thcp_adirek.kh | Install & Integrate |  | 2025-11-30 | 2025-11-11 | 2025-11-11 | Teloneer Company Limited | N/A | Closed | 2025-11-11 14:11:30 | No | No |  |  |  | 2025-11-30 | 2025-11-11 | 2025-11-12 | Teloneer Company Limited | N/A | Closed | 2025-11-12 11:43:18 | Yes | Yes | 2025-11-16 21:27:40 |  | 2025-11-30 | 2025-11-24 | Thanakit Chaleechai | Approved | Closed | 2025-11-25 18:20:45 | Yes | Yes | 2025-11-24 15:17:32 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 19:52:10 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:54 | Yes | Yes | 2025-11-04 09:05:53 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-12 18:50:54 | No | No |  | Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 220 + Remove RRU5513 x 1 NKLAM_H_3 Remove Antenna + (Co AAU5768) + Main Dir = 220 + Remove RRU5505 x 2 NKLAM_H_8 New Sector M (Co AAU5768) + Main Dir = 220 NKLAM_H_M New Sector N (Co AAU5768) + Main Dir = 220 NKLAM_H_N |  | 2025-11-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-12 18:50:54 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKLHM_2025 Capacity Expansion Ph6_EXP_ER | Na Kluea Moo 6 | 2025-11-22 | thcp_adirek.k | Clear Pending |  | 2025-11-30 | 2025-11-15 | 2025-11-15 | Teloneer Company Limited | N/A | Closed | 2025-11-15 16:04:44 | No | No |  |  |  | 2025-11-30 | 2025-11-13 | 2025-11-22 | Teloneer Company Limited | N/A | Closed | 2025-11-22 11:03:57 | Yes | Yes | 2025-11-23 18:19:06 |  | 2025-11-30 | 2025-11-25 | Thanakit Chaleechai | Approved | Closed | 2025-11-26 10:53:32 | Yes | Yes | 2025-11-25 20:13:01 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 19:53:23 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:54 | Yes | Yes | 2025-11-04 09:10:19 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-15 | Reungsak Junkong 00927496 | N/A | Closed | 2025-11-15 18:32:04 | No | No |  | "*** Waiting On-service L09/L07 -- Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R H_3 New L0709 + 4T4R + (RRU5516_900) + (New Antenna LB) L_1 New L0709 + 4T4R + (RRU5516_900) + (New Antenna LB) L_2 New L0709 + 4T4R + (RRU5516_900) + (New Antenna LB) L_3 " |  | 2025-11-17 | Reungsak Junkong 00927496 | N/A | Closed | 2025-11-17 15:35:27 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKLLM_2025 Capacity Expansion Ph6_EXP_ER | Nong Khla Mai - Klong lek | 2025-11-10 | Thcp_adirek.kh | Install & Integrate |  | 2025-11-30 | 2025-11-10 | 2025-11-10 | Teloneer Company Limited | N/A | Closed | 2025-11-10 10:47:01 | No | No |  |  |  | 2025-11-30 | 2025-11-10 | 2025-11-11 | Teloneer Company Limited | N/A | Closed | 2025-11-11 14:56:32 | Yes | Yes | 2025-11-13 22:18:29 |  | 2025-11-30 | 2025-11-24 | Thanakit Chaleechai | Approved | Closed | 2025-11-25 18:20:45 | Yes | Yes | 2025-11-24 14:49:38 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:32 | Yes | Yes | 2026-01-09 19:54:36 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:54 | Yes | Yes | 2025-11-04 09:20:03 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-08 | Reungsak Junkong 00927496 | N/A | Closed | 2025-11-08 18:07:29 | No | No |  | **waiting on-service L7/L9 -- Replace Antenna (Dualband) Sec.2#，3 & New L0709 + 4T4R + (RRU5516_900) + (Co Antenna) Sec.2#，3 |  | 2025-11-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-12 16:15:41 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKRIM_2025 Capacity Expansion Ph6_EXP_SR | Yaek Nong Khri |  |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | Teloneer Company Limited | N/A | Closed | 2025-12-08 13:44:07 | No | No |  |  |  | 2025-12-08 | 2025-12-08 | 2025-12-12 | Teloneer Company Limited | N/A | Closed | 2025-12-12 10:00:18 | Yes | Yes | 2025-12-12 10:02:20 |  | 2025-12-08 | 2025-12-08 | Sirichai Saetang | Approved | Closed | 2026-01-09 09:34:32 | Yes | Yes | 2025-12-08 19:39:20 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 19:57:00 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-12 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-08 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-12-08 18:09:37 | No | No |  | 8 Dec 2025 Add AAU |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKSHM_2025 Capacity Expansion Ph6_EXP_ER | Naklue Soi Sibhok | 2025-11-14 | thcp_Phet.sa | Install & Integrate |  | 2025-11-30 | 2025-11-14 | 2025-11-14 | Teloneer Company Limited | N/A | Closed | 2025-11-14 14:29:30 | No | No |  |  |  | 2025-11-30 | 2025-11-14 | 2025-11-14 | Teloneer Company Limited | N/A | Closed | 2025-11-14 17:20:48 | Yes | Yes | 2025-11-15 15:14:51 |  | 2025-11-30 | 2025-11-15 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-19 13:29:19 | Yes | Yes | 2025-11-15 18:47:44 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:59 | Yes | Yes | 2026-03-20 12:02:13 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:54 | Yes | Yes | 2025-11-04 09:22:26 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-14 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-14 18:13:10 | No | No |  | Replace Antenna (Dualbeam) H_1 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna H_6 |  | 2025-11-14 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-14 18:13:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKSNM_2025 Capacity Expansion Ph6_EXP_ER | Nakluae soi16/1 | 2025-11-15 | THCP_wachira.s | Clear Pending |  | 2025-11-30 | 2025-11-07 | 2025-11-07 | Teloneer Company Limited | N/A | Closed | 2025-11-07 17:36:23 | No | No |  |  |  | 2025-11-30 | 2025-11-17 | 2025-11-17 | Teloneer Company Limited | N/A | Closed | 2025-11-17 13:54:22 | Yes | Yes | 2025-11-19 19:19:05 |  | 2025-11-30 | 2025-11-22 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-25 18:20:45 | Yes | Yes | 2025-11-22 06:18:50 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 19:58:13 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:54 | Yes | Yes | 2025-11-04 09:24:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-07 | Reungsak Junkong 00927496 | N/A | Closed | 2025-11-07 17:57:49 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R Sec-.6 #，Replace RRU (RRU5516_900) + 4T4R Sec.2 |  | 2025-11-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-07 17:57:49 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NL20M_2025 Coverage Expansion Ph2_EXP_BKK | NAVANAKORN 20 | 2025-08-01 |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-01 17:31:33 | No | No |  |  |  | 2025-08-22 | 2025-08-12 | 2025-08-13 | V Contribute Co., Ltd | N/A | Closed | 2025-08-13 09:53:51 | Yes | Yes | 2025-08-13 09:56:20 |  | 2025-08-14 | 2025-08-14 | Chonradee Suwapan | Approved | Closed | 2025-09-30 15:29:15 | Yes | Yes | 2025-08-14 20:59:52 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:53 | Yes | Yes | 2025-10-06 19:16:54 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:55:32 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-01 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-01 17:11:01 | No | No |  | 1-Aug-2025 Add RRU3953 S3 Replace Ant. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
NLK5M_2025 Capacity Expansion Ph2_EXP_BKK | NILADKRABANG 5 | 2025-08-23 |  |  |  | 2025-08-23 | 2025-08-23 | 2025-08-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-23 17:52:43 | No | No |  |  |  | 2025-08-31 | 2025-08-27 | 2025-08-28 | V Contribute Co., Ltd | N/A | Closed | 2025-08-28 10:38:26 | Yes | Yes | 2025-08-28 10:39:50 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2026-06-29 16:19:56 | Yes | Yes | 2025-09-06 19:16:14 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 20:00:40 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:28 | No | Yes | 2025-09-06 19:23:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-23 18:45:46 | No | No |  | 23-08-2025. Add RRU5516 L18#， Ant.8 port Sec.6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-21 |  | N/A | Not assigned |  | No | No
NLYCM_2025 Capacity Expansion NW Modernization_EXP_BKK | NANG LYCHEE RD._3G2100 |  |  |  | 2026-01-28 | 2026-01-28 | 2026-02-17 | 2026-02-17 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-08 22:43:15 | No | No |  |  | 2026-01-28 | 2026-01-28 | 2026-01-29 | 2026-02-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-18 12:19:14 | Yes | Yes | 2026-02-18 12:20:48 |  | 2026-02-09 | 2026-02-09 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-23 15:57:48 | Yes | Yes | 2026-02-18 13:30:20 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:55:56 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:33:34 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-21 19:27:06 | No | No |  | 28-01-2026 On DMM sector2#， and fix vswr 07/09 port1#，rru 3953 #2 sector2 and On DMM sector 2 Done 27 Jan 2026 ***Replace RRU5526 sector1 replace AAU5768 sector3 remove RRU VSWR s1 900 21-01-2026 Replace rru3961 to 5526 sector 1 and ADD CARD UBBP g2 SLOT 0 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NMS2A_2025 Capacity Expansion Ph7_EXP_BKK | NICE MANSION 2 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:24:51 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-02-05 | 2026-02-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-06 12:40:15 | Yes | Yes | 2026-02-11 10:17:35 | SQC Close | 2026-05-20 | 2026-05-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-06 10:19:36 | Yes | Yes | 2026-05-20 11:37:51 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-06 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:46:07 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-30 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-04-30 17:31:16 | No | No |  | 30-Apr-26 Add AAU5636w SC 29-Apr-2026 Add ***Pending Waitting core optic Add AAU5636w Sector C //Add AAU5636w Sector B Done (ยุบเฟส 8 มาทำเฟส 7 Sector B ) 27-01-2026. ***Need AAU5636w Sec.C //Add UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NN03M_2025 Coverage Expansion Ph2_EXP_BKK | NAVANAKORN 3 CO-TOWER | 2025-08-04 |  | Install & Integrate | 2025-08-04 | 2025-08-31 | 2025-09-25 | 2025-09-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2025-09-26 10:52:18 | No | No |  |  |  | 2025-08-31 | 2025-09-26 | 2025-09-26 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2025-09-26 10:52:18 | Yes | Yes | 2025-09-26 10:51:46 |  | 2025-08-08 | 2025-09-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2025-09-08 15:16:13 | Yes | Yes | 2025-09-03 17:32:30 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:53 | Yes | Yes | 2025-10-06 19:19:32 |  | 2025-08-20 | 2025-08-20 | Sattaya Parakij | Approved | Closed | 2025-09-03 22:43:51 | No | Yes | 2025-08-20 23:48:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-04 18:25:31 | No | No |  | 4-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-12 | Jia Rui 80023782 | N/A | Closed | 2025-09-15 15:03:48 | No | No
NNMIM_2025 Coverage Expansion Ph2_EXP_BKK | NORTHERN NAMAI | 2025-08-02 |  |  |  | 2025-08-02 | 2025-08-02 | 2025-08-02 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-02 17:51:49 | No | No |  |  |  | 2025-08-22 | 2025-08-03 | 2025-08-06 | V Contribute Co., Ltd | N/A | Closed | 2025-08-06 11:34:28 | Yes | Yes | 2025-08-06 11:36:11 |  | 2025-08-19 | 2025-08-19 | Chonradee Suwapan | Approved | Closed | 2025-08-25 17:35:18 | Yes | Yes | 2025-08-19 23:16:12 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 19:04:16 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:55:46 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-02 17:51:18 | No | No |  | 2-Aug-2025 Add RRU3953 S1 S2 S3 Replace Ant S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
NNSQP_2025 Capacity Expansion NW Modernization_EXP_BKK | NANA SQUARE |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:24:51 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-19 | 2026-03-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-19 18:22:34 | Yes | Yes | 2026-03-25 09:49:11 |  | 2026-06-04 | 2026-06-04 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-05 16:07:58 | Yes | Yes | 2026-06-04 11:06:42 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:33:48 |  |  | 2026-02-28 | 2026-02-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-24 18:13:07 | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 24-Feb-2026 ***Pending add GPS ////Replace BBU5900 UMPTg2 Add g2 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NOGWM_2025 Capacity Expansion Ph2_EXP_ER | Nong Wa Soi 1 |  |  | Install & Integrate |  | 2025-09-30 | 2025-09-03 | 2025-09-04 | Teloneer Company Limited | N/A | Closed | 2025-09-04 17:35:51 | No | No |  |  |  | 2025-07-31 | 2025-09-01 | 2025-09-05 | Teloneer Company Limited | N/A | Closed | 2025-09-05 10:24:13 | Yes | Yes | 2025-09-12 00:10:54 |  | 2025-07-31 | 2025-09-17 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-03 16:29:22 | Yes | Yes | 2025-09-17 15:53:01 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-09-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:53 | Yes | Yes | 2025-10-06 19:22:14 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:26:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-04 |  | 2025-09-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-03 19:29:21 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R S2 #，Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R S4 #，New L0709 + NR07 + 4T4R + Add RRU5516_900 x 1 + (New Antenna LB) S2 |  | 2025-09-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-03 19:29:21 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPDNM_2025 Capacity Expansion Ph4_EXP_ER | BanNongPaiKlangDon moo2 | 2025-09-05 |  | Install & Integrate |  | 2025-09-30 | 2025-09-05 | 2025-09-07 | Teloneer Company Limited | N/A | Closed | 2025-09-07 16:11:17 | No | No |  |  |  | 2025-09-30 | 2025-09-06 | 2025-09-09 | Teloneer Company Limited | N/A | Closed | 2025-09-11 22:21:41 | Yes | Yes | 2025-09-11 22:21:42 |  | 2025-09-30 | 2025-10-06 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-10 10:16:30 | Yes | Yes | 2025-10-06 17:38:41 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 18:08:09 |  | 2025-09-30 | 2025-10-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-03-02 15:29:20 | Yes | Yes | 2025-10-08 10:53:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-09 |  | 2025-09-05 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-05 18:40:56 | No | No |  | **waiting on-service NR7 -- Replace 1RRU5508 to (RRU5516_900) + Co NR07 + 4T4R S1 #，Co NR07 S2#，3 |  | 2025-09-09 | Reungsak Junkong 00927496 | N/A | Closed | 2025-09-09 18:20:54 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPSCB_2025 Capacity Expansion NW Modernization_EXP_BKK | NATURAL PLACE SUITE CONDOMINIUM |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:24:51 | No | No |  |  | 2026-03-31 | 2026-03-31 | 2026-03-23 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:40:56 | Yes | Yes | 2026-04-03 09:42:17 |  | 2026-04-27 | 2026-04-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-14 16:56:41 | Yes | Yes | 2026-05-04 10:36:52 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-12-29 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:34:02 |  |  | 2026-03-31 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-09 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-03-09 18:29:14 | No | No |  | 2026-03-09_Replace RRU3962 to RRU5507 Sector A#，B **Sector A Config 1T1R |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPSCB_2025 Coverage Expansion Ph1_EXP_BKK | NATURAL PLACE SUITE CONDOMINIUM | [5 empty] | 2025-10-17 | 2025-10-17 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-18 | 2025-10-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-18 16:52:53 | Yes | Yes | 2025-10-29 15:36:44 |  | 2025-10-31 | 2025-10-31 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 15:52:18 | Yes | Yes | 2025-10-31 14:30:31 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 20:16:18 |  | 2025-10-31 | 2025-10-31 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-31 14:52:29 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-18 17:48:27 | No | No |  | 18-10-2025. Replace Ant.12 port Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-10-16 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
NPTPB_2025 Coverage Expansion Ph1_EXP_BKK | NICHE PRIDE TAOPOON-INTERCHANGE |  |  |  |  | 2025-10-21 | 2025-10-21 | 2025-10-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-10-31 | 2025-10-30 | 2025-10-31 | V Contribute Co., Ltd | N/A | Closed | 2025-10-31 16:24:53 | Yes | Yes | 2025-10-31 16:24:54 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-03 20:59:11 | Yes | Yes | 2025-10-30 20:36:16 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-02 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 18:11:57 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-30 20:50:44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-20 17:45:00 | No | No |  | 20-10-2025. Replace Ant.12 port Condo Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
NRCCM_2025 Capacity Expansion Ph2_EXP_BKK | NIRAN CITY CONDO |  |  |  | 2025-08-19 | 2025-09-30 | 2025-10-21 | 2025-10-21 | Akhom Srinara | N/A | Closed | 2025-11-18 09:34:39 | No | No |  |  |  |  | 2025-10-21 | 2025-10-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-28 14:05:39 | Yes | Yes | 2025-11-03 09:42:31 |  | 2025-11-09 | 2026-02-02 | Muhamadnase Chesamae | Approved | Closed | 2026-05-13 11:44:54 | Yes | Yes | 2026-02-02 18:08:28 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-05-17 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-11-15 | 2025-11-15 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:25:38 | No | Yes | 2025-11-15 11:43:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-17 17:35:25 | No | No |  | 17-10-2025. Add UBBPg2#， Replace RRU5516 L900#， Ant.12 port Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | tower load รอสรุป Solution |  |  | Krittee Chamboot 00319410 | N/A | Not assigned |  | No | No
NRK3M_2025 Capacity Expansion Ph6_EXP_BKK | SOI NARAI RAK 3 | 2025-12-03 |  |  |  | 2025-12-31 | 2025-12-04 | 2025-12-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-04 18:19:04 | No | No |  |  |  | 2025-12-31 | 2025-12-18 | 2025-12-19 | V Contribute Co., Ltd | N/A | Closed | 2025-12-19 14:09:32 | Yes | Yes | 2025-12-19 14:09:32 |  | 2025-12-08 | 2025-12-08 | Chonradee Suwapan | Approved | Closed | 2025-12-19 17:39:21 | Yes | Yes | 2026-01-13 22:50:21 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-15 12:23:09 |  | 2025-12-08 | 2025-12-08 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-08 21:27:26 |  |  | 2025-12-31 | 2025-12-03 | V Contribute Co., Ltd | N/A | Closed | 2025-12-03 15:12:26 | No | No |  |  |  |  | 2025-12-03 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-03 17:11:00 | No | No |  | 03-12-2025. Add AIRU5636w Sec.2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NRRTK_2025 Coverage Expansion Ph1_New_SR | Na Rong Rian Ban Tha Ko |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | Nattawoot Suwan | N/A | Closed | 2025-11-11 11:27:17 | No | No |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Teloneer Company Limited | N/A | Closed | 2025-11-06 16:50:17 | Yes | Yes | 2025-11-07 10:21:13 |  | 2025-11-11 | 2025-11-11 | Nattawoot Suwan | Approved | Closed | 2025-12-11 10:27:05 | Yes | Yes | 2025-11-11 11:27:45 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:20 | Yes | Yes | 2025-12-01 20:17:31 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-11-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-06 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-11-06 15:41:23 | No | No |  | BBU3910#，UBBPd5*3 S1 >RRU3826x2> Ant 4 port S2 > RRU3826x2> Ant 4 port S3 > RRU3826x2> Ant 4 port Test cross#，cell#， external alarm done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-10-06 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-10-06 16:44:25 | Yes | Yes | 2025-10-06 15:54:10 |  |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-05 |  | N/A | Not assigned |  | No | No
NSNRS_2025 Capacity Expansion Ph6_EXP_SR | Na San Railway Station |  |  |  | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | Teloneer Company Limited | N/A | Closed | 2025-12-09 13:28:09 | No | No |  |  |  | 2025-12-08 | 2025-12-09 | 2025-12-09 | Teloneer Company Limited | N/A | Closed | 2025-12-09 18:20:31 | Yes | Yes | 2025-12-10 14:53:51 |  | 2025-12-11 | 2025-12-11 | Nattawoot Suwan | Approved | Closed | 2026-01-09 09:34:32 | Yes | Yes | 2025-12-19 11:23:07 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 20:15:21 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-12 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-09 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-12-09 17:39:08 | No | No |  | 9 Dec 2025 Add AAU5636w sector4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-03-31 | Boonchot Boriwut | N/A | Closed | 2026-03-31 11:34:14 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NSW3M_2025 Capacity Expansion NW Modernization_EXP_BKK | NANA SQUARE-SOI SUKHUMVIT 3 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:24:51 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-19 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:42:24 | Yes | Yes | 2026-04-01 10:35:16 |  | 2026-04-17 | 2026-04-17 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-05-26 16:27:26 | Yes | Yes | 2026-04-17 14:00:18 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:34:16 |  |  | 2026-02-28 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-24 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-24 19:40:41 | No | No |  | 24-Feb-2026 Add AAU5768 S2 S3 Remove RRU5507 *5#，4 Add g3a=2 Remove d5 d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NTC1M_2025 Coverage Expansion Ph2_EXP_BKK | Muban Nanthicha 1 | 2025-08-11 |  |  |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-11 19:17:40 | No | No |  |  |  | 2025-08-29 | 2025-08-16 | 2025-08-18 | V Contribute Co., Ltd | N/A | Closed | 2025-08-18 11:54:29 | Yes | Yes | 2025-08-18 12:03:29 |  |  | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 14:48:30 | Yes | Yes | 2025-09-01 00:11:47 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 13:33:46 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:31 | No | Yes | 2025-08-27 15:57:37 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-11 18:23:00 | No | No |  | 11-08-2025. Add RRU3953#， Ant.4 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-08 |  | N/A | Not assigned |  | No | No
NTCDM_2025 Capacity Expansion Ph2_EXP_BKK | NITCHADA THANI CONDOMINIUM |  |  |  | 2025-08-19 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-20 | 2025-08-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-21 11:54:36 | Yes | Yes | 2025-08-28 11:39:12 |  | 2025-08-28 | 2025-09-02 | Kontira Kowapradit | Approved | Closed | 2025-09-15 17:01:13 | Yes | Yes | 2025-09-02 11:44:48 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:14 | Yes | Yes | 2025-09-22 22:56:04 |  | 2025-09-02 | 2025-09-02 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 17:14:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-20 17:09:01 | No | No |  | 20-Aug-2025 Add AAU5636w S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
NUNIM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI NUANNOI_3G2100 |  |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-01-31 | 2026-02-12 | 2026-02-13 | V Contribute Co., Ltd | N/A | Closed | 2026-02-13 16:46:57 | Yes | Yes | 2026-02-13 16:46:57 |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-08-11 16:44:15 | Yes | Yes | 2026-03-11 17:20:14 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-03 | 2026-08-11 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:16:39 | Yes | Yes | 2026-03-05 21:10:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-28 20:20:44 | No | No |  | 28-Jan-2026 AAU5768 S1 S2 Remove RRU5507*4 RRU3962 *1 Sector 1 Remove RRU5507* 4 sector 2 Add RRU5526 Sector 3 Remove RRU3962 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NUNIM_2025 Capacity Expansion Ph5_EXP_BKK | SOI NUANNOI_3G2100 |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-12-28 | 2025-12-11 | 2025-12-15 | V Contribute Co., Ltd | N/A | Closed | 2025-12-15 13:51:36 | Yes | Yes | 2025-12-15 13:51:36 |  | 2025-11-28 | 2025-11-28 | Chonradee Suwapan | Approved | Closed | 2026-03-24 09:25:41 | Yes | Yes | 2025-11-28 19:47:16 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-03-24 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2025-11-28 | 2025-11-28 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-11-28 19:57:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-20 17:27:08 | No | No |  | 20-11-2025. Add AIRU5636w Sec.6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NVTSM_2025 Capacity Expansion NW Modernization_EXP_BKK | NOVOTEL HOTEL SIAM SQUARE |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 16:26:40 | No | No |  |  | 2026-02-14 | 2026-02-25 | 2026-02-14 | 2026-02-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-22 17:21:37 | Yes | Yes | 2026-03-12 10:36:55 |  | 2026-03-24 | 2026-03-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-04-24 16:29:13 | Yes | Yes | 2026-03-24 15:57:47 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-04-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 20:00:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-14 17:35:11 | No | No |  | 14-Feb-2026 Add UBBPg2 Remove eb |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-02-25 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NW48M_2025 Coverage Expansion Ph2_EXP_BKK | NAKNIWAT 48 YAEK 15 |  |  |  | 2025-08-16 |  | 2025-08-18 | 2025-08-18 | Akhom Srinara | N/A | Closed | 2025-08-18 13:04:03 | No | No |  |  |  |  | 2025-08-16 | 2025-08-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-16 17:11:33 | Yes | Yes | 2025-08-18 14:40:26 |  | 2025-08-19 | 2025-08-19 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-22 17:57:48 | Yes | Yes | 2025-08-19 12:58:36 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 13:36:38 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 20:02:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-16 17:11:35 | No | No |  | 16-08-2025. Add RRU3953#， Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-17 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 06:02:16 | No | No
NWKSK_2025 Coverage Expansion Ph2_New_SR | Na Wat Kok Saman Khun |  |  |  |  | 2025-12-24 | 2025-12-25 | 2025-12-25 | Teloneer Company Limited | N/A | Closed | 2025-12-25 18:10:42 | No | No |  |  |  | 2025-12-24 | 2025-12-24 | 2026-01-07 | Teloneer Company Limited | N/A | Closed | 2026-01-07 21:20:22 | Yes | Yes | 2026-02-04 15:20:41 |  | 2026-02-04 | 2026-02-04 | Rosak soko(Teloneer Company Limited) | Approved | Closed | 2026-02-10 07:46:38 | Yes | Yes | 2026-02-20 14:50:41 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-02-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:03 | Yes | Yes | 2026-03-27 17:04:30 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-09 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-01-09 10:37:43 | No | No |  | On Service done ------------- Pending Rep RRU 3953 S2 RF Unit TX Channel Gain Out of Range ------------------------ BBU3910#，d5*3 S1 > RRU3953 > Ant combine MB S2 > RRU3953 > Ant combine MB S3 > RRU3953 > Ant combine MB S1 > RRU3826(2) > Ant 8 port S2 > RRU3826(2) > Ant 8 port S3 > RRU3826(2) > Ant 8 port Test done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Laddawan Wannasri WX1434742 | Approved | Closed | 2025-12-17 14:08:58 | Yes | Yes | 2025-12-15 17:32:20 |  |  | 2026-02-05 | Nattawoot Suwan | N/A | Closed | 2026-02-05 11:17:05 | No | No | [5 empty] | 2025-12-23 |  | N/A | Not assigned |  | No | No
OCVLM_2025 Capacity Expansion Ph6_EXP_BKK | MU BAN ORCHID VILLA | [5 empty] | 2025-12-09 | 2025-12-09 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  |  | 2025-12-04 | 2025-12-06 | 2025-12-06 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-06 18:03:41 | Yes | Yes | 2025-12-09 15:49:03 |  | 2025-12-11 | 2025-12-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-19 17:39:21 | Yes | Yes | 2025-12-11 14:04:44 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-15 12:30:26 |  | 2025-12-12 | 2025-12-12 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:23:08 | Yes | Yes | 2025-12-12 15:13:58 |  |  | 2025-12-31 | 2025-12-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-04 13:54:28 | No | No |  |  |  |  | 2025-12-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-04 15:41:08 | No | No |  | 4-Dec-2025 Add AAU5636w Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ON80M_2025 Coverage Expansion Ph2_EXP_BKK | SOI ONNUCH 80 YAEK 5 |  |  |  | 2025-08-15 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-16 | 2025-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-18 12:20:21 | Yes | Yes | 2025-08-22 09:49:06 |  | 2025-08-25 | 2026-01-16 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-09-30 00:32:56 | Yes | Yes | 2026-01-16 18:51:25 | Already upload New PAT DOC 16/01/2026 | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-09-29 | wangxing 84250914 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-09-02 | 2025-09-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-02 20:27:12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-16 18:23:45 | No | No |  | 16-Aug-2025 Add RRU3953 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | Jia Rui 80023782 | N/A | Not assigned |  | No | No
ORT1B_2025 Capacity Expansion NW Modernization_EXP_BKK | Oriental Hotel (CIAO Building) |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-05-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-26 13:33:54 | Yes | Yes | 2026-05-26 13:36:31 |  | 2026-05-31 | 2026-05-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-08 09:36:09 | Yes | Yes | 2026-05-31 01:33:41 | Page no.6#， need to fill install card activity. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-15 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:34:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-03 18:30:17 | No | No |  | 3-Feb-2026 Add RRU5526 sector A Remove RRU3962 Add g2 Replace Ant 4port No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ORT2B_2025 Capacity Expansion NW Modernization_EXP_BKK | Oriental Hotel (Arthor's Wing) |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  | 2026-02-07 | 2026-02-07 | 2026-03-09 | 2026-05-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-18 18:03:44 | Yes | Yes | 2026-05-18 18:06:24 |  | 2026-05-31 | 2026-05-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-04 16:44:42 | Yes | Yes | 2026-05-31 00:51:11 |  | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-04 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:34:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-26 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-26 17:31:50 | No | No |  | 26-Mar-2026 Clear Alarm VSWR 3-Feb-2026 ***Pending VSWR ///Add RRU5526 sector A Remove RRU3839 Replace Ant 4port No RET Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ORT3B_2025 Capacity Expansion NW Modernization_EXP_BKK | Oriental Hotel (Car Park Building) |  |  |  | 2026-05-31 | 2026-05-31 | 2026-05-31 | 2026-05-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-31 01:14:25 | No | No |  |  | 2026-02-07 | 2026-02-07 | 2026-03-10 | 2026-06-01 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-01 13:23:20 | Yes | Yes | 2026-06-01 13:25:59 |  | 2026-05-31 | 2026-05-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-08 09:36:09 | Yes | Yes | 2026-05-31 01:13:31 | Page-40 DPU-40 need to fill serial number | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-15 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:34:58 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 3-Feb-2026 ***Pending VSWR ///Add RRU5526 sector A Remove RRU3962 Replace Ant 4port No RET Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OYP1B_2025 Coverage Expansion Ph1_EXP_BKK | Onyx by Sansiri Phaholyothin (Side) | [5 empty] | 2025-09-17 | 2025-09-17 | Akhom Srinara | N/A | Closed | 2025-09-25 13:54:36 | No | No |  |  |  |  | 2025-09-12 | 2025-09-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-04-10 15:10:15 | Yes | Yes | 2026-04-10 15:12:43 |  | 2025-09-19 | 2025-09-19 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-06 16:26:47 | Yes | Yes | 2025-09-19 19:27:11 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:02 | Yes | Yes | 2025-10-09 21:17:17 |  | 2025-09-19 | 2025-09-19 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:28:19 | No | Yes | 2025-09-19 18:36:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-12 18:07:29 | No | No |  | 12-09-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-15 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
OYP2B_2025 Coverage Expansion Ph1_EXP_BKK | Onyx by Sansiri Phaholyothin (Garden) | [5 empty] | 2025-09-17 | 2025-09-17 | Akhom Srinara | N/A | Closed | 2025-09-25 13:54:36 | No | No |  |  |  |  | 2025-09-12 | 2025-09-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-15 13:40:14 | Yes | Yes | 2025-09-15 14:20:19 |  | 2025-09-18 | 2025-09-19 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-06 16:26:47 | Yes | Yes | 2025-09-19 19:32:00 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:02 | Yes | Yes | 2025-10-09 21:18:35 |  | 2025-09-18 | 2025-09-18 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:28:19 | No | Yes | 2025-09-18 10:19:00 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-12 16:55:19 | No | No |  | 12-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector B Add d6 E tilt -200 81 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-16 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
P18KM_2025 Coverage Expansion Ph2_EXP_BKK | PRUKSA 18 VILLAGE - KAEW IN | 2025-08-08 |  |  |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-08 18:25:52 | No | No |  |  | 2025-08-08 | 2025-08-15 | 2025-08-08 | 2025-08-10 | V Contribute Co., Ltd | N/A | Closed | 2025-08-10 12:48:13 | Yes | Yes | 2025-08-10 12:48:37 |  | 2025-08-24 | 2025-08-24 | Chonradee Suwapan | Approved | Closed | 2025-08-29 16:53:28 | Yes | Yes | 2025-08-24 20:51:27 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 13:40:41 |  | 2025-08-13 | 2025-08-13 | Annop Auyto | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-13 13:13:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-08 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-08 17:37:04 | No | No |  | 08-08-2025. Add RRU3953 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-07 |  | N/A | Not assigned |  | No | No
P219M_2025 Capacity Expansion Ph3_EXP_BKK | PHUTTHAMONTHON SAI 2 SOI 19 |  |  |  |  | 2025-09-08 | 2025-09-08 | 2025-09-08 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-08 16:55:57 | No | No |  |  |  | 2025-09-26 | 2025-09-25 | 2025-09-26 | V Contribute Co., Ltd | N/A | Closed | 2025-09-26 22:22:32 | Yes | Yes | 2025-09-26 22:22:32 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-10-07 11:01:46 | Yes | Yes | 2025-12-01 15:29:33 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 21:21:02 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 21:29:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-08 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-08 18:41:16 | No | No |  | 2025-09-08_Add UBBPg3a#， AAU5636w Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-07 |  | N/A | Not assigned |  | No | No
P234M_2025 Coverage Expansion Ph2_EXP_BKK | PHUTTHAMONTHON SAI 2 SOI 34 | 2025-08-01 |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-01 17:31:33 | No | No |  |  |  | 2025-08-22 | 2025-08-12 | 2025-08-13 | V Contribute Co., Ltd | N/A | Closed | 2025-08-13 10:08:31 | Yes | Yes | 2025-08-13 10:14:03 |  | 2025-08-19 | 2025-08-19 | Chonradee Suwapan | Approved | Closed | 2025-08-25 17:35:50 | Yes | Yes | 2025-08-19 23:17:19 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 19:06:54 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:41:12 | No | Yes | 2025-08-05 09:06:03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-01 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-01 17:11:01 | No | No |  | 1-Aug-2025 Add RRU3953 S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
P2M2M_2025 Capacity Expansion Ph3_EXP_BKK | PUTTHAMONTHOL SAI 2 STATION 2 |  |  |  | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-19 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-22 17:57:16 | No | No |  |  | 2025-09-12 | 2025-09-15 | 2025-09-17 | 2025-09-18 | Teloneer Company Limited | N/A | Closed | 2025-09-18 17:27:10 | Yes | Yes | 2025-09-19 10:52:40 |  |  | 2025-09-22 | Apichart Kampuang | Approved | Closed | 2025-10-15 14:27:54 | Yes | Yes | 2025-09-22 16:52:50 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:03:46 |  |  | 2025-09-02 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 23:29:51 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-08 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-08 17:10:12 | No | No |  | 08-09-2025. Replace RRU5516 L18#， Ant.8 port Sec.2#， 7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-18 |  | N/A | Not assigned |  | No | No
P316M_2025 Capacity Expansion Ph6_EXP_BKK | PHUTTHAMONTHON SAI 3 SOI 16/3 |  |  |  |  | 2025-12-18 | 2025-12-18 | 2025-12-18 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-18 18:25:00 | No | No |  |  |  | 2025-12-31 | 2025-12-23 | 2025-12-23 | V Contribute Co., Ltd | N/A | Closed | 2025-12-23 12:37:00 | Yes | Yes | 2025-12-23 12:37:00 |  | 2025-12-24 | 2025-12-24 | Chonradee Suwapan | Approved | Closed | 2026-01-06 15:54:30 | Yes | Yes | 2026-03-14 14:49:26 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-09 20:23:20 |  | 2025-12-24 | 2025-12-24 | Chonradee Suwapan | Approved | Closed | 2026-01-07 15:01:03 | Yes | Yes | 2026-01-07 10:16:15 |  |  | 2025-12-31 | 2025-12-18 | V Contribute Co., Ltd | N/A | Closed | 2025-12-18 13:55:02 | No | No |  |  |  |  | 2025-12-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-18 14:16:09 | No | No |  | 18-Dec-2025 Add AAU5636w sector 1 Replace Ant 12port Co 18002100 900 S1 S6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P316M_2025 Coverage Expansion Ph2_EXP_BKK | PHUTTHAMONTHON SAI 3 SOI 16/3 | 2025-08-15 |  |  |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-15 19:00:11 | No | No |  |  |  | 2025-08-29 | 2025-08-28 | 2025-09-01 | V Contribute Co., Ltd | N/A | Closed | 2025-09-01 10:24:56 | Yes | Yes | 2025-09-01 10:26:18 |  |  | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-09 09:04:09 | Yes | Yes | 2025-09-01 00:13:36 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:53 | Yes | Yes | 2025-10-06 19:49:13 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 02:07:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-15 15:32:56 | No | No |  | 15-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-14 |  | N/A | Not assigned |  | No | No
P3BWM_2025 Capacity Expansion Ph2_EXP_BKK | Phutthamonthon Sai 3 - Bang Waek |  |  |  | 2025-09-09 | 2025-09-16 | 2025-09-30 | 2025-09-30 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-30 10:53:47 | No | No |  |  | 2025-09-16 | 2025-09-18 | 2025-09-17 | 2025-09-17 | Teloneer Company Limited | N/A | Closed | 2025-09-17 14:27:29 | Yes | Yes | 2025-09-18 09:17:42 |  | 2025-09-23 | 2025-09-18 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2025-10-06 16:26:47 | Yes | Yes | 2025-10-17 17:27:16 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 21:22:16 |  | 2025-08-31 | 2025-08-31 | Teloneer Company Limited | Approved | Closed | 2025-10-10 17:28:56 | No | Yes | 2025-08-31 16:52:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-09 18:53:58 | No | No |  | 09-09-2025. Add UBBPg2#， RRU5516 L900#， Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-29 |  | N/A | Not assigned |  | No | No
PARCB_2025 Capacity Expansion NW Modernization_EXP_BKK | PARCO CONDOMINIUM |  |  |  |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-29 08:07:45 | No | No |  |  |  | 2026-02-07 | 2026-01-28 | 2026-01-28 | V Contribute Co., Ltd | N/A | Closed | 2026-01-28 21:15:58 | Yes | Yes | 2026-01-28 21:15:58 |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-06-15 09:56:33 | Yes | Yes | 2026-06-05 01:12:47 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-30 | 2026-06-25 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-04 | 2026-02-04 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-04 19:18:42 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-22 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-22 19:33:12 | No | No |  | 22-01-2026 Replace bbu 3900 to 5900#， add g2#，Replace rru3962 to 5526 sector 1 18/21 Done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-20 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 05:53:28 | Yes | Yes | 2026-01-20 16:53:11 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PARCB_2025 Coverage Expansion Ph1_EXP_BKK | PARCO CONDOMINIUM | 2025-09-03 |  |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-03 18:12:42 | No | No |  |  |  | 2025-09-30 | 2025-09-03 | 2025-09-03 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:16:28 | Yes | Yes | 2025-09-30 10:16:28 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:45:39 | Yes | Yes | 2025-09-20 20:09:48 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 19:59:19 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:06:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-03 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-03 19:44:30 | No | No |  | 2025-09-03_Replace to Ant Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-02 |  | N/A | Not assigned |  | No | No
PARMM_2025 Capacity Expansion Ph8_EXP_BKK | SOI PRONG-AROM | [5 empty] | 2026-02-11 | 2026-02-11 | Narongsak wanichachiwa | N/A | Closed | 2026-02-13 18:50:29 | No | No |  |  |  | 2026-01-29 | 2026-01-30 | 2026-01-31 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-01-31 16:02:54 | Yes | Yes | 2026-02-01 15:06:13 |  |  | 2026-02-03 | OATTAPAN AUTTAHON | Approved | Closed | 2026-02-17 16:38:08 | Yes | Yes | 2026-02-03 20:15:08 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:57:49 |  |  | 2026-02-03 | OATTAPAN AUTTAHON | Ready To Approve | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-24 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-24 18:19:45 | No | No |  | 24-01-2025. Add UBBPg3a x2#， AIRU5636w Sec.6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PAY2M_2025 Capacity Expansion NW Modernization_EXP_BKK | PHANIT ANUN YEAK 2 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-05-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-28 15:32:54 | Yes | Yes | 2026-05-28 15:34:52 |  | 2026-05-13 | 2026-05-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-10-01 00:36:40 | Yes | Yes | 2026-09-18 13:35:15 | Page no.9#， need to fill color for install RRU -5 pcs in INV. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 21:35:11 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-31 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-31 16:48:27 | No | No |  | 31-Mar-26 Replace RRU5508>>RRU5516 S1 30-Mar-26 Add UBBPg3a #，Remove RRU to AAU5768 S2 Replace RRU5508>>RRU5516 S2 #，Replace RRU3962 >>>RRU5507*2 S2 Replace RRU5508>>RRU5516 S3 ///Pending Replace RRU5508>>RRU5516 S1 // |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PBBMM_2025 Coverage Expansion Ph2_EXP_BKK | PHUTTHABUCHA ROAD - BANGMOD KLONG |  |  |  | 2025-08-16 | 2025-08-31 | 2025-08-16 | 2025-08-16 | Subpoa Limsaihua | N/A | Closed | 2025-08-28 10:14:26 | No | No |  |  |  |  | 2025-08-16 | 2025-08-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-16 20:24:43 | Yes | Yes | 2025-08-18 21:09:42 |  | 2025-08-19 | 2025-08-19 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:34:38 | Yes | Yes | 2025-12-01 20:46:24 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 13:44:40 |  | 2025-09-03 | 2025-09-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-03 10:32:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-26 16:58:07 | No | No |  | 26-08-2025. Add RRU3953 Sec.2 //16-08-2025. Add RRU3953 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-15 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 21:05:51 | No | No
PCH1M_2025 Capacity Expansion Ph2_EXP_BKK | SOI PRICHA1 | 2025-08-11 |  |  |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-11 19:17:40 | No | No |  |  |  | 2025-08-29 | 2025-08-18 | 2025-08-25 | V Contribute Co., Ltd | N/A | Closed | 2025-08-25 11:16:46 | Yes | Yes | 2025-08-25 11:18:30 |  |  | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-17 18:41:02 | Yes | Yes | 2025-12-01 20:51:33 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:14 | Yes | Yes | 2025-09-22 23:24:40 |  | 2025-09-04 | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-04 20:14:15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-11 18:23:00 | No | No |  | 11-08-2025. Replace RRU5516 L18 Sec.3#， 8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-11 |  | N/A | Not assigned |  | No | No
PCHPM_2025 Capacity Expansion Ph2_EXP_BKK | PRACHA PHATTHANA RD |  |  |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-13 18:57:01 | No | No |  |  |  | 2025-08-29 | 2025-08-18 | 2025-08-20 | V Contribute Co., Ltd | N/A | Closed | 2025-08-20 11:29:57 | Yes | Yes | 2025-08-20 11:31:54 |  |  | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2026-03-10 16:23:29 | Yes | Yes | 2025-12-01 20:56:14 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 20:25:45 |  | 2025-09-04 | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-04 20:15:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-13 19:16:02 | No | No |  | 13-Aug-2025 Add RRU5516 (1800-2100) S1 Remove RRU3962 Replace Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-12 |  | N/A | Not assigned |  | No | No
PCHPM_2025 Capacity Expansion Ph3_EXP_BKK | PRACHA PHATTHANA RD | 2025-09-01 |  |  |  | 2025-09-01 | 2025-09-01 | 2025-09-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-01 18:03:40 | No | No |  |  |  | 2025-09-06 | 2025-09-09 | 2025-09-11 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:16:41 | Yes | Yes | 2025-09-30 10:16:41 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:46:13 | Yes | Yes | 2025-09-13 22:21:20 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:06:13 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-14 13:03:12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-01 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-01 19:42:20 | No | No |  | 1-Sep-2025 Add RRU5516 (1800-2100) S3 S6 S8 remove RRU3962 *3 Replace Ant 8port S3 S6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-10-02 09:31:24 | No | No
PCHPM_2025 Coverage Expansion Ph2_EXP_BKK | PRACHA PHATTHANA RD |  |  |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-13 18:57:01 | No | No |  |  |  | 2025-08-29 | 2025-08-18 | 2025-08-23 | V Contribute Co., Ltd | N/A | Closed | 2025-08-23 09:48:45 | Yes | Yes | 2025-08-23 09:50:01 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-09 09:04:09 | Yes | Yes | 2025-09-02 18:11:25 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:07:29 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 02:14:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-13 19:10:51 | No | No |  | 13-Aug-2025 Add RRU3953 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-12 |  | N/A | Not assigned |  | No | No
PCHSM_2025 Coverage Expansion Ph2_EXP_BKK | PANCHASAP VILLAGE | 2025-08-22 |  |  |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-22 17:15:25 | No | No |  |  |  | 2025-08-22 | 2025-08-26 | 2025-08-27 | V Contribute Co., Ltd | N/A | Closed | 2025-08-27 10:05:04 | Yes | Yes | 2025-08-27 10:05:54 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-10 09:26:14 | Yes | Yes | 2025-12-01 21:14:17 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:14 | Yes | Yes | 2025-09-22 23:28:44 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:56:02 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-22 17:59:08 | No | No |  | 22-08-2025. Add RRU3953 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-21 |  | N/A | Not assigned |  | No | No
PCK2M_2025 Capacity Expansion Ph3_EXP_BKK | PICHAIKHET 2 ROAD |  |  |  | 2025-09-01 | 2025-09-07 | 2025-09-08 | 2025-09-08 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  | 2025-09-07 | 2025-09-09 | 2025-09-08 | 2025-09-09 | Teloneer Company Limited | N/A | Closed | 2025-09-09 11:27:16 | Yes | Yes | 2025-09-09 11:27:17 |  |  | 2025-09-09 | Apichart Kampuang | Approved | Closed | 2025-09-30 15:30:37 | Yes | Yes | 2025-09-09 17:37:09 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:08:44 |  |  | 2025-09-02 | Palagon Prommueangma(Teloneer Company Limited) | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-01 18:38:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-02 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-02 17:59:46 | No | No |  | 2025-09-02_Replace RRU5507 to RRU5516(18-21)#， Replace to Ant 4 port Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-09-07 | Jia Rui 80023782 | N/A | Closed | 2025-10-01 20:48:30 | No | No
PCKRM_2025 Coverage Expansion Ph2_EXP_BKK | PI CHAI KHET ROAD | 2025-08-01 |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-01 17:31:33 | No | No |  |  |  | 2025-08-22 | 2025-08-12 | 2025-08-12 | V Contribute Co., Ltd | N/A | Closed | 2025-08-12 15:20:03 | Yes | Yes | 2025-08-12 15:20:49 |  | 2025-08-19 | 2025-08-19 | Chonradee Suwapan | Approved | Closed | 2025-08-25 17:35:18 | Yes | Yes | 2025-12-02 09:51:47 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 19:09:34 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:56:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-01 16:26:43 | No | No |  | 01-08-2025. Add RRU3953#， Replace Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
PCR1M_2025 Capacity Expansion Ph2_EXP_BKK | SOI PRACHARAT SAI1 | 2025-09-02 |  |  |  | 2025-09-02 | 2025-09-02 | 2025-09-02 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-02 15:53:01 | No | No |  |  |  | 2025-09-30 | 2025-09-09 | 2025-09-10 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:16:54 | Yes | Yes | 2025-09-30 10:16:54 |  | 2025-09-11 | 2025-09-11 | Chonradee Suwapan | Approved | Closed | 2025-09-26 16:35:04 | Yes | Yes | 2025-12-02 10:04:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:09:59 |  | 2025-09-11 | 2025-09-11 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:04 | No | Yes | 2025-09-11 21:31:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-02 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-02 17:37:37 | No | No |  | 02-09-2025. Replace RRU5516 L18#， Ant.12port Sec.3#， 8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-01 |  | N/A | Not assigned |  | No | No
PCRTB_2025 Capacity Expansion Ph2_EXP_BKK | SMALL CELL PRACHARAT RD. FOR CHEWATHAI INTERCHANGE | 2025-10-06 |  |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-10 18:33:54 | No | No |  |  |  | 2025-10-17 | 2025-10-07 | 2025-10-10 | V Contribute Co., Ltd | N/A | Closed | 2025-10-10 15:26:24 | Yes | Yes | 2025-10-10 15:26:25 |  | 2025-10-16 | 2025-10-16 | Chonradee Suwapan | Approved | Closed | 2025-10-24 09:44:53 | Yes | Yes | 2026-01-06 17:11:49 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:55 | Yes | Yes | 2025-10-27 18:18:37 |  | 2025-10-16 | 2025-10-16 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-16 17:23:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-06 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-06 18:13:52 | No | No |  | 2025-10-06_Replace to BBU5900 by UMPTg2#， Add UBBPg3a#， UBBPd5#， Split GPS#， Add RRU5818 Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-09 |  | N/A | Not assigned |  | No | No
PCS2M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHICHAI 2 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  |  | 2026-02-09 | 2026-02-09 | 2026-09-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-09-25 20:25:13 | Yes | Yes | 2026-09-25 20:28:11 | 1.Need before S1 antenna=1pc overview photo. 2..Need before S2 antenna=2pcs overview photos. 3.Need removed antenna 900 M-tit of S2. 4.Need removed antenna 900 SN of S3. 5.Removed antennas are S1=1#，S2=2#，S3=2? 6.RRU 10pcs are how many removed in which sector?Upload all removed RRU and SN overview photos on before section.Pls red mark(10pcs) | 2026-07-10 | 2026-07-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-07-30 12:49:52 | Yes | Yes | 2026-07-10 14:25:19 | page 6 remove UBBPD6 need to fill. Page 19 Before Antenna M-Tilt Photo Need. Page 20 Before Direction antenna and Before Zoom Compass Photo Need. page 23 Before Direction antenna and Before Zoom Compass Wrong Photo. Page 34 After: Card CE Left Installation View Clear Photo Need. Page 44 Before DC-RRU Photo Need. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-29 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 20:14:45 |  |  | 2026-07-13 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-10 19:46:59 | No | No |  | 10-02-2026. Replace RRU3953 to 5516 Sec.2#， 3#， RRU5508 to 5516 Sec.1#， RRU3962 to 5507 Sec.1#， 3#， Ant.8 port Sec.1#， 2#， 3 //Downgrade Sec.6#， 7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 1.back Picture of full body safety harness with lanyard 2.need to upload dismantle antenna SN. clearly photo in EQ Checklist 3.need to fill dismantle filter redmark in EQ Checklist 4.need to upload install S3 1880/2100 Socket Wire strip length is 18mm with scale 1pcs photo 5.need to upload S3 Socket right side 1pcs photo 6.need to upload S1,S3 cover with plug in CPRI and socket DC RRU |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PCS4M_2025 Coverage Expansion Ph2_EXP_BKK | PRACHA SAMRAN STATION 4 | [5 empty] | 2025-08-19 | 2025-08-19 | Palagon Prommueangma | N/A | Closed | 2025-08-19 16:38:33 | No | No |  |  | 2025-08-18 | 2025-08-20 | 2025-08-25 | 2025-08-26 | Teloneer Company Limited | N/A | Closed | 2025-08-26 10:49:19 | Yes | Yes | 2025-08-26 14:53:24 |  |  | 2025-08-29 | Apichart Kampuang | Approved | Closed | 2025-09-02 17:20:53 | Yes | Yes | 2025-10-17 17:27:35 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 13:46:33 |  |  | 2025-08-12 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:08 | No | Yes | 2025-08-12 14:03:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-18 17:23:30 | No | No |  | 18-08-2025. Add RRU3953 Sec.1#， 2#， 3#， Replace Ant.4 port Sec.2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-18 | Jia Rui 80023782 | N/A | Closed | 2025-08-25 06:02:16 | No | No
PCSTM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHICHAI SATHORN |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-07-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-02 20:40:27 | Yes | Yes | 2026-07-10 15:24:16 |  | 2026-07-14 | 2026-07-14 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-05 15:50:06 | Yes | Yes | 2026-07-14 15:03:47 | page.27 need to upload DC-RRU | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 20:14:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-07 18:36:19 | No | No |  | 07-02-2026. Replace RRU3962 to RRU5507 x2 Sec.1#， 3 //Downgrade Sec.6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed. |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PDPMM_2025 Coverage Expansion Ph2_EXP_BKK | Paradise Park Macro Cell |  |  |  | 2025-10-22 | 2025-10-30 | 2025-10-21 | 2025-10-21 | Akhom Srinara(Future Telecom Co.,Ltd.) | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  | 2025-10-22 | 2025-10-24 | 2025-10-22 | 2025-10-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-22 16:08:48 | Yes | Yes | 2025-10-22 16:08:48 |  | 2025-11-17 | 2025-11-17 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-25 16:31:44 | Yes | Yes | 2025-11-17 18:00:19 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 20:41:04 |  | 2025-11-17 | 2025-11-17 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:25:38 | No | Yes | 2025-11-17 18:03:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-22 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-22 18:17:06 | No | No |  | 2025-10-22_Add RRU3953 Sector 2.2(Chain RRU from RRU2.1) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | พาราไดร์ (มีเงินมัดจำ 50000) |  | 2025-10-29 |  | N/A | Not assigned |  | No | No
PDS2B_2025 Capacity Expansion Ph2_EXP_BKK | THE PRESIDENT SATHORN-RATCHAPRUEK PHASE 2 |  |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 20:58:16 | Yes | Yes | 2025-10-30 20:58:17 |  | 2025-10-18 | 2025-10-18 | Chonradee Suwapan | Approved | Closed | 2025-10-24 13:21:41 | Yes | Yes | 2026-01-06 18:12:47 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:55 | Yes | Yes | 2025-10-27 18:21:04 |  | 2025-10-18 | 2025-10-18 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-10-18 20:28:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-07 15:30:06 | No | No |  | 7-Oct-2025 Add RRU5818 SC Add g3a Replace Ant 12port No ret 5/2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
PDS2B_2025 Coverage Expansion Ph1_EXP_BKK | THE PRESIDENT SATHORN-RATCHAPRUEK PHASE 2 | 2025-10-06 |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 16:44:27 | Yes | Yes | 2025-10-30 16:44:28 |  | 2025-10-22 | 2025-10-22 | Chonradee Suwapan | Approved | Closed | 2025-10-29 17:02:35 | Yes | Yes | 2026-01-06 18:20:23 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 18:40:44 |  | 2025-10-22 | 2025-10-22 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-10-22 20:36:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-07 12:17:24 | No | No |  | 7-Oct-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam SA E tilt-200 (No config RET) 6-Oct-2025 ***Pending Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam SA E tilt-200 //Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam SB E tilt-200 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
PDS3B_2025 Coverage Expansion Ph1_EXP_BKK | THE PRESIDENT SATHORN - RATCHAPHRUEK 3 SMALL CELL |  |  |  |  | 2025-10-21 | 2025-10-21 | 2025-10-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-21 17:43:19 | No | No |  |  |  | 2025-10-18 | 2025-10-29 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 16:01:12 | Yes | Yes | 2025-10-30 16:01:13 |  | 2025-10-24 | 2025-10-24 | Chonradee Suwapan | Approved | Closed | 2025-10-29 17:02:35 | Yes | Yes | 2026-01-06 11:01:31 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 18:41:57 |  | 2025-10-24 | 2025-10-24 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-10-24 19:59:30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-10 16:35:48 | No | No |  | 10-Oct-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam SA E-tilt -200 83 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Complted |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
PEARM_2025 Capacity Expansion Ph6_EXP_BKK | PROVINCIAL ELECTRICITY AUTHORITY, RANGSIT DISTRICT OFFICE | 2025-12-03 |  |  |  | 2025-12-31 | 2025-12-04 | 2025-12-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-04 18:19:04 | No | No |  |  |  | 2025-12-31 | 2025-12-16 | 2025-12-16 | V Contribute Co., Ltd | N/A | Closed | 2025-12-16 14:20:08 | Yes | Yes | 2025-12-16 14:20:09 |  | 2025-12-09 | 2025-12-09 | Chonradee Suwapan | Approved | Closed | 2025-12-18 09:25:15 | Yes | Yes | 2026-01-14 17:04:33 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 20:27:00 |  | 2025-12-09 | 2025-12-09 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-09 21:00:10 |  |  | 2025-12-31 | 2025-12-03 | V Contribute Co., Ltd | N/A | Closed | 2025-12-03 15:53:59 | No | No |  |  |  |  | 2025-12-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-03 16:24:15 | No | No |  | 3-Dec-2025 Add AAU5636w sector 8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PEARM_2025 Capacity Expansion Ph8_EXP_BKK | PROVINCIAL ELECTRICITY AUTHORITY, RANGSIT DISTRICT OFFICE |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-24 14:48:20 | No | No |  |  |  | 2026-02-14 | 2026-03-10 | 2026-03-10 | V Contribute Co., Ltd | N/A | Closed | 2026-03-10 16:07:34 | Yes | Yes | 2026-03-10 16:07:34 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-03-04 09:57:31 | Yes | Yes | 2026-03-13 17:13:31 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:59:04 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-23 22:56:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-07 15:05:51 | No | No |  | 7-Feb-2026 Add AAU5636w Sector 7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PGT1B_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland Grand Taksin (Front) | 2025-09-12 |  |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-12 18:29:38 | No | No |  |  |  | 2025-09-30 | 2025-09-22 | 2025-09-23 | V Contribute Co., Ltd | N/A | Closed | 2025-09-23 11:16:25 | Yes | Yes | 2025-09-23 11:16:25 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-10-07 16:22:25 | Yes | Yes | 2025-09-20 20:10:55 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 21:27:22 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:07:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-12 16:55:33 | No | No |  | 12-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A Add d6 E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
PGT2B_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland Grand Taksin (Back) | 2025-09-12 |  |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-12 18:29:38 | No | No |  |  |  | 2025-09-30 | 2025-09-22 | 2025-09-23 | V Contribute Co., Ltd | N/A | Closed | 2025-09-23 11:19:19 | Yes | Yes | 2025-09-23 11:19:19 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-10-07 20:34:19 | Yes | Yes | 2025-12-02 10:18:49 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 21:28:38 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:08:22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-12 16:59:10 | No | No |  | 12-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
PGT3B_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland Grand Taksin (Side) | 2025-09-12 |  |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-12 18:29:38 | No | No |  |  |  | 2025-09-30 | 2025-09-22 | 2025-09-23 | V Contribute Co., Ltd | N/A | Closed | 2025-09-23 12:28:12 | Yes | Yes | 2025-09-23 12:28:12 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-10-07 20:34:19 | Yes | Yes | 2025-09-20 20:13:16 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 21:29:52 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:10:47 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-12 16:59:24 | No | No |  | 12-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
PH49M_2025 Capacity Expansion Ph5_EXP_BKK | SOI PHAHON YOTHIN 49/2 | [5 empty] | 2025-11-19 | 2025-11-19 | Akhom Srinara | N/A | Closed | 2025-11-26 16:34:53 | No | No |  |  |  | 2025-11-13 | 2025-11-14 | 2025-11-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-15 13:35:03 | Yes | Yes | 2025-11-20 20:23:14 |  | 2025-11-21 | 2025-11-21 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-11 09:22:40 | Yes | Yes | 2025-11-23 15:17:10 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 20:30:38 |  | 2025-11-21 | 2025-11-21 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:25:38 | Yes | Yes | 2025-11-21 14:09:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-13 16:26:28 | No | No |  | 13-Nov-2025 Add RRU5526 (1800-2100) S3 Remove RRU3962 Replace Ant 8port Add g2 Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PHCFM_2025 Coverage Expansion Ph2_EXP_BKK | PHRA CHULACHOMKLAO FORT | 2025-08-08 |  |  |  | 2025-08-08 | 2025-08-08 | 2025-08-08 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-08 18:25:52 | No | No |  |  |  | 2025-08-22 | 2025-08-15 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 15:15:45 | Yes | Yes | 2025-08-15 15:17:03 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-09-01 13:12:07 | Yes | Yes | 2025-08-27 14:25:32 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 13:51:51 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:56:34 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-08 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-08 19:14:25 | No | No |  | 8-Aug-2025 Add RRU3953 S3 Replace Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-07 |  | N/A | Not assigned |  | No | No
PHOWY_2025 Capacity Expansion Ph7_EXP_SR | PHO WAY |  |  |  |  | 2025-12-28 | 2026-01-28 | 2026-01-28 | Teloneer Company Limited | N/A | Closed | 2026-01-28 11:55:06 | No | No |  |  |  | 2025-12-08 | 2025-12-23 | 2026-01-28 | Teloneer Company Limited | N/A | Closed | 2026-01-28 16:56:34 | Yes | Yes | 2026-01-29 20:34:28 |  | 2026-01-29 | 2026-01-29 | Nattawoot Suwan | Approved | Closed | 2026-03-05 17:10:15 | Yes | Yes | 2026-02-02 21:00:03 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 14:37:05 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-28 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-01-28 11:15:23 | No | No |  | 28 Jan 2026 Add 1UBBPg3a#， Add AAU5768 DMM S2#， Re L18L21 S2 to S4#， Add new 3G S4. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-02-05 | Nattawoot Suwan | N/A | Closed | 2026-02-05 11:17:05 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PHRAM_2025 Capacity Expansion Ph6_EXP_ER | Bang Phra Moo 11 | 2025-11-17 | thcp_Phet.s | Clear Pending |  | 2025-11-30 | 2025-11-06 | 2025-11-06 | Teloneer Company Limited | N/A | Closed | 2025-11-06 11:09:09 | No | No |  |  |  | 2025-11-30 | 2025-11-06 | 2025-11-06 | Teloneer Company Limited | N/A | Closed | 2025-11-06 19:59:13 | Yes | Yes | 2025-11-12 07:06:25 |  | 2025-11-30 | 2025-11-08 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-11 13:43:39 | Yes | Yes | 2025-11-08 22:12:06 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 20:31:51 |  | 2025-11-25 | 2025-11-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-07 10:30:32 | Yes | Yes | 2025-11-06 16:40:09 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-06 | Reungsak Junkong 00927496 | N/A | Closed | 2025-11-06 17:42:20 | No | No |  | **waiting on-service LNR26 --Add UBBPg3a & New L26F5 + NR26 (New AAU5636w) Sec.2 |  | 2025-11-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-07 18:48:57 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PIANM_2025 Capacity Expansion Ph6_EXP_BKK | SOI PIANON |  |  |  |  | 2025-12-15 | 2025-12-15 | 2025-12-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-15 18:16:03 | No | No |  |  |  | 2025-12-31 | 2025-12-21 | 2025-12-21 | V Contribute Co., Ltd | N/A | Closed | 2025-12-21 17:12:53 | Yes | Yes | 2025-12-21 17:12:54 |  | 2025-12-16 | 2025-12-16 | Chonradee Suwapan | Approved | Closed | 2025-12-19 17:59:27 | Yes | Yes | 2026-01-15 16:08:36 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:03 | Yes | Yes | 2026-01-15 12:36:44 |  | 2025-12-16 | 2025-12-16 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-16 21:26:06 |  |  | 2025-12-31 | 2025-12-15 | V Contribute Co., Ltd | N/A | Closed | 2025-12-15 13:30:25 | No | No |  |  |  |  | 2025-12-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-15 16:38:13 | No | No |  | 15-Dec-2025 Add RRU5516 (700900) sector 7 Add ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PIN3M_2025 Capacity Expansion Ph3_EXP_BKK | PHRA PIN 3 VILLAGE | [5 empty] | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-23 | 2025-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-23 16:16:49 | Yes | Yes | 2025-08-29 14:35:04 |  | 2025-08-30 | 2025-09-02 | Kontira Kowapradit | Approved | Closed | 2025-09-22 15:50:32 | Yes | Yes | 2025-09-24 11:58:59 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:21:57 |  | 2025-09-04 | 2025-09-04 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 14:52:23 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-23 18:15:24 | No | No |  | 23-Aug -2025 Add AAU5636w S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
PIPTA_2025 Capacity Expansion NW Modernization_EXP_BKK | PHIPHAT | 2026-01-19 |  |  |  | 2026-01-19 | 2026-01-30 | 2026-01-30 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-17 22:09:22 | No | No |  |  |  | 2026-01-31 | 2026-01-29 | 2026-01-31 | V Contribute Co., Ltd | N/A | Closed | 2026-01-31 16:06:11 | Yes | Yes | 2026-04-19 18:02:53 |  | 2026-04-21 | 2026-04-21 | Chonradee Suwapan | Approved | Closed | 2026-06-08 09:36:09 | Yes | Yes | 2026-04-21 01:24:21 | 1.Page 9#，Wrong fill colour #，INV & QC mismatch#，in QC not have AC/DC 21021309618ND6007335 activity. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-21 | 2026-06-15 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-21 | 2026-04-21 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-21 09:37:34 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-23 18:07:03 | No | No |  | 2026-01-19_Replace RRU3962 to RRU5526#， Replace to ant 12 port Sector A#，B#， |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PJN4M_2025 Capacity Expansion Ph3_EXP_BKK | POOMJAI NIVATE 4 VILLAGE | [5 empty] | 2025-09-19 | 2025-09-19 | Akhom Srinara | N/A | Closed | 2025-09-25 14:01:42 | No | No |  |  |  |  | 2025-09-08 | 2025-09-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-11 19:18:26 | Yes | Yes | 2025-09-11 19:18:26 |  | 2025-09-21 | 2025-09-21 | Aomchun Jittreemit | Approved | Closed | 2025-10-15 14:27:54 | Yes | Yes | 2025-12-02 11:03:08 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:12:15 |  | 2025-09-12 | 2025-09-12 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:28:45 | No | Yes | 2025-09-12 15:05:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-13 18:37:20 | No | No |  | 13-09-2025. Replace Ant 4 port แก้ Alarm RET //9-Sep-2025 //// Replace BBU5900 UMPTg2 g3a GPS Add AAU5636w S2 Add RRU5516 (18002100) S1 S2 S3 Remove RRU5507 *3 Replace Ant 4port S1 S3 Replace Ant 6port S2 Done 6-Sep-2025 Prework |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-09-01 | Paphawarin Yoopoo WX1434740 | Approved | Closed | 2025-09-23 17:34:23 | Yes | Yes | 2025-09-23 16:49:56 |  |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-17 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
PK15M_2025 Capacity Expansion Ph7_EXP_BKK | PREUKSA15 Village |  |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-20 13:27:35 | No | No |  |  |  | 2026-01-31 | 2026-01-17 | 2026-01-17 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-17 20:20:39 | Yes | Yes | 2026-01-19 09:44:40 |  | 2026-01-20 | 2026-01-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-04 09:24:58 | Yes | Yes | 2026-01-20 13:28:37 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 13:00:21 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 21:46:27 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-14 16:21:55 | No | No |  | 14-Jan-2025 AAU5636w Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PK16M_2025 Capacity Expansion Ph7_EXP_BKK | SOI PHIBUNSONGKHRAM 16 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-12 | 2026-03-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-13 10:09:20 | Yes | Yes | 2026-03-17 08:39:04 |  | 2026-04-23 | 2026-04-23 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-05-06 09:28:48 | Yes | Yes | 2026-04-23 11:44:11 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 21:46:46 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-18 18:21:19 | No | No |  | 18-Feb-26 Add AAU5636w S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKLGM_2025 Capacity Expansion Ph2_EXP_ER | Pakklong | 2025-07-13 |  | Install & Integrate |  | 2025-07-31 | 2025-07-13 | 2025-07-14 | Teloneer Company Limited | N/A | Closed | 2025-07-14 17:36:29 | No | No |  |  |  | 2025-07-31 | 2025-07-15 | 2025-07-21 | Teloneer Company Limited | N/A | Closed | 2025-07-21 17:10:16 | Yes | Yes | 2025-07-30 23:35:27 |  | 2025-07-31 | 2025-09-24 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-26 13:58:41 | Yes | Yes | 2025-09-24 16:59:03 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:32:09 |  | 2025-07-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:27:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-22 |  | 2025-07-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-12 18:15:34 | No | No |  | **waiting on-service -- Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R S3#，New L26F5 + NR26 (New AAU5636w) S3 |  | 2025-07-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-15 16:35:18 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKLPB_2025 Capacity Expansion Ph2_EXP_BKK | The Parkland Phetkasem |  |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-29 | V Contribute Co., Ltd | N/A | Closed | 2025-10-29 10:44:03 | Yes | Yes | 2025-10-29 10:44:03 |  | 2025-10-24 | 2025-10-24 | Chonradee Suwapan | Approved | Closed | 2025-10-29 17:02:35 | Yes | Yes | 2025-10-24 19:46:46 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 18:52:16 |  | 2025-10-24 | 2025-10-24 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-10-24 20:02:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-09 16:45:33 | No | No |  | 9-Oct-2025 Replace BBU59000 UMPTg2 Add g3a Add RRU5818 SA Replace Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
PKLPB_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland Phetkasem | 2025-09-16 |  |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-19 12:21:44 | No | No |  |  |  | 2025-09-30 | 2025-09-30 | 2025-10-01 | V Contribute Co., Ltd | N/A | Closed | 2025-10-01 21:20:19 | Yes | Yes | 2025-10-01 21:20:20 |  | 2025-09-23 | 2025-09-23 | Chonradee Suwapan | Approved | Closed | 2025-10-10 14:08:42 | Yes | Yes | 2025-12-02 11:37:31 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 18:53:31 |  | 2025-09-23 | 2025-09-23 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:20:11 | No | Yes | 2025-09-23 20:31:45 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No |  | 16-Sep-2025 ***Pending Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A (80) /// Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector B ( 82) E tilt -200 ( On-service New cell Sector B L21 2T2R) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-18 |  | N/A | Not assigned |  | No | No
PLA1B_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland Lite SukhumvitPaknam Building A (On Ground) | 2025-09-16 |  |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-19 12:21:44 | No | No |  |  |  | 2025-09-30 | 2025-10-02 | 2025-10-02 | V Contribute Co., Ltd | N/A | Closed | 2025-10-02 19:46:23 | Yes | Yes | 2025-10-02 19:46:23 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-10-14 17:07:34 | Yes | Yes | 2025-12-02 11:45:04 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:13:28 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-22 19:57:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-16 17:05:42 | No | No |  | 16-09-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-18 |  | N/A | Not assigned |  | No | No
PLB1B_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland Lite Sukhumvit-Paknam Building B (On Rooftop) | 2025-09-16 |  |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-19 12:21:44 | No | No |  |  |  | 2025-09-30 | 2025-10-02 | 2025-10-02 | V Contribute Co., Ltd | N/A | Closed | 2025-10-02 19:45:58 | Yes | Yes | 2025-10-02 19:45:58 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-10-14 17:07:34 | Yes | Yes | 2025-09-22 19:43:59 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:14:40 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-22 19:57:50 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-18 |  | N/A | Not assigned |  | No | No
PLCUM_2025 Capacity Expansion Ph2_EXP_BKK | PHAN CHALAEM UTHIT ROAD (SAENG MIT 1) | 2025-08-14 |  |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-14 18:26:57 | No | No |  |  |  | 2025-08-29 | 2025-08-15 | 2025-08-18 | V Contribute Co., Ltd | N/A | Closed | 2025-08-18 11:42:56 | Yes | Yes | 2025-08-18 11:44:59 |  |  | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-09 16:45:53 | Yes | Yes | 2025-12-02 12:01:25 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:13 | Yes | Yes | 2025-09-22 23:57:37 |  | 2025-09-04 | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-04 20:16:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-14 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-14 18:39:44 | No | No |  | 2025-08-14_Add UBBPg3a#， UBBPd6#， Add AAU5636w Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-13 |  | N/A | Not assigned |  | No | No
PLCUM_2025 Coverage Expansion Ph2_EXP_BKK | PHAN CHALAEM UTHIT ROAD (SAENG MIT 1) | 2025-08-14 |  |  |  | 2025-08-14 | 2025-08-14 | 2025-08-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-14 18:26:57 | No | No |  |  |  | 2025-08-29 | 2025-08-19 | 2025-08-25 | V Contribute Co., Ltd | N/A | Closed | 2025-08-25 11:13:38 | Yes | Yes | 2025-08-25 11:16:52 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-05 15:02:32 | Yes | Yes | 2025-09-02 18:12:06 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:35:54 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 02:16:13 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-14 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-14 18:39:44 | No | No |  | 2025-08-14_Add RRU3953#， Ant 4 port Sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-13 |  | N/A | Not assigned |  | No | No
PLGYM_2025 Capacity Expansion Ph7_EXP_ER | Plaeng Yao Moo 11 | 2025-12-13 |  | Install & Integrate |  | 2025-12-31 | 2025-12-13 | 2025-12-14 | Teloneer Company Limited | N/A | Closed | 2025-12-14 09:36:46 | No | No |  |  |  | 2025-12-31 | 2025-12-13 | 2025-12-15 | Teloneer Company Limited | N/A | Closed | 2025-12-15 14:08:21 | Yes | Yes | 2025-12-16 19:21:24 |  | 2025-12-31 | 2025-12-17 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:28:08 | Yes | Yes | 2025-12-17 18:11:03 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 14:38:39 |  | 2025-12-31 | 2025-12-15 | Apichat fangsantthia(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:26:56 | Yes | Yes | 2025-12-15 11:07:15 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-13 17:16:52 | No | No |  | Replace UBBPg1 to UBBPg2_PLGYM_H_1 Replace RRU5508 TO (RRU5516_900) + Co L07 + NR07 + 4T4R_PLGYM_L_1 Replace RRU3953 TO (RRU5516_900) + Co L07 + NR07 + 4T4R_PLGYM_L_4 New L26F5 + NR26 (New AAU5636w)_PLGYM_N_1 REVISE TO 5614 |  | 2025-12-15 | Reungsak Junkong 00927496 | N/A | Closed | 2025-12-15 18:25:08 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLLSB_2025 Capacity Expansion Ph5_EXP_BKK | THE PARKLAND SRINAKARIN LAKE SIDE |  |  |  |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2025-12-28 | 2026-03-26 | 2026-03-27 | V Contribute Co., Ltd | N/A | Closed | 2026-03-27 09:35:46 | Yes | Yes | 2026-03-27 09:35:46 |  | 2026-04-01 | 2026-04-01 | Chonradee Suwapan | Approved | Closed | 2026-05-22 09:05:18 | Yes | Yes | 2026-05-15 11:11:52 | PAT First Time Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-01 | 2026-04-01 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-01 00:52:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-24 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-24 17:47:38 | No | No |  | 24-02-2026. Replace BBU5900#， UMPTg2#， Add UBBPg2#， UBBPg3a#， RRU5818 Sec.B //ไม่ติด GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLP1M_2025 Capacity Expansion Ph2_EXP_BKK | SOI PRAWIT LAE PHUEAN 1 |  |  |  |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-12 18:41:19 | No | No |  |  |  | 2025-08-29 | 2025-08-20 | 2025-08-23 | V Contribute Co., Ltd | N/A | Closed | 2025-08-23 17:07:19 | Yes | Yes | 2025-08-23 17:08:39 |  |  | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2026-03-10 16:23:29 | Yes | Yes | 2025-09-04 20:01:15 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 20:40:21 |  | 2025-09-04 | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-04 20:17:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-12 17:52:26 | No | No |  | 12-08-2025. Replace RRU5516 L18 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-11 |  | N/A | Not assigned |  | No | No
PLPTB_2025 Coverage Expansion Ph1_EXP_BKK | THE PARKLAND PHETKASEM – THAPRA |  |  |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-09-22 11:24:57 | No | No |  |  |  | 2025-09-22 | 2025-09-29 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 18:29:59 | Yes | Yes | 2025-10-01 18:30:00 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-10-20 16:38:16 | Yes | Yes | 2025-09-24 18:18:19 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:15:54 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:20:11 | No | Yes | 2025-09-24 21:35:18 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-17 18:19:15 | No | No |  | 17-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A 80 81 E tili -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install completed |  | 2025-09-21 |  | N/A | Not assigned |  | No | No
PLRTB_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland Ratchada – Thapra |  |  |  |  | 2025-10-22 | 2025-10-22 | 2025-10-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-10-30 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 17:13:04 | Yes | Yes | 2025-10-30 17:13:04 |  | 2025-11-01 | 2025-11-01 | Chonradee Suwapan | Approved | Closed | 2025-11-05 16:33:10 | Yes | Yes | 2025-11-01 20:00:21 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 18:55:56 |  | 2025-11-01 | 2025-11-01 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-01 20:08:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-21 17:16:09 | No | No |  | 21-Oct-2025 Replace to Ant Vertical dual beam SA E tilt -200 80 81 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-21 |  | N/A | Not assigned |  | No | No
PLSTM_2025 Capacity Expansion Ph7_EXP_ER | The Plant Sirisothorn | 2025-12-04 |  | Clear Pending |  | 2025-12-31 | 2025-12-04 | 2025-12-04 | Teloneer Company Limited | N/A | Closed | 2025-12-04 14:54:27 | No | No |  |  |  | 2025-12-31 | 2025-12-04 | 2025-12-04 | Teloneer Company Limited | N/A | Closed | 2025-12-04 19:37:51 | Yes | Yes | 2025-12-06 17:09:20 |  | 2025-12-31 | 2025-12-06 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:38:58 | Yes | Yes | 2025-12-06 21:55:21 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-19 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 14:38:59 |  | 2025-12-31 | 2025-12-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:36:07 | Yes | Yes | 2025-12-04 15:49:30 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-04 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-04 18:51:29 | No | No |  | Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 40 + Remove RRU5505 x 1_PLSTM_H_2 New Sector 7 (Co AAU5768) + Main Dir = 40_PLSTM_H_7 New Sector J (Co AAU5768) + Main Dir = 40_PLSTM_H_J New Sector K (Co AAU5768) + Main Dir = 40_PLSTM_H_K |  | 2025-12-04 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-04 18:51:29 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLT1B_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland TaksinThapra (Front) |  |  |  |  | 2025-10-25 | 2025-10-25 | 2025-10-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-11-04 | 2025-11-04 | V Contribute Co., Ltd | N/A | Closed | 2025-11-04 15:27:29 | Yes | Yes | 2025-11-04 15:27:29 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-11 09:20:58 | Yes | Yes | 2025-11-04 19:58:41 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 20:50:03 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-04 20:24:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-24 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-24 17:07:14 | No | No |  | 24-10-2025. Replace Ant.12 port Condo Sec.A#，B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
PLT2B_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland Taksin-Thapra (Back) |  |  |  |  | 2025-10-25 | 2025-10-25 | 2025-10-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-11-04 | 2025-11-05 | V Contribute Co., Ltd | N/A | Closed | 2025-11-05 15:07:21 | Yes | Yes | 2025-11-05 15:07:21 |  | 2025-11-05 | 2025-11-05 | Chonradee Suwapan | Approved | Closed | 2025-11-11 16:14:42 | Yes | Yes | 2025-11-05 20:06:42 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 20:51:14 |  | 2025-11-05 | 2025-11-05 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-05 20:16:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-24 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-24 17:07:14 | No | No |  | 24-10-2025. Replace Ant.12 port Condo Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
PLW1B_2025 Coverage Expansion Ph1_EXP_BKK | The Parkland Ratchada-Wongsawang (RRU1) | 2025-09-15 |  |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-15 18:10:01 | No | No |  |  |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 16:48:02 | Yes | Yes | 2025-09-30 16:48:03 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-10-10 14:08:42 | Yes | Yes | 2025-12-02 14:54:52 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 18:57:11 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-22 19:58:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-15 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-15 19:06:55 | No | No |  | 2025-09-15_Replace to Ant Vertical Dual Beam Sector A(2RRU) ***RRU 80 Down before |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-14 |  | N/A | Not assigned |  | No | No
PMRPA_2025 Capacity Expansion Ph2_EXP_BKK | SOI PHRAYA MONTHAT RATCHASRI PICHIT |  |  |  |  | 2025-09-10 | 2025-09-18 | 2025-09-18 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-29 | 2025-09-22 | 2025-09-23 | V Contribute Co., Ltd | N/A | Closed | 2025-09-23 17:53:07 | Yes | Yes | 2025-09-23 17:53:07 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-10-08 14:52:51 | Yes | Yes | 2025-09-19 20:24:45 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 21:33:44 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-19 20:37:32 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-10 17:46:37 | No | No |  | 10-09-2025. Add UBBPg2#， RRU5516 L900#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-10 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-17 |  | N/A | Not assigned |  | No | No
PMRSB_2025 Coverage Expansion Ph1_EXP_BKK | PM Riverside condominium (Small cell) | 2025-09-03 |  |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-03 18:12:42 | No | No |  |  |  | 2025-09-30 | 2025-09-03 | 2025-09-03 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:17:09 | Yes | Yes | 2025-09-30 10:17:09 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:45:39 | Yes | Yes | 2025-09-20 20:17:19 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:40:57 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:11:29 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-03 19:40:52 | No | No |  | 3-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A 82 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-02 |  | N/A | Not assigned |  | No | No
PN30M_2025 Capacity Expansion Ph3_EXP_BKK | POEM SIN ROAD SOI 30 | [5 empty] | 2025-09-01 | 2025-09-01 | Akhom Srinara | N/A | Closed | 2025-09-01 09:42:25 | No | No |  |  |  |  | 2025-08-29 | 2025-08-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-29 21:25:52 | Yes | Yes | 2025-09-01 09:00:01 |  | 2025-09-03 | 2025-09-03 | Kontira Kowapradit | Approved | Closed | 2025-10-03 16:14:46 | Yes | Yes | 2025-09-03 17:08:05 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:43:25 |  | 2025-09-04 | 2025-09-04 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-09-04 19:53:44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-29 19:47:08 | No | No |  | 29-Aug-2025 Add AAU5636w S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-31 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
PNCAM_2025_Small DC_4K_with_MOEH_ER | Prinx Chengshan Tire (Thailand) Co., Ltd (A) |  |  |  | N/A | 2026-02-28 | N/A | 2026-01-09 | Teloneer Company Limited | N/A | Closed | 2026-01-09 11:23:36 | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PNGNM_2025 Capacity Expansion Ph3_EXP_BKK | WAT PHRA NGERN | [5 empty] | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-23 | 2025-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-23 17:25:39 | Yes | Yes | 2025-08-23 17:27:40 |  | 2025-08-27 | 2025-08-27 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-20 12:27:00 | Yes | Yes | 2025-08-27 20:05:15 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:44:44 |  | 2025-08-29 | 2025-08-29 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-10 17:27:23 | No | Yes | 2025-08-29 17:11:26 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-23 18:45:46 | No | No |  | 23-08-2025. Add AIRU5636w Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
PNT3M_2025 Coverage Expansion Ph2_EXP_BKK | SOI MU BAN PAN THONG 3 SOI 16 |  |  |  | 2025-09-01 | 2025-09-30 | 2025-09-01 | 2025-09-01 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-01 18:26:18 | No | No |  |  | 2025-09-01 | 2025-09-08 | 2025-09-02 | 2025-09-04 | Teloneer Company Limited | N/A | Closed | 2025-09-04 12:00:55 | Yes | Yes | 2025-09-04 14:22:16 |  |  | 2025-09-09 | Apichart Kampuang | Approved | Closed | 2025-10-03 16:14:46 | Yes | Yes | 2025-10-17 17:27:56 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:47:17 |  |  | 2025-08-14 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-14 17:30:20 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-01 18:01:13 | No | No |  | 01-09-2025. Add RRU3953#， Replace Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-01 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-31 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
PNTHM_2025 Capacity Expansion Ph8_EXP_ER | Poon CharoenTheppharat | 2026-02-05 |  |  |  | 2026-02-28 | 2026-02-04 | 2026-02-04 | Teloneer Company Limited | N/A | Closed | 2026-02-04 17:41:15 | No | No |  |  |  | 2026-02-28 | 2026-02-07 | 2026-02-10 | Teloneer Company Limited | N/A | Closed | 2026-02-10 18:35:06 | Yes | Yes | 2026-02-12 23:34:11 |  | 2026-02-28 | 2026-02-19 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-19 11:00:39 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 14:40:34 |  | 2026-01-31 | 2026-02-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-02-04 08:08:25 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-04 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-04 18:25:28 | No | No |  | Add RRU5505 x 1 + 4T4R_PNTHM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_PNTHM_H_3 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_PNTHM_H_4 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_PNTHM_L_4 |  | 2026-02-05 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-05 15:56:02 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
POLYT_2025 Capacity Expansion Ph3_EXP_SR | Polytechnic School Trang |  |  |  |  | 2025-09-03 | 2025-09-09 | 2025-09-09 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-09 16:31:13 | No | No |  |  |  | 2025-09-05 | 2025-09-03 | 2025-09-04 | Teloneer Company Limited | N/A | Closed | 2025-09-17 11:07:10 | Yes | Yes | 2025-09-17 11:07:10 |  | 2025-09-17 | 2025-09-18 | Teloneer Company Limited | Approved | Closed | 2025-09-26 09:29:03 | Yes | Yes | 2025-09-17 15:46:15 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:48:31 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-09-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-03 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-09-03 17:30:58 | No | No |  | 3 Sep 2025 Add AAU5636m sector3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-09-09 | Teloneer Company Limited | N/A | Closed | 2025-09-09 16:30:47 | No | No | [5 empty] | 2025-09-02 |  | N/A | Not assigned |  | No | No
PPMWM_2025 Capacity Expansion Ph7_EXP_ER | Pimpa Rim motorway | 2025-12-12 |  | Clear Pending |  | 2025-12-31 | 2025-12-11 | 2025-12-11 | Teloneer Company Limited | N/A | Closed | 2025-12-11 17:28:14 | No | No |  |  |  | 2025-12-31 | 2025-12-12 | 2025-12-13 | Teloneer Company Limited | N/A | Closed | 2025-12-13 12:06:50 | Yes | Yes | 2025-12-16 12:33:07 |  | 2025-12-31 | 2025-12-16 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:28:08 | Yes | Yes | 2025-12-16 18:01:43 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-19 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 14:41:12 |  | 2025-12-31 | 2025-12-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:26:56 | Yes | Yes | 2025-12-17 18:08:56 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-11 | Reungsak Junkong 00927496 | N/A | Closed | 2025-12-11 17:36:28 | No | No |  | Replace Antenna (Dualband Dualbeam)_PPMWM_H_1 Replace Antenna (Co Antenna)&Replace RRU (RRU5516_900) + 4T4R_PPMWM_L_1 Replace RRU (RRU5516_900) + 4T4R_PPMWM_L_3 Replace Antenna (Co Antenna)_PPMWM_N_1 New L18L21 + 4T4R+ Add RRU5526 x 1 + Co Antenna_PPMWM_H_6 New L26F5 + NR26 (Co RRU5818) + Co Antenna_PPMWM_N_6 |  | 2025-12-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-12 14:48:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRS4M_2025 Coverage Expansion Ph2_EXP_BKK | PHRAEKSA ROAD 4 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  | 2025-08-11 | 2025-08-12 | 2025-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-12 12:31:33 | Yes | Yes | 2025-08-15 15:24:45 |  | 2025-08-15 | 2025-08-15 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-22 13:14:50 | Yes | Yes | 2025-08-15 19:54:27 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 19:12:06 |  | 2025-09-03 | 2025-09-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-03 10:30:23 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-12 18:56:56 | No | No |  | 12-Aug-2025 Add RRU3953 S1 Replace Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
PS10M_2025 Capacity Expansion Ph3_EXP_BKK | SOI. PHRAEK SA 10 | 2025-09-02 |  |  |  | 2025-09-02 | 2025-09-11 | 2025-09-11 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-30 | 2025-09-10 | 2025-09-11 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:17:23 | Yes | Yes | 2025-09-30 10:17:23 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-10-02 16:17:51 | Yes | Yes | 2025-09-12 21:15:55 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-02 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:54:50 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-12 22:26:44 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-02 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-02 17:59:46 | No | No |  | 2025-09-02_Add AAU5636w Sector 1#， Replace RRU3962 to RRU5516(18-21) #， Replace to Ant 8 port Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-10 |  | N/A | Not assigned |  | No | No
PS4TM_2025 Capacity Expansion Ph6_EXP_BKK | PASSORN 4 TANYABURI |  |  |  |  | 2025-12-23 | 2025-12-23 | 2025-12-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-23 17:47:19 | No | No |  |  |  | 2025-12-31 | 2025-12-22 | 2025-12-23 | V Contribute Co., Ltd | N/A | Closed | 2025-12-23 19:56:24 | Yes | Yes | 2025-12-23 19:56:25 |  | 2026-01-20 | 2026-01-20 | Chonradee Suwapan | Approved | Closed | 2026-01-22 15:33:02 | Yes | Yes | 2026-01-20 22:52:22 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 13:04:28 |  | 2026-01-20 | 2026-01-20 | Chonradee Suwapan | Approved | Closed | 2026-01-29 17:09:02 | Yes | Yes | 2026-01-20 22:56:19 |  |  | 2025-12-31 | 2025-12-20 | V Contribute Co., Ltd | N/A | Closed | 2025-12-20 16:57:21 | No | No |  |  |  |  | 2025-12-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-23 16:55:48 | No | No |  | 23-12-2025. Replace Ant.4 port Sec.7 Fix VSWR //20-12-2025. Add RRU5516 L900#， Ant.4 port Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PS54M_2025 Capacity Expansion Ph2_EXP_BKK | PHETKASEM SOI 54 | 2025-08-18 |  |  |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-18 18:56:06 | No | No |  |  |  | 2025-08-29 | 2025-08-19 | 2025-08-23 | V Contribute Co., Ltd | N/A | Closed | 2025-08-23 12:55:45 | Yes | Yes | 2025-08-23 12:57:11 |  | 2025-09-09 | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-11 11:45:53 | Yes | Yes | 2025-12-02 11:11:36 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:52 | Yes | Yes | 2025-10-06 20:58:38 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:38 | No | Yes | 2025-09-03 20:54:58 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-18 16:39:53 | No | No |  | 18-Aug-2025 Add RRU5516 (1800-2100) S3 S8 Remove RRU3962*2 Replace Ant 12port Add g2 d6=2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-15 |  | N/A | Not assigned |  | No | No
PSDTM_2025 Capacity Expansion NW Modernization_EXP_BKK | President Tower |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  | 2026-04-30 | 2026-04-30 | 2026-05-12 | 2026-05-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-13 10:05:43 | Yes | Yes | 2026-05-20 09:22:54 |  | 2026-06-24 | 2026-06-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-04 16:44:42 | Yes | Yes | 2026-06-24 15:09:22 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-04 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:27:19 | Yes | Yes | 2026-07-14 22:55:14 |  |  | 2026-04-30 | 2026-04-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-22 12:18:59 | No | No |  |  |  |  | 2026-04-21 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-04-21 17:27:51 | No | No |  | 21-Apr-26 Replace RRU3953 > RRU5516 S1 S2#，Replace To RRU5507x2 S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PSKLN_2025 Capacity Expansion Ph6_EXP_SR | Pump Shell Khwanmueang Lang Suan_PEA |  |  |  |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | Teloneer Company Limited | N/A | Closed | 2026-02-03 14:31:56 | No | No |  |  |  | 2025-12-08 | 2026-02-03 | 2026-02-05 | Teloneer Company Limited | N/A | Closed | 2026-02-05 15:38:30 | Yes | Yes | 2026-02-05 15:42:27 |  | 2026-02-05 | 2026-02-05 | Nattawoot Suwan | Approved | Closed | 2026-03-05 17:10:15 | Yes | Yes | 2026-02-11 08:26:20 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 14:42:28 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-02-03 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-02-03 18:30:29 | No | No |  | Add card d5*1#，Add Combiner MB&HB Add RRU5526*1 > Ex Ant No Ret Sector A Add RRU5526*1 > Ex Ant No Ret Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-03-09 | Nattawoot Suwan | N/A | Closed | 2026-03-09 14:42:38 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PSV4M_2025 Capacity Expansion Ph2_EXP_BKK | PHANASON VILLAGE 4 | 2025-08-21 |  |  |  | 2025-08-21 | 2025-08-21 | 2025-08-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-21 17:56:59 | No | No |  |  |  | 2025-08-30 | 2025-08-24 | 2025-08-24 | V Contribute Co., Ltd | N/A | Closed | 2025-08-24 17:59:01 | Yes | Yes | 2025-08-24 18:00:31 |  |  | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-09-15 17:02:19 | Yes | Yes | 2025-09-05 20:59:01 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:13 | Yes | Yes | 2025-09-23 00:37:18 |  | 2025-09-05 | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-05 20:38:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-21 18:00:17 | No | No |  | 21-Aug-2025 Add RRU5516 (1800-2100) S8 Remove RRU5507 Replace Ant 8port add g2 Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-20 |  | N/A | Not assigned |  | No | No
PSV4M_2025 Capacity Expansion Ph3_EXP_BKK | PHANASON VILLAGE 4 | 2025-08-25 |  |  |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-25 17:13:12 | No | No |  |  |  | 2025-08-31 | 2025-09-03 | 2025-09-05 | V Contribute Co., Ltd | N/A | Closed | 2025-09-05 14:49:37 | Yes | Yes | 2025-09-05 14:53:19 |  |  | 2025-09-08 | Chonradee Suwapan | Approved | Closed | 2025-09-18 16:40:10 | Yes | Yes | 2025-09-16 23:26:54 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 19:06:56 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:28 | No | Yes | 2025-09-06 19:31:29 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-25 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-25 17:09:39 | No | No |  | 12-Sep-2025 Clear VSWR S8 25-08-2025. Replace RRU5516 L18#， Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-22 |  | N/A | Not assigned |  | No | No
PT15M_2025 Capacity Expansion Ph2_EXP_BKK | PATTANAKARN SOI 15 | 2025-09-16 |  |  |  | 2025-09-19 | 2025-09-19 | 2025-09-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-19 12:21:44 | No | No |  |  |  | 2025-09-30 | 2025-09-30 | 2025-10-02 | V Contribute Co., Ltd | N/A | Closed | 2025-10-02 16:16:30 | Yes | Yes | 2025-10-02 16:16:30 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-10-17 17:48:05 | Yes | Yes | 2025-09-24 18:18:46 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:19:33 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:20:11 | No | Yes | 2025-09-24 21:37:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-16 17:43:25 | No | No |  | 16-Sep-2025 Add RRU5516 (1800-2100) S1 Remove RRU3962 Replace Ant 8port Co S1 S6 Add RRU5516 (1800-2100) S6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-18 |  | N/A | Not assigned |  | No | No
PT15M_2025 Capacity Expansion Ph7_EXP_BKK | PATTANAKARN SOI 15 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  | 2026-02-11 | 2026-02-28 | 2026-02-11 | 2026-06-09 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-09 15:34:21 | Yes | Yes | 2026-06-10 09:54:39 |  | 2026-06-22 | 2026-06-22 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-16 16:54:20 | Yes | Yes | 2026-06-22 15:14:14 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-16 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:27:19 | Yes | Yes | 2026-08-01 21:47:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-31 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-31 18:30:19 | No | No |  | 31-01-2569. Replace RRU5507 to AAU5768 Sec.2#， UBBPeb to UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PTRNM_2025 Capacity Expansion Ph6_EXP_BKK | SOI MOOBANPATTARANIWET | [5 empty] | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:42:22 | No | No |  |  |  | 2025-12-11 | 2025-12-12 | 2025-12-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-13 10:23:35 | Yes | Yes | 2025-12-19 19:12:16 |  | 2025-12-21 | 2025-12-21 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-22 15:33:02 | Yes | Yes | 2026-01-15 12:14:12 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 13:06:40 |  | 2025-12-21 | 2025-12-21 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 10:15:22 | Yes | Yes | 2025-12-21 19:49:26 |  |  | 2025-12-31 | 2025-12-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-10 15:39:58 | No | No |  |  |  |  | 2025-12-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-10 17:44:02 | No | No |  | 10-Dec-2025 AAU5636w sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PTS1B_2025 Capacity Expansion Ph2_EXP_BKK | PHAYAPIROM REGENT TAKSINSATHORN (ROOFTOP) |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-31 | 2025-10-30 | 2025-10-31 | V Contribute Co., Ltd | N/A | Closed | 2025-10-31 13:34:06 | Yes | Yes | 2025-10-31 13:34:06 |  | 2025-10-28 | 2025-10-28 | Chonradee Suwapan | Approved | Closed | 2025-11-11 16:13:53 | Yes | Yes | 2026-01-06 16:43:45 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 20:57:19 |  | 2025-10-28 | 2025-10-28 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-28 19:32:56 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-14 17:38:55 | No | No |  | 14-10-2025. Add UBBPg2#， RRU5516 L900#， Ant.12 port Sec.C#， D |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
PWBRM_2025 Capacity Expansion Ph3_EXP_BKK | PRAWET-KHLONG BUA ROY ROAD (RO POR CHOR SOR POR 3047) |  |  |  | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-04 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-20 10:22:44 | No | No |  |  | 2025-09-25 | 2025-09-27 | 2025-10-02 | 2025-10-02 | Teloneer Company Limited | N/A | Closed | 2025-10-02 20:03:16 | Yes | Yes | 2025-10-03 15:00:06 |  |  | 2025-10-06 | Apichart Kampuang | Approved | Closed | 2025-10-24 17:46:27 | Yes | Yes | 2026-03-14 14:59:12 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:55 | Yes | Yes | 2025-10-27 18:29:42 |  |  | 2025-09-02 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 23:30:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-22 17:31:04 | No | No |  | 22-09-2025. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， AIRU5636w Sec.1#， 2#， 3#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-04 |  | N/A | Not assigned |  | No | No
PWK2M_2025 Capacity Expansion Ph3_EXP_BKK | PRACHA UTHIT-WAT KHU SANG STATION 2 | [5 empty] | 2025-09-01 | 2025-09-01 | Akhom Srinara | N/A | Closed | 2025-09-01 09:42:25 | No | No |  |  |  |  | 2025-08-30 | 2025-08-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-30 19:21:13 | Yes | Yes | 2025-08-30 19:22:32 |  | 2025-09-03 | 2025-09-03 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-30 15:29:58 | Yes | Yes | 2025-09-03 20:06:41 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:51 | Yes | Yes | 2025-10-06 21:15:09 |  | 2025-09-03 | 2025-09-03 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 19:00:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-30 20:43:51 | No | No |  | 30-Aug-2025 Add RRU5516 (18002100) S8 Remove RRU3962 Replace Ant 8 port Add g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-31 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
PWK2M_2025 Coverage Expansion Ph2_EXP_BKK | PRACHA UTHIT-WAT KHU SANG STATION 2 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-11 | 2025-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-11 19:04:23 | Yes | Yes | 2025-08-11 19:05:54 |  | 2025-08-19 | 2025-08-19 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:35:50 | Yes | Yes | 2025-08-19 15:57:27 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 14:09:31 |  | 2025-08-31 | 2025-08-31 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-08-31 16:11:31 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-11 18:15:26 | No | No |  | 2025-08-11_Add RRU3953#， Replace Ant to 4 port Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
PWMSM_2025 Capacity Expansion Ph5_EXP_ER | Pak Tang Wat Mongkol Sawat | 2025-10-14 | Thcp_phengyang | Install & Integrate |  | 2025-10-31 | 2025-10-14 | 2025-10-14 | Teloneer Company Limited | N/A | Closed | 2025-10-14 20:09:37 | No | No |  |  |  | 2025-10-31 | 2025-10-14 | 2025-10-14 | Teloneer Company Limited | N/A | Closed | 2025-10-14 16:16:55 | Yes | Yes | 2025-10-14 17:09:49 |  | 2025-10-31 | 2025-10-14 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-28 10:26:04 | Yes | Yes | 2025-11-07 13:39:48 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-11-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 19:14:10 |  | 2025-10-15 | 2025-10-09 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-10 14:39:00 | Yes | Yes | 2025-10-09 16:32:25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-14 |  | 2025-10-14 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-14 16:35:25 | No | No |  | **waiting on-service LNR26 -- Add UBBPg3a #，New L26F5 + NR26 (New AAU5636w) S2 |  | 2025-10-16 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-16 16:35:56 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PY83M_2025 Capacity Expansion Ph5_EXP_BKK | PHAHONYOTHIN SOI 83 | [5 empty] | 2025-12-06 | 2025-12-06 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  | 2025-11-18 | 2025-11-20 | 2025-11-20 | 2025-11-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-25 16:26:07 | Yes | Yes | 2025-12-04 13:15:43 |  | 2025-12-08 | 2025-12-08 | Aomchun Jittreemit | Approved | Closed | 2025-12-12 14:57:39 | Yes | Yes | 2025-12-09 14:49:49 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 20:57:19 |  | 2026-04-09 | 2026-04-09 | Aomchun Jittreemit | Approved | Closed | 2026-06-19 15:23:48 | Yes | Yes | 2026-04-09 14:59:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-19 13:58:26 | No | No |  | 19-Nov-2025 Add RRU5526 S2 Remove RRU5507 Replace Ant 8port Add g2 Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PYPNM_2025 Capacity Expansion Ph3_EXP_BKK | SOI PHU YAI PIN (SOI THAVEEWATTANA 13/1) | [5 empty] | 2025-09-01 | 2025-09-01 | Akhom Srinara | N/A | Closed | 2025-09-01 09:42:25 | No | No |  |  |  |  | 2025-08-30 | 2025-08-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-31 10:46:02 | Yes | Yes | 2025-09-01 14:25:38 |  | 2025-09-04 | 2025-09-04 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-30 15:29:58 | Yes | Yes | 2025-09-11 17:32:28 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:51 | Yes | Yes | 2025-10-06 21:16:23 |  | 2025-09-04 | 2025-09-04 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-04 11:00:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-30 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-30 19:00:25 | No | No |  | 30-08-2025. Replace RRU5516 L18#， Ant.8 port Sec.3#， 8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-31 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
PYTSM_2025 Capacity Expansion NW Modernization_EXP_BKK | PARIYAT TITHAM SCHOOL |  |  |  |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-20 18:20:28 | No | No |  |  |  | 2026-02-07 | 2026-02-11 | 2026-03-11 | V Contribute Co., Ltd | N/A | Closed | 2026-03-11 13:16:44 | Yes | Yes | 2026-03-11 13:16:45 |  | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-17 21:40:29 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:08:33 |  | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-17 21:55:13 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-20 18:57:02 | No | No |  | 20-01-2026. Replace RRU5507 to AAU5768 Sec.1#， RRU3962 to RRU5526#， Ant.8 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PYWRM_2025 Capacity Expansion Ph3_EXP_BKK | MU BAN PIYA WARAROM (BAN KLUAI) | 2025-08-30 |  |  |  | 2025-08-30 | 2025-08-31 | 2025-08-31 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-31 12:17:45 | No | No |  |  |  | 2025-09-05 | 2025-09-01 | 2025-09-02 | V Contribute Co., Ltd | N/A | Closed | 2025-09-02 11:15:28 | Yes | Yes | 2025-09-02 11:16:40 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:46:13 | Yes | Yes | 2025-12-02 16:03:40 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:51 | Yes | Yes | 2025-10-06 21:17:38 |  | 2025-09-11 | 2025-09-11 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:04 | No | Yes | 2025-09-11 21:35:48 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-30 20:42:42 | No | No |  | 30-Aug-2025 Add AAU5636w S2 S3 add g2 Before Set MT |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-31 |  | N/A | Not assigned |  | No | No
PYWRM_2025 Coverage Expansion Ph2_EXP_BKK | MU BAN PIYA WARAROM (BAN KLUAI) | 2025-08-02 |  |  |  | 2025-08-02 | 2025-08-02 | 2025-08-02 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-02 17:51:49 | No | No |  |  |  | 2025-08-22 | 2025-08-13 | 2025-08-14 | V Contribute Co., Ltd | N/A | Closed | 2025-08-14 11:19:58 | Yes | Yes | 2025-08-14 11:21:36 |  | 2025-08-19 | 2025-08-19 | Chonradee Suwapan | Approved | Closed | 2025-08-25 17:35:50 | Yes | Yes | 2025-08-19 23:30:56 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 19:14:40 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:41:12 | No | Yes | 2025-08-05 09:06:23 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-02 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-02 17:04:11 | No | No |  | 02-08-2025. Add RRU3953#， Replace Ant.4 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
R116M_2025 Capacity Expansion Ph2_EXP_BKK | SOI RAMKAMHAENG 116 |  |  |  | 2025-08-18 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-18 | 2025-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-18 17:38:56 | Yes | Yes | 2025-08-21 14:51:34 |  | 2025-08-21 | 2025-08-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-15 17:01:20 | Yes | Yes | 2025-08-26 18:21:43 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:13 | Yes | Yes | 2025-09-23 00:55:43 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 20:05:25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-18 16:39:23 | No | No |  | 18-Aug-2025 Add RRU5516 (1800-2100) S8 Remove RRU5507 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
R116M_2025 Capacity Expansion Ph6_EXP_BKK | SOI RAMKAMHAENG 116 | [5 empty] | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:42:22 | No | No |  |  |  | 2025-12-08 | 2025-12-09 | 2025-12-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-09 20:03:32 | Yes | Yes | 2025-12-13 11:43:24 |  | 2025-12-19 | 2025-12-19 | Aomchun Jittreemit | Approved | Closed | 2026-01-09 17:03:57 | Yes | Yes | 2026-01-15 11:43:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 12:46:25 |  | 2025-12-22 | 2025-12-22 | Aomchun Jittreemit | Approved | Closed | 2026-03-12 10:15:22 | Yes | Yes | 2025-12-22 11:40:36 |  |  | 2025-12-31 | 2025-12-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-08 16:15:24 | No | No |  |  |  |  | 2025-12-08 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-08 17:40:06 | No | No |  | 08-12-2025. Add AIRU5636w Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R209M_2025 Capacity Expansion Ph3_EXP_BKK | SOI RAMKHAMHAENG 209 |  |  |  | 2025-09-12 | 2025-09-19 | 2025-09-30 | 2025-09-30 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-30 10:53:47 | No | No |  |  | 2025-09-12 | 2025-09-23 | 2025-09-22 | 2025-09-22 | Teloneer Company Limited | N/A | Closed | 2025-09-22 12:29:58 | Yes | Yes | 2025-09-23 14:37:22 |  |  | 2025-09-23 | Apichart Kampuang | Approved | Closed | 2025-10-16 16:36:07 | Yes | Yes | 2025-09-23 18:21:55 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:24:26 |  |  | 2025-09-02 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 23:30:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-13 18:37:20 | No | No |  | 13-09-2025. Add UBBPg3a#， AIRU5636w#， RRU3953 x2#， Ant.12 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-29 |  | N/A | Not assigned |  | No | No
R250M_2025 Capacity Expansion Ph2_EXP_BKK | RAMA 2 SOI 50 | 2025-11-10 |  |  |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-10 17:58:32 | No | No |  |  |  | 2025-10-31 | 2025-11-17 | 2025-11-17 | V Contribute Co., Ltd | N/A | Closed | 2025-11-17 15:00:58 | Yes | Yes | 2025-11-17 15:00:59 |  | 2025-11-12 | 2025-11-12 | Chonradee Suwapan | Approved | Closed | 2025-11-20 16:09:07 | Yes | Yes | 2025-11-12 18:56:30 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 21:02:09 |  | 2025-11-12 | 2025-11-12 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-12 18:58:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-31 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-31 16:14:20 | No | No |  | 31-Oct-2025 RRU5516 (1800-2100) S6 Replace Ant 12port 4/3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-11-06 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | Completed |  | 2025-11-07 |  | N/A | Not assigned |  | No | No
R292M_2025 Coverage Expansion Ph2_EXP_BKK | Soi Ramkamhaeng 29 Station 2 | [5 empty] | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-21 | 2025-08-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-22 09:59:54 | Yes | Yes | 2025-08-28 13:10:12 |  | 2025-08-29 | 2025-08-29 | Muhamadnase Chesamae | Approved | Closed | 2025-12-02 18:04:31 | Yes | Yes | 2025-09-08 13:54:04 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-03-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:08:52 |  | 2025-09-05 | 2025-09-05 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-09-05 15:42:46 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-21 18:34:48 | No | No |  | 21-08-2025. Add RRU3953#， Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | รอเข้าเปลี่ยน triple mount |  |  | Jia Rui 80023782 | N/A | Not assigned |  | No | No
R301A_2025 Capacity Expansion Ph2_EXP_BKK | SMALL CELL SOI RAMKHAMHAENG 30/1 |  |  |  |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-01 09:34:25 | No | No |  |  |  | 2025-09-30 | 2025-10-02 | 2025-10-03 | V Contribute Co., Ltd | N/A | Closed | 2025-10-03 09:41:45 | Yes | Yes | 2025-10-03 09:41:46 |  | 2025-12-07 | 2025-12-07 | Chonradee Suwapan | Approved | Closed | 2025-12-15 09:24:38 | Yes | Yes | 2025-12-07 23:20:09 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:36 | Yes | Yes | 2026-01-09 21:03:23 |  | 2025-12-07 | 2025-12-07 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-12-07 23:31:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-01 16:20:06 | No | No |  | 26-11-2025. Add RRU5516 L900 Sec.B //19-Sep-2025 Add g2 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-28 |  | N/A | Not assigned |  | No | No
R431M_2025 Capacity Expansion Ph7_EXP_BKK | Soi RAMKHAMHAENG SOI 43/1 |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 16:26:40 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-02-03 | 2026-02-04 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-04 10:23:23 | Yes | Yes | 2026-04-21 12:01:50 |  | 2026-04-29 | 2026-04-29 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-05-08 09:30:04 | Yes | Yes | 2026-04-29 16:51:29 | PAT first time pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:27:19 | Yes | Yes | 2026-08-01 21:47:21 |  |  | 2026-06-23 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-01-24 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-24 20:02:15 | No | No |  | 24-Jan-2026 Add RRU5526 Sector 2#，7 Remove RRU5507 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R522M_2025 Capacity Expansion Ph2_EXP_BKK | SOI RAMKHAMHAENG 52/2 (SIN SETTHI) |  |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-28 | 2025-10-28 | V Contribute Co., Ltd | N/A | Closed | 2025-10-28 19:59:54 | Yes | Yes | 2025-10-28 19:59:55 |  | 2025-10-20 | 2025-10-20 | Chonradee Suwapan | Approved | Closed | 2025-11-03 20:59:11 | Yes | Yes | 2026-01-06 20:34:54 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:24 | Yes | Yes | 2025-11-06 19:17:51 |  | 2025-10-20 | 2025-10-20 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-10-20 17:22:12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-08 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-08 17:32:05 | No | No |  | 08-10-2025. Add RRU5516 L18 Sec.6#， Replace Ant.12 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
R532M_2025 Capacity Expansion Ph2_EXP_BKK | RAMKAMHAENG53 YAEK2 | 2025-08-18 |  |  |  | 2025-08-18 | 2025-08-18 | 2025-08-18 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-18 18:56:06 | No | No |  |  |  | 2025-08-29 | 2025-08-25 | 2025-08-25 | V Contribute Co., Ltd | N/A | Closed | 2025-08-25 18:05:03 | Yes | Yes | 2025-08-25 18:06:48 |  |  | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-09-15 17:01:13 | Yes | Yes | 2025-09-05 20:30:28 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:13 | Yes | Yes | 2025-09-23 00:56:56 |  | 2025-09-05 | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-05 20:39:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-18 16:38:24 | No | No |  | 18-Aug-2025 Add AAU5636w S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-17 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-09-16 16:57:05 | No | No
R533A_2025 Capacity Expansion Ph7_EXP_BKK | RAMKAMHAENG53 YAEK3 |  |  |  |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-01-31 | 2026-02-13 | 2026-04-07 | V Contribute Co., Ltd | N/A | Closed | 2026-04-07 14:58:45 | Yes | Yes | 2026-04-07 14:58:45 |  | 2026-02-07 | 2026-02-07 | Chonradee Suwapan | Approved | Closed | 2026-02-16 16:29:46 | Yes | Yes | 2026-02-07 22:06:54 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:09:11 |  | 2026-02-07 | 2026-02-07 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-07 22:12:13 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-15 14:02:08 | No | No |  | 15-Jan-2026 Add RRU5516 (700900) Sector B#，C Remove RRU3953 *4 Add RRU5526 Sector D Add g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
R613M_2025 Capacity Expansion NW Modernization_EXP_BKK | RAMA6SOI13 |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:30:39 | No | No |  |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-06-08 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-08 17:35:49 | Yes | Yes | 2026-06-09 09:32:36 |  | 2026-06-25 | 2026-06-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approving | Assigned |  | Yes | Yes | 2026-06-25 16:44:49 | 1.Page 6#，remove card must be UBBPeb. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:27:19 | Yes | Yes | 2026-08-01 20:16:22 |  |  | 2026-05-09 | 2026-05-09 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-09 18:20:26 | No | No |  |  |  |  | 2026-05-09 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-05-09 17:14:56 | No | No |  | 09-May-26 Replace RRU2600 > AAU2600 S1 S2#，Remove RRU S6 S7#， Add AAU5768 S1 S2 #，Replace To UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAKKW_2025 Capacity Expansion Ph4_EXP_SR | RAK KHWAN |  |  |  | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-11-05 | Teloneer Company Limited | N/A | Closed | 2025-11-10 09:17:00 | No | No |  |  |  | 2025-09-26 | 2025-10-31 | 2025-11-05 | Teloneer Company Limited | N/A | Closed | 2025-11-05 10:45:05 | Yes | Yes | 2025-11-05 10:46:56 |  | 2025-11-03 | 2025-11-03 | Nattawoot Suwan | Approved | Closed | 2025-11-03 11:19:44 | Yes | Yes | 2025-11-10 21:16:54 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-18 | 2025-11-18 | Chayanat mangmool WX1323423 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 21:03:22 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-10-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-31 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-10-31 12:06:21 | No | No |  | S2 Rep RRU3826(2) to RRU5516MB > existing Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-30 |  | N/A | Not assigned |  | No | No
RAMAM_2025 Capacity Expansion Ph5_EXP_BKK | RAMATHIBADEE HOSPITAL | [5 empty] | 2025-12-11 | 2025-12-11 | Narongsak wanichachiwa | N/A | Closed | 2025-12-23 09:27:43 | No | No |  |  |  | 2025-11-18 | 2025-11-30 | 2025-11-30 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-11-30 10:29:33 | Yes | Yes | 2025-11-30 13:11:33 |  |  | 2025-12-17 | OATTAPAN AUTTAHON | Approved | Closed | 2026-01-07 16:05:42 | Yes | Yes | 2025-12-17 16:15:09 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 21:07:01 |  | 2025-12-25 | 2025-12-25 | Narongsak wanichachiwa(Turnkey Communication Services Public Company Limited.) | Approved | Closed | 2026-03-12 10:15:38 | Yes | Yes | 2025-12-25 16:46:29 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-29 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-29 18:01:22 | No | No |  | 29-11-2025. Replace RRU5526 Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RBC1B_2025 Capacity Expansion Ph2_EXP_BKK | RATBURANA CONDO TOWN |  |  |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-09-22 11:24:57 | No | No |  |  |  | 2025-10-10 | 2025-10-07 | 2025-10-07 | V Contribute Co., Ltd | N/A | Closed | 2025-10-07 20:54:08 | Yes | Yes | 2025-10-07 20:54:09 |  | 2025-09-26 | 2025-09-26 | Chonradee Suwapan | Approved | Closed | 2025-10-21 14:04:31 | Yes | Yes | 2025-12-02 17:25:33 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:25:39 |  | 2025-09-26 | 2025-09-26 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-09-26 18:46:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-20 16:34:41 | No | No |  | 20-Sep-2025 Add RRU5818 SB Replace Ant 12port No RET 5/5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-21 |  | N/A | Not assigned |  | No | No
RBPOM_2025 Capacity Expansion Ph3_EXP_BKK | RATTANATHIBET POST OFFICE | [5 empty] | 2025-10-21 | 2025-10-21 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-09 | 2025-10-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-10 22:57:33 | Yes | Yes | 2025-10-23 14:45:03 |  | 2025-10-21 | 2025-10-23 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-24 13:21:41 | Yes | Yes | 2025-10-25 12:14:48 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:55 | Yes | Yes | 2025-10-27 18:34:24 |  | 2025-10-21 | 2025-10-21 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-28 14:33:42 | No | Yes | 2025-10-21 17:30:06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-11 17:36:17 | No | No |  | 11-10-2025. Replace Ant.8 port Sec.2 //10-10-2025. Replace RRU5516 L18#， Ant.6 port#， Add AIRU5636w Sec.1#， 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-20 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
RCNVB_2025 Coverage Expansion Ph1_New_BKK | Royal Thai Navy Club |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 17:49:52 | No | No |  |  |  | 2026-02-14 | 2026-03-17 | 2026-03-18 | V Contribute Co., Ltd | N/A | Closed | 2026-03-18 10:15:36 | Yes | Yes | 2026-03-18 10:15:36 |  | 2026-02-21 | 2026-02-21 | Chonradee Suwapan | Approving | Assigned |  | Yes | Yes | 2026-04-02 12:23:00 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-19 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | Yes | No |  |  | 2026-02-20 | 2026-02-20 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:45:55 | Yes | Yes | 2026-02-20 21:56:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-12 14:03:17 | No | No |  | 12-Feb-2026 Add RRU3962 Sector A2 sector C Add Ant 4port *2 (No Ret ) ยังไม่มี Cell 10-02-2026. ***RRU Sec.A2#， C เสีย Need Replace //Add RRU3962 x1 Sec.B#， C#， RRU3962 x2 SFN Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-02-18 |  | N/A | Not assigned |  | No | No
RG20B_2025 Capacity Expansion Ph2_EXP_BKK | REGENT HOME 20 PRECHACHUEN 16 | [5 empty] | 2025-10-09 | 2025-10-09 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-01 | 2025-10-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-31 14:12:47 | Yes | Yes | 2025-11-03 13:40:17 |  | 2025-11-03 | 2025-11-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-05 18:20:28 | Yes | Yes | 2025-11-03 17:10:42 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:29:18 |  | 2025-12-18 | 2025-12-18 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:22:14 | No | Yes | 2025-12-18 19:18:56 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-02 18:48:25 | No | No |  | 2-Oct-2025 Add RRU5818 SA Add g3a ///Replace Ant 12port *2 No ret Done 1-Oct-2025 ***Pending Add RRU5818 SA Add g3a ///Replace Ant 12port No ret Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-08 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
RHR1B_2025 Coverage Expansion Ph1_EXP_BKK | Rhythm Ratchada (Swimming Pool) |  |  |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-10-31 | 2025-10-22 | 2025-10-24 | V Contribute Co., Ltd | N/A | Closed | 2025-10-24 21:06:21 | Yes | Yes | 2025-10-24 21:06:21 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-03 20:59:11 | Yes | Yes | 2025-10-30 20:39:16 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-02 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 19:23:55 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-30 20:51:36 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-20 15:36:47 | No | No |  | 20-Oct-2025 Replace to Ant Vertical dual beam SA E tilt -200 80 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-22 |  | N/A | Not assigned |  | No | No
RHR2B_2025 Coverage Expansion Ph1_EXP_BKK | Rhythm Ratchada (Front) |  |  |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-10-31 | 2025-10-22 | 2025-10-24 | V Contribute Co., Ltd | N/A | Closed | 2025-10-24 10:01:08 | Yes | Yes | 2025-10-24 10:01:08 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-03 20:59:11 | Yes | Yes | 2025-10-30 20:40:13 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-02 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 19:25:10 |  | 2025-10-30 | 2025-10-30 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-30 20:52:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-20 15:37:01 | No | No |  | 20-Oct-2025 Replace to Ant Vertical dual beam SA E tilt -200 81 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-22 |  | N/A | Not assigned |  | No | No
RKBKM_2025 Capacity Expansion Ph2_EXP_BKK | RUNGKARN VILLAGE BANG KHU RAT | 2025-09-03 |  |  |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-26 18:32:59 | No | No |  |  |  | 2025-08-31 | 2025-09-11 | 2025-09-11 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:17:36 | Yes | Yes | 2025-09-30 10:17:36 |  | 2025-09-10 | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-25 14:38:34 | Yes | Yes | 2025-12-03 15:21:29 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 19:28:47 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-10 21:25:33 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-26 16:58:07 | No | No |  | 26-08-2025. Replace BBU5900#， UMPTg2 10G#， RRU5516 L18#， Ant.8 port Sec.1#， Add GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-25 |  | N/A | Not assigned |  | No | No
RKBKM_2025 Capacity Expansion Ph3_EXP_BKK | RUNGKARN VILLAGE BANG KHU RAT |  |  |  |  | 2025-09-08 | 2025-09-08 | 2025-09-08 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-08 16:55:57 | No | No |  |  |  | 2025-09-26 | 2025-09-22 | 2025-09-29 | V Contribute Co., Ltd | N/A | Closed | 2025-09-29 11:28:40 | Yes | Yes | 2025-09-29 11:28:41 |  | 2025-09-16 | 2025-09-16 | Chonradee Suwapan | Approved | Closed | 2025-10-07 16:22:25 | Yes | Yes | 2025-10-06 18:31:50 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 21:42:30 |  | 2025-09-16 | 2025-09-16 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 22:17:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-08 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-08 18:41:16 | No | No |  | 2025-09-08_Add UBBPg3a#， UBBPg2#， Add AAU5636w Sector 2#，3#， Replace RRU5507 to RRU5516 Sector 2#，3#， Replace to Ant 8 port Sector 3#， Replace to Ant 6 port Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-07 |  | N/A | Not assigned |  | No | No
RL11M_New site by Co-NT_New_BKK | Lamlukka 11 Road |  |  |  |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-01 09:34:25 | No | No |  |  |  | 2025-12-06 | 2025-11-25 | 2025-11-27 | V Contribute Co., Ltd | N/A | Closed | 2025-11-27 10:26:32 | Yes | Yes | 2025-11-27 10:26:32 |  | 2025-12-09 | 2025-12-09 | Chonradee Suwapan | Approved | Closed | 2026-02-09 17:33:30 | Yes | Yes | 2026-01-14 15:46:13 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-05-26 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-12-09 | 2025-12-09 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:54:33 | No | Yes | 2025-12-09 20:59:09 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-25 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-11-25 16:41:07 | No | No |  | 2025-11-25_Add RRU3962#， Ant 8 port Sector 1#，2#，3#， Set alarm port 0-5#，7//2025-11-24_Newsite Add UBBPd5(3) |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-11-18 | Paphawarin Yoopoo WX1434740 | Approved | Closed | 2025-11-25 06:03:07 | Yes | Yes | 2025-11-24 18:48:45 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
RM4XA_2025 Capacity Expansion NW Modernization_EXP_BKK | RAMA EXPRESSWAY | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  | 2026-02-16 | 2026-02-28 | 2026-02-19 | 2026-02-20 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-20 11:09:17 | Yes | Yes | 2026-02-20 11:33:42 |  | 2026-02-20 | 2026-02-20 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-05-22 16:35:49 | Yes | Yes | 2026-05-22 09:53:58 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-16 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-18 | 2026-03-18 | Pariyakorn Jearwarakul | Approved | Closed | 2026-07-20 10:35:30 | Yes | Yes | 2026-03-24 08:45:32 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-18 18:21:19 | No | No |  | 18-Feb-26 Replace RRU3962 to RRU5526 S1 Add RRU5526 S2 Replace RRU3953 to RRU5516 S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RMIRM_2025 Capacity Expansion Ph2_EXP_BKK | RAM INDRA ROAD |  |  |  | 2025-10-01 | 2025-10-08 | 2025-11-22 | 2025-11-22 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-11-25 17:48:22 | No | No |  |  | 2025-10-08 | 2025-10-10 | 2025-11-20 | 2025-11-21 | Teloneer Company Limited | N/A | Closed | 2025-11-21 11:13:23 | Yes | Yes | 2025-11-21 12:23:45 |  |  | 2026-02-02 | Apichart Kampuang | Approved | Closed | 2026-04-27 09:56:22 | Yes | Yes | 2026-04-22 14:31:12 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-04-29 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-09-29 | 2025-09-30 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-10-01 08:51:36 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-19 14:27:08 | No | No |  | 19-Nov-2025 Add RRU5516(700900) Sector 3 2025-10-02_Add UBBPg2#， Replace to Ant 12 port (NO RET) Sector 3#， ***Waiting Core Add RRU5516(LB) Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  |  |  | N/A | Not assigned |  | No | No
RMPOM_2025 Capacity Expansion NW Modernization_EXP_BKK | RONGMUANG POST OFFICE |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-06-09 | 2026-07-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-22 14:06:37 | Yes | Yes | 2026-07-22 14:09:42 |  | 2026-07-17 | 2026-07-17 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-21 09:40:49 | Yes | Yes | 2026-07-17 11:38:07 | page.6 no.12 same Re-position RRU (pls delete) page.35 need to revise Stripping the wire 1pcs photo page.40 need to revise socket left and right side 1pcs photo page.54 DCDU install not have?(pls revise) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-21 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:27:19 | Yes | Yes | 2026-08-01 20:16:42 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-01 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-04-01 17:12:04 | No | No |  | 1-Apr-2026 Add RRU5507*2 Sector 3 Remove RRU3962 Replace Ant 8port Co 1800900 12-Feb-2026 ***Pending Add RRU5507*2 Sector 3 Remove RRU3962 Replace Ant ///Add AAU5768 S1 S2 Remove RRU3962 *2#， 3 Add g3a Remove eb |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 1.need to fill Re-Position RRU and Re-Position Antenna/AAU horizontal or vertical in Additional Work 2.need to upload Re-Position RRU and Re-Position Antenna/AAU photos 3.need to upload BBP card view and SN.photos 4.need to upload RRU dismantle SN. photo in EQ Checklist 5.need to upload BBP card dismantle SN. photo in EQ Checklist 6.need to upload install AAU and RRU Notch CPRI Cable 4pcs photos 7.need to upload S1,S2 1800/2100 BBU-AAU label and S3 1800/2100 BBU-RRU1 label photos 8.need to upload before and after AC MDB Box photo |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RMPOM_2025 Capacity Expansion Ph7_EXP_BKK | RONGMUANG POST OFFICE |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-05-12 | 2026-06-30 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-30 11:36:24 | Yes | Yes | 2026-06-30 11:39:20 |  | 2026-06-22 | 2026-06-22 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-10 09:17:39 | Yes | Yes | 2026-06-22 15:34:28 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-11 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 21:47:38 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-13 18:27:25 | No | No |  | 13-02-2026. Add AAU5636w Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed. |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RMS5M_2025 Capacity Expansion NW Modernization_EXP_BKK | Rongmuang Soi 5 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-07 | 2026-03-08 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-08 19:11:40 | Yes | Yes | 2026-03-11 09:54:11 |  | 2026-04-03 | 2026-04-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-02 09:35:21 | Yes | Yes | 2026-04-03 11:43:29 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-06-05 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 20:16:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-10 17:06:52 | No | No |  | 10-02-26 swap RRU3962 to RRU5526 S2 S3 #，RRU3953 toRRU5516 S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RMU1M_2025 Capacity Expansion Ph6_EXP_BKK | STUDENT AFFAIRS BUILDING RAJAMANGALA UNIVERSITY OF TECHNOLOGY PHRA NAKHON |  |  |  |  | 2026-02-21 | 2026-02-21 | 2026-02-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-28 | 2026-03-30 | 2026-03-31 | V Contribute Co., Ltd | N/A | Closed | 2026-03-31 16:35:35 | Yes | Yes | 2026-03-31 16:35:36 |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-06-05 16:15:37 | Yes | Yes | 2026-05-04 12:23:24 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-05 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-29 22:26:06 |  |  | 2025-12-31 | 2026-02-21 | V Contribute Co., Ltd | N/A | Closed | 2026-02-21 16:35:44 | No | No |  |  |  |  | 2026-02-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-21 15:27:43 | No | No |  | 21-Feb-2026 Replace BBU5900 UMPTg2 Add GPS Add g3a g2 AAU5636m S1 S3 Add AAU5636w S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RNWDM_2025 Capacity Expansion Ph2_EXP_BKK | Reignwood Park Soi Lamlukka 227 | 2025-08-09 |  |  |  | 2025-08-09 | 2025-08-09 | 2025-08-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-09 16:06:17 | No | No |  |  |  | 2025-08-31 | 2025-08-17 | 2025-09-10 | V Contribute Co., Ltd | N/A | Closed | 2025-09-10 16:20:04 | Yes | Yes | 2026-03-18 18:25:07 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-11 22:40:45 | Yes | Yes | 2025-09-11 22:40:14 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:13 | Yes | Yes | 2025-09-23 01:08:00 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:38 | No | Yes | 2025-09-03 20:55:30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-09 18:06:38 | No | No |  | 09-08-2025. Add UBBPd6 x3#， Replace RRU5516 L18#， Ant.4 port Sec.3#， Rmv RRU 3.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-08 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-09-16 16:57:05 | No | No
ROOGM_2025 Capacity Expansion Ph2_EXP_BKK | SOI RONGONG | 2025-08-23 |  |  |  | 2025-08-23 | 2025-08-23 | 2025-08-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-23 17:52:43 | No | No |  |  |  | 2025-08-31 | 2025-09-02 | 2025-09-02 | V Contribute Co., Ltd | N/A | Closed | 2025-09-02 13:54:03 | Yes | Yes | 2025-09-02 13:55:35 |  | 2025-09-09 | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-19 20:13:57 | Yes | Yes | 2025-09-09 18:56:16 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:13 | Yes | Yes | 2025-09-23 01:09:13 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-09 19:05:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-23 18:45:46 | No | No |  | 23-08-2025. Add RRU5516 L18#， Ant.8 port Sec.6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-21 |  | N/A | Not assigned |  | No | No
ROSHM_2025 Capacity Expansion NW Modernization_EXP_BKK | ROSE HOTEL |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:45:18 | No | No |  |  | 2026-02-11 | 2026-02-28 | 2026-02-11 | 2026-06-03 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-03 16:36:47 | Yes | Yes | 2026-06-03 16:39:30 |  | 2026-03-31 | 2026-03-31 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-10 16:37:29 | Yes | Yes | 2026-04-01 16:43:56 | Page no.6#， Remove antenna is mismatched with QC. Page no.7#，8#， need to fill site name. Page no.41#， need to fill antenna SN in EQ. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 20:17:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-14 17:06:08 | No | No |  | 14-Jan-2025 Replace Ant 4port S1 S3 ( 700900 ) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ROSTB_2025 Coverage Expansion Ph1_EXP_BKK | ROYAL ORCHID SHERATON HOTEL FOR THE ROOM CHAROENKRUNG 30 | [5 empty] | 2025-10-18 | 2025-10-18 | Akhom Srinara | N/A | Closed | 2025-10-28 12:04:24 | No | No |  |  |  |  | 2025-10-17 | 2025-10-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-10-31 11:55:05 | Yes | Yes | 2025-11-03 09:25:04 |  | 2025-11-06 | 2025-11-06 | Aomchun Jittreemit | Approved | Closed | 2025-11-11 16:13:53 | Yes | Yes | 2025-11-06 14:58:22 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 21:14:19 |  | 2025-11-06 | 2025-11-06 | Aomchun Jittreemit | Approved | Closed | 2026-03-12 09:26:46 | No | Yes | 2025-11-06 14:53:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-17 17:35:25 | No | No |  | 17-10-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-10-17 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:56 | No | No
RP08M_2025 Capacity Expansion Ph7_EXP_BKK | SOI RANGSIT PATHUM8 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-03-04 | 2026-03-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-19 09:50:26 | Yes | Yes | 2026-03-19 09:56:39 |  | 2026-04-23 | 2026-04-23 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-05-06 09:28:48 | Yes | Yes | 2026-04-23 11:36:50 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 21:47:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-14 17:45:28 | No | No |  | 14-02-2026. Replace RRU3953 to RRU5516 L900#， Ant.4 port Sec.1#， Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RPBSB_2025 Capacity Expansion Ph2_EXP_BKK | RICH PARK @ BANG SON STATION |  |  |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-10 18:33:54 | No | No |  |  |  | 2025-10-16 | 2025-10-27 | 2025-10-28 | V Contribute Co., Ltd | N/A | Closed | 2025-10-28 17:34:38 | Yes | Yes | 2025-10-28 17:34:38 |  | 2025-10-16 | 2025-10-16 | Chonradee Suwapan | Approved | Closed | 2025-10-22 10:03:18 | Yes | Yes | 2025-10-16 17:20:38 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:55 | Yes | Yes | 2025-10-27 18:36:51 |  | 2025-10-16 | 2025-10-16 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-16 17:24:46 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-06 12:14:22 | No | No |  | 6-Oct-2025 Add RRU5818 SC Replace Ant.12port No RET 5/3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-09 |  | N/A | Not assigned |  | No | No
RPN6M_2025 Capacity Expansion Ph1_EXP_BKK | SOI RUAM PHATTHANA 6 | 2025-05-26 |  |  |  | 2025-06-09 | 2025-06-09 | 2025-06-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-06-09 16:57:15 | No | No |  |  |  | 2025-05-29 | 2025-06-13 | 2025-06-14 | V Contribute Co., Ltd | N/A | Closed | 2025-06-14 14:36:51 | Yes | Yes | 2025-06-14 14:36:53 |  |  | 2025-06-10 | Chonradee Suwapan | Approved | Closed | 2025-06-19 17:10:42 | Yes | Yes | 2025-06-11 14:07:00 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-06-19 | 2025-06-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:17 | Yes | Yes | 2025-08-05 16:04:35 |  | 2025-05-15 | 2025-05-15 | Annop Auyto | Approved | Closed | 2025-06-09 15:03:36 | No | Yes | 2025-05-15 17:49:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-06-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-06-09 15:47:55 | No | No |  | 09-06-2025. Replace UMPTg2 10G#， Add GPS //26-05-2025. Add UBBPg3a#， AIRU5636w Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-06-06 |  | N/A | Not assigned |  | No | No
RPPTM_2025 Capacity Expansion Ph6_EXP_BKK | RATCHAPIPAT HOSPITAL | [5 empty] | 2025-12-18 | 2025-12-18 | Akhom Srinara | N/A | Closed | 2025-12-18 15:39:59 | No | No |  |  |  | 2025-12-15 | 2025-12-17 | 2025-12-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-17 11:36:15 | Yes | Yes | 2025-12-21 22:27:10 |  | 2025-12-25 | 2025-12-25 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-16 16:09:55 | Yes | Yes | 2025-12-25 16:04:43 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:14:33 |  | 2026-01-06 | 2026-01-06 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-06 13:10:21 |  |  | 2025-12-31 | 2025-12-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-16 13:46:51 | No | No |  |  |  |  | 2025-12-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-16 18:23:31 | No | No |  | 16-Dec-2025 Add RRU5526 (1800-2100) sector 2 Remove RRU3962 Replace Ant 8port s2#，S7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RPV1B_2025 Capacity Expansion NW Modernization_EXP_BKK | ROYCE PRIVATE RESIDENCES |  |  |  |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:09:22 | No | No |  |  |  | 2026-02-28 | 2026-02-19 | 2026-03-08 | V Contribute Co., Ltd | N/A | Closed | 2026-03-08 17:45:03 | Yes | Yes | 2026-03-08 17:45:04 |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-06-17 09:32:26 | Yes | Yes | 2026-04-01 10:28:18 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-14 22:26:33 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-16 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-16 16:47:08 | No | No |  | 16 Feb 2026 Replace RRU5507 sector1#，2 add RRU5507 s1#，2 replace BBU5900 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-02-13 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-06-25 04:38:41 | Yes | Yes | 2026-02-17 10:21:13 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RS42B_2025 Coverage Expansion Ph1_EXP_BKK | Rhythm Sukhumvit 42 | 2025-10-27 |  |  |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 11:08:56 | No | No |  |  |  | 2025-11-07 | 2025-11-03 | 2025-11-03 | V Contribute Co., Ltd | N/A | Closed | 2025-11-03 17:47:36 | Yes | Yes | 2025-11-03 17:47:36 |  | 2025-11-05 | 2025-11-05 | Chonradee Suwapan | Approved | Closed | 2025-11-17 17:04:36 | Yes | Yes | 2025-11-05 20:07:32 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Krittee Chamboot 00319410 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 21:15:31 |  | 2025-11-05 | 2025-11-05 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-05 20:18:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-27 17:37:56 | No | No |  | 27-Oct-2025 Replace to Ant Vertical dual beam SA 80#，81 E tilt -200 ( Config RET 81 #， No Config 80) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-10-27 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No | [5 empty] | 2025-10-27 |  | N/A | Not assigned |  | No | No
RS72M_2025 Capacity Expansion Ph3_EXP_BKK | RANGSIT KLONG 7 STATION 2 | 2025-09-01 |  |  |  | 2025-09-01 | 2025-09-01 | 2025-09-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-01 18:03:40 | No | No |  |  |  | 2025-09-06 | 2025-09-01 | 2025-09-02 | V Contribute Co., Ltd | N/A | Closed | 2025-09-02 11:17:14 | Yes | Yes | 2025-09-02 11:17:43 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-30 15:30:37 | Yes | Yes | 2025-12-04 16:52:31 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:51 | Yes | Yes | 2025-10-06 21:43:30 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-14 13:04:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-01 18:01:13 | No | No |  | 01-09-2025. Add AIRU5636w Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | ขาด UBBPd5 |  | 2025-08-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-10-02 09:30:59 | No | No
RSDAM_2025 Capacity Expansion Ph3_EXP_SR | Ban Kaew San |  |  |  | 2025-11-13 | 2025-11-14 | 2025-11-13 | 2025-11-14 | Teloneer Company Limited | N/A | Closed | 2025-11-18 10:23:24 | No | No |  |  |  | 2025-09-05 | 2025-09-04 | 2025-11-14 | Teloneer Company Limited | N/A | Closed | 2025-11-14 15:40:06 | Yes | Yes | 2025-11-14 15:53:09 |  | 2025-11-17 | 2025-11-17 | Teloneer Company Limited | Approved | Closed | 2025-12-26 16:22:30 | Yes | Yes | 2025-11-19 10:13:40 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:35 | Yes | Yes | 2026-01-09 21:21:35 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-10-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-30 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-10-30 18:09:22 | No | No |  | Rep Card UBBPd6*1 to UBBPg3*1 Re LB 1>2#， 2>3#， 3>1 Re MB 3>4 add AAU5768 S3 add new Ant 4port > 1800 S4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-13 |  | N/A | Not assigned |  | No | No
RSK7M_2025 Coverage Expansion Ph2_EXP_BKK | RANGSIT KHLONG 7 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-13 | 2025-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-13 20:19:48 | Yes | Yes | 2025-08-16 01:07:04 |  | 2025-08-16 | 2025-08-16 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-22 17:57:48 | Yes | Yes | 2025-08-16 22:28:22 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 19:18:28 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 19:58:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-13 18:41:35 | No | No |  | 2025-08-13_Add RRU3953#， Replace to Ant 4 port Sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
RSK8M_2025 Capacity Expansion Ph3_EXP_BKK | RANGSIT KHLONG 8 |  |  |  | 2025-09-19 | 2025-09-26 | 2025-10-11 | 2025-10-13 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-20 10:22:44 | No | No |  |  |  | 2025-10-31 | 2025-10-06 | 2025-10-09 | Teloneer Company Limited | N/A | Closed | 2025-10-09 16:14:44 | Yes | Yes | 2025-10-14 09:41:06 |  |  | 2025-10-30 | Apichart Kampuang | Approved | Closed | 2025-11-05 18:20:28 | Yes | Yes | 2025-11-07 15:58:33 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 19:37:15 |  | 2025-09-19 | 2025-09-19 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-10-09 17:02:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-26 17:42:50 | No | No |  | 26-09-2025. Replace RRU5516 L18 Sec.3#， 8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-13 |  | N/A | Not assigned |  | No | No
RSP2M_2025 Capacity Expansion Ph7_EXP_BKK | SOI RANGSITPIROM STATION 2 |  |  |  |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-20 16:16:18 | No | No |  |  |  | 2026-01-31 | 2026-01-22 | 2026-02-02 | V Contribute Co., Ltd | N/A | Closed | 2026-02-02 20:40:00 | Yes | Yes | 2026-02-02 20:40:01 | SQC Close | 2026-01-31 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-04 09:24:58 | Yes | Yes | 2026-01-31 23:47:52 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:16:08 |  | 2026-02-01 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-01 00:13:12 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-20 11:44:49 | No | No |  | 20-Jan-2026 Add RRU5526 Sector 2 Remove RRU5507 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RSPTM_2025 Coverage Expansion Ph2_EXP_BKK | RANGSIT-PATHUMTHANAI RD. | 2025-08-01 |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-01 17:31:33 | No | No |  |  |  | 2025-08-22 | 2025-08-03 | 2025-08-03 | V Contribute Co., Ltd | N/A | Closed | 2025-08-03 16:21:56 | Yes | Yes | 2025-08-03 16:23:25 |  |  | 2025-08-17 | Chonradee Suwapan | Approved | Closed | 2025-08-21 16:47:06 | Yes | Yes | 2025-08-17 00:47:20 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-22 | 2025-08-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 19:19:46 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:56:50 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-01 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-01 17:11:01 | No | No |  | 1-Aug-2025 Add RRU3953 S1 Replace Ant. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
RT21M_2025 Capacity Expansion Ph3_EXP_BKK | SOI RAMINDRA 21 |  |  |  | 2025-09-27 | 2025-10-04 | 2025-10-20 | 2025-10-20 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-28 10:43:04 | No | No |  |  | 2025-10-05 | 2025-10-07 | 2025-10-21 | 2025-10-21 | Teloneer Company Limited | N/A | Closed | 2025-10-21 17:31:19 | Yes | Yes | 2025-10-22 13:11:19 |  |  | 2025-10-22 | Apichart Kampuang | Approved | Closed | 2025-10-31 13:29:05 | Yes | Yes | 2025-10-22 19:08:02 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 19:39:40 |  | 2025-09-25 | 2025-09-26 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-27 08:56:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-29 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-29 17:23:14 | No | No |  | 2025-09-29_Replace RRU5507 to RRU5516(18-21)#， Replace to Ant 8 port Sector 1#，2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-19 |  | N/A | Not assigned |  | No | No
RT64A_2025 Coverage Expansion Ph1_New_BKK | Soi Ramintra 64 |  |  |  |  | 2025-09-16 | 2025-09-16 | 2025-09-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-05 11:54:01 | No | No |  |  |  | 2025-08-29 | 2025-08-14 | 2025-09-16 | V Contribute Co., Ltd | N/A | Closed | 2025-09-16 11:19:23 | Yes | Yes | 2025-09-16 11:22:32 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2026-02-09 17:33:30 | Yes | Yes | 2025-12-04 17:26:16 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-05-05 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:38 | No | Yes | 2025-09-03 12:39:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-08-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-08-11 18:24:17 | No | Yes | 2025-08-11 16:47:33 | 2025-08-13_New site#， Add UBBPd3(3)#， UBBPg3a#， Add RRU3962 Sector A#，B#，C ***Pending SFP RRUSector 2 low |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-08-11 | Paphawarin Yoopoo WX1434740 | Approved | Closed | 2025-08-25 19:06:56 | Yes | Yes | 2025-08-25 18:50:47 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  | Integrate แล้วมี Alarm ตอนนอก |  |  |  | N/A | Not assigned |  | No | No
RTABM_2025 Capacity Expansion Ph7_EXP_BKK | Office of Donmuang RTAF Base Commander | 2026-01-07 |  |  |  | 2026-01-09 | 2026-01-09 | 2026-01-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-09 13:43:30 | No | No |  |  |  | 2026-01-31 | 2026-01-07 | 2026-01-07 | V Contribute Co., Ltd | N/A | Closed | 2026-01-07 18:30:47 | Yes | Yes | 2026-01-07 18:30:48 |  | 2026-01-26 | 2026-01-26 | Chonradee Suwapan | Approved | Closed | 2026-01-29 09:17:05 | Yes | Yes | 2026-01-26 16:50:04 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:17:04 |  | 2026-01-26 | 2026-01-26 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-01-26 02:02:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-07 13:53:45 | No | No |  | 7-Jan-2026 Add AAU5636w sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RTBPM_2025 Coverage Expansion Ph2_EXP_BKK | RACHA THEWA BANGPHLI |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  | 2025-08-11 | 2025-08-12 | 2025-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-12 16:18:44 | Yes | Yes | 2025-08-20 10:01:30 |  | 2025-08-23 | 2025-08-27 | Kontira Kowapradit | Approved | Closed | 2025-09-01 13:12:07 | Yes | Yes | 2025-08-27 11:31:48 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-02 | 2025-09-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 14:21:45 |  | 2025-09-04 | 2025-09-04 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 12:40:10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-12 18:57:13 | No | No |  | 12-Aug-2025 Add RRU3953 S2 Replace Ant 4port //***Pending VSWR Subrack 101 #， 140#，145 Subrack 101 #，138#，137 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
RUJTM_2025 Capacity Expansion Ph5_EXP_BKK | RUAM JIT |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-12-28 | 2025-12-07 | 2025-12-11 | V Contribute Co., Ltd | N/A | Closed | 2025-12-11 11:42:39 | Yes | Yes | 2025-12-11 11:42:40 |  | 2025-11-25 | 2025-11-25 | Chonradee Suwapan | Approved | Closed | 2025-12-04 09:36:04 | Yes | Yes | 2025-11-25 18:12:41 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2025-12-09 11:49:42 |  | 2025-11-25 | 2025-11-25 | Chonradee Suwapan | Approved | Closed | 2025-12-04 09:45:23 | Yes | Yes | 2025-11-25 19:09:01 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-18 17:13:42 | No | No |  | 18-Nov-2025 Add RRU5526 (1800-2100) S1#，S6 Remove RRU3962 *2 Replace Ant 8port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-11-18 |  |  | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RUNSM_2025 Capacity Expansion Ph3_EXP_BKK | SOI RUNG SUP | 2025-09-02 |  |  |  | 2025-09-02 | 2025-09-11 | 2025-09-11 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:48 | No | No |  |  |  | 2025-09-05 | 2025-09-11 | 2025-09-11 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:17:48 | Yes | Yes | 2025-09-30 10:17:49 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-10-03 16:34:16 | Yes | Yes | 2025-09-12 21:16:44 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:51 | Yes | Yes | 2025-10-06 21:44:46 |  | 2025-09-12 | 2025-09-12 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-12 22:27:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-02 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-02 17:37:37 | No | No |  | 02-09-2025. Add RRU5516 L18 Sec.7#， 8#， Replace Ant.8 port Sec.2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-10 |  | N/A | Not assigned |  | No | No
RUNSM_2025 Coverage Expansion Ph2_EXP_BKK | SOI RUNG SUP | 2025-08-02 |  |  |  | 2025-08-02 | 2025-08-02 | 2025-08-02 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-02 17:51:49 | No | No |  |  |  | 2025-08-22 | 2025-08-14 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 15:33:22 | Yes | Yes | 2025-08-15 15:34:40 |  | 2025-08-19 | 2025-08-19 | Chonradee Suwapan | Approved | Closed | 2025-08-22 17:57:48 | Yes | Yes | 2025-08-19 23:20:21 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:13 | Yes | Yes | 2025-08-26 19:21:03 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:41:12 | No | Yes | 2025-08-05 09:06:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-02 17:50:43 | No | No |  | 2-Aug-2025 Add RRU3953 S1 S3 Add Ant S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
RUYDM_2025 Coverage Expansion Ph2_EXP_BKK | SOI RUAMYARD |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-11 | 2025-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-11 21:06:25 | Yes | Yes | 2025-08-11 21:08:33 |  | 2025-08-19 | 2025-08-19 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:34:38 | Yes | Yes | 2025-08-19 12:25:40 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 14:23:13 |  | 2025-08-31 | 2025-08-30 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-08-31 11:07:51 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-11 18:23:00 | No | No |  | 11-08-2025. Add RRU3953#， Replace Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
RV21B_2025 Coverage Expansion Ph1_EXP_BKK | Riverside Villa Condominium 2 (Front) |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:10 | No | No |  |  |  | 2025-11-07 | 2025-11-05 | 2025-11-29 | V Contribute Co., Ltd | N/A | Closed | 2025-11-29 11:39:13 | Yes | Yes | 2025-11-29 11:39:13 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-19 09:48:21 | Yes | Yes | 2025-11-08 18:11:04 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 21:19:10 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-08 16:45:45 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-28 16:17:51 | No | No |  | 28-Oct-2025 Replace to Ant Vertical Dual Beam Sector A#，80 81 82 E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
RVS1B_2025 Coverage Expansion Ph1_EXP_BKK | RIVERSIDE VILLA CONDOMINIUM (SIDE) |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:10 | No | No |  |  |  | 2025-11-07 | 2025-11-06 | 2025-11-15 | V Contribute Co., Ltd | N/A | Closed | 2025-11-15 10:41:45 | Yes | Yes | 2025-11-15 10:41:45 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-19 09:48:21 | Yes | Yes | 2025-11-08 18:11:38 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 12:59:29 |  | 2025-11-08 | 2025-11-08 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-08 16:46:25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-28 18:34:48 | No | No |  | 28-10-2025. Repalce Ant.12 port Condo Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
RWRPM_2025 Coverage Expansion Ph2_EXP_BKK | RADAWAN RATCHAPHRUEK-PINKLAO VILLAGE | [5 empty] | 2025-08-29 | 2025-08-29 | Teloneer Company Limited | N/A | Closed | 2025-08-31 16:23:46 | No | No |  |  | 2025-08-26 | 2025-08-30 | 2025-09-04 | 2025-09-10 | Teloneer Company Limited | N/A | Closed | 2025-09-10 15:00:23 | Yes | Yes | 2025-09-10 18:50:09 |  |  | 2025-09-15 | Apichart Kampuang | Approved | Closed | 2025-09-25 14:36:40 | Yes | Yes | 2025-10-20 13:22:55 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:51 | Yes | Yes | 2025-10-06 21:46:01 |  |  | 2025-08-14 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-14 17:30:40 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-29 19:52:44 | No | No |  | 29-Aug-2025 Add RRU3953 S1 S3 Replace Ant. 4port S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-28 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
S192M_2025 Coverage Expansion Ph2_EXP_BKK | SOI THETSABAN SAMRONG TAI 19 STATION 2 |  |  |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-13 18:57:01 | No | No |  |  |  | 2025-08-22 | 2025-08-18 | 2025-08-18 | V Contribute Co., Ltd | N/A | Closed | 2025-08-18 16:17:27 | Yes | Yes | 2025-08-18 16:18:29 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2026-01-27 15:29:52 | Yes | Yes | 2025-10-02 12:05:49 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2026-01-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:17:42 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:00:29 | No | Yes | 2025-07-30 13:57:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-13 18:41:35 | No | No |  | 1-Oct-2025 Clear Pending work Add DCDU 2025-08-13_Add RRU3953#， No act Ant Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
S742M_2025 Capacity Expansion Ph3_EXP_BKK | SOI SUK SAWAT 74 STATION 2 |  |  |  | 2025-09-22 | 2025-09-29 | 2025-10-25 | 2025-10-25 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-28 10:43:04 | No | No |  |  | 2025-10-21 | 2025-10-23 | 2025-10-21 | 2025-10-27 | Teloneer Company Limited | N/A | Closed | 2025-10-27 17:48:08 | Yes | Yes | 2025-10-27 17:50:43 |  |  | 2025-10-27 | Apichart Kampuang | Approved | Closed | 2025-11-19 16:03:47 | Yes | Yes | 2025-10-27 19:17:02 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:35 | Yes | Yes | 2026-01-09 21:26:25 |  |  | 2025-09-04 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-10-21 09:52:37 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-07 15:30:40 | No | No |  | 7-Oct-2025 Add RRU5516 (1800-2100) S3 Remove RRU3962 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-26 |  | N/A | Not assigned |  | No | No
SA13M_2025 Coverage Expansion Ph2_EXP_BKK | SOI SAKAE NGAM 13 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  | 2025-08-11 | 2025-08-12 | 2025-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-12 16:27:12 | Yes | Yes | 2025-08-15 18:44:04 |  | 2025-08-19 | 2025-08-19 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:34:38 | Yes | Yes | 2025-08-26 14:11:14 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 14:24:57 |  | 2025-09-02 | 2025-09-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-02 20:21:50 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-12 17:52:26 | No | No |  | 12-08-2025. Add RRU3953#， Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
SAENM_2025 Coverage Expansion Ph2_New_BKK | Soi Saeng Si San | [5 empty] | 2025-11-17 | 2025-11-17 | Akhom Srinara | N/A | Closed | 2025-11-26 16:34:53 | No | No |  |  |  |  | 2025-11-12 | 2025-11-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-12 20:34:28 | Yes | Yes | 2025-11-18 13:05:21 |  | 2025-11-19 | 2025-11-19 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2025-11-24 10:42:05 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-11-19 | 2025-11-19 | Future Telecom Co.,Ltd. | Approved | Closed | 2026-03-12 09:25:38 | No | Yes | 2025-11-19 13:54:32 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-11 17:33:52 | No | No |  | 11-11-2025. New Site Small Cell Add RRU3962#， Ant.4 port Sec.A#， B#， C |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-11-06 | Paphawarin Yoopoo WX1434740 | Approved | Closed | 2025-11-25 06:03:15 | Yes | Yes | 2025-11-24 18:29:34 |  |  |  |  | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
SAPRM_2025 Capacity Expansion Ph3_EXP_BKK | SOI SAPPRASERT |  |  |  | 2025-09-16 | 2025-09-23 | 2025-09-30 | 2025-09-30 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-30 10:53:47 | No | No |  |  | 2025-09-23 | 2025-09-25 | 2025-09-25 | 2025-09-26 | Teloneer Company Limited | N/A | Closed | 2025-09-26 11:57:10 | Yes | Yes | 2025-09-26 15:10:31 |  |  | 2025-09-30 | Apichart Kampuang | Approved | Closed | 2025-10-14 15:39:01 | Yes | Yes | 2025-10-17 17:28:20 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-14 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:43:39 |  |  | 2025-09-02 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:30:49 | No | Yes | 2025-09-02 23:31:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-17 17:18:34 | No | No |  | 17-09-2025. Add AIRU5636w Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-29 |  | N/A | Not assigned |  | No | No
SARAM_2025 Capacity Expansion Ph7_EXP_BKK | SARAWITTAYA SCHOOL |  |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-29 09:34:01 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-28 | 2026-01-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-28 15:11:17 | Yes | Yes | 2026-01-29 13:44:10 | SQC Close | 2026-02-01 | 2026-01-30 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-04 09:24:58 | Yes | Yes | 2026-01-30 11:13:23 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:18:39 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 21:48:13 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-13 14:39:27 | No | No |  | 13-Jan-2026 Add AAU5636w sector 6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SATGM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SAENGTHONG |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-03-04 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 16:02:34 | Yes | Yes | 2026-04-01 13:07:17 |  | 2026-04-22 | 2026-04-22 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-04 09:20:47 | Yes | Yes | 2026-04-24 17:45:12 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-05 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 20:17:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-07 18:36:19 | No | No |  | 07-02-2026. Replace SFP to 25G Sec.1#， RRU3962 to RRU5507 Sec.2#， Add UBBPg2#， RRU3953 Sec.3 //6 Feb 2026 Replace AAU5768 s1 only |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAVOA_2025 Capacity Expansion Ph2_EXP_BKK | Save One Go Market |  |  |  | 2025-10-14 | 2025-10-21 | 2025-10-25 | 2025-10-25 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-28 10:43:04 | No | No |  |  | 2025-10-21 | 2025-10-23 | 2025-10-25 | 2025-10-29 | Teloneer Company Limited | N/A | Closed | 2025-10-29 17:23:53 | Yes | Yes | 2025-10-29 17:26:47 |  |  | 2025-10-27 | Apichart Kampuang | Approved | Closed | 2025-10-31 13:29:05 | Yes | Yes | 2026-01-06 11:25:40 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 19:46:18 |  | 2025-10-13 | 2025-10-13 | Teloneer Company Limited | Approved | Closed | 2025-11-28 14:34:00 | No | Yes | 2025-10-14 09:15:30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-14 16:07:20 | No | No |  | 14-Oct-2025 Add RRU5516 (700900) SA Add g2 0/2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
SBK9M_2025 Coverage Expansion Ph2_EXP_BKK | SOI SIHABURANUKIT 9 | [5 empty] | 2025-08-27 | 2025-08-27 | Teloneer Company Limited | N/A | Closed | 2025-08-31 16:23:46 | No | No |  |  | 2025-08-24 | 2025-08-26 | 2025-09-05 | 2025-09-08 | Teloneer Company Limited | N/A | Closed | 2025-09-08 15:36:49 | Yes | Yes | 2025-09-08 15:36:49 |  |  | 2025-09-09 | Apichart Kampuang | Approved | Closed | 2025-09-23 22:28:06 | Yes | Yes | 2025-09-09 15:34:07 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:51 | Yes | Yes | 2025-10-06 21:55:56 |  |  | 2025-08-12 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:08 | No | Yes | 2025-08-12 14:04:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-28 17:48:49 | No | No |  | 28-Aug-2025 Add RRU3953 S3 Add Ant.4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-26 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
SBLBM_2025 Capacity Expansion Ph4_EXP_ER | Soi Ban Na Thao , Laem Chabang Port | 2025-10-03 | THCP_Phet.S | Clear Alarm |  | 2025-10-31 | 2025-10-03 | 2025-10-03 | Teloneer Company Limited | N/A | Closed | 2025-10-03 16:55:30 | No | No |  |  |  | 2025-09-30 | 2025-10-03 | 2025-10-04 | Teloneer Company Limited | N/A | Closed | 2025-10-04 14:16:02 | Yes | Yes | 2025-10-08 16:47:23 |  | 2025-09-30 | 2025-10-08 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-20 18:04:14 | Yes | Yes | 2025-11-07 13:40:16 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:58 | Yes | Yes | 2025-10-21 18:44:51 |  | 2025-09-30 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2026-03-02 15:29:20 | Yes | Yes | 2025-10-08 10:56:37 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-03 |  | 2025-10-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-03 17:48:24 | No | No |  | Add UBBPg2 #，New L26F5 + NR26 (New AAU5636w) S1#，2#，3 |  | 2025-10-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-03 17:48:24 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCMTM_2025 Capacity Expansion Ph5_EXP_BKK | WELFARE BUILDING OF SUPREME COMMAND HEADQUARTER(MUANGTHONG ) |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-12-28 | 2025-12-10 | 2025-12-12 | V Contribute Co., Ltd | N/A | Closed | 2025-12-12 15:21:29 | Yes | Yes | 2025-12-12 15:21:29 |  | 2025-12-01 | 2025-12-01 | Chonradee Suwapan | Approved | Closed | 2025-12-11 09:22:40 | Yes | Yes | 2025-12-01 18:16:08 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 21:36:30 |  | 2025-12-01 | 2025-12-01 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-12-01 18:22:22 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-11-19 17:15:47 | No | No |  | 2025-11-19_Add AAU5636w Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCMTM_2025 Capacity Expansion Ph7_EXP_BKK | WELFARE BUILDING OF SUPREME COMMAND HEADQUARTER(MUANGTHONG ) |  |  |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-16 05:17:44 | No | No |  |  |  | 2026-01-31 | 2026-01-26 | 2026-01-26 | V Contribute Co., Ltd | N/A | Closed | 2026-01-26 11:11:05 | Yes | Yes | 2026-01-26 11:11:05 |  | 2026-01-31 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-04 09:24:58 | Yes | Yes | 2026-03-11 12:10:15 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:20:13 |  | 2026-02-01 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-01 00:09:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-15 14:26:52 | No | No |  | 15-Jan-2026 Add RRU5526 Sector 2 Remove RR3962 Replace Ant * 2 >>> Ant 8port CO 700900 18002100 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCYNM_2025 Capacity Expansion Ph2_EXP_BKK | SACHAYAN COURT |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:58 | No | No |  |  |  | 2025-11-07 | 2025-11-10 | 2025-11-10 | V Contribute Co., Ltd | N/A | Closed | 2025-11-10 18:06:58 | Yes | Yes | 2025-11-10 18:06:59 |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2025-11-25 09:28:41 | Yes | Yes | 2025-11-11 19:26:17 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 21:31:16 |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:14:05 | No | Yes | 2025-11-11 19:33:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-30 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-30 17:13:59 | No | No |  | 30-10-2025. Add RRU5516 L18 Sec.6#， Replace Ant.8 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
SDCPP_2025 Capacity Expansion NW Modernization_EXP_BKK | SIAM DISCOVERY CARPARK |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:10:15 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:22:25 | Yes | Yes | 2026-03-23 15:22:25 |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-04-28 16:54:50 | Yes | Yes | 2026-03-11 21:38:43 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-04-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-11 21:53:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-16 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-16 19:13:00 | No | No |  | 16-Feb-26 Replace BBU3900 To BBU5900 Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SEK9M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI EKKAMAI 9 |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-02-21 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:14:06 | Yes | Yes | 2026-03-23 15:14:06 |  | 2026-02-19 | 2026-02-19 | Chonradee Suwapan | Approved | Closed | 2026-03-16 17:56:27 | Yes | Yes | 2026-04-03 16:46:56 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-08 | 2026-03-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-19 | 2026-02-19 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-19 22:09:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-05 20:41:09 | No | No |  | 5-Feb-2026 Add AAU5768 Sector3 Remove RRU5507*2 Cancel Add RRU5507 *2 sector 2 Replace Ant 12port Add RRU5508 *2 Sector 2 Existing DMM S2 _D2 ยุบไป BBU เดียวกัน Remove d5 d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SESWM_2025 Capacity Expansion Ph2_EXP_ER | Sermsuwan Road | 2025-08-11 |  | Clear Pending |  | 2025-08-31 | 2025-08-06 | 2025-08-07 | Teloneer Company Limited | N/A | Closed | 2025-08-07 09:10:08 | No | No |  |  |  | 2025-08-31 | 2025-08-07 | 2025-08-16 | Teloneer Company Limited | N/A | Closed | 2025-08-16 16:18:31 | Yes | Yes | 2025-08-21 19:44:13 |  | 2025-08-31 | 2025-10-02 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-21 14:59:23 | Yes | Yes | 2025-10-02 17:24:29 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-12-31 | 2025-10-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-21 18:52:03 |  | 2025-08-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:28:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-07 |  | 2025-08-05 | Reungsak Junkong 00927496 | N/A | Closed | 2025-08-05 19:27:02 | No | No |  | Add UBBPg2 #，New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB) Sec.8 |  | 2025-08-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-15 18:31:59 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SFAPM_2025 Coverage Expansion Ph2_EXP_BKK | SRIFAH FAMILY APARTMENT | 2025-08-15 |  |  |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-15 18:59:38 | No | No |  |  |  | 2025-08-29 | 2025-08-25 | 2025-08-28 | V Contribute Co., Ltd | N/A | Closed | 2025-08-28 12:03:20 | Yes | Yes | 2025-08-28 12:05:21 |  |  | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-04 09:25:37 | Yes | Yes | 2025-09-01 00:14:55 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:12 | Yes | Yes | 2025-09-23 01:30:04 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 02:19:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-15 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-15 17:27:01 | No | No |  | 15-08-2025. Add RRU3953#， Ant.4 port Sec.1#， 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-14 |  | N/A | Not assigned |  | No | No
SGLPA_2025 Coverage Expansion Ph1_New_BKK | SHANGRI-LA CAR PARK |  |  |  |  | 2026-02-17 | 2026-03-06 | 2026-03-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-18 16:37:14 | No | No |  |  |  | 2026-02-28 | 2026-03-02 | 2026-03-06 | V Contribute Co., Ltd | N/A | Closed | 2026-03-06 10:13:16 | Yes | Yes | 2026-03-06 10:13:16 |  | 2026-03-20 | 2026-03-20 | Chonradee Suwapan | Approving | Assigned |  | Yes | Yes | 2026-05-19 10:39:08 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-03-20 | 2026-03-20 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:27:49 | Yes | Yes | 2026-03-20 21:43:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-17 17:16:23 | No | No |  | 17-02-2026. New Site Small Cell Add RRU3962#， Ant.2 port Sec.A#， B#， Replace WBBP x2 to UBBPd5 x2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-02-16 |  | N/A | Not assigned |  | No | No
SHALM_2025 Coverage Expansion Ph1_New_BKK | Samut Prakan Hospital OPD Building | [5 empty] | 2025-12-25 | 2025-12-25 | Akhom Srinara | N/A | Closed | 2025-12-25 10:07:39 | No | No |  |  |  | 2025-12-19 | 2025-12-20 | 2025-12-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-23 15:54:16 | Yes | Yes | 2025-12-26 13:47:21 |  | 2026-01-04 | 2026-01-04 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-01-04 10:19:57 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-04 | 2026-01-04 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-04 10:20:32 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-19 19:03:05 | No | No |  | 19-Dec-2205 New site BBU3900 Add RRU3962 S1 S2 S3 d5=3 Add Ant 12port S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-12-19 | Supatong Juntorn WX1461874 | Approved | Closed | 2025-12-25 06:10:09 | Yes | Yes | 2025-12-19 14:29:39 |  |  |  |  | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
SHNKM_2025 Capacity Expansion Ph4_EXP_SR | Singha Nakorn | [5 empty] | 2026-01-27 | 2026-01-27 | Nattawoot Suwan | N/A | Closed | 2026-01-27 14:33:49 | No | No |  |  |  | 2026-01-26 | 2026-01-26 | 2026-01-27 | Teloneer Company Limited | N/A | Closed | 2026-01-27 09:35:09 | Yes | Yes | 2026-02-25 14:17:59 |  | 2026-02-25 | 2026-02-25 | Teloneer Company Limited | Approved | Closed | 2026-02-26 20:30:34 | Yes | Yes | 2026-02-25 17:16:26 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-03-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:58 | Yes | Yes | 2026-03-20 15:30:40 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-01-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-26 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-01-26 15:45:03 | No | No |  | 26 Jan 2026 Add 2AAU5636w 2600 S1#， S3. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-02-05 | Nattawoot Suwan | N/A | Closed | 2026-02-05 11:17:05 | No | No | [7 empty] | N/A | Not assigned |  | No | No
SHSCM_2025 Capacity Expansion Ph5_EXP_SR | Sahasad School |  |  |  |  | 2025-11-15 | 2025-11-15 | 2025-11-15 | Teloneer Company Limited | N/A | Closed | 2025-11-15 16:31:37 | No | No |  |  |  | 2025-11-15 | 2025-11-15 | 2025-11-17 | Teloneer Company Limited | N/A | Closed | 2025-11-17 09:45:02 | Yes | Yes | 2025-11-19 14:53:08 |  | 2025-11-19 | 2025-11-19 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2025-12-11 10:28:02 | Yes | Yes | 2025-11-20 10:42:42 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:19 | Yes | Yes | 2025-12-01 21:35:06 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-11-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-15 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-11-15 17:39:41 | No | No |  | Add new AAU5636w Sector S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-13 |  | N/A | Not assigned |  | No | No
SJIEM_2025 Capacity Expansion Ph6_EXP_ER | S&J International Enterprises Public Company Limited | 2025-12-02 | thcp_Adirek.k | Clear Pending |  | 2025-11-30 | 2025-12-02 | 2025-12-02 | Teloneer Company Limited | N/A | Closed | 2025-12-02 09:35:58 | No | No |  |  |  | 2025-11-30 | 2025-11-28 | 2025-12-02 | Teloneer Company Limited | N/A | Closed | 2025-12-02 19:28:13 | Yes | Yes | 2025-12-04 11:04:35 |  | 2025-11-30 | 2025-12-04 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:38:58 | Yes | Yes | 2025-12-04 13:07:24 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 21:47:25 |  | 2025-11-30 | 2025-11-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-25 18:20:01 | Yes | Yes | 2025-11-25 13:15:22 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-28 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-28 18:21:22 | No | No |  | **waiting on-service LNR26 -- Add UBBPg3a + Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_SJIEM_H_A New L26F5 + NR26 (New RRU5818) + Co Antenna_SJIEM_N_A |  | 2025-12-01 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-01 17:57:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SK23B_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SUKHUMWIT 23 FOR ASHTON ASOKE |  |  |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-05 08:14:49 | No | No |  |  |  | 2026-02-12 | 2026-03-17 | 2026-03-18 | V Contribute Co., Ltd | N/A | Closed | 2026-03-18 10:57:46 | Yes | Yes | 2026-03-18 10:57:47 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approving | Assigned |  | Yes | Yes | 2026-06-16 18:25:01 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | No | No |  |  | 2026-02-27 | 2026-02-27 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-27 01:36:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-11 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-11 18:05:16 | No | No |  | 11-Feb-26 Replace 3962 To RRU5526 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SK33M_2025 Capacity Expansion NW Modernization_EXP_BKK | SUKHUMWIT SOI 33 | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  | 2026-02-09 | 2026-02-28 | 2026-02-16 | 2026-02-16 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-16 17:12:14 | Yes | Yes | 2026-02-17 09:53:04 |  | 2026-02-17 | 2026-02-17 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-05-12 16:26:02 | Yes | Yes | 2026-04-24 10:42:05 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-20 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-29 | 2026-01-29 | Pariyakorn Jearwarakul | Approved | Closed | 2026-07-20 10:36:04 | Yes | Yes | 2026-03-24 12:00:52 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-12 20:33:43 | No | No |  | 12-Feb-2026 Add RRU5516 S1 S2 S3 Remove RRU3953 S1 S2 S3 Add g3a Remove d5 Replace Ant 8port S1 s2 s3 co 1800900 Remove RRU5507*2 Sector 1 ( 1800/2100 downgrade to Single 4T S1) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SK37M_2025 Capacity Expansion NW Modernization_EXP_BKK | SUKHUMWIT SOI 37 |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-02-27 | 2026-03-21 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:29:58 | Yes | Yes | 2026-03-23 15:29:59 |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-05-07 16:20:16 | Yes | Yes | 2026-05-19 12:27:14 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-08 | 2026-03-11 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-18 22:55:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-04 17:09:21 | No | No |  | 4-Feb-2026 Add AAU5768 sector 3 Remove RRU5526 Add RRU3953 S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SK37M_2025 Capacity Expansion Ph5_EXP_BKK | SUKHUMWIT SOI 37 |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-12-28 | 2025-12-09 | 2025-12-10 | V Contribute Co., Ltd | N/A | Closed | 2025-12-10 14:16:15 | Yes | Yes | 2025-12-10 14:16:15 |  | 2025-11-26 | 2025-11-26 | Chonradee Suwapan | Approved | Closed | 2026-03-24 09:25:41 | Yes | Yes | 2025-11-26 17:41:57 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-03-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:21:48 |  | 2025-11-26 | 2025-11-26 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-11-26 17:44:56 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-11-19 17:15:47 | No | No |  | 2025-11-19_Replace RRU5507(2) to RRU5526(18-21) Sector 3#， No act ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SK49M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SUKHUMVIT 49 |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:11:05 | No | No |  |  |  | 2026-02-21 | 2026-02-03 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:03:04 | Yes | Yes | 2026-03-23 15:03:04 |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-07-31 18:23:03 | Yes | Yes | 2026-05-19 14:48:16 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-07-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-10 22:21:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-03 18:31:15 | No | No |  | 3-Feb-2026 Add RRU5507 *2 S1 Remove RRU3962 *2 Add RRU5507 *2 S3 Remove RRU3962 *2 Replace Ant 8port S1#，S2 #，S3 Co1800 900 S2 S7 downgrade |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SK63B_2025 Capacity Expansion NW Modernization_EXP_BKK | SUKHUMVIT 63 (FOR CONDO) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:30:08 | Yes | Yes | 2026-04-01 10:36:28 |  | 2026-04-17 | 2026-04-17 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:49:14 | Yes | Yes | 2026-04-17 10:14:54 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 20:18:09 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-23 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-23 16:54:34 | No | No |  | 23-Feb-26 Replace RRU3962 To RRU5526 SA SB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SK63M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SUKHUMVIT 63 |  |  |  | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2026-04-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-28 16:38:18 | No | No |  |  |  | 2026-03-25 | 2026-03-18 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 15:01:21 | Yes | Yes | 2026-04-03 09:46:50 |  | 2026-04-28 | 2026-04-28 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-08 17:18:28 | Yes | Yes | 2026-04-28 16:38:42 | page.40 need to upload S1#，S3 1800/2100 RRU2 socket left and right photo page.67 need to upload another 3people team member full body photos. Not update yet | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 20:18:32 |  |  | 2026-03-10 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-06 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-06 19:15:56 | No | No |  | 2026-03-09_Replace RRU3962 to RRU5507(2)#， Replace RRU3953 to RRU5516#， Replace Ant to 8 port Sector 3 06-Mar-26 Replace RRU3962 To DMM S2 #， Replace RRUu3953 To RRU5516 #， Replace RRU3962 To RRU5507 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKDPM_2025 Coverage Expansion Ph2_EXP_BKK | MU BAN SAP KANDA-PATHUM THANI | 2025-08-01 |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-01 17:31:33 | No | No |  |  |  | 2025-08-22 | 2025-08-02 | 2025-08-03 | V Contribute Co., Ltd | N/A | Closed | 2025-08-03 16:12:42 | Yes | Yes | 2025-08-03 16:13:32 |  |  | 2025-08-17 | Chonradee Suwapan | Approved | Closed | 2025-08-25 17:35:18 | Yes | Yes | 2025-08-17 00:48:26 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:12 | Yes | Yes | 2025-08-26 19:28:52 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:57:22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-01 16:26:43 | No | No |  | 01-08-2025. Add RRU3953 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-31 |  | N/A | Not assigned |  | No | No
SKE1M_2025 Capacity Expansion Ph7_EXP_BKK | SAMUKKEE 1 | 2026-01-14 |  |  |  | 2026-01-14 | 2026-01-14 | 2026-01-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-14 16:19:24 | No | No |  |  |  | 2026-01-31 | 2026-02-07 | 2026-02-07 | V Contribute Co., Ltd | N/A | Closed | 2026-02-07 16:52:35 | Yes | Yes | 2026-02-07 16:52:35 | SQC CLose | 2026-01-31 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-04 09:24:58 | Yes | Yes | 2026-02-24 16:42:36 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:22:27 |  | 2026-02-01 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-01 00:10:36 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-14 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-14 17:30:56 | No | No |  | 2026-01-14_Add AAU5636w Sector 7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKKBM_2025 Coverage Expansion Ph2_EXP_BKK | SOI KLONG KRATIAM-KLONG BUA ROY | 2025-08-05 |  |  |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-05 16:45:51 | No | No |  |  |  | 2025-08-22 | 2025-08-05 | 2025-08-06 | V Contribute Co., Ltd | N/A | Closed | 2025-08-06 12:13:57 | Yes | Yes | 2025-08-06 12:15:32 |  | 2025-08-22 | 2025-08-22 | Chonradee Suwapan | Approved | Closed | 2025-08-28 16:37:42 | Yes | Yes | 2025-08-22 07:55:34 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-08-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:10 | Yes | Yes | 2025-09-04 14:35:00 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:41:12 | No | Yes | 2025-08-05 09:06:58 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-05 19:13:14 | No | No |  | 2025-08-05_Add RRU3953#， Replace Ant to 4 port Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-04 |  | N/A | Not assigned |  | No | No
SKP5M_2025 Capacity Expansion Ph7_EXP_BKK | Sukhaphiban 5 Soi 32 |  |  |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-20 14:02:04 | No | No |  |  |  | 2026-01-31 | 2026-01-17 | 2026-01-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-18 10:28:52 | Yes | Yes | 2026-01-19 09:38:08 |  | 2026-01-20 | 2026-01-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-01-29 09:17:05 | Yes | Yes | 2026-01-21 16:09:04 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:22:46 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 21:48:29 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-16 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-16 18:09:35 | No | No |  | 16 Jan 2026 Add AAU5636w sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKPMM_2025 Capacity Expansion NW Modernization_EXP_BKK | S.K. APARTMENT |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  |  | 2026-02-28 | 2026-02-19 | 2026-03-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-06 11:57:48 | Yes | Yes | 2026-03-11 10:58:13 |  | 2026-04-20 | 2026-04-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 17:40:28 | Yes | Yes | 2026-04-26 16:43:42 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 20:18:52 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-05 16:09:32 | No | No |  | 5-Feb-2026 Add RRU5507 sector 3.2 Replace Ant 8port Co 18002100 S3 31-01-2569. ***Need RRU5507#， Ant.8 port Sec.3 //Add RRU5507#， Ant.8 port Sec.2#， Replace RRU5508 to RRU5516 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKROM_2025 Coverage Expansion Ph2_EXP_BKK | SI KHAO RD. |  |  |  | 2025-09-15 | 2025-09-22 | 2025-09-30 | 2025-09-30 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-30 10:53:47 | No | No |  |  | 2025-09-22 | 2025-09-24 | 2025-09-23 | 2025-09-25 | Teloneer Company Limited | N/A | Closed | 2025-09-25 12:37:16 | Yes | Yes | 2025-09-25 14:27:09 |  |  | 2025-09-29 | Apichart Kampuang | Approved | Closed | 2025-10-10 14:08:42 | Yes | Yes | 2025-10-20 13:23:17 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 20:00:23 |  |  | 2025-08-12 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:08 | No | Yes | 2025-08-12 14:04:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-16 17:45:06 | No | No |  | 16-Sep-2025 Add RRU3953 S1 S3 Add Ant 4port S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-29 |  | N/A | Not assigned |  | No | No
SKTPM_2025 Coverage Expansion Ph2_EXP_BKK | MU BANSAHAKON KHEHASA THAN SAENG THIP | 2025-08-04 |  |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-04 14:49:49 | No | No |  |  |  | 2025-08-22 | 2025-08-14 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 15:54:28 | Yes | Yes | 2025-08-15 15:55:38 |  | 2025-08-22 | 2025-08-22 | Chonradee Suwapan | Approved | Closed | 2025-08-25 17:35:50 | Yes | Yes | 2025-08-22 07:56:18 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:12 | Yes | Yes | 2025-08-26 19:30:08 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:41:12 | No | Yes | 2025-08-05 09:07:15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-04 18:26:26 | No | No |  | 4-Aug-2025 Add RRU3953 S1 Replace Ant. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-01 |  | N/A | Not assigned |  | No | No
SKW1B_2025 Capacity Expansion NW Modernization_EXP_BKK | Sky Walk Condominium (Front) | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  | 2026-02-16 | 2026-02-28 | 2026-02-19 | 2026-02-19 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-19 15:04:58 | Yes | Yes | 2026-02-20 08:42:11 |  | 2026-02-20 | 2026-02-20 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-04-29 16:49:13 | Yes | Yes | 2026-03-08 11:30:07 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-27 | 2026-01-27 | Pariyakorn Jearwarakul | Approved | Closed | 2026-07-20 10:36:04 | Yes | Yes | 2026-03-24 14:56:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-09 17:57:53 | No | No |  | 17-Feb-26 Replace RRU3962 to RRU5526 S1 09-02-2026. Add UBBPg3a x2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKWCM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI KHUN WICHIT |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:10:15 | No | No |  |  |  | 2026-02-06 | 2026-03-20 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:08:09 | Yes | Yes | 2026-03-23 15:08:09 |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-04-16 09:25:08 | Yes | Yes | 2026-05-19 15:11:33 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | No | No |  |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-11 21:54:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-02 19:21:08 | No | No |  | 2026-02-02_Replace RRU3962(2) to RRU5507(2)#， Replace to ant 8 port Sector 1#， Replace RRU to AAU5768 Sector 2#，3#， Replace UBBPd5#， UBBPd6 to UBBPg3a(2) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SLBLM_2025 Capacity Expansion Ph2_EXP_BKK | SUKHUMVIT-LAT WAI-KAN KHEHA BANG PHLI RD. |  |  |  | 2025-08-18 | 2025-08-31 | 2025-09-01 | 2025-09-01 | Akhom Srinara | N/A | Closed | 2025-09-01 09:42:25 | No | No |  |  |  |  | 2025-08-29 | 2025-08-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-30 12:14:10 | Yes | Yes | 2025-09-08 17:07:01 |  | 2025-09-09 | 2025-09-09 | Aomchun Jittreemit | Approved | Closed | 2025-09-26 16:35:04 | Yes | Yes | 2025-12-08 17:13:38 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 20:10:35 |  | 2025-09-07 | 2025-09-07 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:29:19 | No | Yes | 2025-09-07 16:01:26 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-29 19:46:08 | No | No |  | 29-Aug-2025 Replace BBU5900 UMPTg2 GPS g3a Add AAU5636w S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-28 |  | N/A | Not assigned |  | No | No
SLD1M_2025 Capacity Expansion NW Modernization_EXP_BKK | SALADAENG SOI 1 |  |  |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-05 08:14:49 | No | No |  |  |  | 2026-02-14 | 2026-03-12 | 2026-03-17 | V Contribute Co., Ltd | N/A | Closed | 2026-03-17 21:08:34 | Yes | Yes | 2026-03-17 21:08:34 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-05-12 16:26:02 | Yes | Yes | 2026-05-08 13:36:13 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-05-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-28 22:54:19 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-10 10:46:55 | No | No |  | 09-02-26 Replace 5526 S1 #，5507*2 S2 Remove RRU S7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SLEGM_2025 Capacity Expansion NW Modernization_EXP_BKK | SILOM EDGE MACRO CELL | [5 empty] | 2026-01-23 | 2026-01-23 | Narongsak wanichachiwa | N/A | Closed | 2026-01-27 10:40:32 | No | No |  |  |  | 2026-01-20 | 2026-01-20 | 2026-01-21 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-01-21 16:10:39 | Yes | Yes | 2026-01-25 13:27:22 | SQC Close |  | 2026-01-25 | OATTAPAN AUTTAHON | Approved | Closed | 2026-02-18 10:24:26 | Yes | Yes | 2026-02-09 17:26:28 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:24:03 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-20 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-20 19:48:43 | No | No |  | 20-1-2026 Add rru5507 sector 2#，3 freq 18#，21 and chain rru sector rruchain rr5507 rru80#，81 4t4r Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SLLSM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI LALAISAP |  |  |  |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-18 14:00:21 | No | No |  |  |  | 2026-01-31 | 2026-03-20 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:31:05 | Yes | Yes | 2026-03-23 15:31:06 |  | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-09-04 20:49:14 | Yes | Yes | 2026-05-19 15:33:05 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-17 | 2026-02-17 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-17 21:57:52 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-04 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-04 17:23:25 | No | No |  | 4 Feb 2026 Replace RRU5516 sector1#，2 replace ANT12port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | ติดตั้งไม่ได้หน้างานไม่ตรงข้อมูล TOR / wall mounting tower overload | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SM34M_2025 Capacity Expansion Ph3_EXP_BKK | SAIMAI 34 | [5 empty] | 2025-09-01 | 2025-09-01 | Akhom Srinara | N/A | Closed | 2025-09-01 09:42:25 | No | No |  |  |  |  | 2025-08-29 | 2025-08-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-29 22:50:15 | Yes | Yes | 2025-09-06 20:05:23 |  | 2025-09-11 | 2025-09-11 | Aomchun Jittreemit | Approved | Closed | 2025-10-03 16:14:46 | Yes | Yes | 2025-10-20 17:03:25 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 20:14:15 |  | 2025-09-07 | 2025-09-07 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:29:19 | No | Yes | 2025-09-07 16:01:58 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-29 19:47:24 | No | No |  | 29-Aug-2025 AAU5636w S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-31 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
SMBKM_2025 Capacity Expansion Ph6_EXP_BKK | SOI MU BAN KLOM PHIRUN | [5 empty] | 2025-12-19 | 2025-12-19 | Akhom Srinara | N/A | Closed | 2025-12-19 11:21:37 | No | No |  |  |  | 2025-12-17 | 2025-12-17 | 2025-12-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-24 10:38:02 | Yes | Yes | 2025-12-26 13:31:21 |  | 2025-12-28 | 2025-12-28 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-16 16:09:55 | Yes | Yes | 2025-12-28 11:03:16 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:24:59 |  | 2025-12-28 | 2025-12-28 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2025-12-28 01:39:06 |  |  | 2025-12-31 | 2025-12-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-17 09:56:56 | No | No |  |  |  |  | 2025-12-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-16 18:23:16 | No | No |  | 16-Dec-2025 Add AAU5614 Sector 1 Add RRU5516 (700900) Sector 7 Add Ant 4port S7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMGMM_2025 Capacity Expansion Ph2_EXP_BKK | SIAM MONGKOL MARINE CO._ LTD. |  |  |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-10 18:33:54 | No | No |  |  |  | 2025-10-16 | 2025-10-24 | 2025-10-24 | V Contribute Co., Ltd | N/A | Closed | 2025-10-24 17:10:53 | Yes | Yes | 2025-10-24 17:10:53 |  | 2025-10-14 | 2025-10-14 | Chonradee Suwapan | Approved | Closed | 2025-10-20 15:40:02 | Yes | Yes | 2026-01-06 18:05:15 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-21 18:54:32 |  | 2025-10-14 | 2025-10-14 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-14 16:47:50 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-04 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-04 18:28:11 | No | No |  | 04-10-2025. Add UBBPg2 RRU5516 L900 Sec.1#， 3#， Replace RRU5516 L900 Sec.2 //3-Oct-2025 Replace Ant 12 port S1 S2 S3 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-09 |  | N/A | Not assigned |  | No | No
SMGMM_2025 Coverage Expansion Ph2_EXP_BKK | SIAM MONGKOL MARINE CO., LTD. | 2025-09-03 |  |  |  | 2025-09-03 | 2025-09-03 | 2025-09-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-03 18:12:42 | No | No |  |  |  | 2025-09-30 | 2025-09-11 | 2025-09-11 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:18:02 | Yes | Yes | 2025-09-30 10:18:02 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:44:55 | Yes | Yes | 2025-12-08 17:42:49 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:51 | Yes | Yes | 2025-10-06 22:40:56 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-14 13:08:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-03 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-03 19:44:30 | No | No |  | 2025-09-03_Add RRU3953#， Ant 4 port Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-02 |  | N/A | Not assigned |  | No | No
SN21M_2025 Capacity Expansion Ph7_EXP_BKK | SAMRONG NUEA 21 |  |  |  | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-02 11:40:53 | No | No |  |  | 2026-01-27 | 2026-01-31 | 2026-01-27 | 2026-02-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-19 09:44:21 | Yes | Yes | 2026-02-19 09:45:23 |  | 2026-02-02 | 2026-02-02 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-19 14:45:45 | Yes | Yes | 2026-02-19 17:53:15 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-19 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:26:16 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 21:48:46 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-26 18:26:07 | No | No |  | 2026-01-26_Add RRU5516(18-21) Sector 7#， Replace Ant to 12 port Sector 2#，7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOKDM_2025 Capacity Expansion Ph4_EXP_ER | Soi Khao Din Patana 2 | 2025-09-11 |  | Install & Integrate |  | 2025-09-30 | 2025-09-12 | 2025-09-12 | Teloneer Company Limited | N/A | Closed | 2025-09-12 17:38:52 | No | No |  |  |  | 2025-09-30 | 2025-09-11 | 2025-09-14 | Teloneer Company Limited | N/A | Closed | 2025-09-29 14:55:00 | Yes | Yes | 2025-10-04 22:24:02 |  | 2025-09-30 | 2025-10-05 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-10 10:16:30 | Yes | Yes | 2025-11-07 13:40:45 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 20:22:46 |  | 2025-09-30 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2026-03-02 15:29:20 | Yes | Yes | 2025-10-08 11:00:13 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-16 |  | 2025-09-09 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-09 17:15:42 | No | No |  | **waiting on-service NR7 -- Add UBBPg2 #， Replace RRU5505 to (RRU5516_1800) + 4T4R S1 #，Replace RRU5505 to (RRU5516_1800) + Co L21F2 + 4T4R S3 #，Replace RRU5508 to (RRU5516_900) + Co NR07 + 4T4R S3 |  | 2025-09-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-11 17:18:09 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SOKKM_2025 Capacity Expansion Ph2_EXP_BKK | S.KHONKAEN FOODS PUBLIC COMPANY LIMITED |  |  |  |  | 2025-10-21 | 2025-10-21 | 2025-10-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-21 17:43:19 | No | No |  |  |  | 2025-10-17 | 2025-10-29 | 2025-10-29 | V Contribute Co., Ltd | N/A | Closed | 2025-10-29 20:02:11 | Yes | Yes | 2025-10-29 20:02:11 |  | 2025-10-29 | 2025-10-29 | Chonradee Suwapan | Approved | Closed | 2025-11-07 15:15:50 | Yes | Yes | 2025-10-29 20:15:14 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-01 21:52:02 |  | 2025-10-29 | 2025-10-29 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-29 20:25:03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-11 17:36:17 | No | No |  | 11-10-2025. Add RRU5516 L18 Sec.6#， Replace Ant.12 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Complted |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
SOMCM_2025 Capacity Expansion Ph2_EXP_BKK | SOI MITCHARAT | 2025-08-21 |  |  |  | 2025-08-21 | 2025-08-21 | 2025-08-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-21 17:56:59 | No | No |  |  |  | 2025-08-30 | 2025-08-27 | 2025-08-30 | V Contribute Co., Ltd | N/A | Closed | 2025-08-30 18:53:26 | Yes | Yes | 2025-08-30 18:54:53 |  |  | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-09-17 13:07:46 | Yes | Yes | 2025-09-05 20:32:36 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:12 | Yes | Yes | 2025-09-23 01:43:30 |  | 2025-09-05 | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-05 20:39:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-21 18:34:48 | No | No |  | 21-08-2025. Replace RRU5516 L18#， Ant.8 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-20 |  | N/A | Not assigned |  | No | No
SOMCM_2025 Capacity Expansion Ph3_EXP_BKK | SOI MITCHARAT | 2025-08-27 |  |  |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-27 18:39:50 | No | No |  |  |  | 2025-09-05 | 2025-08-28 | 2025-08-28 | V Contribute Co., Ltd | N/A | Closed | 2025-08-28 10:31:47 | Yes | Yes | 2025-08-28 10:33:42 |  | 2025-09-09 | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-25 14:38:34 | Yes | Yes | 2025-09-09 18:56:49 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 20:24:00 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-09 19:06:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-27 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-28 02:03:21 | No | No |  | 2025-08-27_Add AAU5636w Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-26 |  | N/A | Not assigned |  | No | No
SP34M_2025 Coverage Expansion Ph2_EXP_BKK | SOI SATHUPRADIT 34 YAEK 11 |  |  |  | 2025-08-16 |  | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-22 | 2025-08-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-22 21:05:16 | Yes | Yes | 2025-08-28 08:54:33 |  | 2025-08-29 | 2025-08-29 | Aomchun Jittreemit | Approved | Closed | 2025-09-17 16:23:58 | Yes | Yes | 2025-09-03 20:02:35 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:12 | Yes | Yes | 2025-09-23 01:45:55 |  | 2025-09-05 | 2025-09-05 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-09-05 12:07:15 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-22 17:59:08 | No | No |  | 22-08-2025. Add RRU3953 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
SP37M_2025 Coverage Expansion Ph2_EXP_BKK | SATIT PATTANA SCHOOL HATHAIRAT37 |  |  |  | 2025-08-16 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-22 | 2025-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-23 09:56:54 | Yes | Yes | 2025-08-25 23:15:56 |  | 2025-08-28 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-17 09:17:13 | Yes | Yes | 2025-09-03 13:59:44 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:12 | Yes | Yes | 2025-09-23 01:47:08 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 21:01:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-22 17:59:08 | No | No |  | 22-08-2025. Add RRU3953#， Ant.4 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
SPABM_2025 Coverage Expansion Ph2_EXP_BKK | SOI SUPHAP BURUT |  |  |  |  | 2025-08-12 | 2025-08-12 | 2025-08-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-12 18:41:19 | No | No |  |  |  | 2025-08-29 | 2025-08-18 | 2025-08-18 | V Contribute Co., Ltd | N/A | Closed | 2025-08-18 14:08:47 | Yes | Yes | 2025-08-18 14:10:09 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-09 09:04:09 | Yes | Yes | 2025-09-02 18:20:39 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:12 | Yes | Yes | 2025-09-23 01:48:21 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:31 | No | Yes | 2025-08-27 15:54:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-12 17:52:26 | No | No |  | 12-08-2025. Add UBBPd6#， RRU3953#， Ant.4 port Sec.1#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-11 |  | N/A | Not assigned |  | No | No
SPKNM_2025 Coverage Expansion Ph2_EXP_BKK | SUPHAWAN SRINAKHARIN VILLAGE |  |  |  | 2025-08-16 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-22 | 2025-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-23 16:02:27 | Yes | Yes | 2025-08-28 12:18:49 |  | 2025-08-29 | 2025-09-03 | Kontira Kowapradit | Approved | Closed | 2025-09-18 16:40:10 | Yes | Yes | 2025-09-03 16:54:32 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:12 | Yes | Yes | 2025-09-23 01:54:31 |  | 2025-09-04 | 2025-09-04 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 14:17:50 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-22 17:02:32 | No | No |  | 22-Aug-2025 Add RRU3953 S3 Replace Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
SPKWA_2025 Capacity Expansion Ph8_EXP_BKK | SAPHANKWAI SMALL CELL |  |  |  | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-06-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-26 18:54:47 | No | No |  |  | 2026-06-25 | 2026-06-25 | 2026-06-27 | 2026-06-29 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-29 16:05:09 | Yes | Yes | 2026-07-03 13:27:51 |  | 2026-07-17 | 2026-07-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-10 09:32:19 | Yes | Yes | 2026-07-20 15:31:19 | Remove breaker is 16A/1P=2pcs.Revise in pg-6. Wrong site name in pg-7#，8#，9#，10. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-29 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-07-14 22:57:53 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-06-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-06-22 16:59:51 | No | No |  | 22-Jun-2026 Replace BBU5900 UMPTg2 Add g3a g2 Add RRU5818 Sector A co B ติด GPS ไม่ได้ Run NB Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPKWB_2025 Capacity Expansion Ph2_EXP_BKK | SAPHAN KWAI FOR THE LINE PHAHON-PRADIPAT & THE RESERVE PHAHON-PRADIPAT | 2025-09-30 |  |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 10:49:05 | No | No |  |  |  | 2025-10-10 | 2025-10-24 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 15:52:07 | Yes | Yes | 2025-10-30 15:52:08 |  | 2025-10-04 | 2025-10-04 | Chonradee Suwapan | Approved | Closed | 2025-10-20 17:17:30 | Yes | Yes | 2026-01-07 10:17:42 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-21 18:59:25 |  | 2025-10-04 | 2025-10-04 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-04 21:04:22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-30 17:15:02 | No | No |  | 30-Sep-2025 Add RRU5818 SB Add g3a 5/3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK40 |  | 2025-09-30 |  | N/A | Not assigned |  | No | No
SPN2M_2025 Capacity Expansion Ph3_EXP_BKK | SUKHAPIBAN 2 | 2025-08-29 |  |  |  | 2025-08-30 | 2025-08-30 | 2025-08-30 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-30 09:04:17 | No | No |  |  |  | 2025-09-05 | 2025-09-08 | 2025-09-09 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:18:16 | Yes | Yes | 2025-09-30 10:18:17 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-26 16:35:46 | Yes | Yes | 2025-12-05 10:53:50 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:22 | Yes | Yes | 2025-11-06 20:31:05 |  | 2025-09-11 | 2025-09-11 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:04 | No | Yes | 2025-09-11 21:36:47 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-29 19:46:39 | No | No |  | 29-Aug-2025 Add RRU5516 (1800-2100) Sector M Replace Ant 12port Tri Beam S3 S8 SM |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-28 |  | N/A | Not assigned |  | No | No
SPNYM_2025 Capacity Expansion Ph6_EXP_BKK | SOI SAPHAN YAO | 2025-12-03 |  |  |  | 2025-12-31 | 2025-12-04 | 2025-12-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-04 18:19:04 | No | No |  |  |  | 2025-12-31 | 2025-12-16 | 2025-12-17 | V Contribute Co., Ltd | N/A | Closed | 2025-12-17 19:53:05 | Yes | Yes | 2025-12-17 19:53:05 |  | 2025-12-09 | 2025-12-09 | Chonradee Suwapan | Approved | Closed | 2025-12-19 17:39:21 | Yes | Yes | 2026-01-14 17:20:04 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-15 13:16:09 |  | 2025-12-09 | 2025-12-09 | Chonradee Suwapan | Approved | Closed | 2025-12-19 13:53:15 | Yes | Yes | 2025-12-09 21:00:37 |  |  | 2025-12-31 | 2025-12-03 | V Contribute Co., Ltd | N/A | Closed | 2025-12-03 15:27:29 | No | No |  |  |  |  | 2025-12-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-03 16:24:32 | No | No |  | 3-Dec-2025 Add AAU5636w sector 7 Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPPNM_2025 Capacity Expansion Ph4_EXP_SR | Sam Yaek PhunPhin |  |  |  | 2025-10-07 | 2025-10-07 | 2025-10-07 | 2025-10-07 | Nattawoot Suwan | N/A | Closed | 2025-10-10 11:40:14 | No | No |  |  |  | 2025-09-26 | 2025-10-02 | 2025-10-07 | Teloneer Company Limited | N/A | Closed | 2025-10-07 21:13:41 | Yes | Yes | 2025-10-08 15:21:01 |  | 2025-10-10 | 2025-10-10 | Nattawoot Suwan | Approved | Closed | 2025-10-14 09:16:12 | Yes | Yes | 2025-10-15 17:31:35 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:28 | Yes | Yes | 2025-10-27 18:51:33 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-10-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-02 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-10-02 18:10:16 | No | No |  | Clear Work & Take Photo |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-06 |  | N/A | Not assigned |  | No | No
SPRVB_2025 Capacity Expansion Ph2_EXP_BKK | SUPALAI RIVA GRANDE |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-11-30 | 2025-11-24 | 2025-11-26 | V Contribute Co., Ltd | N/A | Closed | 2025-11-26 12:01:45 | Yes | Yes | 2025-11-26 12:01:45 |  | 2025-11-27 | 2025-11-27 | Chonradee Suwapan | Approved | Closed | 2025-12-02 11:01:42 | Yes | Yes | 2025-11-27 20:14:56 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:54:34 |  | 2025-11-27 | 2025-11-27 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-27 20:23:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-21 18:40:13 | No | No |  | 21-Nov-2025 Add RRU5818 Sector A Replace Ant 12port No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-24 |  | N/A | Not assigned |  | No | No
SPTMM_2025 Capacity Expansion Ph5_EXP_BKK | SOI PERM TERM | [5 empty] | 2025-11-26 | 2025-11-26 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  | 2025-11-19 | 2025-11-20 | 2025-11-20 | 2025-11-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-20 20:30:27 | Yes | Yes | 2025-11-20 20:30:27 |  | 2025-11-28 | 2025-11-28 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-30 21:14:02 | Yes | Yes | 2025-11-28 14:21:40 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-03-20 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2025-11-28 | 2025-11-28 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:24:43 | Yes | Yes | 2025-11-28 14:19:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-18 17:50:30 | No | No |  | 18-11-2025. Add RRU5516 L900 Sec.8#， Replace Ant.8 port Sec.3#， 8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPY1M_2025 Capacity Expansion NW Modernization_EXP_BKK | SIPRAYA 1 |  |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-01-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-28 11:48:30 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-20 | 2026-01-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-25 16:07:36 | Yes | Yes | 2026-01-25 16:08:47 |  | 2026-01-28 | 2026-01-28 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-13 09:38:32 | Yes | Yes | 2026-02-25 18:01:38 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:29:07 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 20:19:15 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-17 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-17 20:22:52 | No | No |  | 17 Jan 2026 replace 5507 to AAU5768 On DMM sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SQ1PP_2025 Capacity Expansion NW Modernization_EXP_BKK | Siam Square One |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-24 14:48:20 | No | No |  |  |  | 2026-02-07 | 2026-02-16 | 2026-02-23 | V Contribute Co., Ltd | N/A | Closed | 2026-02-23 10:46:12 | Yes | Yes | 2026-02-23 10:46:12 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-03-13 10:58:27 | Yes | Yes | 2026-02-23 21:21:00 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-07 | 2026-03-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:29:26 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-23 22:48:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-21 19:27:06 | No | No |  | 21-01-2026 Replace bbu 3900 to 5900 Done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-20 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 05:53:28 | Yes | Yes | 2026-01-20 16:53:27 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SR41M_2025 Capacity Expansion Ph3_EXP_BKK | SOI PHRAYA SUREN 41 | [5 empty] | 2025-09-01 | 2025-09-01 | Akhom Srinara | N/A | Closed | 2025-09-01 09:42:25 | No | No |  |  |  |  | 2025-08-29 | 2025-08-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-30 13:58:13 | Yes | Yes | 2025-09-01 17:51:33 |  | 2025-09-04 | 2025-09-04 | Muhamadnase Chesamae | Approved | Closed | 2025-10-03 16:14:46 | Yes | Yes | 2025-09-10 18:52:48 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-06 23:12:21 |  | 2025-09-05 | 2025-09-05 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-09-05 15:45:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-29 18:39:45 | No | No |  | 29-08-2025. Add UBBPg2#， AIRU5636w Sec.2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-31 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
SR41M_2025 Capacity Expansion Ph6_EXP_BKK | SOI PHRAYA SUREN 41 | [5 empty] | 2025-12-23 | 2025-12-23 | Akhom Srinara | N/A | Closed | 2025-12-23 09:33:12 | No | No |  |  |  | 2025-12-18 | 2025-12-21 | 2025-12-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-22 10:11:07 | Yes | Yes | 2025-12-23 11:26:37 |  | 2025-12-26 | 2026-01-26 | Muhamadnase Chesamae | Approved | Closed | 2026-02-02 09:28:07 | Yes | Yes | 2026-01-26 12:47:30 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-03 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:29:45 |  | 2025-12-26 | 2025-12-26 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2025-12-26 14:11:22 |  |  | 2025-12-31 | 2025-12-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-18 13:23:14 | No | No |  |  |  |  | 2025-12-18 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-12-18 18:13:37 | No | No |  | 2025-12-18_Add AAU5636w Sector 1#， Add RRU3962#， Replace to ant 8 port Sector8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SRK9A_2025 Capacity Expansion Ph2_EXP_BKK | SOI SURAO KHLONG NUENG 9_4 |  |  |  |  | 2025-09-25 | 2025-09-25 | 2025-09-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-25 09:53:30 | No | No |  |  |  | 2025-09-30 | 2025-10-16 | 2025-10-20 | V Contribute Co., Ltd | N/A | Closed | 2025-10-20 20:30:23 | Yes | Yes | 2025-10-20 20:30:24 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2025-10-20 17:17:30 | Yes | Yes | 2025-09-29 19:36:26 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-21 19:01:51 |  | 2025-09-29 | 2025-09-29 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-09-29 12:46:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-24 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-24 16:59:01 | No | No |  | 24-09-2025. Add RRU5516 L900#， Replace Ant.12 port Sec.C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-09-24 |  | N/A | Not assigned |  | No | No
SRKJN_2025 Coverage Expansion Ph1_New_SR | Si Kanchana Maen Chan |  |  |  |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | Teloneer Company Limited | N/A | Closed | 2026-02-24 15:27:07 | No | No |  |  |  | 2026-02-13 | 2026-02-24 | 2026-02-25 | Teloneer Company Limited | N/A | Closed | 2026-02-25 15:56:07 | Yes | Yes | 2026-03-04 11:08:56 |  | 2026-03-04 | 2026-03-04 | Teloneer Company Limited | Approved | Closed | 2026-03-05 09:51:32 | Yes | Yes | 2026-03-06 10:29:28 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-24 | 2026-03-17 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-02-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-24 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-24 17:40:45 | No | No |  | 24 Feb 2026 New site Add 8RRU3826 4RRU3953 4UBBPd5 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-22 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-22 21:09:46 | Yes | Yes | 2026-01-22 15:18:55 |  |  | 2026-03-09 | Nattawoot Suwan | N/A | Closed | 2026-03-09 14:42:38 | No | No | [5 empty] | 2026-02-23 |  | N/A | Not assigned |  | No | No
SRPBM_2025 Coverage Expansion CO-NT Tower_EXP_ER | Soi RuamPhattana Banchang | 2025-08-19 |  | Clear Pending |  | 2025-08-31 | 2025-08-19 | 2025-08-20 | Teloneer Company Limited | N/A | Closed | 2025-08-20 11:57:18 | No | No |  |  |  | 2025-08-31 | 2025-08-18 | 2025-08-21 | Teloneer Company Limited | N/A | Closed | 2025-08-21 22:01:03 | Yes | Yes | 2025-09-15 20:40:24 |  | 2025-08-31 | 2025-09-16 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-26 13:45:51 | Yes | Yes | 2025-09-16 13:53:47 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-12-31 | 2025-09-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:21 | Yes | Yes | 2025-11-06 20:38:04 |  | 2025-08-31 | 2025-07-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-12 15:43:17 | Yes | Yes | 2025-08-29 17:29:10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-20 |  | 2025-08-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-15 18:29:38 | No | No |  | **waiting on-service -- add 1ug2 #，resector LB S3 to S8 & rep.rru5508 to 5516 Co NR07#，New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB) S3#，Replace Antenna (Dualband Dualbeam) 18/21 S1 co S6 co LB S1 Co NR07 |  | 2025-08-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-15 18:29:38 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SRRCB_2025 Coverage Expansion Ph1_EXP_BKK | Siri Residence |  |  |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-10-25 | 2025-10-29 | V Contribute Co., Ltd | N/A | Closed | 2025-10-29 16:57:17 | Yes | Yes | 2025-10-29 16:57:18 |  | 2025-11-03 | 2025-11-03 | Chonradee Suwapan | Approved | Closed | 2025-11-07 16:24:47 | Yes | Yes | 2026-01-07 15:46:52 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-01 22:04:11 |  | 2025-11-03 | 2025-11-03 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-03 20:03:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-22 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-22 18:17:06 | No | No |  | 2025-10-22_Replace to Ant vertical dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-22 |  | N/A | Not assigned |  | No | No
SRWEA_2025 Capacity Expansion NW Modernization_EXP_BKK | SRI WEANG RD. |  |  |  |  | 2026-01-16 | 2026-03-04 | 2026-03-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-08 22:43:15 | No | No |  |  |  | 2026-01-31 | 2026-02-20 | 2026-03-05 | V Contribute Co., Ltd | N/A | Closed | 2026-03-05 11:24:33 | Yes | Yes | 2026-03-05 11:24:33 |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-07-23 09:23:17 | Yes | Yes | 2026-05-19 16:53:46 | PAT pass | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-23 | 2026-07-23 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-24 21:43:53 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-15 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-15 19:52:17 | No | No |  | 15-01-2026. Replace BBU5900#， UMPTg2 10G#， Add UBBPg2 //ติด GPS ไม่ได้ |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-13 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-13 16:07:27 | Yes | Yes | 2026-01-13 10:26:23 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SS59B_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL CONDOMINIUM SOI SUKUMVIT 59 |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:32:04 | No | No |  |  | 2026-04-30 | 2026-04-30 | 2026-05-17 | 2026-05-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-18 16:08:08 | Yes | Yes | 2026-05-19 11:33:12 |  | 2026-06-24 | 2026-06-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-28 22:13:51 | Yes | Yes | 2026-06-24 16:10:19 | Page no.6#， remove and install antenna unit wrong#， must be stes (not sector). Page no.6#， 16 and 19 remove antenna model must be TS-890/2170-15 in remark. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-29 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-07-14 22:58:18 |  |  | 2026-04-30 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 18:15:35 | No | No |  |  |  |  | 2026-04-23 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-04-23 19:38:42 | No | No |  | 23 Apr 2026 Add RRU5507 sector A replace ANT |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSEAM_2025 Capacity Expansion Ph6_EXP_ER | Thai Samsung Electronics Company Limited , ATB Building floor Top Roof | 2025-11-25 | THCP_Phet.S |  |  | 2025-11-30 | 2025-11-25 | 2025-11-25 | Teloneer Company Limited | N/A | Closed | 2025-11-25 13:45:56 | No | No |  |  |  | 2025-11-30 | 2025-11-25 | 2025-11-25 | Teloneer Company Limited | N/A | Closed | 2025-11-25 18:24:12 | Yes | Yes | 2025-11-25 19:09:26 |  | 2025-11-30 | 2025-11-25 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-26 10:53:32 | Yes | Yes | 2025-11-25 19:58:29 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-09 22:12:53 |  | 2025-11-30 | 2025-11-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-25 18:20:01 | Yes | Yes | 2025-11-25 12:52:48 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-25 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-11-25 18:27:06 | No | No |  | 25-Nov-2025 Add 1AAU5636w sector 3 #， Add 1UBBPg3a |  | 2025-11-26 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-10 11:08:32 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSHNM_2025 Capacity Expansion Ph5_EXP_BKK | SIRINDHORN SCIENCE HOME (NECTEC) | [5 empty] | 2025-12-11 | 2025-12-11 | Narongsak wanichachiwa | N/A | Closed | 2025-12-23 09:27:43 | No | No |  |  |  | 2025-11-18 | 2025-12-10 | 2025-12-10 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-12-10 20:17:20 | Yes | Yes | 2026-05-10 10:51:44 |  |  | 2025-12-14 | Sukhum Parintawong | Approved | Closed | 2025-12-18 09:25:15 | Yes | Yes | 2025-12-14 13:16:07 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 22:14:05 |  | 2025-12-25 | 2025-12-25 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-03-12 10:15:38 | Yes | Yes | 2025-12-25 16:48:34 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-26 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-26 15:20:34 | No | No |  | 27-Nov-2025 Clear Pending work Re-diraction 700900 Sector 2 26-Nov-2025 AAU5636w sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSKNF_2025 Capacity Expansion Ph2_EXP_SR | ELECTRIC POLE SAFE SKIN FACTORY DORMITORY_POINT 1 |  |  |  |  | 2025-11-28 | 2025-12-24 | 2025-12-24 | Patompong Rodrakum(Turnkey Communication Services Public Company Limited.) | N/A | Closed | 2025-12-24 11:04:02 | No | No |  |  |  | 2025-11-27 | 2025-12-25 | 2026-01-07 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-01-07 12:24:14 | Yes | Yes | 2026-01-09 11:30:03 |  |  | 2026-01-09 | Rosak soko | Approved | Closed | 2026-01-23 09:45:24 | Yes | Yes | 2026-01-10 12:00:05 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-03-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 18:21:15 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-09 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-12-09 17:39:08 | No | No |  | 7 Jan 2025 Test Alarm// add PMU#，add Battety*2 9 Dec 2025 Promote BBU add New 5516 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-27 |  | N/A | Not assigned |  | No | No
SSNGM_2025 Coverage Expansion Ph1_New_BKK | Sinsap Nakorn Garden Macro Cell |  |  |  |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-27 18:40:12 | No | No |  |  |  | 2025-08-29 | 2025-09-16 | 2025-09-17 | V Contribute Co., Ltd | N/A | Closed | 2025-09-17 11:49:38 | Yes | Yes | 2025-09-17 11:49:39 |  |  | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2026-02-09 17:33:30 | Yes | Yes | 2025-12-05 12:16:12 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-05-20 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-09-05 | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:38 | No | Yes | 2025-09-05 08:40:29 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-27 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-28 02:03:21 | No | Yes | 2025-08-11 16:48:33 | 2025-08-27_New Site Add RRU3962#， Ant 6 port Sector 1#，2#，3#， Add UBBPd5(3)#， UBBPg3a |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2025-08-11 | Paphawarin Yoopoo WX1434740 | Approved | Closed | 2025-08-25 19:06:56 | Yes | Yes | 2025-08-25 18:51:05 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
SSQOM_2025 Capacity Expansion NW Modernization_EXP_BKK | SUN SQUARE OPTIC REPEATER | 2026-01-19 |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-24 14:48:20 | No | No |  |  |  | 2026-01-31 | 2026-02-03 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:48:12 | Yes | Yes | 2026-03-23 15:48:13 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-03-09 09:30:25 | Yes | Yes | 2026-05-19 17:32:34 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:31:02 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-23 22:49:58 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-19 |  | N/A | Not assigned |  | No | No |  | 19-01-2026. Replace RRU5502 to AAU5768#， RRU3953 to RRU5516#， Ant.4 port Sec.2 //16-01-2026. Replace Ant.8 port Sec.3 17 Jan 2026 ADD AAU5768 On DMM SECTOR 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSRWB_2025 Capacity Expansion NW Modernization_EXP_BKK | SIAMESE SURAWONG |  |  |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | 2026-01-29 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-30 11:11:49 | No | No |  |  | 2026-01-24 | 2026-01-24 | 2026-01-24 | 2026-02-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-02 11:34:43 | Yes | Yes | 2026-02-02 11:37:17 |  | 2026-02-01 | 2026-01-30 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-11 09:40:40 | Yes | Yes | 2026-01-30 12:04:53 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:31:21 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 20:19:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-21 14:44:26 | No | No |  | 21-Jan-2026 Add RRU5526 Sector A Remove RRU3962 Add g3a =2 Remove g2 =2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSSLM_2025 Capacity Expansion Ph6_EXP_ER | Soi Sao Sung Alai | 2025-11-27 | thcp_Phet.s | Clear Pending |  | 2025-11-30 | 2025-11-06 | 2025-11-06 | Teloneer Company Limited | N/A | Closed | 2025-11-06 16:56:09 | No | No |  |  |  | 2025-11-30 | 2025-11-06 | 2025-11-07 | Teloneer Company Limited | N/A | Closed | 2025-11-07 10:59:09 | Yes | Yes | 2025-11-12 07:04:48 |  | 2025-11-30 | 2025-11-27 | Thanakit Chaleechai | Approved | Closed | 2025-12-02 14:49:44 | Yes | Yes | 2025-11-27 16:17:05 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-09 22:16:30 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:12 | Yes | Yes | 2025-11-04 09:27:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-06 | Reungsak Junkong 00927496 | N/A | Closed | 2025-11-06 17:42:20 | No | No |  | **waiting on-service LNR26 -- New L26F5 + NR26 (New RRU5818) + Co Antenna Sec.6#，7 |  | 2025-11-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-07 18:48:57 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSTPM_2025 Capacity Expansion Ph2_EXP_BKK | SOI SAENG THIP | 2025-08-11 |  |  |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-11 19:17:40 | No | No |  |  |  | 2025-08-29 | 2025-08-13 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 16:51:52 | Yes | Yes | 2025-08-15 16:53:10 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2026-03-11 16:32:23 | Yes | Yes | 2025-09-03 21:10:26 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:35 | Yes | Yes | 2026-01-09 22:17:43 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-03 20:56:06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-11 18:23:00 | No | No |  | 11-08-2025. Replace RRU5516 L18 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-08 |  | N/A | Not assigned |  | No | No
SSW8A_2025 Capacity Expansion Ph2_EXP_BKK | SOI SUKSAWAT 8 |  |  |  |  | 2025-09-10 | 2025-09-17 | 2025-09-17 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:49 | No | No |  |  |  | 2025-09-29 | 2025-09-20 | 2025-09-22 | V Contribute Co., Ltd | N/A | Closed | 2025-09-22 09:40:12 | Yes | Yes | 2025-09-22 09:40:12 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-10-08 14:52:51 | Yes | Yes | 2025-09-18 20:03:07 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 21:56:30 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 21:33:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-09 18:51:10 | No | No |  | 9-Sep-2025 Add RRU5516(18002100) S3 S8 Remove RRU3962 *2 Replace Ant 8port S3 S8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-16 |  | N/A | Not assigned |  | No | No
STEXM_2025 Capacity Expansion NW Modernization_EXP_BKK | SATHORN EXPRESS WAY |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 16:26:40 | No | No |  |  | 2026-02-17 | 2026-02-17 | 2026-02-18 | 2026-02-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-19 14:50:15 | Yes | Yes | 2026-02-23 15:37:43 |  | 2026-02-24 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-03-27 13:47:47 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 20:20:02 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-16 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-16 19:13:00 | No | No |  | 16-Feb-26 Replace Ant 8 Port S2 13-Feb-2026 ***Pending Replace Ant 8port Sector 2 Co 18002100 RRU3953 fail 1/2 ///Add RRU5507 *2 Sector 3 Remove RRU3962 Replace Ant 8port co 1800900 S3 Add RRU3953 *2 Sector 3 Done 1/2 1/5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STN8A_2025 Capacity Expansion NW Modernization_EXP_BKK | SATHON 8 | 2026-01-13 |  |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-13 14:10:59 | No | No |  |  |  | 2026-01-31 | 2026-01-13 | 2026-01-13 | V Contribute Co., Ltd | N/A | Closed | 2026-01-13 18:22:15 | Yes | Yes | 2026-01-13 18:22:16 |  | 2026-01-31 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-12 14:35:31 | Yes | Yes | 2026-02-11 11:46:36 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:32:18 |  | 2026-02-01 | 2026-01-31 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-01 00:00:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-13 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-13 17:56:34 | No | No |  | 13 Jan 2026 Replace ant form 4 port to 8 port only and No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STPVM_2025 Coverage Expansion Ph2_EXP_BKK | SUAN THEP PRATHAN VILLAGE | 2025-08-15 |  |  |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-15 18:59:38 | No | No |  |  | 2025-08-08 | 2025-08-15 | 2025-08-08 | 2025-08-20 | V Contribute Co., Ltd | N/A | Closed | 2025-08-20 19:56:11 | Yes | Yes | 2025-08-20 19:56:12 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-05 17:11:19 | Yes | Yes | 2025-09-02 18:21:38 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:12 | Yes | Yes | 2025-09-23 02:10:44 |  | 2025-08-13 | 2025-08-13 | Annop Auyto | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-13 13:13:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-15 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-15 17:34:49 | No | No |  | 2025-08-15_Add RRU3953#， No act Ant Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-14 |  | N/A | Not assigned |  | No | No
STRXM_2025 Capacity Expansion Ph5_EXP_BKK | SITHARA PLACE |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-12-28 | 2025-12-17 | 2025-12-17 | V Contribute Co., Ltd | N/A | Closed | 2025-12-17 17:52:13 | Yes | Yes | 2025-12-17 17:52:14 |  | 2025-11-28 | 2025-11-28 | Chonradee Suwapan | Approved | Closed | 2025-12-18 16:45:53 | Yes | Yes | 2025-11-28 19:51:12 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-15 13:25:13 |  | 2025-11-28 | 2025-11-28 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-11-28 19:58:12 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-21 17:57:01 | No | No |  | 21-11-2025. Replace RRU5526#， Ant.8 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SU34M_2025 Coverage Expansion Ph2_EXP_BKK | SOI SUKHONTHASAWAT 34 | 2025-08-19 |  |  |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-19 18:17:20 | No | No |  |  |  | 2025-08-29 | 2025-08-25 | 2025-08-26 | V Contribute Co., Ltd | N/A | Closed | 2025-08-26 10:22:41 | Yes | Yes | 2025-09-05 11:49:33 |  |  | 2025-09-05 | Chonradee Suwapan | Approved | Closed | 2025-09-12 19:05:01 | Yes | Yes | 2025-09-05 20:33:21 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:12 | Yes | Yes | 2025-09-23 02:11:59 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-02 17:26:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-19 17:52:35 | No | No |  | 2025-08-19_Add RRU3953#， No act Ant Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-18 |  | N/A | Not assigned |  | No | No
SU3AB_DPU40_OPM30_Replacement_BKK | Dormitory Building 3A Shinawatra University | 2026-01-08 |  |  |  | 2026-01-08 | 2026-01-08 | 2026-01-08 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-08 17:10:04 | No | No |  |  |  | 2025-12-31 | 2026-01-08 | 2026-01-08 | V Contribute Co., Ltd | N/A | Closed | 2026-01-08 15:18:00 | Yes | Yes | 2026-01-08 15:18:00 |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-01-27 15:52:45 | Yes | Yes | 2026-01-18 19:48:55 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-28 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-18 20:16:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-08 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-08 17:35:33 | No | No |  | 8-Jan-2026 SU3AB_DPU40_OPM30_Replacement_BKK |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2026-01-07 |  | N/A | Not assigned |  | No | No
SUDSM_2025 Capacity Expansion Ph6_EXP_BKK | SOI S.UDOMSUP | [5 empty] | 2025-12-25 | 2025-12-25 | Akhom Srinara | N/A | Closed | 2025-12-25 09:52:09 | No | No |  |  |  | 2025-12-22 | 2025-12-23 | 2025-12-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-24 11:52:42 | Yes | Yes | 2025-12-26 20:45:28 |  | 2026-01-08 | 2026-01-22 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-27 15:29:52 | Yes | Yes | 2026-01-22 16:06:31 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:32:57 |  | 2026-01-05 | 2026-01-05 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-05 17:47:14 |  |  | 2025-12-31 | 2025-12-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-20 16:57:48 | No | No |  |  |  |  | 2025-12-24 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-24 13:42:58 | No | No |  | 24-Dec-2025 Add AAU 5614 Sector 2 20-12-2025. ***Need AIRU5614 Sec.2 //Add AIRU5614 Sec.1#， Replace RRU3953 to RRU5516 L900 Sec.3#， UBBPd5 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUKTB_2025 Capacity Expansion Ph2_EXP_BKK | KENSINGTON SUKHUMVIT-THEPHARAK | 2025-09-22 |  |  |  | 2025-09-24 | 2025-09-24 | 2025-09-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-24 09:51:37 | No | No |  |  |  | 2025-09-30 | 2025-10-03 | 2025-10-07 | V Contribute Co., Ltd | N/A | Closed | 2025-10-07 22:40:50 | Yes | Yes | 2025-10-07 22:40:51 |  | 2025-09-26 | 2025-09-26 | Chonradee Suwapan | Approved | Closed | 2025-10-20 16:38:16 | Yes | Yes | 2025-12-09 16:03:09 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-21 19:05:30 |  | 2025-09-26 | 2025-09-26 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-09-26 18:47:23 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-22 17:31:04 | No | No |  | 22-09-2025. Add UBBPg3a#， RRU5818 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  | 2025-09-23 |  | N/A | Not assigned |  | No | No
SUPLA_2025 Capacity Expansion NW Modernization_EXP_BKK | SUAN PHLU POST OFFICE |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:59:53 | No | No |  |  | 2026-02-16 | 2026-02-23 | 2026-06-11 | 2026-06-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-15 09:52:25 | Yes | Yes | 2026-06-19 14:45:38 |  | 2026-06-24 | 2026-06-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-07-31 10:10:31 | Yes | Yes | 2026-06-24 10:48:40 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 20:20:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-21 17:40:44 | No | No |  | 21-Jan-2026 Add RRU5526 Sector A#， B#， C#， D Remove RRU3962 *4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUPMB_2025 Capacity Expansion Ph5_EXP_BKK | SARANSOOK SUPREME |  |  |  | 2025-12-09 | 2025-12-16 | 2025-12-19 | 2025-12-19 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2025-12-19 13:10:27 | No | No |  |  |  | 2025-11-20 | 2025-12-22 | 2025-12-23 | Teloneer Company Limited | N/A | Closed | 2025-12-23 10:20:28 | Yes | Yes | 2025-12-23 10:30:35 |  |  | 2025-12-23 | Apichart Kampuang | Approved | Closed | 2026-01-06 15:54:30 | Yes | Yes | 2025-12-24 16:32:03 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-15 13:28:54 |  |  | 2025-12-08 | Teloneer Company Limited | Approved | Closed | 2026-03-12 09:23:08 | Yes | Yes | 2025-12-09 09:29:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-11 18:38:29 | No | No |  | 11-Dec-2025 Add RRU5818*1 sector AB add g2 Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUTLB_2025 Capacity Expansion Ph2_EXP_BKK | SUPALAI PARK TALAT PHLU STATION |  |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-11 17:27:06 | No | No |  |  |  | 2025-10-31 | 2025-11-28 | 2025-11-29 | V Contribute Co., Ltd | N/A | Closed | 2025-11-29 17:44:28 | Yes | Yes | 2025-11-29 17:44:29 |  | 2025-11-17 | 2025-11-17 | Chonradee Suwapan | Approved | Closed | 2025-12-01 16:22:32 | Yes | Yes | 2026-01-07 10:57:44 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 11:59:24 |  | 2025-11-17 | 2025-11-17 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-17 21:51:33 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-05 12:49:24 | No | No |  | 5-Nov-2025 Add AAU5246 SB Add RRU5516 (700900) SC Add g2 g3a Add Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-10 |  | N/A | Not assigned |  | No | No
SVSUB_2025 Capacity Expansion NW Modernization_EXP_BKK | SUKHUMVIT SUITE (SMALL CELL) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:18:33 | Yes | Yes | 2026-04-01 13:21:27 |  | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-04 20:50:30 | Yes | Yes | 2026-05-04 15:15:36 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 20:20:33 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-21 16:32:29 | No | No |  | 21-Feb-2026 Add RRU5526 Sector 1#，2 Remove RRU3826 RRU3962 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SW13M_2025 Coverage Expansion Ph2_EXP_BKK | SUWINTHAWONG 13 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-08 | 2025-08-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-08 17:16:42 | Yes | Yes | 2025-08-14 14:17:05 |  |  | 2025-08-19 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:35:50 | Yes | Yes | 2025-08-19 21:41:04 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:20 | Yes | Yes | 2025-09-04 15:07:31 |  | 2025-09-02 | 2025-09-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-02 20:15:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-08 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-08 19:13:02 | No | No |  | 8-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
SW53M_2025 Coverage Expansion Ph2_EXP_BKK | SUWINTHAWONG KM.53 |  |  |  |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-07 17:44:53 | No | No |  |  | 2025-08-07 | 2025-08-14 | 2025-08-07 | 2025-08-08 | V Contribute Co., Ltd | N/A | Closed | 2025-08-08 17:40:37 | Yes | Yes | 2025-08-08 17:41:05 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2026-03-11 16:32:23 | Yes | Yes | 2025-09-02 18:22:43 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:34:13 |  | 2025-08-13 | 2025-08-13 | Annop Auyto | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-13 13:14:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-07 17:52:12 | No | No |  | 07-08-2025. Add RRU3953 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
SW57M_2025 Capacity Expansion Ph2_EXP_BKK | SUWINTHAWONG SOI 57 |  |  |  | 2025-08-18 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-18 | 2025-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-20 16:45:57 | Yes | Yes | 2025-08-20 16:57:35 |  | 2025-08-24 | 2025-08-24 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-20 13:21:12 | Yes | Yes | 2025-08-24 19:10:27 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 13:31:20 |  | 2025-08-30 | 2025-08-30 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-10 17:27:23 | No | Yes | 2025-08-30 18:41:33 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-18 17:23:30 | No | No |  | 18-08-2025. Replace RRU5516 L18 Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
SW57M_2025 Coverage Expansion Ph2_EXP_BKK | SUWINTHAWONG SOI 57 |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-08 | 2025-08-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-08 22:21:42 | Yes | Yes | 2025-08-13 15:49:09 |  | 2025-08-13 | 2025-08-13 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-05-27 09:05:16 | Yes | Yes | 2026-01-20 17:21:20 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-05-27 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-09-03 | 2025-09-03 | Future Telecom Co.,Ltd. | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-03 10:26:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-08 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-08 19:12:30 | No | No |  | 8-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | No | No
SWCRM_2025 Capacity Expansion Ph8_EXP_BKK | SOI WAT CHANGRUEANG PHAWANARAM |  |  |  |  | 2026-02-02 | 2026-02-23 | 2026-02-23 | Akhom Srinara | N/A | Closed | 2026-02-23 17:44:36 | No | No |  |  |  | 2026-02-02 | 2026-02-04 | 2026-02-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-02-05 19:49:42 | Yes | Yes | 2026-02-25 22:28:54 |  | 2026-02-27 | 2026-02-27 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-09 17:39:42 | Yes | Yes | 2026-02-27 17:02:00 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:34:32 |  | 2026-06-21 | 2026-06-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-22 20:47:07 | Yes | Yes | 2026-06-21 02:56:35 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-03 17:19:22 | No | No |  | 3-Feb-2026 Add AAU5636w Sector3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWK2M_2025 Capacity Expansion Ph2_EXP_BKK | SOI WATTHANAKHAM 2 | 2025-08-25 |  |  |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-25 17:13:12 | No | No |  |  |  | 2025-08-31 | 2025-09-01 | 2025-09-02 | V Contribute Co., Ltd | N/A | Closed | 2025-09-02 17:49:05 | Yes | Yes | 2025-09-02 17:50:02 |  |  | 2025-09-08 | Chonradee Suwapan | Approved | Closed | 2026-01-27 15:29:52 | Yes | Yes | 2025-10-02 12:07:01 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:35 | Yes | Yes | 2026-01-09 22:38:15 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:28 | No | Yes | 2025-09-06 19:32:59 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-25 18:37:56 | No | No |  | 25-Aug-2025 Add RRU5516 (1800-2100) S1 Remove RRU5507 Replace Ant 8port Add RRU5516 (1800-2100) S3 Remove RRU5507 Replace Ant 8port Add RRU5516 (1800-2100) S6 Add Ant 8port S6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-22 |  | N/A | Not assigned |  | No | No
SWORM_2025 Coverage Expansion Ph2_EXP_BKK | SAWAI- WEST OUTER RING | [5 empty] | 2025-09-04 | 2025-09-04 | Teloneer Company Limited | N/A | Closed | 2025-09-04 08:47:00 | No | No |  |  | 2025-08-27 | 2025-08-29 | 2025-08-30 | 2025-09-03 | Teloneer Company Limited | N/A | Closed | 2025-09-03 18:08:03 | Yes | Yes | 2025-09-04 14:19:00 |  | 2025-09-30 | 2025-09-10 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2025-09-25 14:36:40 | Yes | Yes | 2025-10-17 17:28:43 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-24 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:21 | Yes | Yes | 2025-11-06 20:55:47 |  |  | 2025-08-14 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-14 17:31:00 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-26 16:58:07 | No | No |  | 26-08-2025. Add RRU3953#， Replace Ant.4 port Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-03 | Jia Rui 80023782 | N/A | Closed | 2025-10-01 17:59:07 | No | No
SYBYM_2025 Capacity Expansion Ph3_EXP_BKK | SAM YAEK BANG YAI | [5 empty] | 2025-09-16 | 2025-09-16 | Akhom Srinara | N/A | Closed | 2025-09-25 14:02:33 | No | No |  |  |  |  | 2025-09-10 | 2025-09-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-11 15:20:10 | Yes | Yes | 2025-09-11 15:20:10 |  | 2025-09-11 | 2025-09-11 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-08 14:52:51 | Yes | Yes | 2025-09-11 20:59:43 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 21:59:00 |  | 2025-09-18 | 2025-09-18 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:28:19 | No | Yes | 2025-09-18 14:56:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-10 17:46:37 | No | No |  | 10-09-2025. Add UBBPg2#， Replace RRU5516 L18#， Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-14 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
SYKMS_2025 Capacity Expansion Ph7_EXP_SR | Sam Yaek Komo Sun |  |  |  |  | 2025-12-25 | 2025-12-15 | 2025-12-15 | Teloneer Company Limited | N/A | Closed | 2025-12-15 14:06:28 | No | No |  |  |  | 2025-12-08 | 2025-12-15 | 2025-12-15 | Teloneer Company Limited | N/A | Closed | 2025-12-15 15:02:49 | Yes | Yes | 2025-12-15 19:48:58 |  | 2025-12-16 | 2025-12-16 | Nattawoot Suwan | Approved | Closed | 2026-01-26 10:02:55 | Yes | Yes | 2025-12-17 17:39:00 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 22:44:14 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-15 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-15 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-12-15 17:27:40 | No | No |  | 15 Dec 2025 Add RRU5516 sector4 add 1UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-03-31 | Boonchot Boriwut | N/A | Closed | 2026-03-31 11:34:14 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYMTB_2025 Capacity Expansion NW Modernization_EXP_BKK | CONDO SAMYAN MITRTOWN |  |  |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-05 08:14:49 | No | No |  |  |  | 2026-02-28 | 2026-03-10 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:28:35 | Yes | Yes | 2026-03-23 15:28:36 |  | 2026-03-02 | 2026-03-02 | Chonradee Suwapan | Approved | Closed | 2026-05-11 09:29:24 | Yes | Yes | 2026-04-02 17:08:35 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-02 | 2026-03-02 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:17:02 | Yes | Yes | 2026-03-02 20:55:33 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-13 18:27:25 | No | No |  | 13-02-2026. Replace RRU5507 to RRU5516#， Ant.12 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYNKM_2025 Capacity Expansion Ph4_EXP_SR | Sam Yaek Na Khao |  |  |  | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | Nattawoot Suwan | N/A | Closed | 2025-10-10 15:16:14 | No | No |  |  |  | 2025-09-26 | 2025-10-09 | 2025-10-10 | Teloneer Company Limited | N/A | Closed | 2025-10-10 11:58:41 | Yes | Yes | 2025-10-10 12:01:55 |  | 2025-10-10 | 2025-10-10 | Nattawoot Suwan | Approved | Closed | 2025-10-14 09:16:00 | Yes | Yes | 2025-10-15 14:56:17 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:28 | Yes | Yes | 2025-10-27 19:03:10 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-10-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-09 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-10-09 17:03:31 | No | No |  | 09 Oct 2025 Replace RRU5516 sector3 900/LNR700 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-08 |  | N/A | Not assigned |  | No | No
SYPGM_2025 Coverage Expansion Ph2_EXP_BKK | SOI YAEM PHAGA | [5 empty] | 2025-08-23 | 2025-08-23 | Palagon Prommueangma | N/A | Closed | 2025-08-25 11:40:23 | No | No |  |  | 2025-08-22 | 2025-08-23 | 2025-08-26 | 2025-08-26 | Teloneer Company Limited | N/A | Closed | 2025-08-26 16:00:32 | Yes | Yes | 2025-08-28 14:31:45 |  |  | 2025-09-02 | Apichart Kampuang | Approved | Closed | 2025-09-09 09:04:09 | Yes | Yes | 2025-09-02 14:53:55 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:12 | Yes | Yes | 2025-09-23 02:23:00 |  |  | 2025-08-14 | Khathahat Sitthihong | Approved | Closed | 2025-09-03 22:42:24 | No | Yes | 2025-08-14 17:31:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-23 18:18:22 | No | No |  | 23-Aug-2025 Add RRU3953 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 100% |  | 2025-08-22 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
T11BM_2025 Capacity Expansion Ph3_EXP_BKK | SOI TESSABAN 11/1 BANG BUA THONG | 2025-09-04 |  |  |  | 2025-09-04 | 2025-09-12 | 2025-09-12 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:49 | No | No |  |  |  | 2025-09-26 | 2025-09-12 | 2025-09-12 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:18:30 | Yes | Yes | 2025-09-30 10:18:31 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-10-06 16:50:14 | Yes | Yes | 2025-09-13 20:24:21 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 22:00:15 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-14 13:14:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-04 17:21:18 | No | No |  | 4-Sep-2025 Add AAU5636w S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
TABBM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI TALAT BO BE |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:59:53 | No | No |  |  | 2026-02-04 | 2026-02-04 | 2026-03-15 | 2026-05-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-27 15:11:49 | Yes | Yes | 2026-05-28 09:37:17 |  | 2026-06-10 | 2026-06-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-24 09:32:47 | Yes | Yes | 2026-06-12 15:07:19 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 20:20:48 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-30 17:44:23 | No | No |  | 2026-06-08_Config RET700#，900 Sector 1#，3 30-01-2026 On DMM 1#，3 and Remove sector 6#，8 Done 2026-01-29_Replace UBBPd6 to UBBPg3a#， ***Pending AAU5768 Sector 1#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TACIF_2025 Capacity Expansion Ph7_EXP_SR | Tha Chi Football Field |  |  |  |  | 2025-12-25 | 2025-12-17 | 2025-12-17 | Teloneer Company Limited | N/A | Closed | 2025-12-17 13:30:08 | No | No |  |  |  | 2025-12-08 | 2025-12-17 | 2025-12-17 | Teloneer Company Limited | N/A | Closed | 2025-12-17 17:26:33 | Yes | Yes | 2025-12-18 10:06:16 |  | 2025-12-18 | 2025-12-18 | Nattawoot Suwan | Approved | Closed | 2026-01-26 10:03:10 | Yes | Yes | 2025-12-18 12:50:39 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:32 | Yes | Yes | 2026-01-09 22:51:19 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-18 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-17 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-12-17 16:10:59 | No | No |  | 17 Dec 2025 Add AAU5636w sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-03-31 | Boonchot Boriwut | N/A | Closed | 2026-03-31 11:34:14 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBASB_2025 Coverage Expansion Ph1_EXP_BKK | THE BASE PHETKASEM CONDOMINIUM |  |  |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-09-22 11:24:57 | No | No |  |  |  | 2025-10-10 | 2025-10-02 | 2025-10-03 | V Contribute Co., Ltd | N/A | Closed | 2025-10-03 13:31:39 | Yes | Yes | 2025-10-03 13:31:39 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-10-20 16:38:16 | Yes | Yes | 2025-09-24 18:19:14 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-21 19:16:27 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:20:11 | No | Yes | 2025-09-24 21:37:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-17 17:18:34 | No | No |  | 17-09-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install completed |  | 2025-09-21 |  | N/A | Not assigned |  | No | No
TBKDM_2025 Capacity Expansion Ph8_EXP_ER | Ban Talad BangKrud | 2026-01-20 |  |  |  | 2026-02-28 | 2026-01-20 | 2026-01-20 | Teloneer Company Limited | N/A | Closed | 2026-01-20 14:04:26 | No | No |  |  |  | 2026-02-28 | 2026-01-19 | 2026-01-24 | Teloneer Company Limited | N/A | Closed | 2026-01-24 11:39:49 | Yes | Yes | 2026-01-24 23:35:43 |  | 2026-02-28 | 2026-01-28 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:20:22 | Yes | Yes | 2026-01-28 10:59:02 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:25 | Yes | Yes | 2026-03-24 18:29:56 |  | 2026-01-31 | 2026-01-19 | Adisak Chanmao(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-01-19 13:36:29 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-20 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-01-20 17:43:07 | No | No |  | Add UBBPg3a Replace Antenna (Dualband) + Add RRU5505 x 1 + 4T4R TBKDM_H_4 Replace Antenna (Co Antenna) TBKDM_L_4 New L26F5 + NR26 (New AAU5636w) TBKDM_N_4 |  | 2026-01-21 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-21 16:53:31 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBYJM_2025 Capacity Expansion Ph6_EXP_ER | Tesabal Road 1 Soi 27 |  |  | Install & Integrate |  | 2025-11-30 | 2025-11-15 | 2025-11-15 | Teloneer Company Limited | N/A | Closed | 2025-11-15 14:56:02 | No | No |  |  |  | 2025-11-30 | 2025-11-10 | 2025-11-27 | Teloneer Company Limited | N/A | Closed | 2025-11-27 15:42:33 | Yes | Yes | 2025-11-30 16:22:32 |  | 2025-11-30 | 2025-12-09 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:38:58 | Yes | Yes | 2025-12-09 20:13:33 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 22:58:25 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:12 | Yes | Yes | 2025-11-04 10:48:13 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-26 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-11-26 17:11:46 | No | No |  | 25-Nov-2025 Add 3AAU5636w sector 1&2&3 #， Add 1UBBPg3a |  | 2025-12-01 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-01 17:57:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TC30M_2025 Capacity Expansion Ph7_EXP_BKK | Soi Thep Kunchon 30 |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-06 16:03:37 | No | No |  |  |  | 2026-02-07 | 2026-01-30 | 2026-01-30 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-30 16:24:51 | Yes | Yes | 2026-02-04 08:54:42 | SQC Close | 2026-02-06 | 2026-02-06 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-11 09:40:40 | Yes | Yes | 2026-02-06 16:16:21 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:36:27 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-08-01 21:49:03 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-30 17:16:01 | No | No |  | 30-01-2026. Replace RRU3962 to AAU5768 Sec.1#， UBBPdeb to UBBPg2#， UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TCNHM_2025 Capacity Expansion Ph4_EXP_SR | Tha Chana Hospital |  |  |  | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | Nattawoot Suwan | N/A | Closed | 2025-10-14 11:08:45 | No | No |  |  |  | 2025-09-26 | 2025-10-10 | 2025-10-12 | Teloneer Company Limited | N/A | Closed | 2025-10-12 12:10:53 | Yes | Yes | 2025-10-14 10:01:32 |  | 2025-10-14 | 2025-10-14 | Nattawoot Suwan | Approved | Closed | 2025-10-20 10:35:55 | Yes | Yes | 2025-10-15 15:01:21 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:28 | Yes | Yes | 2025-10-27 19:05:37 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-10-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-10 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-10-10 15:28:54 | No | No |  | 10 Oct 2025 Replace RRU5516 sector3 900/700 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-09 |  | N/A | Not assigned |  | No | No
TCRBE_2025 Capacity Expansion Ph6_EXP_SR | TCRBE |  |  |  | 2025-12-11 | 2025-12-25 | 2025-12-11 | 2025-12-11 | Teloneer Company Limited | N/A | Closed | 2025-12-11 14:15:16 | No | No |  |  |  | 2025-12-08 | 2025-12-11 | 2025-12-11 | Teloneer Company Limited | N/A | Closed | 2025-12-11 15:58:31 | Yes | Yes | 2025-12-15 19:46:20 |  | 2025-12-15 | 2025-12-15 | Nattawoot Suwan | Approved | Closed | 2026-01-09 09:34:32 | Yes | Yes | 2025-12-17 17:48:15 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:59 | Yes | Yes | 2026-03-19 18:23:47 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-11 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-11 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-12-11 18:03:17 | No | No |  | Add d5*1 Rep RRU3826(2) to 5526MB Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TE09M_2025 Coverage Expansion Ph2_EXP_BKK | SOI THAITHANI 9 | 2025-08-15 |  |  |  | 2025-08-15 | 2025-08-15 | 2025-08-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-15 18:59:38 | No | No |  |  |  | 2025-08-29 | 2025-08-18 | 2025-08-19 | V Contribute Co., Ltd | N/A | Closed | 2025-08-19 09:52:49 | Yes | Yes | 2025-08-19 09:56:58 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-05 17:11:19 | Yes | Yes | 2025-09-02 18:23:26 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 02:42:41 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 02:21:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-15 15:31:57 | No | No |  | 15-Aug-2025 Add RRU3953 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-14 |  | N/A | Not assigned |  | No | No
TECBA_DPU40_OPM30_Replacement_BKK | THE ESCAPE CONDOMINIUM BUILDING B |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-26 | 2026-01-07 | V Contribute Co., Ltd | N/A | Closed | 2026-01-07 13:20:42 | Yes | Yes | 2026-01-07 13:20:43 |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-01-26 09:23:37 | Yes | Yes | 2026-01-18 19:49:21 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-26 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-18 20:16:37 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-26 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-26 15:51:54 | No | No |  | 26-Dec-2025 Replace DPU30 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
TECDA_DPU40_OPM30_Replacement_BKK | THE ESCAPE CONDOMINIUM BUILDING D |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-26 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 16:07:06 | Yes | Yes | 2025-12-26 16:07:07 |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-01-26 09:23:37 | Yes | Yes | 2026-01-18 19:49:52 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-26 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-18 20:17:04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-26 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-26 15:51:54 | No | No |  | 26-Dec-2025 Replace DPU30 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
TEM10_2025 Capacity Expansion NW Modernization_EXP_BKK | EVENT_TEM10_CHULAHOSPITAL |  |  |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-05 08:14:49 | No | No |  |  |  | 2026-02-12 | 2026-03-19 | 2026-03-20 | V Contribute Co., Ltd | N/A | Closed | 2026-03-20 15:01:42 | Yes | Yes | 2026-03-20 15:01:42 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-09 09:23:58 | Yes | Yes | 2026-05-19 18:18:31 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-03-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:37:05 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-28 22:56:18 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-11 14:50:57 | No | No |  | 11-Feb-2026 Replace BBU5900 UMPTg2 Add GPS Add g2 Adddd RRU5526 Sector C Remove RRU3962 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-29 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-06-25 04:38:41 | Yes | Yes | 2026-01-29 09:59:13 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TESEA_DPU40_OPM30_Replacement_BKK | THE ESCAPE CONDOMINIUM BUILDING E |  |  |  |  | 2026-01-07 | 2026-01-07 | 2026-01-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-07 11:37:36 | No | No |  |  |  | 2025-12-31 | 2025-12-26 | 2025-12-26 | V Contribute Co., Ltd | N/A | Closed | 2025-12-26 15:39:02 | Yes | Yes | 2025-12-26 15:39:02 |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-01-26 09:23:37 | Yes | Yes | 2026-02-26 20:08:36 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-01-26 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-01-18 | 2026-01-18 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:55:31 | Yes | Yes | 2026-01-18 20:17:31 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-12-26 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-26 15:51:54 | No | No |  | 26-Dec-2025 Replace DPU30 to OPM15 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-01-06 |  | N/A | Not assigned |  | No | No
THBPM_2025 Capacity Expansion Ph3_EXP_BKK | TUMBOL HEALTH PROMOTING HOSPITAL, BUNG KUM PROI | 2025-09-03 |  |  |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-26 18:32:59 | No | No |  |  |  | 2025-08-31 | 2025-08-27 | 2025-08-28 | V Contribute Co., Ltd | N/A | Closed | 2025-08-28 10:24:44 | Yes | Yes | 2025-08-28 10:25:14 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-23 22:28:06 | Yes | Yes | 2025-09-22 14:39:00 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-07 00:01:18 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-10 21:26:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-26 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-26 18:58:29 | No | No |  | 2025-08-26_Replace RRU3962 to RRU5516(18-21)#， Replace Ant to 4 port Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-25 |  | N/A | Not assigned |  | No | No
THEBB_2025 Capacity Expansion Ph2_EXP_BKK | THE BASE SAPHANMAI | 2025-09-23 |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-11 17:27:06 | No | No |  |  |  | 2025-09-30 | 2025-10-07 | 2025-10-10 | V Contribute Co., Ltd | N/A | Closed | 2025-10-10 11:24:16 | Yes | Yes | 2025-10-10 11:24:17 |  | 2025-11-18 | 2025-11-18 | Chonradee Suwapan | Approved | Closed | 2025-11-26 09:23:51 | Yes | Yes | 2025-11-18 19:20:47 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 13:58:22 |  | 2025-11-18 | 2025-11-18 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-18 17:42:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-11 11:19:28 | No | No |  | 11-Nov-2025 Add RRU5818 sector A 2025-09-25_Replace to new UMPTg2#， Re-config RRU5818 Sector B#， Add GPS ***Pending RRU5818 Sector A//23-09-2025. ***Need GPS#， Replace UMPT#， RRU5818 Sec.A //Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a#， RRU5818 Sec.B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-10 |  | N/A | Not assigned |  | No | No
THEBB_2025 Coverage Expansion Ph1_EXP_BKK | THE BASE SAPHANMAI | 2025-09-15 |  |  |  | 2025-09-15 | 2025-09-15 | 2025-09-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-15 18:10:01 | No | No |  |  |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 19:52:43 | Yes | Yes | 2025-09-30 19:52:43 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-10-10 16:47:37 | Yes | Yes | 2025-09-22 19:45:18 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:21 | Yes | Yes | 2025-11-06 21:09:34 |  | 2025-09-22 | 2025-09-22 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:20:11 | No | Yes | 2025-09-22 19:58:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-15 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-15 19:06:55 | No | No |  | 2025-09-15_Replace to Ant Vertical Dual Beam Sector A#，B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-14 |  | N/A | Not assigned |  | No | No
THLHB_2025 Capacity Expansion Ph2_EXP_BKK | THE LINE PHAHON-PRADIPAT |  |  |  |  | 2025-10-24 | 2025-10-24 | 2025-10-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-24 11:50:47 | No | No |  |  |  | 2025-10-31 | 2025-10-31 | 2025-11-05 | V Contribute Co., Ltd | N/A | Closed | 2025-11-05 15:18:38 | Yes | Yes | 2025-11-05 15:18:38 |  | 2025-10-29 | 2025-10-29 | Chonradee Suwapan | Approved | Closed | 2025-11-26 16:08:44 | Yes | Yes | 2026-01-07 11:53:37 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-17 | Krittee Chamboot 00319410 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-01 22:44:15 |  | 2025-10-29 | 2025-10-29 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-29 20:27:22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-16 17:03:25 | No | No |  | 16-10-2025. Add RRU5818 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
TIM5M_2025 Coverage Expansion Ph2_EXP_BKK | THA IT MOO 5 | 2025-08-16 |  |  |  | 2025-08-16 | 2025-08-16 | 2025-08-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-16 15:37:02 | No | No |  |  |  | 2025-08-31 | 2025-08-18 | 2025-08-19 | V Contribute Co., Ltd | N/A | Closed | 2025-08-19 10:11:09 | Yes | Yes | 2025-08-19 10:11:33 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-09 09:04:09 | Yes | Yes | 2025-09-02 18:24:00 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 02:53:29 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:41:12 | No | Yes | 2025-08-05 09:07:31 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-16 18:23:12 | No | No |  | 16-Aug-2025 Add RRU3953 S1 Add Ant. 4port S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-14 |  | N/A | Not assigned |  | No | No
TK10M_2025 Capacity Expansion Ph3_EXP_BKK | THANYABURI KLONG10 |  |  |  |  | 2025-09-10 | 2025-09-17 | 2025-09-17 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:49 | No | No |  |  |  | 2025-09-26 | 2025-09-22 | 2025-09-22 | V Contribute Co., Ltd | N/A | Closed | 2025-09-22 14:58:27 | Yes | Yes | 2025-09-22 14:58:28 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-10-10 16:48:15 | Yes | Yes | 2025-12-17 20:44:54 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:21 | Yes | Yes | 2025-11-06 21:23:02 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 21:37:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-10 17:46:37 | No | No |  | 10-09-2025. Add AIRU5636w Sec.2#， Replace RRU5516 L18 Sec.2#， 3#， 8#， Ant.6 port Sec.2#， Ant.8 port Sec.3#， 8#， Add RRU5516 L18#， Ant.8 port Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan Wk37 |  | 2025-09-16 |  | N/A | Not assigned |  | No | No
TK11M_2025 Capacity Expansion Ph7_EXP_BKK | SOI THEP KUNCHON 11 |  |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-19 16:19:23 | No | No |  |  |  | 2026-01-31 | 2026-01-17 | 2026-01-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-18 10:26:39 | Yes | Yes | 2026-01-19 09:38:29 |  | 2026-01-20 | 2026-01-19 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-01-29 09:17:05 | Yes | Yes | 2026-01-19 16:21:08 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:38:02 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-08-01 21:49:20 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-16 21:33:23 | No | No |  | 16-Jan-2026 Add RRU5516 (700900) Sector 2 Remove RRU3953 Add Ant 4port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TK24M_2025 Capacity Expansion Ph3_EXP_BKK | SOI THAWI WATTHANA-KANCHANAPHISEK 24 | 2025-08-27 |  |  |  | 2025-08-27 | 2025-08-27 | 2025-08-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-27 18:39:50 | No | No |  |  |  | 2025-09-05 | 2025-09-03 | 2025-09-03 | V Contribute Co., Ltd | N/A | Closed | 2025-09-03 14:35:13 | Yes | Yes | 2025-09-03 14:36:44 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-25 14:38:34 | Yes | Yes | 2025-09-22 18:18:31 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:21 | Yes | Yes | 2025-11-06 21:24:26 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-10 21:27:14 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-27 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-28 02:03:21 | No | No |  | 2025-08-27_Add RRU5516(18-21) Sector 6#， Replace to Ant 8 port Sector 1#，6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-27 | liuhaoyuan 00952771 | N/A | Closed | 2025-11-03 09:04:06 | No | No
TKS1B_2025 Coverage Expansion Ph1_EXP_BKK | THE KEY SATHORN RATCHAPREUK (CARPARK) |  |  |  |  | 2025-11-17 | 2025-11-02 | 2025-11-02 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-20 09:22:21 | No | No |  |  |  | 2025-11-07 | 2025-11-26 | 2025-11-27 | V Contribute Co., Ltd | N/A | Closed | 2025-11-27 16:22:59 | Yes | Yes | 2025-11-27 16:23:00 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-11 09:20:58 | Yes | Yes | 2025-11-04 19:59:07 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-01 22:52:45 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-04 20:30:22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-07 11:55:55 | No | No |  | 21-Oct-2025 Replace to Ant Vertical dual beam SA E tilt -200 80 81 82 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-01 | Krittee Chamboot 00319410 | N/A | Closed | 2025-11-20 09:23:00 | No | No
TKSCB_2025 Coverage Expansion Ph1_EXP_BKK | THE KEY SATHON CHAREONRACH |  |  |  |  | 2025-10-21 | 2025-10-21 | 2025-10-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-10-31 | 2025-10-30 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 17:01:30 | Yes | Yes | 2025-10-30 17:01:30 |  | 2025-10-31 | 2025-10-31 | Chonradee Suwapan | Approved | Closed | 2025-11-06 15:52:18 | Yes | Yes | 2025-10-31 20:15:07 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 14:09:22 |  | 2025-10-31 | 2025-10-31 | Chonradee Suwapan | Approved | Closed | 2025-11-06 09:32:06 | No | Yes | 2025-10-31 20:52:12 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-20 15:37:14 | No | No |  | 20-Oct-2025 Replace to Ant Vertical dual beam SA AB SC E tilt -200 82 83 84 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-20 |  | N/A | Not assigned |  | No | No
TKUSB_2025 Coverage Expansion Ph1_EXP_BKK | THE KEY UDOMSUK |  |  |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-11-04 | 2025-11-04 | V Contribute Co., Ltd | N/A | Closed | 2025-11-04 14:53:58 | Yes | Yes | 2025-11-04 14:53:59 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-11 09:20:58 | Yes | Yes | 2025-11-04 19:59:39 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-01 22:56:31 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-04 20:31:58 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-22 17:51:42 | No | No |  | 22-Oct-2025 Replace to Ant Vertical dual beam SA SB SC E tilt-200 80 81 82 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-22 |  | N/A | Not assigned |  | No | No
TL3CB_2025 Capacity Expansion Ph2_EXP_BKK | THE LOG 3 | 2025-09-25 |  |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-17 16:18:56 | No | No |  |  |  | 2025-09-30 | 2025-10-09 | 2025-10-15 | V Contribute Co., Ltd | N/A | Closed | 2025-10-15 17:42:27 | Yes | Yes | 2025-10-15 17:42:28 |  | 2025-11-22 | 2025-11-22 | Chonradee Suwapan | Approved | Closed | 2026-03-19 16:33:13 | Yes | Yes | 2026-02-03 11:41:39 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-03-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:38:40 |  | 2025-11-22 | 2025-11-22 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-11-22 20:13:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-13 16:25:04 | No | No |  | 13-Nov-2025 Add g3a Add RRU5818 SD (5/3) Set mt 25-Sep-2025 ***Pending add g3a Add RRU5818 SD (5/3) //Replace BBU5900 UMPTg2 g3a=1 Add AAU5246 SA (5/0) Replace Ant 12port No RET Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  |  |  | N/A | Not assigned |  | No | No
TL3CB_2025 Coverage Expansion Ph1_EXP_BKK | THE LOG 3 | 2025-09-26 |  |  |  | 2025-09-30 | 2025-09-30 | 2025-09-30 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-30 11:12:59 | No | No |  |  |  | 2025-09-30 | 2025-09-29 | 2025-09-29 | V Contribute Co., Ltd | N/A | Closed | 2025-09-29 21:16:23 | Yes | Yes | 2025-09-29 21:16:24 |  | 2025-10-01 | 2025-10-01 | Chonradee Suwapan | Approved | Closed | 2025-10-21 23:17:17 | Yes | Yes | 2025-10-01 18:09:30 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:28 | Yes | Yes | 2025-10-27 19:09:15 |  | 2025-10-01 | 2025-10-01 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:16 | No | Yes | 2025-10-01 18:15:27 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-26 17:42:50 | No | No |  | 26-09-2025. Replace Ant.12 port Sec.E#， F |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-09-29 |  | N/A | Not assigned |  | No | No
TLBIM_2025 Capacity Expansion Ph8_EXP_ER | Talad Banmai | 2026-01-22 |  |  |  | 2026-02-28 | 2026-01-22 | 2026-01-22 | Teloneer Company Limited | N/A | Closed | 2026-01-22 13:39:09 | No | No |  |  |  | 2026-02-28 | 2026-01-22 | 2026-01-22 | Teloneer Company Limited | N/A | Closed | 2026-01-22 15:15:00 | Yes | Yes | 2026-01-22 23:23:33 |  | 2026-02-28 | 2026-01-26 | Apichat fangsantthia(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:20:22 | Yes | Yes | 2026-01-27 12:09:52 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:25 | Yes | Yes | 2026-03-24 18:39:48 |  | 2026-01-31 | 2026-01-21 | Adisak Chanmao(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-01-21 18:55:13 |  | 2026-01-20 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-20 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-01-20 16:50:22 | No | No |  | Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 130 + Remove RRU x 2_TJKCM_H_3 Remove Antenna + (New AAU5768) + Main Dir = 210 + Remove RRU x 2_TJKCM_H_4 Co L07 + NR07_TJKCM_L_4 New Sector 8 (Co AAU5768) + Main Dir = 130_TJKCM_H_8 New Sector M (Co AAU5768) + Main Dir = 130_TJKCM_H_M New Sector M (Co AAU5768) + Main Dir = 130_TJKCM_H_N New Sector 9 (Co AAU5768) + Main Dir = 210_TJKCM_H_9 New Sector I (Co AAU5768) + Main Dir = 210_TJKCM_H_I New Sector L (Co AAU5768) + Main Dir = 210_TJKCM_H_L |  | 2026-01-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-22 18:31:58 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TLDMM_2025 Capacity Expansion Ph2_EXP_BKK | SOI TALADKLANG DOMMUANG | 2025-08-09 |  |  |  | 2025-08-09 | 2025-08-09 | 2025-08-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-09 16:06:17 | No | No |  |  | 2025-08-09 | 2025-08-16 | 2025-08-10 | 2025-08-10 | V Contribute Co., Ltd | N/A | Closed | 2025-08-10 12:55:03 | Yes | Yes | 2025-08-10 12:57:53 |  |  | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-09 16:45:53 | Yes | Yes | 2025-09-04 20:02:32 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 02:59:39 |  | 2025-09-04 | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-04 20:19:04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-09 16:44:47 | No | No |  | 9-Aug-2025 Add RRU5516 (1800-2100) Remove RRU3962 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-08 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-09-16 16:57:05 | No | No
TLDNS_2025 Capacity Expansion Ph5_EXP_SR | Talatnat Soi 2 |  |  |  |  | 2025-11-18 | 2025-11-12 | 2025-11-12 | Teloneer Company Limited | N/A | Closed | 2025-11-12 14:04:50 | No | No |  |  |  | 2025-11-12 | 2025-11-12 | 2025-11-12 | Teloneer Company Limited | N/A | Closed | 2025-11-12 17:53:16 | Yes | Yes | 2025-11-13 09:16:31 |  | 2025-11-13 | 2025-11-13 | Nattawoot Suwan | Approved | Closed | 2025-12-11 10:46:23 | Yes | Yes | 2025-11-15 11:01:20 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 14:10:35 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-11-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-12 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-11-12 18:11:48 | No | No |  | Add new AAU5636w Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-17 |  | N/A | Not assigned |  | No | No
TLRPM_2025 Capacity Expansion Ph8_EXP_ER | Talad Roy Pee | 2026-03-09 |  | Clear Alarm |  | 2026-02-28 | 2026-01-19 | 2026-01-19 | Teloneer Company Limited | N/A | Closed | 2026-01-19 17:34:40 | No | No |  |  |  | 2026-02-28 | 2026-01-19 | 2026-01-22 | Teloneer Company Limited | N/A | Closed | 2026-01-22 10:04:08 | Yes | Yes | 2026-01-22 19:00:13 |  | 2026-02-28 | 2026-01-28 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:20:22 | Yes | Yes | 2026-01-28 18:21:59 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:25 | Yes | Yes | 2026-03-24 18:41:47 |  | 2026-01-31 | 2026-01-19 | Adisak Chanmao(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-01-19 11:22:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-09 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-03-09 18:23:34 | No | No |  | 2026-03-09_fix ret lb S1 done ***Alarm RET Antenna Motor Fault LB Sector 1 Add UBBPg2_TLRPM_H_1 ReSectorname S1 to S6_TLRPM_L_6 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_TLRPM_L_1 |  | 2026-01-21 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-21 16:53:31 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-01-19 | 2026-01-19 | Teloneer Company Limited | N/A | Closed | 2026-01-19 11:32:32 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMC2M_2025 Capacity Expansion Ph5_EXP_BKK | THANOMMITR PARK CONDOMINIUM STATION 2 | [5 empty] | 2025-11-27 | 2025-11-27 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  |  | 2025-11-21 | 2025-11-22 | 2025-11-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-22 14:31:16 | Yes | Yes | 2025-11-24 21:14:51 |  | 2025-11-29 | 2025-11-29 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-15 14:40:35 | Yes | Yes | 2025-11-29 16:49:21 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-09 23:28:27 |  | 2025-11-29 | 2025-11-29 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 09:24:43 | Yes | Yes | 2025-11-29 16:50:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-21 17:57:01 | No | No |  | 21-11-2025. Add UBBPg2#， Replace RRU5526#， Ant.8 port Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMCPM_2025 Capacity Expansion Ph6_EXP_ER | Thanon Mahachakkapat | 2025-11-22 | THCP_Phet.S |  |  | 2025-11-30 | 2025-11-21 | 2025-11-21 | Teloneer Company Limited | N/A | Closed | 2025-11-21 16:30:28 | No | No |  |  |  | 2025-11-30 | 2025-11-26 | 2025-11-27 | Teloneer Company Limited | N/A | Closed | 2025-11-27 19:16:46 | Yes | Yes | 2025-12-03 09:12:54 |  | 2025-12-15 | 2025-12-03 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-04 15:50:52 | Yes | Yes | 2025-12-03 14:18:47 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 14:14:18 |  | 2025-11-30 | 2025-11-21 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-11-21 16:47:33 | Yes | Yes | 2025-11-21 11:45:02 |  | 2025-11-21 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-21 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-11-21 17:24:46 | No | No |  | 21-Nov-2025 Replace 1RRU5508 to 5516 sector 4 L0709 / Add 1DMM AAU5768 sector 2&7&J&K #， Remove 5RRU5505 sector 2&7&J&K&L #，Replace 1UBBPg1 to 1UBBPg3a |  | 2025-11-21 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-10 11:08:32 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMSRM_2025 Capacity Expansion Ph2_EXP_BKK | THAMMASIRI |  |  |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-13 18:57:01 | No | No |  |  |  | 2025-08-29 | 2025-08-19 | 2025-08-21 | V Contribute Co., Ltd | N/A | Closed | 2025-08-21 19:48:13 | Yes | Yes | 2025-08-21 20:10:56 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-09-12 19:05:30 | Yes | Yes | 2025-09-03 21:10:59 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 03:05:30 |  |  | 2025-09-03 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:17:51 | No | Yes | 2025-09-03 20:56:46 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-13 18:41:35 | No | No |  | 2025-08-13_Replace RRU3962 to RRU5516(18-21) Sector 8#， Replace to Ant 12 port Sector 3#，8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-12 |  | N/A | Not assigned |  | No | No
TMSRM_2025 Capacity Expansion Ph3_EXP_BKK | THAMMASIRI | 2025-08-28 |  |  |  | 2025-08-28 | 2025-08-28 | 2025-08-28 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-28 16:57:01 | No | No |  |  |  | 2025-09-05 | 2025-09-03 | 2025-09-05 | V Contribute Co., Ltd | N/A | Closed | 2025-09-05 19:40:18 | Yes | Yes | 2025-09-05 19:41:18 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-26 16:35:46 | Yes | Yes | 2025-09-10 20:57:53 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-07 00:17:39 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-10 21:27:57 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-28 17:08:50 | No | No |  | 28-08-2025. Replace RRU5516 L1800 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-27 |  | N/A | Not assigned |  | No | No
TMYAM_2025 Coverage Expansion CO-NT Tower_EXP_ER | Thanon Mabya | 2025-08-11 |  | Install & Integrate |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Teloneer Company Limited | N/A | Closed | 2025-08-14 15:57:00 | No | No |  |  |  | 2025-08-31 | 2025-08-15 | 2025-08-18 | Teloneer Company Limited | N/A | Closed | 2025-08-18 11:49:25 | Yes | Yes | 2025-08-21 19:53:35 |  | 2025-08-31 | 2025-09-17 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-26 13:45:51 | Yes | Yes | 2025-09-17 16:07:13 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-12-31 | 2025-09-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:21 | Yes | Yes | 2025-11-06 21:36:55 |  | 2025-08-31 | 2025-10-01 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-07 11:09:00 | Yes | Yes | 2025-08-29 17:30:10 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-14 |  | 2025-08-11 | Reungsak Junkong 00927496 | N/A | Closed | 2025-08-11 18:54:17 | No | No |  | add UBBPg3a #， Re Direction 270 to 300 + ReSectorname S3 to S8 + Add L07 + NR07 + Replace RRU (RRU5516_900) + 4T4R |  | 2025-08-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-15 18:29:38 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TNBAM_2025 Capacity Expansion Ph7_EXP_ER | Tanon Ban Kao Soi 5 | 2025-12-13 |  | Install & Integrate |  | 2025-12-31 | 2025-12-13 | 2025-12-13 | Teloneer Company Limited | N/A | Closed | 2025-12-13 16:30:55 | No | No |  |  |  | 2025-12-31 | 2025-12-13 | 2025-12-13 | Teloneer Company Limited | N/A | Closed | 2025-12-13 17:32:25 | Yes | Yes | 2025-12-16 12:32:55 |  | 2025-12-31 | 2025-12-16 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:28:08 | Yes | Yes | 2025-12-16 19:27:29 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:25 | Yes | Yes | 2026-03-24 18:42:48 |  | 2025-12-31 | 2025-12-15 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:26:56 | Yes | Yes | 2025-12-15 11:43:58 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-13 17:16:52 | No | No |  | Add UBBPg3a + Remove Antenna + (New AAU5768) + Main Dir = 0 + Remove RRU x 2_TNBAM_H_1 New Antenna (LB)_TNBAM_L_1 New Sector 6 (Co AAU5768) + Main Dir = 0_TNBAM_H_6 New Sector G (Co AAU5768) + Main Dir = 0_TNBAM_H_G New Sector H (Co AAU5768) + Main Dir = 0_TNBAM_H_H |  | 2025-12-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-10 11:05:14 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TNCSA_2025 Capacity Expansion NW Modernization_EXP_BKK | THE NEST CHULA-SAMYAN Small cell |  |  |  | 2026-03-18 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-01-19 | 2026-01-19 | 2026-03-18 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:28:54 | Yes | Yes | 2026-03-23 15:51:52 |  | 2026-04-03 | 2026-04-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-31 10:10:31 | Yes | Yes | 2026-04-20 10:50:57 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-08-01 20:21:11 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-16 21:33:09 | No | No |  | 16-Jan-2026 Add RRU5526 SA SB Remove RRU3962 *2 Add g2 82#，83 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TNNIB_2025 Capacity Expansion Ph3_EXP_SR | THANON NAI BAN |  |  |  |  | 2025-09-02 | 2025-09-09 | 2025-09-09 | Nattawoot Suwan(Teloneer Company Limited) | N/A | Closed | 2025-09-09 16:31:13 | No | No |  |  |  | 2025-09-02 | 2025-09-02 | 2025-09-03 | Teloneer Company Limited | N/A | Closed | 2025-09-17 11:03:53 | Yes | Yes | 2025-09-17 11:03:53 |  | 2025-09-17 | 2025-09-18 | Teloneer Company Limited | Approved | Closed | 2025-09-26 09:29:25 | Yes | Yes | 2025-09-17 15:46:40 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:21 | Yes | Yes | 2025-11-06 21:39:21 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-09-02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-02 | 2025-09-02 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-09-02 18:15:29 | No | No |  | On cell1800 S3 Rep S3 MB > RRU3826*2 to 5516*1 MB > existing Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2025-09-09 | Teloneer Company Limited | N/A | Closed | 2025-09-09 16:30:47 | No | No | [5 empty] | 2025-09-01 |  | N/A | Not assigned |  | No | No
TNRMM_2025 Capacity Expansion Ph3_EXP_BKK | MUBAN THANAROM | [5 empty] | 2025-09-01 | 2025-09-01 | Akhom Srinara | N/A | Closed | 2025-09-01 09:42:25 | No | No |  |  |  |  | 2025-08-29 | 2025-08-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-29 23:02:09 | Yes | Yes | 2025-09-01 12:09:49 |  | 2025-09-01 | 2025-09-05 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-14 15:39:01 | Yes | Yes | 2025-09-05 12:53:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-14 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-21 19:26:10 |  | 2025-09-03 | 2025-09-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 13:25:02 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-29 19:47:38 | No | No |  | 29-Aug-2025 AAU5636w S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-31 | Jia Rui 80023782 | N/A | Closed | 2025-09-02 15:48:33 | No | No
TP25M_2025 Capacity Expansion Ph3_EXP_BKK | THEPHARAK KM.25 |  |  |  |  | 2025-09-05 | 2025-09-14 | 2025-09-14 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:49 | No | No |  |  |  | 2025-09-26 | 2025-09-05 | 2025-09-10 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:18:44 | Yes | Yes | 2025-09-30 10:18:44 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2026-03-11 16:32:23 | Yes | Yes | 2025-09-15 17:28:48 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-12-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:35 | Yes | Yes | 2026-01-09 23:42:55 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 17:47:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-05 19:41:44 | No | No |  | 5-Sep-2025 Add AAU5636w S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-13 |  | N/A | Not assigned |  | No | No
TPCSM_2025 Coverage Expansion Ph2_EXP_BKK | Talat Pak Khlong Chao School |  |  |  |  | 2025-08-07 | 2025-08-07 | 2025-08-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-07 17:44:53 | No | No |  |  |  | 2025-08-22 | 2025-08-07 | 2025-08-08 | V Contribute Co., Ltd | N/A | Closed | 2025-08-08 15:39:02 | Yes | Yes | 2025-08-08 15:40:32 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-09-01 13:12:38 | Yes | Yes | 2025-08-27 14:27:55 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:20 | Yes | Yes | 2025-09-04 15:15:16 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:57:46 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-07 16:10:20 | No | No |  | 7-Aug-2025 Add RRU3953 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-06 |  | N/A | Not assigned |  | No | No
TPLBM_2025 Capacity Expansion Ph5_EXP_ER | Trailer truck parking lot , Laem Chabang Port | 2025-10-14 | Thcp_Phet.s | Install & Integrate |  | 2025-10-31 | 2025-10-14 | 2025-10-14 | Teloneer Company Limited | N/A | Closed | 2025-10-14 20:08:36 | No | No |  |  |  | 2025-10-31 | 2025-10-14 | 2025-10-15 | Teloneer Company Limited | N/A | Closed | 2025-10-15 11:17:22 | Yes | Yes | 2025-10-15 19:38:53 |  | 2025-10-31 | 2025-10-21 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-28 10:26:04 | Yes | Yes | 2025-11-07 13:41:13 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-11-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:21 | Yes | Yes | 2025-11-06 21:49:11 |  | 2025-10-15 | 2025-10-09 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-10 14:39:00 | Yes | Yes | 2025-10-09 16:32:48 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-14 |  | 2025-10-14 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-14 16:35:25 | No | No |  | **waiting on-service LNR26 -- New L26F5 + NR26 (New AAU5636w) S3 |  | 2025-10-16 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-10-16 16:35:56 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPMPM_2025 Capacity Expansion Ph7_EXP_ER | Talad Pimpa | 2025-12-12 |  | Clear Pending |  | 2025-12-31 | 2025-12-11 | 2025-12-11 | Teloneer Company Limited | N/A | Closed | 2025-12-11 14:22:28 | No | No |  |  |  | 2025-12-31 | 2025-12-11 | 2025-12-12 | Teloneer Company Limited | N/A | Closed | 2025-12-12 15:18:36 | Yes | Yes | 2025-12-13 16:48:41 |  | 2025-12-31 | 2025-12-13 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:28:08 | Yes | Yes | 2025-12-13 18:23:04 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:25 | Yes | Yes | 2026-03-24 18:46:59 |  | 2025-12-31 | 2025-12-11 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-13 21:12:48 | Yes | Yes | 2025-12-11 14:42:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-11 | Reungsak Junkong 00927496 | N/A | Closed | 2025-12-11 17:36:28 | No | No |  | Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 320 + Remove RRU x 1_TPMPM_H_3 (Co AAU5768) + Main Dir = 320 + Remove RRU x 1_TPMPM_H_8 New Sector M (Co AAU5768) + Main Dir = 320_TPMPM_H_M New Sector N (Co AAU5768) + Main Dir = 320_TPMPM_H_N |  | 2025-12-11 | Reungsak Junkong 00927496 | N/A | Closed | 2025-12-11 17:36:28 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPN1B_2025 Capacity Expansion Ph5_EXP_BKK | The Pano (Side) |  |  |  |  | 2025-12-01 | 2025-12-01 | 2025-12-01 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-12-01 09:34:25 | No | No |  |  |  | 2025-12-28 | 2025-12-11 | 2025-12-19 | V Contribute Co., Ltd | N/A | Closed | 2025-12-19 16:36:34 | Yes | Yes | 2025-12-19 16:36:34 |  | 2025-12-04 | 2025-12-04 | Chonradee Suwapan | Approved | Closed | 2025-12-09 10:16:02 | Yes | Yes | 2026-01-13 17:22:36 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:04 | Yes | Yes | 2026-01-15 14:28:01 |  | 2025-12-04 | 2025-12-04 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-12-04 21:36:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-25 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-11-25 16:41:07 | No | No |  | 2025-11-25_Change Braker#， Add RRU3962 จุดที่ 2 config SFN 4T4R 3 จุด//21-Nov-2025 Pending Add RRU3962 85 4/5 // Add RRU5526 SA Remove RRU3962 Replace Ant 12 port No Ret Add g2 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPPAM_2025 Capacity Expansion Ph7_EXP_ER | Soi Thetsaban Pimpa 2 | 2025-12-10 |  | Install & Integrate |  | 2025-12-31 | 2025-12-11 | 2025-12-11 | Teloneer Company Limited | N/A | Closed | 2025-12-11 17:14:35 | No | No |  |  |  | 2025-12-31 | 2025-12-10 | 2025-12-17 | Teloneer Company Limited | N/A | Closed | 2025-12-17 17:00:56 | Yes | Yes | 2025-12-18 18:49:37 |  | 2025-12-31 | 2025-12-18 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-01-06 16:30:08 | Yes | Yes | 2025-12-18 20:47:06 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:25 | Yes | Yes | 2026-03-24 18:47:34 |  | 2025-12-31 | 2025-12-10 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:37:44 | Yes | Yes | 2025-12-10 10:22:43 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-10 | Reungsak Junkong 00927496 | N/A | Closed | 2025-12-10 18:10:59 | No | No |  | "** Waiting on-service LNR7/L9 -- Add UBBPg2 + Replace Antenna (Dualband)_TPPAM_H_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_TPPAM_L_1 " |  | 2025-12-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-11 18:18:22 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-12-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPSVB_2025 Capacity Expansion NW Modernization_EXP_BKK | THE PRESIDENT SUKHUMVIT |  |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-27 | 2026-03-23 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 11:43:16 | Yes | Yes | 2026-03-24 11:43:17 |  | 2026-04-30 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-07-07 09:28:07 | Yes | Yes | 2026-04-30 00:01:04 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-07 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-30 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-30 00:07:42 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-25 17:13:06 | No | No |  | 6-Feb-2026 Add RRU5526 Sector B Remove RRU3962 Add g2 Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TR21B_2025 Capacity Expansion NW Modernization_EXP_BKK | The Room Sukhumvit 21 Condominium |  |  |  | 2026-01-24 | 2026-01-24 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:26:57 | Yes | Yes | 2026-03-23 15:59:07 |  | 2026-04-03 | 2026-04-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-02 09:35:21 | Yes | Yes | 2026-04-20 16:34:53 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-05 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-08-01 20:21:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-24 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-24 18:19:45 | No | No |  | 24-01-2025. Replace 2RRU3962 to 2RRU5526 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-01-24 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TR69B_2025 Capacity Expansion NW Modernization_EXP_BKK | The Room Sukhumvit 69 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-27 | 2026-02-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-28 09:52:54 | Yes | Yes | 2026-03-11 14:37:49 |  | 2026-03-19 | 2026-03-19 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:50:30 | Yes | Yes | 2026-04-01 17:17:11 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-04-28 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-08-01 20:21:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-03 18:22:54 | No | No |  | 03-02-2026. Replace BBU5900#， UMPTg2#， RRU3962 to RRU5526 Sec.1#， 2#， 3#， Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRBSM_2025 Capacity Expansion Ph7_EXP_BKK | TALAD RUNGSIT BUS STATION |  |  |  | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-20 10:47:35 | No | No |  |  |  | 2026-01-31 | 2026-01-17 | 2026-01-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-18 09:44:08 | Yes | Yes | 2026-01-19 09:43:24 |  | 2026-01-20 | 2026-01-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-01-29 09:17:05 | Yes | Yes | 2026-01-20 10:48:31 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:56 | Yes | Yes | 2026-04-09 13:42:28 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-08-01 21:49:36 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-15 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-15 18:20:12 | No | No |  | 15 Jan 2026 Add AAU5636w sector 8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRKLM_2025 Capacity Expansion Ph5_EXP_BKK | THAI RAT WITTHAYA 69 SCHOOL (KHLONG LUANG) |  |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-12-28 | 2025-11-20 | 2025-11-26 | V Contribute Co., Ltd | N/A | Closed | 2025-11-26 12:04:11 | Yes | Yes | 2025-11-26 12:04:12 |  | 2025-11-26 | 2025-11-26 | Chonradee Suwapan | Approved | Closed | 2025-12-11 09:22:40 | Yes | Yes | 2025-11-26 17:42:21 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-09 23:53:28 |  | 2025-11-26 | 2025-11-26 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:00:23 | Yes | Yes | 2025-11-26 17:45:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-18 17:13:21 | No | No |  | 18-Nov-2025 Add RRU5526 (1800-2100) S2 Remove RRU3962 Replace Ant 8port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-11-18 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRP2B_2025 Capacity Expansion NW Modernization_EXP_BKK | THE ROYAL PLACE 2 |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:32:04 | No | No |  |  | 2026-04-30 | 2026-04-30 | 2026-04-19 | 2026-04-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-20 10:02:53 | Yes | Yes | 2026-04-23 13:55:23 |  | 2026-06-16 | 2026-06-16 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-03 09:26:53 | Yes | Yes | 2026-06-16 16:03:49 | Wrong site name in pg-1#，7#，8#，10#，11. Wrong splitter quantity in remark.pg-18 Need to fill phase name in pg-47#，48. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-08-01 20:22:00 |  |  | 2026-04-30 | 2026-04-21 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-21 21:19:42 | No | No |  |  |  |  | 2026-04-17 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-04-20 14:22:09 | No | No |  | 17-04-2026. Replace BBU5900#， UMPTg2#， RRU3962 to RRU5507 x2 Sec.A#， Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRV1B_2025 Coverage Expansion Ph1_EXP_BKK | Tiw River Place (Front) |  |  |  |  | 2025-10-25 | 2025-10-25 | 2025-10-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-11-03 | 2025-11-19 | V Contribute Co., Ltd | N/A | Closed | 2025-11-19 16:28:35 | Yes | Yes | 2025-11-19 16:28:35 |  | 2025-11-06 | 2025-11-06 | Chonradee Suwapan | Approved | Closed | 2025-11-11 16:14:42 | Yes | Yes | 2026-01-07 12:27:22 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-01 23:15:24 |  | 2025-11-06 | 2025-11-06 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-06 18:11:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-24 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-24 17:39:32 | No | No |  | 2025-10-24_Replace to Ant Vertical Dual Beam Sector A (2Ea) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
TSHUM_2025 Capacity Expansion NW Modernization_EXP_BKK | TS HOUSE |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-21 | 2026-03-21 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:14:51 | Yes | Yes | 2026-03-23 15:14:52 |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-07-07 09:28:07 | Yes | Yes | 2026-04-21 16:02:57 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-12-29 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-08 11:27:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-05 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-03-05 19:22:21 | No | No |  | 05-03-2026. Add RRU5507#， Ant.8 port Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TT19M_2025 Coverage Expansion Ph2_EXP_BKK | SOI THIAN THALE 19 | 2025-08-11 |  |  |  | 2025-08-11 | 2025-08-11 | 2025-08-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-11 19:17:40 | No | No |  |  |  | 2025-08-29 | 2025-08-16 | 2025-08-17 | V Contribute Co., Ltd | N/A | Closed | 2025-08-17 11:31:34 | Yes | Yes | 2025-08-17 11:32:33 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-09 09:05:18 | Yes | Yes | 2025-09-02 18:24:32 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 03:16:36 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:31 | No | Yes | 2025-08-27 15:53:35 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-11 18:15:26 | No | No |  | 2025-08-11_Add RRU3953#， Ant 4 port Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-09-16 16:57:05 | No | No
TT33B_2025 Capacity Expansion Ph2_EXP_BKK | SOI THOET THAI 33 ( ALTITUDE UNICORN SATHORN) | 2025-09-04 |  |  |  | 2025-09-04 | 2025-09-04 | 2025-09-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-04 16:04:28 | No | No |  |  |  | 2025-09-26 | 2025-09-16 | 2025-09-17 | V Contribute Co., Ltd | N/A | Closed | 2025-09-17 13:33:21 | Yes | Yes | 2025-09-17 13:33:22 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-26 13:44:34 | Yes | Yes | 2025-09-13 20:28:36 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-07 00:46:24 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-14 13:17:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-04 17:20:16 | No | No |  | 4-Sep-2025 Add RRU5516 (700900)S1 Add Ant 4port add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-03 |  | N/A | Not assigned |  | No | No
TT40M_2025 Capacity Expansion Ph2_EXP_BKK | SOI TERDTHAI40 | 2025-08-22 |  |  |  | 2025-08-22 | 2025-08-22 | 2025-08-22 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-22 17:15:25 | No | No |  |  |  | 2025-08-31 | 2025-08-24 | 2025-08-25 | V Contribute Co., Ltd | N/A | Closed | 2025-08-25 10:45:38 | Yes | Yes | 2025-08-25 10:48:29 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-17 13:07:46 | Yes | Yes | 2025-12-14 13:46:58 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 03:19:05 |  |  | 2025-09-06 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:28 | No | Yes | 2025-09-06 19:24:11 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-22 17:59:08 | No | No |  | 22-08-2025. Replace RRU5516 L18#， Ant.12 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-21 |  | N/A | Not assigned |  | No | No
TT72M_2025 Capacity Expansion Ph2_EXP_BKK | SOI THIAN THALE 7 YAK 2 MACRO |  |  |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-09-22 11:24:57 | No | No |  |  |  | 2025-09-22 | 2025-09-17 | 2025-10-01 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-01 10:10:07 | Yes | Yes | 2025-10-01 10:10:07 |  | 2025-09-25 | 2025-09-25 | Chonradee Suwapan | Approved | Closed | 2025-10-21 14:04:31 | Yes | Yes | 2025-12-14 13:56:57 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:57 | Yes | Yes | 2025-10-21 19:31:00 |  | 2025-09-25 | 2025-09-25 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:38 | No | Yes | 2025-09-25 18:46:56 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-17 17:18:34 | No | No |  | 17-09-2025. Add UBBPg2#， Replace RRU5516 L900#， Ant.12 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install completed |  | 2025-09-21 |  | N/A | Not assigned |  | No | No
TT72M_2025 Capacity Expansion Ph3_EXP_BKK | SOI THIAN THALE 7 YAK 2 MACRO |  |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-29 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 16:05:26 | Yes | Yes | 2025-10-30 16:05:26 |  | 2025-10-22 | 2025-10-22 | Chonradee Suwapan | Approved | Closed | 2025-10-31 13:29:05 | Yes | Yes | 2026-01-07 16:25:16 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:21 | Yes | Yes | 2025-11-06 21:54:21 |  | 2025-10-22 | 2025-10-22 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-22 20:37:43 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-09 18:26:53 | No | No |  | 09-10-2025. Add RRU5516 L900#， Replace RRU5516 L18#， Ant.8 port Sec.1#， 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
TT72M_2025 Coverage Expansion Ph2_EXP_BKK | SOI THIAN THALE 7 YAK 2 MACRO | 2025-09-03 |  |  |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-26 18:32:59 | No | No |  |  |  | 2025-08-31 | 2025-09-09 | 2025-09-10 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:18:57 | Yes | Yes | 2025-09-30 10:18:57 |  |  | 2025-09-10 | Chonradee Suwapan | Approved | Closed | 2025-09-25 14:36:40 | Yes | Yes | 2025-09-11 20:54:45 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-07 00:47:39 |  | 2025-09-11 | 2025-09-11 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:04 | No | Yes | 2025-09-11 21:38:36 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-26 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-26 18:58:29 | No | No |  | 2025-08-26_Add RRU3953#， Ant 4 port Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-25 |  | N/A | Not assigned |  | No | No
TTBPM_2025 Capacity Expansion Ph8_EXP_ER | Toyota Banpho | 2026-01-22 |  |  |  | 2026-02-28 | 2026-01-22 | 2026-01-22 | Teloneer Company Limited | N/A | Closed | 2026-01-22 12:26:33 | No | No |  |  |  | 2026-02-28 | 2026-01-22 | 2026-01-22 | Teloneer Company Limited | N/A | Closed | 2026-01-22 16:00:11 | Yes | Yes | 2026-01-22 23:25:32 |  | 2026-02-28 | 2026-01-24 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:20:22 | Yes | Yes | 2026-01-24 13:40:42 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:25 | Yes | Yes | 2026-03-24 18:52:49 |  | 2026-01-31 | 2026-01-21 | Adisak Chanmao(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-01-21 19:08:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-21 17:23:06 | No | No |  | Replace UBBPg1 to UBBPg3a + Remove Antenna + (New AAU5768) + Main Dir = 20 + Remove RRU5505 x 2_TTBPM_H_1 Remove Antenna + (New AAU5768) + Main Dir = 260 + Remove RRU5505 x 2_TTBPM_H_3 Remove Antenna + (Co AAU5768) + Main Dir = 20 + Remove RRU5505 x 2_TTBPM_H_6 Remove Antenna + (Co AAU5768) + Main Dir = 260 + Remove RRU5505 x 2_TTBPM_H_8 New Sector G (Co AAU5768) + Main Dir = 20_TTBPM_H_G New Sector H (Co AAU5768) + Main Dir = 20_TTBPM_H_H New Sector M (Co AAU5768) + Main Dir = 260_TTBPM_H_M New Sector N (Co AAU5768) + Main Dir = 260_TTBPM_H_N |  | 2026-01-21 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-21 17:23:58 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TTGWM_2025 Capacity Expansion Ph7_EXP_ER | Toyota Gateway | 2025-12-06 | Thcp_adirek.kh | Install & Integrate |  | 2025-12-31 | 2025-12-06 | 2025-12-06 | Teloneer Company Limited | N/A | Closed | 2025-12-06 16:26:23 | No | No |  |  |  | 2025-12-31 | 2025-12-06 | 2025-12-07 | Teloneer Company Limited | N/A | Closed | 2025-12-07 10:43:21 | Yes | Yes | 2025-12-08 21:10:10 |  | 2025-12-31 | 2025-12-09 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:38:58 | Yes | Yes | 2025-12-09 13:20:11 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:24 | Yes | Yes | 2026-03-24 18:54:00 |  | 2025-12-31 | 2025-12-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:37:44 | Yes | Yes | 2025-12-06 12:17:21 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-06 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-12-06 18:21:28 | No | No |  | "Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 120 + Remove RRU x 1_TTGWM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_TTGWM_H_3 Remove Antenna + (Co AAU5768) + Main Dir = 120 + Remove RRU x 1_TTGWM_H_7 New Sector J (Co AAU5768) + Main Dir = 120_TTGWM_H_J New Sector K (Co AAU5768) + Main Dir = 120_TTGWM_H_K" |  | 2025-12-06 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-12-06 20:49:08 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TTPTM_2025 Capacity Expansion Ph6_EXP_ER | TPT Petrochemicals Public Company Limited | 2025-11-19 | thcp_Phet.sa | Install & Integrate |  | 2025-11-30 | 2025-11-19 | 2025-11-19 | Teloneer Company Limited | N/A | Closed | 2025-11-19 16:46:03 | No | No |  |  |  | 2025-11-30 | 2025-11-19 | 2025-11-20 | Teloneer Company Limited | N/A | Closed | 2025-11-20 11:23:29 | Yes | Yes | 2025-11-23 22:03:23 |  | 2025-11-30 | 2025-11-24 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-25 18:20:45 | Yes | Yes | 2025-11-24 15:07:38 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 14:47:56 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:12 | Yes | Yes | 2025-11-04 11:02:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-19 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-19 18:11:25 | No | No |  | **waiting on-service L9/LNR7 -- Add UBBPg2 Replace Antenna (Dualband) + Add RRU5505 x 1 + 4T4R H_2 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna) L_2 |  | 2025-11-21 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-21 16:48:25 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TTWHA_2025 Capacity Expansion NW Modernization_EXP_BKK | THE TRANTAWAN HOTEL SURAWONG |  |  |  | 2026-01-20 | 2026-01-20 | 2026-01-20 | 2026-01-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-20 16:34:01 | No | No |  |  | 2026-01-31 | 2026-01-31 | 2026-01-16 | 2026-01-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-18 10:39:38 | Yes | Yes | 2026-01-19 09:42:29 |  | 2026-01-20 | 2026-01-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-02 09:33:47 | Yes | Yes | 2026-02-27 11:41:23 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:56 | Yes | Yes | 2026-04-09 13:43:06 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-08-01 20:22:15 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-10 17:40:52 | No | No |  | 10-01-2026. Replace RRU3962 to RRU5526 Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TUR1M_2025 Capacity Expansion Ph3_EXP_BKK | Thammasat Rangsit University Rangsit 1 |  |  |  |  | 2025-11-11 | 2025-11-11 | 2025-11-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-11 17:27:06 | No | No |  |  |  | 2025-11-15 | 2025-11-27 | 2025-11-28 | V Contribute Co., Ltd | N/A | Closed | 2025-11-28 20:46:23 | Yes | Yes | 2025-11-28 20:46:23 |  | 2025-11-14 | 2025-11-14 | Chonradee Suwapan | Approved | Closed | 2025-11-24 09:54:36 | Yes | Yes | 2026-01-07 17:43:31 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 14:50:23 |  | 2025-11-14 | 2025-11-14 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-11-14 20:19:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-04 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-11-04 17:52:43 | No | No |  | 04-11-2025. Add UBBPg2#， AIRU5636w Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-10 |  | N/A | Not assigned |  | No | No
TW46M_2025 Capacity Expansion Ph3_EXP_BKK | SOI TIWANON 46 | 2025-08-28 |  |  |  | 2025-08-28 | 2025-08-28 | 2025-08-28 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-28 16:57:01 | No | No |  |  |  | 2025-09-05 | 2025-09-03 | 2025-09-05 | V Contribute Co., Ltd | N/A | Closed | 2025-09-05 19:55:05 | Yes | Yes | 2025-09-05 19:56:16 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-26 16:35:46 | Yes | Yes | 2025-09-13 20:30:24 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-07 00:51:23 |  | 2025-09-13 | 2025-09-13 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:46 | No | Yes | 2025-09-14 13:17:09 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-28 17:08:50 | No | No |  | 28-08-2025. Replace RRU5516 L18#， Ant.8 port#， RRU5516 L900#， Ant.4 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-27 |  | N/A | Not assigned |  | No | No
TW46M_2025 Coverage Expansion Ph2_EXP_BKK | SOI TIWANON 46 | 2025-08-19 |  |  |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-19 18:17:20 | No | No |  |  |  | 2025-08-29 | 2025-08-25 | 2025-08-26 | V Contribute Co., Ltd | N/A | Closed | 2025-08-26 10:28:54 | Yes | Yes | 2025-08-26 10:30:10 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-12 19:05:01 | Yes | Yes | 2025-09-02 18:25:08 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 03:25:12 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 02:20:41 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-19 17:52:35 | No | No |  | 2025-08-19_Add RRU3953#， Ant 4 port Sector 1#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-18 |  | N/A | Not assigned |  | No | No
TWRSM_2025 Capacity Expansion Ph3_EXP_BKK | TIWANON-RANGSIT |  |  |  | 2025-09-10 | 2025-09-17 | 2025-09-30 | 2025-09-30 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-09-30 10:53:47 | No | No |  |  | 2025-09-17 | 2025-09-19 | 2025-09-19 | 2025-09-20 | Teloneer Company Limited | N/A | Closed | 2025-09-20 10:39:43 | Yes | Yes | 2026-04-22 15:47:39 |  |  | 2025-10-31 | Nopparat Jaiwongsa 84166092 | Approved | Closed | 2025-11-05 18:20:28 | Yes | Yes | 2025-12-29 17:31:19 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 14:54:02 |  |  | 2025-09-04 | Teloneer Company Limited | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-09-10 08:52:13 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-11 19:19:18 | No | No |  | 11-Sep-2025 Add RRU5516 (1800-2100) S3 S8 Remove RRU3962 *2 Replace Ant 8port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-30 |  | N/A | Not assigned |  | No | No
TWSHM_2025 Capacity Expansion Ph3_EXP_BKK | VENERABLE THAWISAK JUTINDHARO HOSPITAL |  |  |  |  | 2025-09-06 | 2025-09-15 | 2025-09-15 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:49 | No | No |  |  |  | 2025-09-26 | 2025-09-16 | 2025-09-16 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:19:11 | Yes | Yes | 2025-09-30 10:19:12 |  | 2025-09-16 | 2025-09-16 | Chonradee Suwapan | Approved | Closed | 2025-10-07 16:23:19 | Yes | Yes | 2025-12-17 17:40:12 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:20 | Yes | Yes | 2025-11-06 22:02:54 |  | 2025-09-16 | 2025-09-16 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 22:18:16 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-06 18:42:23 | No | No |  | 6-Sep-2025 Add AAU5636w S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-14 |  | N/A | Not assigned |  | No | No
TWTTH_2025 Capacity Expansion Ph5_EXP_SR | Tai Watsadu Tha Thong |  |  |  | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | Teloneer Company Limited | N/A | Closed | 2025-11-13 15:01:10 | No | No |  |  |  | 2025-11-12 | 2025-11-13 | 2025-11-17 | Teloneer Company Limited | N/A | Closed | 2025-11-17 11:31:07 | Yes | Yes | 2025-11-17 11:33:10 |  | 2025-11-18 | 2025-11-18 | Nattawoot Suwan | Approved | Closed | 2025-12-11 10:28:02 | Yes | Yes | 2025-11-18 18:44:49 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:38 | Yes | Yes | 2025-12-09 12:05:30 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-11-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-13 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-11-13 18:19:54 | No | No |  | Add new AAU5636w S1#，S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-12 |  | N/A | Not assigned |  | No | No
UB12B_2025 Coverage Expansion Ph1_EXP_BKK | U Delight Bangsue Station (Back) |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:58 | No | No |  |  |  | 2025-11-07 | 2025-11-05 | 2025-11-07 | V Contribute Co., Ltd | N/A | Closed | 2025-11-07 10:58:14 | Yes | Yes | 2025-11-07 10:58:14 |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2026-05-20 20:07:47 | Yes | Yes | 2025-11-11 19:26:48 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-05-21 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-11-10 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-10 17:44:40 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-30 18:13:01 | No | No |  | 30-Oct-2025 Replace to Ant Vertical dual beam SA 81 82 E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  |  |  | N/A | Not assigned |  | No | No
UB22B_2025 Coverage Expansion Ph1_EXP_BKK | U Delight 2 Bangsue Station (Back) | 2025-08-20 |  |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-20 16:21:33 | No | No |  |  |  | 2025-08-31 | 2025-08-27 | 2025-08-28 | V Contribute Co., Ltd | N/A | Closed | 2025-08-28 11:03:34 | Yes | Yes | 2025-08-28 11:03:43 | 1.Need to fill dismantle RRU 1pcs in EQ. 2.Need to upload panorama photos. |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-19 16:33:12 | Yes | Yes | 2025-12-24 10:24:57 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 03:30:06 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 15:52:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-20 17:10:59 | No | No |  | 20-Aug-2025 Replace Ant.to Ant.Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-19 |  | N/A | Not assigned |  | No | No
UBNAB_2025 Coverage Expansion Ph1_EXP_BKK | URBANO ABSOLUTE SATHONTAKSIN | [5 empty] | 2025-09-20 | 2025-09-20 | Akhom Srinara | N/A | Closed | 2025-09-25 13:54:36 | No | No |  |  |  |  | 2025-09-18 | 2025-09-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-18 20:17:54 | Yes | Yes | 2025-09-18 20:17:55 |  | 2025-09-22 | 2025-09-22 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-10 14:08:42 | Yes | Yes | 2025-09-22 14:48:54 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:20 | Yes | Yes | 2025-11-06 22:04:04 |  | 2025-09-22 | 2025-09-22 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-22 14:15:00 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-18 16:58:55 | No | No |  | 18-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A E-tilt -200 (80) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-18 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
UBNBB_2025 Coverage Expansion Ph1_EXP_BKK | Urbano Absolute SathonTaksin (Back) | [5 empty] | 2025-09-20 | 2025-09-20 | Akhom Srinara | N/A | Closed | 2025-09-25 13:54:36 | No | No |  |  |  |  | 2025-09-18 | 2025-09-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-09-18 21:22:11 | Yes | Yes | 2025-09-20 22:08:06 |  | 2025-09-22 | 2025-09-22 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-10-10 16:47:37 | Yes | Yes | 2025-09-22 17:24:00 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:20 | Yes | Yes | 2025-11-06 22:05:18 |  | 2025-09-22 | 2025-09-22 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:27:56 | No | Yes | 2025-09-22 17:43:53 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-18 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-18 17:34:21 | No | No |  | 2025-09-18_Replace to Ant Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 14/08/2025 >> รอเบิกของ |  | 2025-09-18 | Jia Rui 80023782 | N/A | Closed | 2025-10-05 18:51:31 | No | No
UBS1B_2025 Coverage Expansion Ph1_EXP_BKK | U Delight Bangsue Station (Front) |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:10 | No | No |  |  |  | 2025-11-28 | 2025-11-05 | 2025-11-05 | V Contribute Co., Ltd | N/A | Closed | 2025-11-05 15:50:59 | Yes | Yes | 2025-11-05 15:50:59 |  | 2025-11-10 | 2025-11-10 | Chonradee Suwapan | Approved | Closed | 2025-11-19 09:48:21 | Yes | Yes | 2026-01-07 10:12:30 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-01 23:43:04 |  | 2025-11-10 | 2025-11-10 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-10 17:45:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-29 17:03:34 | No | No |  | 29-Oct-2025 Replace to Ant Vertical dual beam SA 80 E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-10-30 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
UBS2B_2025 Coverage Expansion Ph1_EXP_BKK | U Delight 2 Bangsue Station (Front) | 2025-08-20 |  |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-20 16:21:33 | No | No |  |  |  | 2025-08-31 | 2025-08-27 | 2025-08-28 | V Contribute Co., Ltd | N/A | Closed | 2025-08-28 11:06:28 | Yes | Yes | 2025-08-28 11:06:41 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-19 16:33:12 | Yes | Yes | 2026-01-16 10:45:30 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 03:31:21 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 15:52:54 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-20 20:02:21 | No | No |  | 2025-08-20_Replace to Ant Vertical dual Beam |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-19 |  | N/A | Not assigned |  | No | No
UCK1B_2025 Coverage Expansion Ph1_EXP_BKK | U DELIGHT CHATUCHAK STATION (SWIMMING POOL) |  |  |  |  | 2025-09-22 | 2025-09-22 | 2025-09-22 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-09-22 11:24:57 | No | No |  |  |  | 2025-09-22 | 2025-10-01 | 2025-10-02 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-02 11:12:47 | Yes | Yes | 2025-10-02 11:12:47 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-10-21 13:58:32 | Yes | Yes | 2025-09-24 18:19:41 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:28 | Yes | Yes | 2025-10-27 19:24:00 |  | 2025-09-24 | 2025-09-24 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:20:11 | No | Yes | 2025-09-24 21:36:20 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-18 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-09-18 17:34:21 | No | No |  | 2025-09-18_Replace to Ant Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install completed |  | 2025-09-21 |  | N/A | Not assigned |  | No | No
UCK2B_2025 Coverage Expansion Ph1_EXP_BKK | U DELIGHT CHATUCHAK STATION (FRONT) |  |  |  |  | 2025-10-26 | 2025-10-26 | 2025-10-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-10-25 | 2025-10-27 | V Contribute Co., Ltd | N/A | Closed | 2025-10-27 10:05:16 | Yes | Yes | 2025-10-27 10:05:16 |  | 2025-11-05 | 2025-11-05 | Chonradee Suwapan | Approved | Closed | 2025-11-11 11:05:21 | Yes | Yes | 2025-11-05 20:08:37 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 14:56:27 |  | 2025-11-05 | 2025-11-05 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-05 20:19:03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-24 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-24 17:39:32 | No | No |  | 2025-10-24_Replace to Ant Vertical Dual Beam Sector A#，B ( Sector B No RET) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
UCK3B_2025 Coverage Expansion Ph1_EXP_BKK | U DELIGHT CHATUCHAK STATION (BACK) |  |  |  |  | 2025-10-26 | 2025-10-26 | 2025-10-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-10-26 | 2025-10-27 | V Contribute Co., Ltd | N/A | Closed | 2025-10-27 10:22:30 | Yes | Yes | 2025-10-27 10:22:30 |  | 2025-11-06 | 2025-11-06 | Chonradee Suwapan | Approved | Closed | 2025-11-19 09:48:21 | Yes | Yes | 2025-11-06 18:06:58 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-01 23:46:55 |  | 2025-11-05 | 2025-11-05 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-05 20:19:30 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-24 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-24 17:39:32 | No | No |  | 2025-10-24_Replace to Ant Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-23 |  | N/A | Not assigned |  | No | No
UDP1B_2025 Coverage Expansion Ph1_EXP_BKK | U Delight Residence Pattanakarn-Thonglor (Left) | 2025-08-20 |  |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-20 16:21:33 | No | No |  |  |  | 2025-08-31 | 2025-08-24 | 2025-08-25 | V Contribute Co., Ltd | N/A | Closed | 2025-08-25 10:47:47 | Yes | Yes | 2025-08-25 10:53:14 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-18 17:11:26 | Yes | Yes | 2025-09-15 18:04:37 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 03:32:33 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 15:53:22 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-20 20:02:21 | No | No |  | 2025-08-20_Replace to Ant Vertical dual Beam |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-19 |  | N/A | Not assigned |  | No | No
UDP2B_2025 Coverage Expansion Ph1_EXP_BKK | U DELIGHT RESIDENCE PATTANAKARN-THONGLOR (RIGHT) | 2025-08-20 |  |  |  | 2025-08-20 | 2025-08-20 | 2025-08-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-20 16:21:33 | No | No |  |  |  | 2025-08-31 | 2025-08-24 | 2025-08-25 | V Contribute Co., Ltd | N/A | Closed | 2025-08-25 10:46:43 | Yes | Yes | 2025-08-25 10:50:51 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-18 17:11:26 | Yes | Yes | 2025-09-15 17:28:00 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 03:33:45 |  | 2025-09-15 | 2025-09-15 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-15 15:53:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-20 17:10:41 | No | No |  | 20-Aug-2025 Replace Ant.to Ant.Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-19 |  | N/A | Not assigned |  | No | No
UDR3B_2025 Coverage Expansion Ph1_EXP_BKK | U DELIGHT RESIDENCE RIVERFRONT RAMA 3 | 2025-10-27 |  |  |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-11-03 | 2025-11-03 | V Contribute Co., Ltd | N/A | Closed | 2025-11-03 18:26:26 | Yes | Yes | 2025-11-03 18:26:27 |  | 2025-11-05 | 2025-11-05 | Chonradee Suwapan | Approved | Closed | 2025-11-11 11:05:21 | Yes | Yes | 2025-11-05 20:05:07 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-01 23:50:46 |  | 2025-11-05 | 2025-11-05 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-05 20:19:57 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-27 17:38:14 | No | No |  | 27-Oct-2025 Replace to Ant Vertical dual beam SA SB SC 80#，81#，82 E tilt -200 On-service New cell (L18 2T2R ) SA SC |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-10-27 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | install 100% |  | 2025-10-27 |  | N/A | Not assigned |  | No | No
UDSPM_2025 Capacity Expansion Ph3_EXP_BKK | SOI UDOM SAP |  |  |  |  | 2025-09-05 | 2025-09-15 | 2025-09-15 | Krittee Chamboot 00319410 | N/A | Closed | 2025-10-01 20:45:49 | No | No |  |  |  | 2025-09-26 | 2025-09-18 | 2025-09-19 | V Contribute Co., Ltd | N/A | Closed | 2025-09-19 18:31:34 | Yes | Yes | 2025-09-19 18:31:34 |  | 2025-09-16 | 2025-09-16 | Chonradee Suwapan | Approved | Closed | 2025-10-10 16:48:15 | Yes | Yes | 2025-12-24 12:23:55 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 14:58:54 |  | 2025-09-16 | 2025-09-16 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 22:19:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-06 17:44:02 | No | No |  | 06-09-2025. Add AIRU5636w Sec.2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-09-14 |  | N/A | Not assigned |  | No | No
UDTPB_2025 Coverage Expansion Ph1_EXP_BKK | U-Delight at Talad Phlu Station Site |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:10 | No | No |  |  |  | 2025-11-28 | 2025-11-04 | 2025-11-04 | V Contribute Co., Ltd | N/A | Closed | 2025-11-04 20:14:09 | Yes | Yes | 2025-11-04 20:14:09 |  | 2025-11-10 | 2025-11-10 | Chonradee Suwapan | Approved | Closed | 2025-11-24 09:54:36 | Yes | Yes | 2025-11-10 17:39:45 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 15:00:06 |  | 2025-11-10 | 2025-11-10 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-10 17:45:50 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-29 17:04:31 | No | No |  | 29-Oct-2025 Replace to Ant Vertical dual beam SA 80 81 82 SB 81 SC 82 E tilt -200 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-10-30 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
UHWAB_2025 Coverage Expansion Ph1_EXP_BKK | U Delight Huaikhwang Station | 2025-09-12 |  |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-12 18:29:38 | No | No |  |  |  | 2025-09-30 | 2025-09-15 | 2025-09-15 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:19:24 | Yes | Yes | 2025-09-30 10:19:24 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-10-05 20:25:56 | Yes | Yes | 2025-09-19 20:25:24 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-07 00:56:21 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-19 20:35:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-12 18:07:29 | No | No |  | 12-09-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
UHWCB_2025 Coverage Expansion Ph1_EXP_BKK | U Delight Huaikhwang Station (Tower C) | 2025-09-12 |  |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-12 18:29:38 | No | No |  |  |  | 2025-09-30 | 2025-09-15 | 2025-09-15 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:19:37 | Yes | Yes | 2025-09-30 10:19:38 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-10-05 20:25:56 | Yes | Yes | 2025-09-19 20:25:58 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-07 00:57:35 |  | 2025-09-19 | 2025-09-19 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-19 20:36:06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-12 18:07:29 | No | No |  | 12-09-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
UHWDB_2025 Coverage Expansion Ph1_EXP_BKK | U Delight Huaikhwang Station (Tower D) | 2025-09-12 |  |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-12 18:29:38 | No | No |  |  |  | 2025-09-30 | 2025-09-15 | 2025-09-15 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:19:51 | Yes | Yes | 2025-09-30 10:19:51 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-10-05 20:25:56 | Yes | Yes | 2025-09-20 20:19:05 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-07 00:58:49 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:12:46 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-12 18:07:29 | No | No |  | 12-09-2025. Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
UNCOM_2025 Coverage Expansion Ph2_EXP_BKK | UNICO GOLF COURT |  |  |  | 2025-08-16 |  | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-22 | 2025-08-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-22 12:19:59 | Yes | Yes | 2025-08-22 12:20:58 |  | 2025-08-27 | 2025-08-27 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-18 16:40:10 | Yes | Yes | 2025-08-27 13:48:24 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:11 | Yes | Yes | 2025-09-23 03:36:13 |  | 2025-08-31 | 2025-08-31 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-08-31 15:18:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-22 11:13:28 | No | No |  | 22-Aug-2025 RRU3953 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
UON1B_2025 Coverage Expansion Ph1_EXP_BKK | U DELIGHT ONNUT STATION (FRONT) |  |  |  |  | 2025-10-23 | 2025-10-23 | 2025-10-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-10-30 | 2025-10-30 | V Contribute Co., Ltd | N/A | Closed | 2025-10-30 15:01:35 | Yes | Yes | 2025-10-30 15:01:36 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-11 09:20:58 | Yes | Yes | 2025-11-04 20:00:47 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 15:05:22 |  | 2025-11-04 | 2025-11-04 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-04 20:37:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-22 17:50:52 | No | No |  | 22-Oct-2025 Replace to Ant Vertical dual beam SA E tilt-200 80 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | install 100% |  | 2025-10-22 |  | N/A | Not assigned |  | No | No
UP31B_2025 Coverage Expansion Ph1_EXP_BKK | U Delight 3 Prachachuen-Bangsue (Front) | 2025-09-12 |  |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-12 18:29:38 | No | No |  |  |  | 2025-09-30 | 2025-09-22 | 2025-09-22 | V Contribute Co., Ltd | N/A | Closed | 2025-09-22 18:23:09 | Yes | Yes | 2025-09-22 18:23:09 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-10-07 20:34:19 | Yes | Yes | 2025-09-20 20:20:49 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:25:01 | Yes | Yes | 2025-10-09 22:29:59 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:13:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-12 18:07:29 | No | No |  | 12-09-2025. Add UBBPd6#， Replace Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
UP32B_2025 Coverage Expansion Ph1_EXP_BKK | U Delight 3 Prachachuen-Bangsue (Back) | 2025-09-12 |  |  |  | 2025-09-12 | 2025-09-12 | 2025-09-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-12 18:29:38 | No | No |  |  |  | 2025-09-30 | 2025-09-22 | 2025-09-22 | V Contribute Co., Ltd | N/A | Closed | 2025-09-22 18:22:34 | Yes | Yes | 2025-09-22 18:22:34 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-10-07 20:34:19 | Yes | Yes | 2025-09-20 20:22:29 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-02 00:00:49 |  | 2025-09-20 | 2025-09-20 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:54 | No | Yes | 2025-09-20 23:14:02 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-09-12 16:54:56 | No | No |  | 12-Sep-2025 Replace Ant to Ant '4x4H Small Cell Vertical Dual Beam Sector A E tilt -200 81 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan WK38-39 |  | 2025-09-11 |  | N/A | Not assigned |  | No | No
UR26M_2025 Capacity Expansion Ph2_EXP_BKK | UDOMSUK ROAD 26 YAK 2 |  |  |  | 2025-08-18 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-19 | 2025-08-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-21 09:57:27 | Yes | Yes | 2025-08-28 08:54:03 |  | 2025-08-28 | 2025-11-27 | Aomchun Jittreemit | Approved | Closed | 2025-12-02 18:21:55 | Yes | Yes | 2025-11-27 17:35:35 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-10-31 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:35 | Yes | Yes | 2026-01-10 00:24:56 |  | 2025-09-05 | 2025-09-05 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-09-05 13:11:08 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-20 20:02:21 | No | No |  | 2025-08-20_Add AAU5636w Sector 3#， GPS//2025-08-19_Add UBBPd6#， UBBPg3a#， Add AAU5636w Sector 1#，2#， ***Pending Add AAU5636w Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
URB1B_2025 Coverage Expansion Ph1_EXP_BKK | U DELIGHT RATTANATHIBET (FRONT) | 2025-10-27 |  |  |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-11-04 | 2025-11-05 | V Contribute Co., Ltd | N/A | Closed | 2025-11-05 13:39:38 | Yes | Yes | 2025-11-05 13:39:38 | SQC Closed | 2025-11-06 | 2025-11-06 | Chonradee Suwapan | Approved | Closed | 2025-11-20 16:09:07 | Yes | Yes | 2025-11-06 18:07:33 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 15:09:02 |  | 2025-11-06 | 2025-11-06 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-06 18:12:13 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-27 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-27 17:09:41 | No | No |  | 2025-10-27_Replace to Ant Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-10-27 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | install 100% |  | 2025-10-27 |  | N/A | Not assigned |  | No | No
URB2B_2025 Coverage Expansion Ph1_EXP_BKK | U DELIGHT RATTANATHIBET (BACK) | 2025-10-27 |  |  |  | 2025-10-28 | 2025-10-28 | 2025-10-28 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-28 10:54:11 | No | No |  |  |  | 2025-11-07 | 2025-11-05 | 2025-11-13 | V Contribute Co., Ltd | N/A | Closed | 2025-11-13 12:38:13 | Yes | Yes | 2025-11-13 12:38:13 |  | 2025-11-06 | 2025-11-06 | Chonradee Suwapan | Approved | Closed | 2025-11-20 16:09:07 | Yes | Yes | 2025-11-06 18:08:12 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-21 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 15:10:15 |  | 2025-11-06 | 2025-11-06 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:11:23 | No | Yes | 2025-11-06 18:12:38 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-27 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-10-27 17:09:41 | No | No |  | 2025-10-27_Replace to Ant Vertical Dual Beam Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2025-10-27 |  | V Contribute Co., Ltd | N/A | Assigned |  | No | No |  |  |  | install 100% |  | 2025-10-27 |  | N/A | Not assigned |  | No | No
VEVBB_2025 Capacity Expansion NW Modernization_EXP_BKK | VERVE BANGKOK SMALL CELL |  |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-28 | 2026-03-24 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 16:00:32 | Yes | Yes | 2026-03-24 16:00:33 |  | 2026-03-31 | 2026-03-31 | Chonradee Suwapan | Approved | Closed | 2026-04-23 10:52:27 | Yes | Yes | 2026-03-31 00:10:25 | page no 24: need to upload before ground bar photo (not update yet) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-23 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-31 | 2026-03-31 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-31 00:21:14 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-23 17:25:38 | No | No |  | 23-02-2026. Replace RRU3826 to RRU5526#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VINTM_2025 Capacity Expansion Ph2_EXP_ER | VINYTHAI | 2025-09-22 |  | Clear Pending |  | 2025-08-31 | 2025-08-09 | 2025-08-09 | Teloneer Company Limited | N/A | Closed | 2025-08-09 17:05:40 | No | No |  |  |  | 2025-08-31 | 2025-08-18 | 2025-08-21 | Teloneer Company Limited | N/A | Closed | 2025-08-21 09:55:39 | Yes | Yes | 2025-08-22 16:09:03 |  | 2025-08-31 | 2025-09-01 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-26 13:45:51 | Yes | Yes | 2025-09-01 14:56:08 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-09-30 | 2025-09-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:50 | Yes | Yes | 2025-10-07 01:00:04 |  | 2025-07-31 | 2025-10-01 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-07 11:09:00 | Yes | Yes | 2025-08-29 17:30:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-09 |  | 2025-08-14 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-24 16:14:18 | No | No |  | Change Remote RRU to Remote BBU + Add BBU + Replace Antenna (Dualband)) + Replace RRU5516_1800 Sec.A#，B & New L18L21 + 4T4R+ Add RRU5516_1800 x 2+ New Antenna (Dualband) Sec.D#，E & New L26F1F5 + NR26 (New RRU5818)x2 + Co Antenna Sec D#，E |  | 2025-09-22 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-22 17:07:27 | No | No |  |  |  | 2025-07-11 | Angsana Jituafua WX1434741 | Approved | Closed | 2025-07-22 13:37:41 | Yes | Yes | 2025-07-22 12:06:13 |  |  | 2025-08-27 | Teloneer Company Limited | N/A | Closed | 2025-08-28 14:38:08 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VS11M_2025 Capacity Expansion Ph7_EXP_BKK | SOI VONG SAWANG 11 | 2026-01-13 |  |  |  | 2026-01-13 | 2026-01-13 | 2026-01-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-01-13 17:44:17 | No | No |  |  |  | 2026-01-31 | 2026-01-13 | 2026-01-14 | V Contribute Co., Ltd | N/A | Closed | 2026-01-14 10:34:08 | Yes | Yes | 2026-01-14 10:34:09 |  | 2026-01-26 | 2026-01-26 | Chonradee Suwapan | Approved | Closed | 2026-05-08 09:30:04 | Yes | Yes | 2026-05-05 16:48:13 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-26 | 2026-01-26 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-01-26 02:04:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-13 17:06:17 | No | No |  | 13-01-2026. Add AIRU5636w Sec.6#， Replace UBBPeb to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
W77BB_2025 Capacity Expansion NW Modernization_EXP_BKK | The Base Park West Sukhumvit 77 (Back) |  |  |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-05 08:14:49 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:26:22 | Yes | Yes | 2026-03-23 15:26:22 |  | 2026-03-02 | 2026-03-02 | Chonradee Suwapan | Approved | Closed | 2026-05-08 09:30:04 | Yes | Yes | 2026-05-20 17:43:47 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-02 | 2026-03-02 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:17:02 | Yes | Yes | 2026-03-02 20:56:18 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-13 18:27:25 | No | No |  | 13-02-2026. Replace RRU3962 x2 to RRU5526 x2 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
W77FB_2025 Capacity Expansion NW Modernization_EXP_BKK | The Base Park West Sukhumvit 77 (Front) |  |  |  |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-06 18:17:38 | No | No |  |  |  | 2026-02-28 | 2026-03-15 | 2026-03-17 | V Contribute Co., Ltd | N/A | Closed | 2026-03-17 15:12:16 | Yes | Yes | 2026-03-17 15:12:16 |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-06-09 16:36:07 | Yes | Yes | 2026-05-29 01:52:05 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-21 | 2026-06-15 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:17:02 | Yes | Yes | 2026-03-05 21:12:32 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-13 18:27:25 | No | No |  | 13-02-2026. Replace RRU3962 to RRU5526 Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WARSM_2025 Coverage Expansion Ph2_EXP_BKK | SOI WAT RAT RANGSAN |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-11 | 2025-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-12 10:37:40 | Yes | Yes | 2025-08-21 12:13:44 |  | 2025-08-24 | 2025-08-24 | Kontira Kowapradit | Approved | Closed | 2025-09-01 13:12:38 | Yes | Yes | 2025-08-24 14:14:18 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-02 | 2025-09-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:20 | Yes | Yes | 2025-09-04 15:26:45 |  | 2025-09-04 | 2025-09-04 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 13:09:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-11 18:23:00 | No | No |  | 11-08-2025. Add RRU3953#， Replace Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
WBAKM_2025 Coverage Expansion Ph1_New_BKK | Wat Bang Khan (Khlong Luang) |  |  |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-17 16:18:56 | No | No |  |  |  | 2025-11-15 | 2025-11-14 | 2025-11-16 | V Contribute Co., Ltd | N/A | Closed | 2025-11-16 13:33:52 | Yes | Yes | 2025-11-16 13:33:52 |  | 2025-11-20 | 2025-11-20 | Chonradee Suwapan | Approved | Closed | 2026-02-09 17:33:30 | Yes | Yes | 2025-11-20 19:45:19 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | 2026-05-05 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No |  |  | 2025-11-20 | 2025-11-20 | Chonradee Suwapan | Approved | Closed | 2025-12-09 16:01:02 | No | Yes | 2025-11-20 22:50:00 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-12 16:09:09 | No | No |  | 12-Nov-2025 New site Small cell Add RRU3962 S1 S2 S3 Add Ant 12 port S1 S2 S3 4/3 4/4 4/5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | completed |  |  |  | N/A | Not assigned |  | No | No
WBCLM_2025 Capacity Expansion Ph6_EXP_BKK | WAT BANG CHALONG NAI | [5 empty] | 2025-12-19 | 2025-12-19 | Akhom Srinara | N/A | Closed | 2025-12-19 11:20:07 | No | No |  |  |  | 2025-12-15 | 2025-12-15 | 2025-12-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-16 16:34:09 | Yes | Yes | 2025-12-18 10:15:35 |  | 2025-12-22 | 2025-12-22 | Muhamadnase Chesamae | Approved | Closed | 2026-06-25 09:14:47 | Yes | Yes | 2026-05-20 10:23:07 | แก้ไข Tower Overload >>เพิ่มหน้า 19#，20#，21 / แก้หน้า 22#，23#，24 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-02-25 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2025-12-19 | 2025-12-19 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2025-12-19 20:33:30 |  |  | 2025-12-31 | 2025-12-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-13 17:15:28 | No | No |  |  |  |  | 2025-12-13 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-13 18:09:14 | No | No |  | 2026-05-18_Replace Ant to 8 port Sector 3#，8 (Fix tower load) 13-12-2025. Add RRU5516 L900#， Ant.4 port Sec.8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WBHNM_2025 Capacity Expansion Ph6_EXP_ER | Wat Bo Hin | 2025-11-07 | THCP_Phet.S |  |  | 2025-11-30 | 2025-11-07 | 2025-11-07 | Teloneer Company Limited | N/A | Closed | 2025-11-07 14:37:47 | No | No |  |  |  | 2025-11-30 | 2025-11-07 | 2025-11-07 | Teloneer Company Limited | N/A | Closed | 2025-11-07 18:07:29 | Yes | Yes | 2025-11-12 07:08:48 |  | 2025-11-30 | 2025-11-12 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-14 16:34:33 | Yes | Yes | 2025-11-12 12:38:26 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-10 00:35:52 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:12 | Yes | Yes | 2025-11-04 11:35:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-07 17:57:49 | No | No |  | **waiting on-service L9/L7 -- New L0709 + 4T4R + (RRU5516_900) + (New Antenna LB) S4#，8 |  | 2025-11-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-10 11:08:32 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WBKDM_2025 Capacity Expansion Ph3_EXP_BKK | WAT BANG KRADI |  |  |  |  | 2025-11-06 | 2025-11-06 | 2025-11-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-06 09:12:58 | No | No |  |  |  | 2025-11-07 | 2025-11-10 | 2025-11-13 | V Contribute Co., Ltd | N/A | Closed | 2025-11-13 18:10:24 | Yes | Yes | 2025-11-13 18:10:24 |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2025-11-19 16:03:47 | Yes | Yes | 2026-01-07 13:54:58 | APT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 15:22:09 |  | 2025-11-11 | 2025-11-11 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-11-11 19:34:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-10-30 18:11:51 | No | No |  | 30-Oct-2025 Add AAU5636w S1 Add g3 Remove d5 5/0 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-05 |  | N/A | Not assigned |  | No | No
WBKDM_2025 Coverage Expansion Ph2_EXP_BKK | WAT BANG KRADI | 2025-08-05 |  |  |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-05 16:45:51 | No | No |  |  |  | 2025-08-22 | 2025-08-14 | 2025-08-15 | V Contribute Co., Ltd | N/A | Closed | 2025-08-15 10:11:24 | Yes | Yes | 2025-08-15 10:15:54 |  | 2025-08-24 | 2025-08-24 | Chonradee Suwapan | Approved | Closed | 2025-09-01 13:12:07 | Yes | Yes | 2025-08-24 20:52:54 | Pat Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:20 | Yes | Yes | 2025-09-04 15:28:02 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:41:12 | No | Yes | 2025-08-05 09:09:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-05 19:13:14 | No | No |  | 2025-08-05_Add RRU3953 Sector 3#， No act Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-04 |  | N/A | Not assigned |  | No | No
WBPKM_2025 Coverage Expansion Ph2_EXP_BKK | WAT BANG PHRAEK | [5 empty] | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-22 | 2025-08-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-22 16:54:45 | Yes | Yes | 2025-08-25 17:09:58 |  | 2025-08-25 | 2025-08-25 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-09 09:05:18 | Yes | Yes | 2025-10-06 12:31:25 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 03:53:26 |  | 2025-09-03 | 2025-09-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-03 10:35:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-22 17:01:38 | No | No |  | 2-Oct-2025 Clear VSWR Subrack 111 22-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Hold เบิกของ 6/8/25 solution เปลี่ยน 14/8/25 แจ้งเบิกของใหม่ |  | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
WBRWM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI WAT BOROMMANIWAT |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-24 14:48:20 | No | No |  |  |  | 2026-02-21 | 2026-02-20 | 2026-02-24 | V Contribute Co., Ltd | N/A | Closed | 2026-02-24 09:59:23 | Yes | Yes | 2026-02-24 09:59:24 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-03-20 09:21:29 | Yes | Yes | 2026-03-09 20:44:09 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-07 | 2026-03-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:56 | Yes | Yes | 2026-04-09 13:45:39 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-23 22:54:08 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-05 19:48:28 | No | No |  | 5 Feb 2026 Replace RRU5507 s1 #，2#，3 downgrade s3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WBTOM_2025 Capacity Expansion Ph7_EXP_SR | Ban wang bua toom |  |  |  |  | 2025-12-25 | 2026-03-27 | 2026-03-27 | Teloneer Company Limited | N/A | Closed | 2026-03-27 16:23:49 | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WCDHM_2025 Coverage Expansion Ph2_EXP_BKK | WAT CHEDIHOI | 2025-08-05 |  |  |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-05 16:45:51 | No | No |  |  |  | 2025-08-22 | 2025-08-15 | 2025-08-16 | V Contribute Co., Ltd | N/A | Closed | 2025-08-16 09:58:43 | Yes | Yes | 2025-08-16 09:59:08 |  | 2025-08-24 | 2025-08-24 | Chonradee Suwapan | Approved | Closed | 2025-09-01 13:12:07 | Yes | Yes | 2025-08-24 20:53:59 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:20 | Yes | Yes | 2025-09-04 15:34:29 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:41:12 | No | Yes | 2025-08-05 09:09:42 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-05 19:13:14 | No | No |  | 2025-08-05_Add RRU3953#， Replace Ant to 4 port Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-04 |  | N/A | Not assigned |  | No | No
WCLHM_2025 Capacity Expansion Ph7_EXP_BKK | WAT CHAENG LAM HIN |  |  |  | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-02 11:40:53 | No | No |  |  | 2026-01-28 | 2026-01-28 | 2026-01-28 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:07:20 | Yes | Yes | 2026-03-23 15:10:11 |  | 2026-02-02 | 2026-02-02 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-19 14:45:45 | Yes | Yes | 2026-02-02 16:31:14 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-19 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:56 | Yes | Yes | 2026-04-09 13:46:17 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 21:49:56 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-17 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-17 20:24:27 | No | No |  | 17 Jan 2026 add rru5516 sector 8 18/21 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WGLEM_2025 Capacity Expansion NW Modernization_EXP_BKK | WANGLEE TOWER |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-01-31 | 2026-02-10 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:24:57 | Yes | Yes | 2026-03-23 15:24:57 |  | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-02-25 09:26:15 | Yes | Yes | 2026-04-02 11:29:05 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:56 | Yes | Yes | 2026-04-09 13:46:36 |  | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-12 22:34:11 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-17 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-17 20:25:46 | No | No |  | 17 Jan 2026 Add AAU5768 On DMM sector#，1#，2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHKBM_2025 Capacity Expansion Ph3_EXP_BKK | Wathuakrabeu | 2025-08-28 |  |  |  | 2025-08-28 | 2025-08-27 | 2025-08-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-27 18:39:50 | No | No |  |  |  | 2025-09-05 | 2025-09-02 | 2025-09-06 | V Contribute Co., Ltd | N/A | Closed | 2025-09-06 11:29:07 | Yes | Yes | 2025-09-06 11:30:33 |  | 2025-09-09 | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-29 15:46:13 | Yes | Yes | 2025-09-09 18:57:23 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:49 | Yes | Yes | 2025-10-07 01:16:35 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-09 19:07:09 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-27 19:45:16 | No | No |  | 27-Aug-2025 Add RRU5516 (700900) S1 Add Ant 4port Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-27 |  | N/A | Not assigned |  | No | No
WHLPM_2025 Capacity Expansion Ph1_EXP_BKK | WAT HAULAMPHONG |  |  |  |  | 2025-07-17 | 2025-07-17 | 2025-07-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-07-17 11:11:44 | No | No |  |  |  | 2025-07-12 | 2025-10-08 | 2025-10-08 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2025-10-08 16:48:54 | Yes | Yes | 2025-10-08 16:48:54 |  | 2025-07-23 | 2025-07-23 | Chonradee Suwapan | Approved | Closed | 2025-11-11 09:19:44 | Yes | Yes | 2025-07-23 00:58:43 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-11-11 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 15:27:03 |  | 2025-06-17 | 2025-06-17 | Annop Auyto | Approved | Closed | 2025-06-24 13:18:53 | No | Yes | 2025-06-19 12:47:25 | CB เต็ม |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-07-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-07-16 17:40:14 | No | No |  | 16-07-2025. Add UBBPg3a //27-06-2025. Add RRU5502#， AIRU5636w Sec.6#， Replace Ant.12 port Sec.1#， 3#， Relocate RRU Sec.2 //26-Jun-2025 Add g3a =1 Remove g3=1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-07-16 |  | N/A | Not assigned |  | No | No
WKBYM_2025 Capacity Expansion Ph4_EXP_ER | Wat KhaoBoyang | 2025-09-10 |  | Install & Integrate |  | 2025-09-30 | 2025-09-10 | 2025-09-10 | Teloneer Company Limited | N/A | Closed | 2025-09-10 18:31:01 | No | No |  |  |  | 2025-09-30 | 2025-09-10 | 2025-09-11 | Teloneer Company Limited | N/A | Closed | 2025-09-11 20:06:37 | Yes | Yes | 2025-09-11 20:06:38 |  | 2025-09-30 | 2025-09-11 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-10-10 10:16:30 | Yes | Yes | 2025-09-11 23:13:30 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-10-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:34 | Yes | Yes | 2026-01-15 15:28:16 |  | 2025-09-30 | 2025-10-08 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2026-03-02 15:29:20 | Yes | Yes | 2025-10-08 11:02:41 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-10 |  | 2025-09-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-10 18:49:45 | No | No |  | Replace RRU5508 to (RRU5516_900) + 4T4R S2 |  | 2025-09-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-09-10 18:49:56 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKGSM_2025 Capacity Expansion Ph2_EXP_BKK | WAT KHLONG SUAN | 2025-08-16 |  |  |  | 2025-08-16 | 2025-08-16 | 2025-08-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-16 15:37:02 | No | No |  |  |  | 2025-08-31 | 2025-08-24 | 2025-08-25 | V Contribute Co., Ltd | N/A | Closed | 2025-08-25 16:58:03 | Yes | Yes | 2025-08-25 16:59:10 |  |  | 2025-09-04 | Chonradee Suwapan | Approved | Closed | 2025-09-09 16:45:53 | Yes | Yes | 2025-09-04 20:01:51 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:13:42 |  | 2025-08-27 | 2025-08-27 | Chonradee Suwapan | Approved | Closed | 2025-10-10 17:21:38 | No | Yes | 2025-08-27 15:50:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-16 17:11:35 | No | No |  | 16-08-2025. Add RRU5516 L900 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-14 |  | N/A | Not assigned |  | No | No
WKGSM_2025 Capacity Expansion Ph3_EXP_BKK | WAT KHLONG SUAN |  |  |  |  | 2025-09-08 | 2025-09-09 | 2025-09-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-09-09 18:08:45 | No | No |  |  |  | 2025-09-26 | 2025-09-11 | 2025-09-11 | V Contribute Co., Ltd | N/A | Closed | 2025-09-30 10:21:28 | Yes | Yes | 2025-09-30 10:21:29 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-10-07 10:58:15 | Yes | Yes | 2025-12-22 15:36:59 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-02 00:32:48 |  | 2025-09-18 | 2025-09-18 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:19:32 | No | Yes | 2025-09-18 21:40:39 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-09 18:53:58 | No | No |  | 09-09-2025. Add RRU5516 L900#， Ant.4 port Sec.1#， Replace RRU5516 L18#， Ant.4 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Plan Wk37 |  | 2025-09-08 |  | N/A | Not assigned |  | No | No
WKGSM_2025 Coverage Expansion Ph2_EXP_BKK | WAT KHLONG SUAN | 2025-08-16 |  |  |  | 2025-08-16 | 2025-08-16 | 2025-08-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-16 15:37:02 | No | No |  |  |  | 2025-08-31 | 2025-08-24 | 2025-08-25 | V Contribute Co., Ltd | N/A | Closed | 2025-08-25 10:06:13 | Yes | Yes | 2025-08-25 10:07:07 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-17 13:06:53 | Yes | Yes | 2025-09-02 18:25:58 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:14:59 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:41:12 | No | Yes | 2025-08-05 09:10:04 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-16 17:11:35 | No | No |  | 16-08-2025. Add RRU3953#， Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-16 |  | N/A | Not assigned |  | No | No
WKN2M_2025 Capacity Expansion Ph6_EXP_BKK | WAT KHAE NAI 2 | [5 empty] | 2025-12-19 | 2025-12-19 | Akhom Srinara | N/A | Closed | 2025-12-19 11:20:07 | No | No |  |  |  | 2025-12-15 | 2025-12-16 | 2025-12-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-17 10:37:20 | Yes | Yes | 2025-12-19 15:13:46 |  | 2025-12-19 | 2025-12-19 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-01-05 16:26:33 | Yes | Yes | 2025-12-19 20:42:49 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 15:29:31 |  | 2025-12-18 | 2025-12-18 | Charuwan Limsaihua | Approved | Closed | 2026-03-12 09:22:14 | Yes | Yes | 2025-12-18 15:30:32 |  |  | 2025-12-31 | 2025-12-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-15 13:30:51 | No | No |  |  |  |  | 2025-12-15 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-15 17:11:18 | No | No |  | 15-12-2025. Replace RRU3962 to RRU5526#， Ant.8 port Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKUSB_2025 Capacity Expansion Ph4_EXP_SR | kuan su bun temple nsasan |  |  |  | 2025-10-01 | 2025-10-01 | 2025-10-01 | 2025-10-01 | Nattawoot Suwan | N/A | Closed | 2025-10-02 09:54:28 | No | No |  |  |  | 2025-09-26 | 2025-10-01 | 2025-10-01 | Teloneer Company Limited | N/A | Closed | 2025-10-01 17:22:54 | Yes | Yes | 2025-10-02 09:58:53 |  | 2025-10-02 | 2025-10-02 | Nattawoot Suwan | Approved | Closed | 2025-10-08 07:26:09 | Yes | Yes | 2025-10-15 12:54:25 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-10-22 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:28 | Yes | Yes | 2025-10-27 19:32:26 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-10-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-01 | 2025-10-01 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-10-01 18:22:45 | No | No |  | On cell 1800 S2 Rep RRU S2 > RRU3826(2) to RRU5516MB > existing Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-09-30 |  | N/A | Not assigned |  | No | No
WLAIM_2025 Capacity Expansion Ph6_EXP_BKK | SOI WILALAI | [5 empty] | 2025-12-23 | 2025-12-23 | Akhom Srinara | N/A | Closed | 2025-12-23 09:33:12 | No | No |  |  |  | 2025-12-18 | 2025-12-19 | 2025-12-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-20 09:56:58 | Yes | Yes | 2026-09-18 08:28:49 |  | 2026-01-19 | 2026-09-24 | Aomchun Jittreemit | Approved | Closed | 2026-09-29 23:58:28 | Yes | Yes | 2026-09-24 16:12:42 | แก้ไข้ Diff Tower Overlode 20260518 | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 |  | wangxing 84250914 | N/A | Not assigned |  | No | No |  |  | 2026-01-09 | 2026-01-09 | Aomchun Jittreemit | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-09 09:40:55 |  |  | 2025-12-31 | 2025-12-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-18 17:03:49 | No | No |  |  |  |  | 2025-12-18 | Suthee Khamhom WX1452991 | N/A | Closed | 2025-12-18 17:43:10 | No | No |  | 2026-09-16 Replace ant 12 port Sec.1&Sec.2 Replace ant 4 port Sec.6 2025-12-18 WLAIM - Install 1*RRU5516 ANT 4P for LB S6 config RET already/No alarm. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WLFPM_2025 Coverage Expansion Ph2_EXP_BKK | WAT LAEM FA PHA | 2025-08-05 |  |  |  | 2025-08-05 | 2025-08-05 | 2025-08-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-05 16:45:51 | No | No |  |  |  | 2025-08-22 | 2025-08-15 | 2025-08-18 | V Contribute Co., Ltd | N/A | Closed | 2025-08-18 11:49:48 | Yes | Yes | 2025-08-18 12:15:22 |  | 2025-08-24 | 2025-08-24 | Chonradee Suwapan | Approved | Closed | 2025-09-01 13:12:38 | Yes | Yes | 2025-08-24 20:55:54 | Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:20 | Yes | Yes | 2025-09-04 15:40:55 |  | 2025-07-30 | 2025-07-30 | Annop Auyto | Approved | Closed | 2025-09-03 12:01:06 | No | Yes | 2025-07-30 13:58:03 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-05 16:10:42 | No | No |  | 5-Aug-2025 Add RRU3953 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-04 |  | N/A | Not assigned |  | No | No
WLGWM_2025 Capacity Expansion Ph7_EXP_ER | Wellgrow | 2025-12-15 |  | Install & Integrate |  | 2025-12-31 | 2025-12-15 | 2025-12-15 | Teloneer Company Limited | N/A | Closed | 2025-12-15 18:04:37 | No | No |  |  |  | 2025-12-31 | 2025-12-15 | 2025-12-16 | Teloneer Company Limited | N/A | Closed | 2025-12-16 15:56:07 | Yes | Yes | 2025-12-18 10:20:33 |  | 2025-12-31 | 2025-12-18 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-01-06 16:30:08 | Yes | Yes | 2025-12-18 16:36:40 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:03 | Yes | Yes | 2026-03-27 17:09:49 |  | 2025-12-31 | 2025-12-15 | Apichat fangsantthia(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:26:56 | Yes | Yes | 2025-12-15 15:54:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-15 18:28:19 | No | No |  | "Replace UBBPg1 x 2 to UBBPg2 x 2 + Add UBBPg3a_WLGWM_H_1 Remove Antenna + (New AAU5768) + Main Dir = 180 + Remove RRU5505 x 1_WLGWM_H_3 (Co AAU5768) + Main Dir = 180 + Remove RRU5505 x 1_WLGWM_H_8 (Co AAU5768) + Main Dir = 180 + Remove RRU5505 x 1_WLGWM_H_M (Co AAU5768) + Main Dir = 180 + Remove RRU5505 x 1_WLGWM_H_N Remove Sector + Remove RRU5505 x 1_zz-Offservice ReSectorname S1 to S6 + Co L07 + NR07_WLGWM_L_6 ReSectorname S2 to S3 + Co NR07_WLGWM_L_3 ReSectorname S3 to S4 + Replace RRU5508 to (RRU5516_900) + Co NR07 + 4T4R_WLGWM_L_4 ReSectorname S1 to S2_WLGWM_N_2 ReSectorname S2 to S3 + ReDirection 180 to 140_WLGWM_N_3 ReSectorname S3 to S4_WLGWM_N_4 New L26F5 + NR26 (New AAU5636w)_WLGWM_N_8 revise to aau5614 " |  | 2025-12-17 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-17 18:31:14 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WNALM_2025 Capacity Expansion Ph8_EXP_ER | Soi Mu Ban Wana Land | 2026-01-20 |  |  |  | 2026-02-28 | 2026-01-20 | 2026-01-20 | Teloneer Company Limited | N/A | Closed | 2026-01-20 17:22:39 | No | No |  |  |  | 2026-02-28 | 2026-01-19 | 2026-01-20 | Teloneer Company Limited | N/A | Closed | 2026-01-20 15:57:05 | Yes | Yes | 2026-01-21 21:44:02 |  | 2026-02-28 | 2026-01-23 | Apichat fangsantthia(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:20:22 | Yes | Yes | 2026-01-23 21:52:59 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:02 | Yes | Yes | 2026-04-09 11:36:39 |  | 2026-01-31 | 2026-01-19 | Adisak Chanmao(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-01-19 11:23:13 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-01-19 19:07:53 | No | No |  | Replace Antenna (Dualbeam)_WNALM_H_1 Replace Antenna (Dualbeam) + Add RRU5505 x 1 + 4T4R_WNALM_H_2 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_WNALM_H_7 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_WNALM_H_6 |  | 2026-01-19 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-22 18:31:58 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WNHST_2025 Coverage Expansion Ph1_New_SR | Wang Chiat |  |  |  |  | 2026-02-03 | 2026-02-03 | 2026-02-03 | Teloneer Company Limited | N/A | Closed | 2026-02-03 15:03:53 | No | No |  |  |  | 2026-02-03 | 2026-02-03 | 2026-02-04 | Teloneer Company Limited | N/A | Closed | 2026-02-04 09:37:41 | Yes | Yes | 2026-02-25 10:01:41 | SQC Close | 2026-02-25 | 2026-02-25 | Teloneer Company Limited | Approved | Closed | 2026-02-26 20:30:29 | Yes | Yes | 2026-03-04 11:04:08 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-03-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:03 | Yes | Yes | 2026-03-27 17:11:08 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-02-03 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-03 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-02-03 15:39:57 | No | No |  | BBU3910 #，Add UBBPd5*3 Confirm By P.BOOM (Plan d5*4) S1 > RRU3826*2 > Single 4*4 S2 > RRU3826*2 > Single 4*4 S3 > RRU3826*2 > Single 4*4 S4 > RRU3826*2 > Single 4*4 Test Done |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-01-06 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-01-07 17:31:41 | Yes | Yes | 2026-01-06 17:40:57 |  |  | 2026-02-05 | Nattawoot Suwan | N/A | Closed | 2026-02-05 11:17:05 | No | No | [5 empty] | 2026-02-02 |  | N/A | Not assigned |  | No | No
WNPNM_2025 Capacity Expansion Ph2_EXP_ER | Wat Nongpaknam | 2025-07-13 |  | Install & Integrate |  | 2025-07-31 | 2025-07-15 | 2025-07-16 | Teloneer Company Limited | N/A | Closed | 2025-07-16 15:38:16 | No | No |  |  |  | 2025-07-31 | 2025-07-13 | 2025-07-20 | Teloneer Company Limited | N/A | Closed | 2025-07-20 13:20:14 | Yes | Yes | 2025-07-30 23:42:36 |  | 2025-07-31 | 2025-09-12 | Thanakit Chaleechai | Approved | Closed | 2025-09-18 15:00:39 | Yes | Yes | 2025-09-12 11:43:37 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2025-12-31 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:21:07 |  | 2025-07-31 | 2025-07-31 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-07 11:11:46 | Yes | Yes | 2025-08-29 17:31:41 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-22 |  | 2025-07-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-13 16:45:51 | No | No |  | Replace Antenna (HB) + Add RRU5505 x 1 + 4T4R S4 |  | 2025-07-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-07-13 16:48:59 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WNSRZ_2025 Capacity Expansion Ph6_EXP_BKK | WAT NOISUWANNARAM | [5 empty] | 2025-12-23 | 2025-12-23 | Akhom Srinara | N/A | Closed | 2025-12-23 19:02:27 | No | No |  |  |  | 2025-12-22 | 2025-12-25 | 2025-12-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-26 18:02:55 | Yes | Yes | 2026-01-09 11:00:22 |  | 2026-01-12 | 2026-01-12 | Aomchun Jittreemit | Approved | Closed | 2026-06-29 16:19:56 | Yes | Yes | 2026-01-16 14:09:33 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-03-20 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-09 | 2026-01-09 | Aomchun Jittreemit | Approved | Closed | 2026-03-12 09:56:37 | Yes | Yes | 2026-01-09 12:04:15 |  |  | 2025-12-31 | 2025-12-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-24 17:40:04 | No | No |  |  |  |  | 2025-12-22 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-12-22 17:46:41 | No | No |  | 22-12-2025. Add AAU5614#， RRU5516 L900#， Ant.4 port Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WNSWM_2025 Capacity Expansion Ph2_EXP_ER | Wat Noensutthawas | 2025-07-25 |  | Install & Integrate |  | 2025-08-31 | 2025-07-26 | 2025-07-27 | Teloneer Company Limited | N/A | Closed | 2025-07-27 18:21:13 | No | No |  |  |  | 2025-07-31 | 2025-07-25 | 2025-07-26 | Teloneer Company Limited | N/A | Closed | 2025-07-26 13:52:17 | Yes | Yes | 2025-07-31 23:48:51 |  | 2025-07-31 | 2025-08-06 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-09-18 15:00:39 | Yes | Yes | 2025-09-01 14:37:27 |  | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:23:33 |  | 2025-07-31 | 2025-07-31 | Sermsiri Bampentam(Teloneer Company Limited) | Approved | Closed | 2025-10-07 11:11:46 | No | Yes | 2025-08-29 17:32:13 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-07-29 |  | 2025-07-25 | Reungsak Junkong 00927496 | N/A | Closed | 2025-07-25 19:30:10 | No | No |  | *** Waiting on-service -- Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R Sec.1 |  | 2025-08-06 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-08-06 18:48:50 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-07-26 | 2025-07-22 |  | N/A | Closed | 2025-07-22 16:00:05 | No | No
WPBCM_2025 Coverage Expansion Ph2_EXP_BKK | WAT PHUTTHA BUCHA |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  | 2025-08-11 | 2025-08-13 | 2025-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-13 18:17:41 | Yes | Yes | 2025-08-20 11:45:39 |  | 2025-08-28 | 2025-08-28 | Aomchun Jittreemit | Approved | Closed | 2025-09-09 09:05:18 | Yes | Yes | 2025-08-28 08:22:33 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:27:14 |  | 2025-09-04 | 2025-09-04 | Aomchun Jittreemit | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 13:05:05 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-13 18:41:35 | No | No |  | 2025-08-13_Add RRU3953#， Replace to Ant 4 port Sector 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
WPNRM_2025 Capacity Expansion Ph8_EXP_ER | Wat Phanitaram | 2026-01-22 |  |  |  | 2026-02-28 | 2026-01-22 | 2026-01-22 | Teloneer Company Limited | N/A | Closed | 2026-01-22 15:22:23 | No | No |  |  |  | 2026-02-28 | 2026-01-22 | 2026-01-22 | Teloneer Company Limited | N/A | Closed | 2026-01-22 18:27:05 | Yes | Yes | 2026-01-23 17:21:35 |  | 2026-02-28 | 2026-01-23 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-02-13 10:42:51 | Yes | Yes | 2026-01-23 20:46:00 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:02 | Yes | Yes | 2026-04-09 11:38:50 |  | 2026-01-31 | 2026-01-22 | Adisak Chanmao(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-01-22 18:27:49 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-22 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-01-22 18:22:07 | No | No |  | Add UBBPg3a New L26F5 + NR26 (New AAU5636w)_WPNRM_N_1 New L26F5 + NR26 (New AAU5636w)_WPNRM_N_3 |  | 2026-01-23 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-10 10:55:21 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WPPMM_2025 Coverage Expansion Ph2_EXP_BKK | WAT PAN PRASITTHARAM |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-09 | 2025-08-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-09 16:02:53 | Yes | Yes | 2025-08-14 19:58:03 |  | 2025-08-19 | 2025-08-19 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-25 17:35:50 | Yes | Yes | 2025-08-30 22:01:16 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:20 | Yes | Yes | 2025-09-04 15:47:25 |  | 2025-08-30 | 2025-08-30 | Godchakon Kampan(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-08-30 21:42:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-09 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-09 18:06:38 | No | No |  | 09-08-2025. Add RRU3953 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
WPWSM_2025 Capacity Expansion Ph3_EXP_BKK | WAT PANCHATHAYIKAWAT SCHOOL | 2025-09-03 |  |  |  | 2025-08-26 | 2025-08-26 | 2025-08-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-26 18:32:59 | No | No |  |  |  | 2025-08-31 | 2025-09-02 | 2025-09-03 | V Contribute Co., Ltd | N/A | Closed | 2025-09-03 16:12:22 | Yes | Yes | 2025-09-03 16:13:18 |  | 2025-09-09 | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-23 22:28:06 | Yes | Yes | 2025-12-30 17:07:22 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-12-31 | 2025-09-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:49 | Yes | Yes | 2025-10-07 01:34:49 |  |  | 2025-09-09 | Chonradee Suwapan | Approved | Closed | 2025-09-24 22:18:14 | No | Yes | 2025-09-09 19:07:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-26 16:58:07 | No | No |  | 26-08-2025. Replace RRU5516 L18 Sec.3#， move RRU3962 to Sec.8 4T4R |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-25 |  | N/A | Not assigned |  | No | No
WSLTM_2025 Coverage Expansion Ph2_EXP_BKK | WAT SAMRONGTAI | 2025-08-19 |  |  |  | 2025-08-19 | 2025-08-19 | 2025-08-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-19 18:17:20 | No | No |  |  |  | 2025-08-29 | 2025-08-24 | 2025-08-24 | V Contribute Co., Ltd | N/A | Closed | 2025-08-24 17:31:46 | Yes | Yes | 2025-08-24 17:32:15 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-15 17:01:13 | Yes | Yes | 2025-09-02 18:28:58 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:40:49 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-02 17:27:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-19 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-19 17:45:16 | No | No |  | 19-08-2025. Add RRU3953 Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-18 |  | N/A | Not assigned |  | No | No
WSNIM_2025 Capacity Expansion Ph8_EXP_ER | Wat Sampatuannai | 2026-03-10 |  | Clear Alarm |  | 2026-02-28 | 2026-01-16 | 2026-01-16 | Teloneer Company Limited | N/A | Closed | 2026-01-16 17:47:18 | No | No |  |  |  | 2026-02-28 | 2026-01-16 | 2026-01-17 | Teloneer Company Limited | N/A | Closed | 2026-01-17 15:26:36 | Yes | Yes | 2026-01-23 20:52:07 |  | 2026-02-28 | 2026-02-12 | Apichat fangsantthia(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-12 14:43:50 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-17 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:02 | Yes | Yes | 2026-04-09 11:39:27 |  | 2026-01-31 | 2026-01-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-01-16 11:29:32 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-03-10 17:41:33 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WSNIM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WSNIM_H_4 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_WSNIM_L_4 |  | 2026-03-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-03-11 12:18:20 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-03-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WSNOM_2025 Capacity Expansion Ph7_EXP_ER | Wang SueaNoi | 2025-12-25 |  | Clear Alarm |  | 2025-12-31 | 2025-12-11 | 2025-12-11 | Teloneer Company Limited | N/A | Closed | 2025-12-11 16:27:32 | No | No |  |  |  | 2025-12-31 | 2025-12-11 | 2025-12-17 | Teloneer Company Limited | N/A | Closed | 2025-12-17 16:55:23 | Yes | Yes | 2025-12-18 18:45:20 |  | 2025-12-31 | 2025-12-18 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-21 19:02:14 | Yes | Yes | 2025-12-18 19:57:52 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:03 | Yes | Yes | 2026-03-27 17:12:27 |  | 2025-12-31 | 2025-12-11 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-13 21:12:48 | Yes | Yes | 2025-12-11 14:24:48 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-25 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-25 18:54:24 | No | No |  | Replace UBBPg1 to UBBPg3a New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_WSNOM_L_3 |  | 2025-12-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-12-12 14:48:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WSRIM_2025 Coverage Expansion Ph2_EXP_BKK | WONG SIRI RD. |  |  |  |  | 2025-08-06 | 2025-08-06 | 2025-08-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-06 17:03:49 | No | No |  |  | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-07 | V Contribute Co., Ltd | N/A | Closed | 2025-08-07 15:57:27 | Yes | Yes | 2025-08-07 15:58:00 |  | 2025-08-25 | 2025-08-25 | Chonradee Suwapan | Approved | Closed | 2025-08-26 09:26:48 | Yes | Yes | 2025-08-25 09:17:30 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-27 | 2025-08-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:12 | Yes | Yes | 2025-08-26 20:08:29 |  | 2025-08-13 | 2025-08-13 | Annop Auyto | Approved | Closed | 2025-09-03 22:42:08 | No | Yes | 2025-08-13 13:14:36 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-06 16:58:00 | No | No |  | 06-08-2025. Add RRU3953 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-05 |  | N/A | Not assigned |  | No | No
WSROM_2025 Coverage Expansion Ph2_EXP_BKK | Soi Wat Samrongtai | [5 empty] | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-21 | 2025-08-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-21 14:37:26 | Yes | Yes | 2025-08-22 16:06:45 |  | 2025-08-22 | 2025-08-27 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-08 16:35:17 | Yes | Yes | 2025-08-27 14:36:08 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:43:23 |  | 2025-09-03 | 2025-09-03 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-03 10:35:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-21 18:34:48 | No | No |  | 21-08-2025. Add RRU3953#， Replace Ant.12 port Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Hold เบิกของ 6/8/25 solution เปลี่ยน 14/8/25 แจ้งเบิกของใหม่ |  | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
WSRVM_2025 Capacity Expansion Ph6_EXP_ER | Warasiri2 Village | 2025-11-07 | Thcp_adirek.kh | Install & Integrate |  | 2025-11-30 | 2025-11-07 | 2025-11-07 | Teloneer Company Limited | N/A | Closed | 2025-11-07 16:25:10 | No | No |  |  |  | 2025-11-30 | 2025-11-10 | 2025-11-10 | Teloneer Company Limited | N/A | Closed | 2025-11-10 21:23:07 | Yes | Yes | 2025-11-12 07:09:09 |  | 2025-11-30 | 2025-11-15 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-17 09:58:56 | Yes | Yes | 2025-11-15 15:29:17 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-10 01:02:37 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:12 | Yes | Yes | 2025-11-04 11:21:18 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-07 17:57:49 | No | No |  | Add UBBPg3a #，Remove Antenna + (New AAU5768) + Main Dir = 230 + Remove 2RRU5505 x 2 S3 #，(Co AAU5768) + Main Dir = 230 + Remove 2RRU5505 x 2 S3 #，Replace 1RRU5508 to (RRU5516_900) + 4T4R S3#，New Sector M#，N (Co AAU5768) + Main Dir = 230 |  | 2025-11-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-07 17:57:49 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WSTKM_2025 Capacity Expansion Ph6_EXP_BKK | WAT SAD THONGKHLANG | [5 empty] | 2025-12-23 | 2025-12-23 | Akhom Srinara | N/A | Closed | 2025-12-23 19:02:27 | No | No |  |  |  | 2025-12-22 | 2025-12-23 | 2025-12-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-23 16:47:23 | Yes | Yes | 2025-12-26 20:28:05 |  | 2025-12-29 | 2026-02-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-05-22 16:35:49 | Yes | Yes | 2026-02-26 19:55:38 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-05-01 | 2026-02-25 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-08 | 2026-01-08 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-03-12 10:15:22 | Yes | Yes | 2026-01-08 18:23:57 |  |  | 2025-12-31 | 2025-12-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-12-22 16:37:41 | No | No |  |  |  |  | 2025-12-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-12-22 15:11:05 | No | No |  | 22-Dec-2025 Add AAU5636w Sector 8#， AAU5614 Sector 1 20-12-2025. ***Need AIRU5636w Sec.8#， AIRU5614 Sec.1 //Add UBBPg3a x2#， UBBPg2#， Remove UBBPd6#， UBBPeb#， UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WSTOM_2025 Capacity Expansion Ph7_EXP_BKK | WAT SOI THONG |  |  |  |  | 2026-01-15 | 2026-01-15 | 2026-01-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-01-31 | 2026-01-25 | 2026-04-07 | V Contribute Co., Ltd | N/A | Closed | 2026-04-07 16:13:31 | Yes | Yes | 2026-04-07 16:13:31 |  | 2026-02-05 | 2026-02-11 | Chonradee Suwapan | Approved | Closed | 2026-03-12 11:43:46 | Yes | Yes | 2026-02-25 17:34:21 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:56 | Yes | Yes | 2026-04-09 13:50:08 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:04 | Yes | Yes | 2026-02-05 22:23:09 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-15 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-15 18:20:12 | No | No |  | 15 Jan 2026 Add AAU5636w sector 7#， Add card g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WT38M_2025 Capacity Expansion Ph2_EXP_BKK | SOI WACHIRATHAM SATHIT 38 |  |  |  | 2025-08-18 | 2025-08-31 | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-19 | 2025-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-20 13:38:03 | Yes | Yes | 2026-03-18 18:20:44 |  | 2025-08-28 | 2025-08-28 | Kontira Kowapradit | Approved | Closed | 2025-09-15 17:01:13 | Yes | Yes | 2025-08-29 10:32:10 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-15 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:44:36 |  | 2025-09-04 | 2025-09-04 | Kontira Kowapradit | Approved | Closed | 2025-11-06 09:29:42 | No | Yes | 2025-09-04 18:01:45 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-19 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-19 17:45:16 | No | No |  | 19-08-2025. Add AIRU5636w Sec.1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
WTGWM_2025 Capacity Expansion Ph7_EXP_ER | Water Treatment Plant Gateway | 2025-12-06 | THCP_Wachira.s | Install & Integrate |  | 2025-12-31 | 2025-12-06 | 2025-12-06 | Teloneer Company Limited | N/A | Closed | 2025-12-06 15:24:14 | No | No |  |  |  | 2025-12-31 | 2025-12-06 | 2025-12-09 | Teloneer Company Limited | N/A | Closed | 2025-12-09 11:36:16 | Yes | Yes | 2025-12-13 12:28:48 |  | 2025-12-31 | 2025-12-13 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-12-18 11:28:08 | Yes | Yes | 2025-12-13 13:59:09 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:03 | Yes | Yes | 2026-03-27 17:14:21 |  | 2025-12-31 | 2025-12-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-12-10 18:37:44 | Yes | Yes | 2025-12-06 11:05:22 |  | 2025-12-06 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-06 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-12-06 18:21:28 | No | No |  | "Replace UBBPg1 to UBBPg2 Replace Antenna (Dualbeam)_WTGWM_H_3 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_WTGWM_H_8" |  | 2025-12-06 | Panupong Saiyod WX1434739 | N/A | Closed | 2025-12-06 20:49:08 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTHBA_2025 Coverage Expansion Ph1_New_BKK | Wat Thongbon | [5 empty] | 2025-11-22 | 2025-11-22 | Akhom Srinara | N/A | Closed | 2025-11-26 16:34:53 | No | No |  |  |  |  | 2025-11-11 | 2025-11-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-13 12:02:38 | Yes | Yes | 2025-11-18 15:53:40 |  | 2025-11-24 | 2025-11-24 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2025-11-24 08:35:49 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-11-29 | 2025-11-29 | Muhamadnase Chesamae | Approved | Closed | 2026-03-12 09:24:43 | No | Yes | 2025-11-29 14:56:47 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-11 17:27:12 | No | No |  | 11-Nov-2025 Add BBU3900 Add RRU3962 S1 S2 S3 Add Ant 8port S1 S2 No Ret S3 Ant 12port No ret D5=3 Run NB Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
WTKOM_2025 Capacity Expansion Ph2_EXP_BKK | WAT KO SUWANNARAM |  |  |  | 2025-09-03 | 2025-09-10 | 2025-09-14 | 2025-09-14 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2025-10-01 20:45:49 | No | No |  |  | 2025-09-10 | 2025-09-13 | 2025-09-11 | 2025-09-12 | Teloneer Company Limited | N/A | Closed | 2025-09-15 10:22:17 | Yes | Yes | 2025-09-15 10:22:18 |  |  | 2025-09-15 | Apichart Kampuang | Approved | Closed | 2025-09-30 15:29:15 | Yes | Yes | 2025-10-17 17:29:31 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-09-30 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:49 | Yes | Yes | 2025-10-07 01:46:09 |  | 2025-08-31 | 2025-08-31 | Teloneer Company Limited | Approved | Closed | 2025-10-10 17:28:56 | No | Yes | 2025-08-31 16:53:28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-09-04 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-09-04 18:31:27 | No | No |  | 04-09-2025. Add UBBPg2#， RRU5516 L900#， Ant.4 port Sec.3 //2025-09-03_Pre work |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 100% |  | 2025-09-13 |  | N/A | Not assigned |  | No | No
WTM2A_2025 Capacity Expansion Ph2_EXP_BKK | WANGTIM MANSION 2 | 2025-09-22 |  |  |  | 2025-11-25 | 2025-11-25 | 2025-11-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-11-25 12:46:41 | No | No |  |  |  | 2025-09-30 | 2025-10-03 | 2025-10-16 | V Contribute Co., Ltd | N/A | Closed | 2025-10-16 14:23:09 | Yes | Yes | 2025-10-16 14:23:09 |  | 2025-12-02 | 2025-12-02 | Chonradee Suwapan | Approved | Closed | 2025-12-16 15:59:15 | Yes | Yes | 2025-12-02 20:27:29 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-12-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:33 | Yes | Yes | 2026-01-15 15:37:03 |  | 2025-12-02 | 2025-12-02 | Chonradee Suwapan | Approved | Closed | 2025-12-09 15:58:58 | No | Yes | 2025-12-02 20:40:55 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-24 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-24 16:43:44 | No | No |  | 27-Nov-2025 Add UBBPg3a 24-Nov-2025 Add RU5818 Sector C AAU5246 Sector B Need Add g3a =1 on cell 23-Sep-2025 Add RRU5818 SA Add g3a GPS 2025-09-22_Replace to BBU5900 by UMPTg2#， Add UBBPg3a#， GPS#， Add RRU5818 Sector A#， ***Pending RRU5818 Sector C#， AAU5246 Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-11-24 |  | N/A | Not assigned |  | No | No
WTPBM_2025 Capacity Expansion Ph6_EXP_ER | wat thepphabut | 2025-11-11 | thcp_wachira.s | Install & Integrate |  | 2025-11-30 | 2025-11-11 | 2025-11-11 | Teloneer Company Limited | N/A | Closed | 2025-11-11 14:37:53 | No | No |  |  |  | 2025-11-30 | 2025-11-12 | 2025-11-12 | Teloneer Company Limited | N/A | Closed | 2025-11-12 18:25:58 | Yes | Yes | 2025-11-13 15:04:47 |  | 2025-11-30 | 2025-11-15 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2025-11-19 13:29:19 | Yes | Yes | 2025-11-15 15:23:33 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:32 | Yes | Yes | 2026-01-10 01:09:51 |  | 2025-11-25 | 2025-11-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2025-11-04 14:36:39 | Yes | Yes | 2025-11-04 09:28:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-11 17:06:54 | No | No |  | **waiting on-service LNR26 -- Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R WTPBM_H_2 ReSectorname S2 to S3 WTPBM_L_3 ReSectorname S3 to S8 WTPBM_L_8 New L26F5 + NR26 (New AAU5636w) WTPBM_N_3#，8 |  | 2025-11-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2025-11-12 16:15:41 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTPWM_2025 Coverage Expansion Ph2_EXP_BKK | SOI WATTHIPPAWAS |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  |  |  | 2025-08-13 | 2025-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-13 18:14:19 | Yes | Yes | 2025-08-19 10:52:05 |  | 2025-08-20 | 2025-08-20 | Muhamadnase Chesamae | Approved | Closed | 2025-08-29 16:53:48 | Yes | Yes | 2025-08-20 10:03:22 |  | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-30 | 2025-08-29 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:16:20 | Yes | Yes | 2025-09-04 15:52:35 |  | 2025-09-04 | 2025-09-04 | Muhamadnase Chesamae | Approved | Closed | 2025-11-06 09:30:15 | No | Yes | 2025-09-04 14:56:49 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-13 19:11:35 | No | No |  | 13-Aug-2025 Add RRU3953 S1 S2 Replace Ant.S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
WTWAM_2025 Capacity Expansion Ph8_EXP_ER | Wat Wang au | 2026-02-03 |  |  |  | 2026-02-28 | 2026-02-03 | 2026-02-03 | Teloneer Company Limited | N/A | Closed | 2026-02-03 10:26:34 | No | No |  |  |  | 2026-02-28 | 2026-02-04 | 2026-02-04 | Teloneer Company Limited | N/A | Closed | 2026-02-04 15:18:11 | Yes | Yes | 2026-02-04 18:47:35 | SQC Close | 2026-02-28 | 2026-02-12 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-12 15:13:27 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-02 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:02 | Yes | Yes | 2026-04-09 11:40:23 |  | 2026-01-31 | 2026-02-03 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:17:17 | Yes | Yes | 2026-02-03 07:50:26 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-02 17:48:22 | No | No |  | "Replace Antenna (MB) + Replace RRU5526 + 4T4R_WTWAM_H_4 Replace RRU (RRU5516_900) + 4T4R_WTWAM_L_4 New L26F5 + NR26 (New AAU5636w)_WTWAM_N_4 " |  | 2026-02-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-03 18:00:53 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WVPMM_2025 Capacity Expansion NW Modernization_EXP_BKK | Wave Place Macro |  |  |  |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:44:49 | No | No |  |  |  | 2026-02-28 | 2026-03-20 | 2026-03-20 | V Contribute Co., Ltd | N/A | Closed | 2026-03-20 10:50:46 | Yes | Yes | 2026-03-20 10:50:47 |  | 2026-03-25 | 2026-03-25 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-05-20 21:28:10 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-25 | 2026-03-25 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-25 21:57:28 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-21 14:05:24 | No | No |  | 21-Feb-2026 Add AAU5768 S2 Remove RRU502 Remove Ant *1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WWBWM_2025 Coverage Expansion Ph2_EXP_BKK | WONGWAEN BANGWAEK | [5 empty] | 2025-08-25 | 2025-08-25 | Akhom Srinara | N/A | Closed | 2025-08-25 10:15:00 | No | No |  |  |  |  | 2025-08-23 | 2025-08-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-24 14:37:19 | Yes | Yes | 2025-08-25 17:26:21 |  | 2025-08-26 | 2025-08-26 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-09 09:05:18 | Yes | Yes | 2025-09-19 17:15:58 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:48:21 |  | 2025-09-02 | 2025-09-02 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-09-03 11:58:36 | No | Yes | 2025-09-02 20:38:07 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-23 18:18:36 | No | No |  | 23-Aug-2025 Add RRU3953 S1 S2 S3 Replace Ant 4port S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Hold เบิกของ 6/8/25 solution เปลี่ยน 14/8/25 แจ้งเบิกของใหม่ |  | 2025-08-24 | Jia Rui 80023782 | N/A | Closed | 2025-08-27 15:38:01 | No | No
WYMSM_2025 Small DC Inb Cov Ex_Ph1 | Wang Yen Moo 3 |  |  |  | N/A | 2026-02-28 | N/A | 2026-01-05 | Teloneer Company Limited | N/A | Closed | 2026-01-05 15:50:49 | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WYNWM_2025 Capacity Expansion NW Modernization_EXP_BKK | WAT YANNAWA | [5 empty] | 2026-02-23 | 2026-02-23 | Akhom Srinara | N/A | Closed | 2026-02-23 17:44:37 | No | No |  |  | 2026-01-23 | 2026-01-31 | 2026-01-31 | 2026-02-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-02-21 18:09:06 | Yes | Yes | 2026-05-28 13:36:40 |  | 2026-05-29 | 2025-05-30 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-09-04 20:51:35 | Yes | Yes | 2026-05-30 21:37:51 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-06-19 | 2026-06-19 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-19 15:23:48 | Yes | Yes | 2026-06-19 09:51:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-28 18:23:24 | No | No |  | 2026-01-29_Add RRU3959 Sector 3.2#， 8.2//28-01-2026. Replace RRU3953 to RRU5516 Sec.2#， RRU5502 to AAU5768 Sec.3 //27-Jan-2025 Add RRU5516 (700900) Sector 1 Remove RRURRU3953 *1 Replace Ant 8port Add AAU5768 Sector1 Remove RRU3962 S1 Add g3a Remove eb Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
XTSPM_2025 Capacity Expansion NW Modernization_EXP_BKK | SUAN PHLU MARKET |  |  |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-02 16:43:53 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-02-25 | 2026-02-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-25 14:56:52 | Yes | Yes | 2026-02-27 12:41:11 |  | 2026-03-02 | 2026-03-02 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-24 09:32:47 | Yes | Yes | 2026-03-02 16:46:07 | Pg-22 Need to upload AAU M-Tilt photo for S3. ( not update yet) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-20 | 2026-08-24 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 20:23:08 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-10 19:46:59 | No | No |  | 10-02-2026. Add UBBPg2#， UBBPg3a#， Replace RRU5507 to AAU5768 Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YANIM_2025 Coverage Expansion Ph2_EXP_BKK | SOI YANIMPATTANA |  |  |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-13 18:57:01 | No | No |  |  |  | 2025-08-29 | 2025-08-14 | 2025-08-14 | V Contribute Co., Ltd | N/A | Closed | 2025-08-14 11:17:34 | Yes | Yes | 2025-08-14 11:17:54 |  | 2025-09-02 | 2025-09-02 | Chonradee Suwapan | Approved | Closed | 2025-09-05 17:11:19 | Yes | Yes | 2025-09-02 18:29:36 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2025-09-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:14:58 | Yes | Yes | 2025-09-23 04:50:48 |  | 2025-09-01 | 2025-09-01 | Chonradee Suwapan | Approved | Closed | 2025-09-03 22:44:51 | No | Yes | 2025-09-01 02:22:52 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-13 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2025-08-13 18:41:35 | No | No |  | 2025-08-13_Replace to UBBPd6(2)#， Add RRU3953#， No act Ant Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-12 |  | N/A | Not assigned |  | No | No
YANSM_2025 Capacity Expansion Ph7_EXP_SR | Yan Seu |  |  |  | 2025-12-27 | 2025-12-27 | 2025-12-27 | 2025-12-27 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-12-27 15:42:29 | No | No |  |  |  | 2025-12-28 | 2025-12-27 | 2025-12-29 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-12-29 10:53:06 | Yes | Yes | 2026-01-09 11:29:08 |  | 2026-01-13 | 2026-01-13 | Rosak soko | Approved | Closed | 2026-01-27 11:48:49 | Yes | Yes | 2026-01-13 12:24:14 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:59 | Yes | Yes | 2026-03-20 11:27:20 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-29 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-27 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-12-27 18:10:35 | No | No |  | Add AAU5636w Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YBKKM_2025 Capacity Expansion Ph2_EXP_BKK | YAEK BANGNA-KINGKAEW |  |  |  |  | 2025-10-15 | 2025-10-15 | 2025-10-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-10-15 11:01:33 | No | No |  |  |  | 2025-10-17 | 2025-10-07 | 2025-10-15 | V Contribute Co., Ltd | N/A | Closed | 2025-10-15 17:20:35 | Yes | Yes | 2025-10-15 17:20:36 |  | 2025-10-18 | 2025-10-18 | Chonradee Suwapan | Approved | Closed | 2025-10-27 16:54:48 | Yes | Yes | 2025-10-18 20:20:08 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-11-13 09:24:28 | Yes | Yes | 2025-10-29 15:42:28 |  | 2025-10-18 | 2025-10-18 | Chonradee Suwapan | Approved | Closed | 2025-11-13 14:15:56 | No | Yes | 2025-10-18 20:29:01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-10-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-10-07 17:18:36 | No | No |  | 07-10-2025. Add RRU5516 L18 Sec.7#， Replace Ant.12 port Sec.2#， 7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-10-14 |  | N/A | Not assigned |  | No | No
YNCKM_2025 Coverage Expansion Ph2_EXP_BKK | YAEK NONG CHOK |  |  |  |  | 2025-08-31 | 2025-08-14 | 2025-08-14 | Akhom Srinara | N/A | Closed | 2025-08-14 12:09:28 | No | No |  |  | 2025-08-08 |  | 2025-08-08 | 2025-08-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-08-08 22:33:46 | Yes | Yes | 2025-08-13 12:32:17 |  | 2025-08-13 | 2025-08-15 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-08-22 17:57:48 | Yes | Yes | 2025-08-15 17:45:50 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:12 | Yes | Yes | 2025-08-26 20:12:30 |  | 2025-09-03 | 2025-09-03 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-11-06 09:30:33 | No | Yes | 2025-09-03 19:48:00 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-08 | Puthipat Thanosawan WX630156 | N/A | Closed | 2025-08-08 17:37:04 | No | No |  | 08-08-2025. Add RRU3953#， Replace Ant.4 port Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-08-14 | 2025-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2025-08-15 14:02:57 | No | No
YNGNM_2025 Capacity Expansion Ph4_EXP_SR | Yaek Nongnin |  |  |  | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | Nattawoot Suwan | N/A | Closed | 2025-11-10 21:05:07 | No | No |  |  |  | 2025-09-26 | 2025-11-04 | 2025-11-04 | Teloneer Company Limited | N/A | Closed | 2025-11-04 16:38:36 | Yes | Yes | 2025-11-05 10:17:04 |  | 2025-11-05 | 2025-11-05 | Nattawoot Suwan | Approved | Closed | 2025-11-09 20:09:44 | Yes | Yes | 2025-11-10 21:17:14 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-18 | 2025-11-18 | Chayanat mangmool WX1323423 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-02 00:57:30 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-11-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-11-04 | Laddawan Wannasri WX1434742 | N/A | Closed | 2025-11-04 17:09:14 | No | No |  | 4 Nov 2025 Add AAU5636w sector4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-11-03 |  | N/A | Not assigned |  | No | No
YNPOA_2025 Capacity Expansion NW Modernization_EXP_BKK | YANNAWA POST OFFICE |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-02-24 | 2026-02-24 | 2026-03-04 | 2026-03-05 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-05 12:02:38 | Yes | Yes | 2026-03-12 11:18:14 |  | 2026-03-25 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-05-22 16:35:49 | Yes | Yes | 2026-05-19 14:46:33 | Page no.10#， need to upload before antenna INV. Page no.6#， remove breaker is 32A #，not 10A. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 20:26:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-18 17:48:09 | No | No |  | 18-02-2026. Add UBBPg2#， Replace RRU3962 to RRU5526#， Ant.12 port Sec.A#， B#， C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YNPOB_2025 Capacity Expansion NW Modernization_EXP_BKK | YANNAWA POST OFFICE |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:53:54 | Yes | Yes | 2026-03-24 14:17:38 |  | 2026-04-20 | 2026-04-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:51:35 | Yes | Yes | 2026-04-20 13:30:24 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-11 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 20:23:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-18 17:48:09 | No | No |  | 18-02-2026. Replace RRU3962 to RRU5526#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YRWSH_2025 Capacity Expansion Ph4_EXP_SR | Yuppharat Wiang Sa Hospital |  |  |  | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-13 | Teloneer Company Limited | N/A | Closed | 2025-11-10 09:15:00 | No | No |  |  |  | 2025-09-26 | 2025-10-11 | 2025-10-13 | Teloneer Company Limited | N/A | Closed | 2025-10-13 16:08:18 | Yes | Yes | 2025-10-14 10:01:16 |  | 2025-10-15 | 2025-10-15 | Anucha Borikut | Approved | Closed | 2025-10-20 10:35:19 | Yes | Yes | 2025-11-04 10:18:12 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-11-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:35:18 | Yes | Yes | 2025-12-02 01:01:07 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-10-11 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2025-10-11 | 2025-10-11 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-10-11 17:59:45 | No | No |  | Add new S1 5516LB > Ant 4 port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2025-10-09 |  | N/A | Not assigned |  | No | No
YS24M_2025 Capacity Expansion Ph5_EXP_BKK | SOI YU SUK 24 | [5 empty] | 2025-11-24 | 2025-11-24 | Akhom Srinara | N/A | Closed | 2025-12-12 12:48:31 | No | No |  |  |  | 2025-11-20 | 2025-11-20 | 2025-11-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2025-11-21 11:15:58 | Yes | Yes | 2025-11-26 16:56:43 |  | 2025-11-26 | 2025-11-26 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-18 16:45:53 | Yes | Yes | 2025-11-26 21:20:01 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-07 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-15 15:38:18 |  | 2025-12-18 | 2025-12-18 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2025-12-18 16:46:01 | Yes | Yes | 2025-12-18 15:31:20 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-20 17:35:44 | No | No |  | 20-Nov-2025 Add AAU5636m S7 Add g3a Remove d6 Replace Ant 12 port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YSBNM_2025 Capacity Expansion Ph5_EXP_BKK | YAEK SANAM BIN NAM | [5 empty] | 2025-11-21 | 2025-11-21 | Narongsak wanichachiwa | N/A | Closed | 2025-11-27 10:58:20 | No | No |  |  |  | 2025-11-18 | 2025-11-24 | 2025-11-24 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2025-11-24 12:05:29 | Yes | Yes | 2025-11-24 12:08:04 |  |  | 2025-11-25 | OATTAPAN AUTTAHON | Approved | Closed | 2025-12-16 16:00:28 | Yes | Yes | 2026-01-07 18:27:27 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2025-12-16 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:34:02 | Yes | Yes | 2026-01-10 01:22:18 |  | 2025-12-25 | 2025-12-25 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-03-12 10:15:38 | Yes | Yes | 2025-12-25 16:49:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2025-11-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-11-21 18:40:57 | No | No |  | 21-Nov-2025 AAU5636w S8 Add g3a Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YSMAI_2025 Capacity Expansion Ph6_EXP_SR | Yaek Sam Mai |  |  |  |  | 2025-12-28 | 2025-12-23 | 2025-12-23 | Teloneer Company Limited | N/A | Closed | 2025-12-23 17:54:06 | No | No |  |  |  | 2025-12-08 | 2025-12-23 | 2025-12-26 | Teloneer Company Limited | N/A | Closed | 2025-12-26 16:08:13 | Yes | Yes | 2026-01-05 08:25:22 |  | 2026-01-06 | 2026-01-06 | Nattawoot Suwan | Approved | Closed | 2026-01-26 10:02:12 | Yes | Yes | 2026-01-08 10:37:22 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-01-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:59 | Yes | Yes | 2026-03-19 18:25:20 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2025-12-23 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2025-12-23 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2025-12-23 19:53:51 | No | No |  | Rep card d6*1 to g2*1 Re LB S7>S3#，S3>S4 Re MB S2>S3#，S7>S8#，S3>S4 Re HB S7>S3#，S3>S4 Add AAU5768 Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YTTRM_2025 Coverage Expansion Ph2_EXP_BKK | YOTHATHIKAN NONTHABURI SUKSAWNAG ROAD | 2025-08-04 |  |  |  | 2025-08-04 | 2025-08-04 | 2025-08-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2025-08-04 14:49:49 | No | No |  |  |  | 2025-08-22 | 2025-08-05 | 2025-08-06 | V Contribute Co., Ltd | N/A | Closed | 2025-08-06 11:38:51 | Yes | Yes | 2025-08-06 11:38:58 |  | 2025-08-19 | 2025-08-19 | Chonradee Suwapan | Approved | Closed | 2025-08-25 17:35:18 | Yes | Yes | 2025-08-19 23:26:20 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-08-26 | 2025-08-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2025-10-09 11:17:12 | Yes | Yes | 2025-08-26 20:13:48 |  | 2025-08-05 | 2025-08-05 | Annop Auyto | Approved | Closed | 2025-09-03 22:40:47 | No | Yes | 2025-08-05 09:10:19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2025-08-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2025-08-04 18:26:44 | No | No |  | 4-Aug-2025 Add RRU3953 S2 Replace Ant. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Completed |  | 2025-08-01 |  | N/A | Not assigned |  | No | No
ZSRSM_2025 Capacity Expansion NW Modernization_EXP_BKK | ZENSATION THE RESIDENSE |  |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-07 07:32:17 | No | No |  |  |  | 2026-02-07 | 2026-02-23 | 2026-03-05 | V Contribute Co., Ltd | N/A | Closed | 2026-03-05 20:33:48 | Yes | Yes | 2026-03-05 20:33:49 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-17 16:38:08 | Yes | Yes | 2026-03-13 10:36:46 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:56 | Yes | Yes | 2026-04-09 13:54:36 |  | 2026-02-05 | 2026-02-05 | Chonradee Suwapan | Approved | Closed | 2026-02-13 09:52:32 | Yes | Yes | 2026-02-05 22:25:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-21 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-21 19:00:21 | No | No |  | 21-Jan-2026 Add AAU5768 Sector 1#，2 Remove RRU5507 *4 Remove RRU3962 *2 S2 Add RRU5526 sector 3 Remove RRU3962 *2 Add g3a Remove d5 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
41IBM_2025 Capacity Expansion NW Modernization_EXP_BKK | 4-1 INFANTRY BATTALION (KINGS GUARDS) |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:47:23 | No | No |  |  | 2026-03-31 | 2026-03-31 | 2026-03-23 | 2026-06-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-02 09:40:37 | Yes | Yes | 2026-06-02 11:43:20 |  | 2026-06-09 | 2026-06-09 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approving | Assigned |  | Yes | Yes | 2026-06-09 11:24:25 | bbp 1 eb 98 1.Page 6#，In SOW need to fill remove ANT model. 2.Page 62#，AIS passport have 2pcs but team member have 3person.(need to upload another passport) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:55:44 | Yes | Yes | 2026-07-14 22:35:54 |  |  | 2026-03-31 | 2026-08-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-08-10 18:21:47 | No | No |  |  |  |  | 2026-03-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-03-28 17:14:25 | No | No |  | 28-03-2026. Replace RRU3962 to 5507#， Ant.8 port Sec.1#， to AAU5768 Sec.2#， 3#， UBBPeb to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
5S4AB_2025 Capacity Expansion NW Modernization_EXP_BKK | 5 STAR 4 APARMENT |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:47:23 | No | No |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-05-06 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-06 10:33:54 | Yes | Yes | 2026-05-06 10:36:45 |  | 2026-05-31 | 2026-05-31 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-06-04 16:56:28 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:55:44 | Yes | Yes | 2026-08-01 19:51:50 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-17 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-03-17 19:31:56 | No | No |  | 2026-03-16_Replace to BBU5900 by UMPTg2#， Add UBBPg2#， GPS#， Repalcr RRU3962 to RRU5507(2) Sector A#，B#，C //16 Mar 2026 Replace RRU5507 sectorA#，B only |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A183A_2026 Capacity Expansion NW Modernization_EXP_BKK | TOT Pole SOI RAEWADI 31/1 | [5 empty] | 2026-09-22 | 2026-09-22 | Thossapan Chaloemrit | N/A | Closed | 2026-09-23 21:55:28 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 16:09:33 | No | No |  |  |  |  | 2026-09-18 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-18 18:53:14 | No | No |  | 2026-09-18 SA Replace RRU3962 to RRU5502#， Replace to Ant TS-698-2700-10-14-4(43) SB Replace RRU3962 to RRU5507 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A184A_2026 Capacity Expansion NW Modernization_EXP_BKK | REWADI RD. (NONTHABURI 6) | [5 empty] | 2026-09-22 | 2026-09-22 | Thossapan Chaloemrit | N/A | Closed | 2026-09-23 21:55:28 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 16:16:19 | No | No |  |  |  |  | 2026-09-18 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-18 18:53:14 | No | No |  | 2026-09-22 clear pending 2026-09-18_Replace UBBPd5 to UBBPg3 SA Replace RRU3962 to RRU5502 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A185A_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI NEAM PREM | [5 empty] | 2026-09-22 | 2026-09-22 | Thossapan Chaloemrit | N/A | Closed | 2026-09-23 21:55:28 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 16:23:31 | No | No |  |  |  |  | 2026-09-21 | Methat Shoeisawat 84327465 | N/A | Closed | 2026-09-21 16:57:29 | No | No |  | 20260921 Sector A 18/21 Replace RRU3962 to RRU5507 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A186A_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI WAT SAMONRAKOT | [5 empty] | 2026-09-22 | 2026-09-22 | Thossapan Chaloemrit | N/A | Closed | 2026-09-23 21:55:28 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 16:31:17 | No | No |  |  |  |  | 2026-09-21 | Methat Shoeisawat 84327465 | N/A | Closed | 2026-09-21 16:57:29 | No | No |  | 20260921 Sector A 18/21 Replace RRU3962 to RRU5507 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A311A_2026 Capacity Expansion NW Modernization_EXP_BKK | Nonthaburi Mansion | [5 empty] | 2026-09-21 | 2026-09-21 | Thossapan Chaloemrit | N/A | Closed | 2026-09-28 16:14:22 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 12:20:38 | No | No |  |  |  |  | 2026-09-22 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-09-22 11:30:09 | No | No |  | 2026-09-22 sB replace RRU3962*2 to RRU5507*2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
A314A_2026 Capacity Expansion NW Modernization_EXP_BKK | Soi Nonthaburi 48_1 | [5 empty] | 2026-09-28 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-29 13:25:23 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 16:47:14 | No | No |  |  |  |  | 2026-09-28 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-09-28 19:39:55 | No | No |  | "2026/09/28 SA REP RRU3962 > RRU5507 Replace by BBU5900 + Replace by UMPTg2 + GPS Add Card to UBBPh2a" |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AB9VM_2025 Capacity Expansion Ph8_EXP_BKK | AEKBURI 9 VILLAGE |  |  |  |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-28 | 2026-02-18 | 2026-02-20 | V Contribute Co., Ltd | N/A | Closed | 2026-02-20 11:06:27 | Yes | Yes | 2026-02-20 11:06:28 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:25:25 | Yes | Yes | 2026-03-13 12:09:49 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-10 | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:53:15 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:16:39 | Yes | Yes | 2026-03-07 19:49:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-14 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-14 17:32:45 | No | No |  | 14-Feb-2026 Add AAU5636w Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ABHPM_2026 Capacity Expansion Ph2_EXP_ER | Anamai BanHuayprab | 2026-09-21 |  | Install & Integrate |  | 2026-09-30 | 2026-09-21 | 2026-09-21 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-22 07:14:32 | No | No |  |  |  | 2026-09-30 | 2026-09-22 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 17:57:43 | Yes | Yes | 2026-09-23 20:28:20 |  | 2026-09-30 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-25 21:08:48 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-21 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:42:32 | Yes | Yes | 2026-09-21 13:01:42 |  |  | 2026-09-30 | 2026-09-21 | Teloneer Company Limited | N/A | Closed | 2026-09-21 15:43:52 | No | No |  |  |  |  | 2026-09-21 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-21 18:18:55 | No | No |  | Add UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 260 + Remove RRU x 1_ABHPM_H_3 ReSectorname S4 to S8 + Remove Antenna + (Co AAU5775) + Main Dir = 260 + Remove RRU x 2_ABHPM_H_8 Add RRU5508 x 1 + 4T4R_ABHPM_L_3 New Sector M (Co AAU5775) + Main Dir = 260_ABHPM_H_M New Sector N (Co AAU5775) + Main Dir = 260_ABHPM_H_N |  | 2026-09-21 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-21 18:19:12 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ADDCB_2025 Capacity Expansion NW Modernization_EXP_BKK | The Address Chidlom |  |  |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-09 18:10:08 | No | No |  |  |  | 2026-02-28 | 2026-02-17 | 2026-03-08 | V Contribute Co., Ltd | N/A | Closed | 2026-03-08 19:09:25 | Yes | Yes | 2026-03-08 19:09:25 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 11:43:46 | Yes | Yes | 2026-03-07 19:36:15 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-22 | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:53:33 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:16:39 | Yes | Yes | 2026-03-07 19:53:18 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-13 18:58:33 | No | No |  | 13-Feb-26 Replace BBU3900 To RRU900 Replace RRU5526 S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AGWNM_2026 Capacity Expansion Ph1_EXP_ER | AngWian | 2026-07-11 | Team : thcp_apichat.f Tel : 0960126111 | Clear Pending | 2026-06-01 | 2026-07-20 | 2026-07-10 | 2026-07-10 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-11 10:10:51 | No | No |  |  |  | 2026-07-20 | 2026-07-11 | 2026-07-13 | Teloneer Company Limited | N/A | Closed | 2026-07-13 11:54:55 | Yes | Yes | 2026-07-13 21:25:11 |  | 2026-07-20 | 2026-07-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-27 16:14:05 | Yes | Yes | 2026-07-23 23:09:31 |  | Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:28:20 | No | Yes | 2026-09-12 10:28:06 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:45 | No | No |  |  | 2026-07-31 | 2026-07-03 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:42 | Yes | Yes | 2026-07-03 09:53:12 |  | 2026-07-13 | 2026-07-20 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 20:22:13 | No | No |  |  |  |  | 2026-07-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-10 22:15:02 | No | No |  | Change BBU5900A to BBU5900 + Add UBBPh3a + UBPPg3a_AGWNM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 120 + Remove RRU x 2_AGWNM_H_2 (Co AAU5775) + Main Dir = 120 + Remove RRU x 1_AGWNM_H_7 ReDirection 0 to 30_AGWNM_N_1 ReDirection 240 to 210 + Co NR26_AGWNM_N_3 New Sector J (Co AAU5775) + Main Dir = 120_AGWNM_H_J New Sector K (Co AAU5775) + Main Dir = 120_AGWNM_H_K New L26F5 + NR26 (New AAU5656)_AGWNM_N_8 |  | 2026-07-13 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-13 17:18:12 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-13 | Nattawoot Suwan | N/A | Closed | 2026-07-13 13:17:29 | No | No |  |  |  | Day1 : 50% , Day2 : 80% , Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AKBBM_2026 Capacity Expansion Modernize_EXP_ER | Apartment Kanboon TanonBangsan Sai 3 | 2026-09-08 | isdp : thcp_apichat.f Tel : 0960126111 |  |  | 2026-09-15 | 2026-09-08 | 2026-09-08 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-09 06:33:01 | No | No |  |  |  | 2026-09-15 | 2026-09-07 | 2026-09-09 | Teloneer Company Limited | N/A | Closed | 2026-09-09 18:12:45 | Yes | Yes | 2026-09-10 21:30:10 | 1.Need to upload remove Antenna SN photo in EQ 2.Need to upload Sector A before ground bar 3.Need to upload remove Antenna and RRU SN photo in before 4.Need to upload before master ground bar 5.Need to fill tower type | 2026-09-15 | 2026-09-22 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-22 23:32:36 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-16 | 2026-09-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:46:21 | Yes | Yes | 2026-09-08 13:14:43 |  |  | 2026-09-15 | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-08 14:39:52 | No | No |  |  |  |  | 2026-09-07 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-07 16:05:07 | No | No |  | Add UBBPg2 --revise to h2a Replace ant + Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_AKBBM_L_B --revise to rep 2*5508 Co L21(F2) SA#，SB#，SC |  | 2026-09-08 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-08 16:42:49 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : Wait change ant0% , Day2 : 80% Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AKW2M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI ATTAKRAWEE 2 | [5 empty] | 2026-03-24 | 2026-03-24 | Akhom Srinara | N/A | Closed | 2026-04-21 20:46:18 | No | No |  |  |  | 2026-02-24 | 2026-03-15 | 2026-03-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-03-26 09:30:39 | Yes | Yes | 2026-06-01 15:42:46 |  | 2026-06-01 | 2026-06-01 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-06-01 23:44:37 | 1.Page 7#，10#，SOW#，RRU INV & QC mismatch.(in QC only remove RRU 3pcs) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-06-19 | 2026-06-19 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-19 15:28:26 | Yes | Yes | 2026-06-19 09:31:25 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-11 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-11 16:58:00 | No | No |  | 11-Mar-26 Replace RRU5508 To RRU5516 S1 Replace RRU3953 TO RRU5516 S2 S3 26-Feb-2026 Clear Alarm GPS Done 24-Feb-2026 ****Pending Add RRU5516 S1 S2 S3 Remove RRU5508 S1 RRU3953 S2 RRU3953 S3 ////Add g3a g2 Remove d5 d6 Add AAU5768 S1 S3 Remove RRU5507 *4 RRU3826 *2 #， RRU5507*4 Remove RRU507*2 sector 2 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AMNKM_2026 Capacity Expansion Modernize_EXP_ER | Amata Co Tower Near Thai Nakano | 2026-08-04 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 17:34:48 | No | No |  |  |  | 2026-08-15 | 2026-08-05 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 17:29:12 | Yes | Yes | 2026-08-06 10:48:14 |  | 2026-08-20 | 2026-08-07 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:54:54 | Yes | Yes | 2026-08-07 21:55:17 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:25 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:13:53 |  |  | 2026-08-15 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 17:51:34 | No | No |  |  |  |  | 2026-08-04 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-04 18:19:18 | No | No |  | Add RRU5505 x 1 + 4T4R_AMNKM_H_6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ARI4M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI ARI 4 |  |  |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-19 15:33:07 | No | No |  |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-16 16:16:22 | Yes | Yes | 2026-06-19 10:51:05 |  | 2026-06-19 | 2026-06-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-07-07 16:24:19 | Yes | Yes | 2026-06-19 15:32:07 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:31:05 | Yes | Yes | 2026-07-14 22:37:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-06-15 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-06-15 17:37:42 | No | No |  | 15 Jun 2026 Replace RRU5507 sector1#，2 RRU5526 sector3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASC2M_2025 Capacity Expansion NW Modernization_EXP_BKK | ANUSAWALEE CHAI SAMORAPHUM 2 |  |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-27 13:27:45 | No | No |  |  |  | 2026-02-12 | 2026-03-12 | 2026-03-13 | V Contribute Co., Ltd | N/A | Closed | 2026-03-13 18:04:54 | Yes | Yes | 2026-03-13 18:04:54 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-09 09:30:25 | Yes | Yes | 2026-04-01 15:16:38 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:54:29 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-26 21:31:09 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-11 17:29:02 | No | No |  | 11-02-2026. Replace RRU5507 to AAU5768 Sec.1#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASNWB_2026 Capacity Expansion NW Modernization_EXP_BKK | ASPIRE NGAMWONGWAN | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ASREB_2025 Capacity Expansion NW Modernization_EXP_BKK | A SPACE ASOKE - RATCHADA (BUILDING E) |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:47:23 | No | No |  |  | 2026-03-25 | 2026-03-25 | 2026-03-26 | 2026-05-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-26 12:24:57 | Yes | Yes | 2026-05-26 12:27:49 |  | 2026-04-22 | 2026-04-29 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-02 09:19:52 | Yes | Yes | 2026-04-29 16:46:47 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:55:44 | Yes | Yes | 2026-07-14 22:39:10 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-13 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-13 17:32:46 | No | No |  | 13-Mar-26 Replace RRU3962 >> RRU5507*2 SA SB SC |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
AWBPM_2025 Capacity Expansion NW Modernization_EXP_BKK | ARMY WELFARE BUILDING PHYATHAI |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-17 16:22:25 | No | No |  |  |  | 2026-02-06 | 2026-02-02 | 2026-02-20 | V Contribute Co., Ltd | N/A | Closed | 2026-02-20 10:18:34 | Yes | Yes | 2026-02-20 10:18:34 |  | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-16 22:05:14 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:55:44 |  | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-16 22:21:33 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-02 19:21:08 | No | No |  | 2026-02-02_Replace RRU5507(4) to AAU5768 Sector 3#， Replace RRU3962(4) to AAU5768 Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B024A_2025 Capacity Expansion Ph8_EXP_BKK | Thetsaban Tambon Bang Pu 71_1 |  |  |  |  | 2026-07-08 | 2026-07-20 | 2026-07-20 | นายอภิชาติ ปางปัญญากุลชัย(Turnkey Communication Services Public Company Limited.) | N/A | Closed | 2026-07-20 21:02:47 | No | No |  |  |  | 2026-07-15 | 2026-07-17 | 2026-08-10 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-08-10 15:02:13 | Yes | Yes | 2026-08-10 20:29:04 |  | 2026-08-31 | 2026-08-11 | Oasawin Charmpoonote(Turnkey Communication Services Public Company Limited.) | Approved | Closed | 2026-10-02 02:13:27 | Yes | Yes | 2026-08-11 17:48:10 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-17 | 2026-07-17 | Narongsak wanichachiwa | Approving | Assigned |  | Yes | Yes | 2026-07-14 11:59:55 |  |  | 2026-08-01 | 2026-08-01 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-08-01 15:10:29 | No | No |  |  |  |  | 2026-07-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-07-10 17:07:57 | No | No |  | 10-Jul-2026 Add RRU5818 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B025A_2025 Capacity Expansion Ph8_EXP_BKK | Thetsaban Tambon Bang Pu 71_2 |  |  |  |  | 2026-07-08 | 2026-08-11 | 2026-08-11 | Oasawin Charmpoonote(Turnkey Communication Services Public Company Limited.) | N/A | Closed | 2026-08-11 08:32:46 | No | No |  |  |  | 2026-07-15 | 2026-07-21 | 2026-08-04 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-08-04 19:31:56 | Yes | Yes | 2026-08-04 21:26:51 |  |  | 2026-08-07 | Oasawin Charmpoonote | Approving | Assigned |  | Yes | Yes | 2026-08-07 17:08:45 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-17 | 2026-07-17 | Narongsak wanichachiwa | Approving | Assigned |  | Yes | Yes | 2026-07-14 13:14:09 |  |  | 2026-08-01 | 2026-08-01 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-08-01 15:15:34 | No | No |  |  |  |  | 2026-08-06 | Autumporn Masing WX1434753 | N/A | Closed | 2026-08-06 17:34:07 | No | No |  | 2026-07-10 alarm clear 10-Jul-2026 ***Pending Alarm power too low Add RRU5818 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B026A_2025 Capacity Expansion Ph8_EXP_BKK | Thetsaban Tambon Bang Pu 71_3 |  |  |  |  | 2026-07-08 | 2026-07-20 | 2026-07-20 | นายอภิชาติ ปางปัญญากุลชัย(Turnkey Communication Services Public Company Limited.) | N/A | Closed | 2026-07-20 21:02:47 | No | No |  |  |  | 2026-07-15 | 2026-07-21 | 2026-08-04 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-08-04 13:57:45 | Yes | Yes | 2026-08-04 20:13:02 |  | 2026-08-30 | 2026-08-05 | Oasawin Charmpoonote | Approving | Assigned |  | Yes | Yes | 2026-08-05 19:25:44 | Page 8 Add RRU qty Wrong . Page 18 Grounding Kit at bar ground and wraping tape Photo Need . Page 25 Dc-RRU photo Need. Page 33 Before and After C1 Alarm Chrome Photo Need. Page 45 Site Code Need. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-17 | 2026-07-17 | Narongsak wanichachiwa | Approving | Assigned |  | Yes | Yes | 2026-07-14 13:19:09 |  |  | 2026-08-01 | 2026-08-01 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-08-01 18:34:58 | No | No |  |  |  |  | 2026-07-09 | Autumporn Masing WX1434753 | N/A | Closed | 2026-07-09 23:02:08 | No | No |  | 2026-07-09 s1 add RRU5818 **Pending SFP 25G BBU Side#， RRU Side |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B486A_2026 Capacity Expansion Ph1_EXP_BKK | MUEANG MAI BANG PLI RD. STATION 2 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Thossapan Chaloemrit | Approving | Assigned |  | Yes | Yes | 2026-07-20 11:30:05 |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B508A_2026 Capacity Expansion Ph1_EXP_BKK | BANGPHI INDUSTRIAL ESTATE INTERSECTION (TOT POLE) | [5 empty] | 2026-08-21 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  |  | 2026-07-31 | 2026-08-24 | 2026-08-28 | Teloneer Company Limited | N/A | Closed | 2026-08-28 17:08:42 | Yes | Yes | 2026-09-03 10:17:37 |  | 2026-09-04 | 2026-09-03 | Khathahat Sitthihong(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-04 00:17:53 | page.5 need to revise DPU#，Antenna pcs page.5 GPS or GPS Surge(pls revise) page.5 need to upload remove breaker activity page.27 need to upload 700/900RRU Socket left and right | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-20 11:30:23 |  |  | 2026-06-30 | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-18 17:18:56 | No | No |  |  |  |  | 2026-08-18 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-08-18 18:43:10 | No | No |  | 2026-08-18 SA Replace AAU3940 > Add RRU3962 (18/21) 2T + Add RRU5872 (26) + Replace Ant 4port No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:02:43 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
B615A_2026 Capacity Expansion Ph2_BKK | JIRAWAT APARTMENT | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BACHO_2026 Capacity Expansion Ph1_EXP_SR | Bacho Hospital | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-18 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-18 | 2026-08-31 | 2026-09-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-18 20:32:16 | No | No |  |  |  |  | 2026-09-18 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-18 17:30:16 | No | No |  | S1 > Rep RRU3953*2 to RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BASBM_2025 Capacity Expansion Ph8_EXP_BKK | BUNG AI SIAB |  |  |  |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-17 | 2026-02-20 | V Contribute Co., Ltd | N/A | Closed | 2026-02-20 13:34:59 | Yes | Yes | 2026-02-20 13:34:59 |  | 2026-02-21 | 2026-02-21 | Chonradee Suwapan | Approved | Closed | 2026-03-04 09:57:31 | Yes | Yes | 2026-02-21 20:57:40 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:56:22 |  | 2026-02-21 | 2026-02-21 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-21 21:12:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-11 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-11 18:05:16 | No | No |  | 11-Feb-26 Add AAU5636w S1 S6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BBBDP_2026 Capacity Expansion NW Modernization_EXP_BKK | BB BUILDING | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BBCPN_2026 Capacity Expansion Ph1_EXP_SR | BEHIND BIG C PATTANI | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-21 | 2026-09-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-28 12:04:05 | Yes | Yes | 2026-10-01 19:25:33 |  | 2026-10-01 | 2026-10-01 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-10-01 21:11:57 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-10-01 | 2026-10-01 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-10-01 21:18:12 |  | 2026-09-20 | 2026-08-31 | 2026-09-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-21 16:25:30 | No | No |  |  |  |  | 2026-09-20 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-20 19:56:55 | No | No |  | add d6*1 Rep Ant MB S2 S2 > RRU5516*1 > Ant Combine MB S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BBMNE_2026 Capacity Expansion NW Modernization_EXP_SR | Ban Bang Mi Nuea | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-09-05 | 2026-09-03 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-24 | 2026-08-31 | 2026-08-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-25 15:17:38 | No | No |  |  |  |  | 2026-08-24 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-24 19:18:22 | No | No |  | 2026-08-25 alarm RRU S3 down S1 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S2 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S3 > Rep RRU3826*2 to RRU3962*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BBPNM_2026 Capacity Expansion Modernize_EXP_ER | Soi Banbueng Phattana | 2026-06-20 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-06-30 | 2026-06-20 | 2026-06-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-21 08:46:26 | No | No |  |  |  | 2026-06-30 | 2026-06-20 | 2026-06-22 | Teloneer Company Limited | N/A | Closed | 2026-06-22 09:44:33 | Yes | Yes | 2026-06-24 13:57:32 |  | 2026-06-30 | 2026-06-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-28 22:14:43 | Yes | Yes | 2026-06-25 15:17:54 |  | Pass |  | 2026-08-19 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-19 16:15:21 | No | Yes | 2026-08-19 16:13:27 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-17 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-20 14:20:48 | No | No |  |  | 2026-06-30 | 2026-06-20 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-25 08:21:58 | Yes | Yes | 2026-06-20 10:19:14 |  | 2026-06-22 | 2026-06-30 | 2026-06-20 | Teloneer Company Limited | N/A | Closed | 2026-06-20 16:06:50 | No | No |  |  |  |  | 2026-06-20 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-20 17:38:47 | No | No |  | Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_BBPNM_L_7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-20 | Boonchot Boriwut | N/A | Closed | 2026-06-25 22:57:05 | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BBPNM_2026 Capacity Expansion Ph1_EXP_ER | Soi Banbueng Phattana | 2026-07-01 | Team : thcp_apichat.f Tel : 0960126111 |  | 2026-06-01 | 2026-06-30 | 2026-07-02 | 2026-07-02 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-02 17:15:09 | No | No |  |  |  | 2026-06-30 | 2026-07-01 | 2026-07-02 | Teloneer Company Limited | N/A | Closed | 2026-07-02 10:21:17 | Yes | Yes | 2026-07-02 13:32:55 |  | 2026-06-30 | 2026-07-07 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-11 11:50:38 | Yes | Yes | 2026-07-07 17:15:18 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-05 11:49:56 | No | No |  |  | 2026-06-30 | 2026-07-01 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:43 | Yes | Yes | 2026-07-01 10:36:47 |  | 2026-07-02 | 2026-06-30 | 2026-06-20 | Teloneer Company Limited | N/A | Closed | 2026-06-20 11:46:11 | No | No |  |  |  |  | 2026-07-01 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-01 18:12:10 | No | No |  | Add UBBPg3a New L26F5 + NR26 (New AAU5656)_BBPNM_N_7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-01 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:47:15 | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BCD2M_2026 Capacity Expansion Ph2_BKK | Soi Baen Chado 2 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BCHAN_2026 Capacity Expansion Ph1_EXP_SR | BAN CHUAI ANAN_CO-DTAC | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-25 | 2026-09-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-26 16:02:03 | Yes | Yes | 2026-09-30 09:57:26 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-15 |  | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 | 2026-08-31 | 2026-09-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-25 20:46:51 | No | No |  |  |  |  | 2026-09-25 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-25 19:08:43 | No | No |  | Rep BBU5900#，add g3a*1#，add gps S1&S2 > RRU5872(1) > Ex Ant Combine MB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BCHLS_2026 Capacity Expansion NW Modernization_EXP_SR | Ranong Hospital | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-09-05 | 2026-09-03 | 2026-09-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-30 15:25:35 | Yes | Yes | 2026-09-30 15:28:36 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-27 | 2026-08-31 | 2026-08-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-27 20:37:25 | No | No |  |  |  |  | 2026-08-27 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-27 20:44:58 | No | No |  | 27 Aug 2026 Replace RRU3962 sector1#，2#，3#，4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BDATO_2026 Capacity Expansion Ph1_EXP_SR | Ban Da To | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-28 | 2026-08-31 | 2026-09-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-28 20:37:59 | No | No |  |  |  |  | 2026-09-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-28 20:25:05 | No | No |  | add h3a*1 Re MB S2 > S1 S2 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BDYBT_2026 Capacity Expansion Ph1_EXP_SR | Ban Don Yang Bo Thong | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-08-29 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-21 | 2026-08-31 | 2026-08-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-25 11:53:03 | No | No |  |  |  |  | 2026-08-21 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-21 18:03:20 | No | No |  | add UBBPh2a*1 Rep Ant MB S1#，S2 S1 > RRU5516*1 > Ant combine MB S1 S2 > RRU5516*1 > Ant combine MB S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BFAYM_2025 Capacity Expansion Ph8_EXP_BKK | BANG FAY |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 17:49:52 | No | No |  |  |  | 2026-02-14 | 2026-03-10 | 2026-03-10 | V Contribute Co., Ltd | N/A | Closed | 2026-03-10 15:24:16 | Yes | Yes | 2026-03-10 15:24:17 |  | 2026-02-21 | 2026-02-21 | Chonradee Suwapan | Approved | Closed | 2026-03-23 16:15:41 | Yes | Yes | 2026-03-13 17:32:33 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-09 | 2026-03-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:57:37 |  | 2026-02-21 | 2026-02-21 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-21 21:13:03 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-07 18:36:19 | No | No |  | 07-02-2026. Add UBBPg3a#， AAU5636w Sec.6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BHKJM_2026 Capacity Expansion Ph1_EXP_ER | Ban Huakunjae | 2026-06-12 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate | 2026-06-01 | 2026-06-30 | 2026-06-12 | 2026-06-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-13 06:26:49 | No | No |  |  |  | 2026-06-30 | 2026-06-13 | 2026-06-13 | Teloneer Company Limited | N/A | Closed | 2026-06-13 18:38:30 | Yes | Yes | 2026-06-15 09:02:57 |  | 2026-06-30 | 2026-06-16 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:17:37 | Yes | Yes | 2026-06-16 08:52:01 |  | Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:29:21 | No | Yes | 2026-09-12 10:28:59 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-14 15:06:49 | No | No |  |  | 2026-06-30 | 2026-06-11 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:37:15 | Yes | Yes | 2026-06-11 13:21:01 |  | 2026-06-12 | 2026-06-30 | 2026-06-12 | Teloneer Company Limited | N/A | Closed | 2026-06-12 16:36:51 | No | No |  |  |  |  | 2026-06-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-12 18:50:45 | No | No |  | Replace UBBPg1 to UBBPh3a done Replace Antenna (Dualbeam)_BHKJM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 235 + Remove RRU5505 x 2_BHKJM_H_4 Remove Antenna + (Co AAU5775) + Main Dir = 235 + Remove RRU5505 x 2_BHKJM_H_9 New Antenna (LB)_BHKJM_L_9 New Sector I (Co AAU5775) + Main Dir = 235_BHKJM_H_I New Sector L (Co AAU5775) + Main Dir = 235_BHKJM_H_L New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_BHKJM_H_6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-12 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BHMFM_2026 Capacity Expansion Ph2_EXP_ER | Ban Huai Ma Fai |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BHPBM_2026 Capacity Expansion Ph2_EXP_ER | BanHuayprab | 2026-09-21 |  | Install & Integrate |  | 2026-09-30 | 2026-09-21 | 2026-09-21 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-22 07:14:32 | No | No |  |  |  | 2026-09-30 | 2026-09-22 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 12:29:45 | Yes | Yes | 2026-09-30 21:04:20 | Need panorama photo completely. Need to upload combiner install photo & model photo at AD#， fill remark. This antenna jumper must have cold shrinks. Need this before photo. | 2026-09-30 | 2026-10-01 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-10-02 00:13:48 |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-21 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:42:32 | Yes | Yes | 2026-09-21 14:27:26 |  |  | 2026-09-30 | 2026-09-21 | Teloneer Company Limited | N/A | Closed | 2026-09-21 19:56:31 | No | No |  |  |  |  | 2026-09-21 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-21 18:19:59 | No | No |  | New NR26 (New RRU5818) + Co Antenna_BHPBM_N_7 New NR26 (Co RRU5818) + Co Antenna_BHPBM_N_8 |  | 2026-09-22 | Reungsak Junkong 00927496 | N/A | Closed | 2026-09-22 16:05:29 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BJRMM_2026 Capacity Expansion Modernize_EXP_ER | BoonJira Mantion | 2026-08-15 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-20 | 2026-08-15 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 21:05:37 | No | No |  |  |  | 2026-08-20 | 2026-08-17 | 2026-08-17 | Teloneer Company Limited | N/A | Closed | 2026-08-17 17:46:15 | Yes | Yes | 2026-08-19 22:09:48 |  | 2026-08-20 | 2026-08-19 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-28 23:19:56 | Yes | Yes | 2026-08-19 23:13:10 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:25 | No | No |  |  | 2026-08-20 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 17:57:59 |  |  | 2026-08-20 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 12:03:01 | No | No |  |  |  |  | 2026-08-15 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-15 18:02:41 | No | No |  | Add UBBPh2a Co NR07_BJRMM_L_1 Replace RRU (RRU5516_900) + NR07 + 4T4R_BJRMM_L_2 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_BJRMM_L_4 |  | 2026-08-17 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-17 17:25:00 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BKFCM_2026 Capacity Expansion Ph1_EXP_SR | Ban Khao Fa Chee | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-07 | 2026-08-31 | 2026-09-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-05 16:09:18 | No | No |  |  |  |  | 2026-09-05 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-05 18:40:08 | No | No |  | add g3a*1 S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BKJNM_2026 Capacity Expansion Modernize_EXP_ER | Boongunjanaram soi 5 | 2026-07-25 | Team : Team_Pooriwat Tel : 0925094222 |  |  | 2026-07-31 | 2026-07-25 | 2026-07-25 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-26 06:20:32 | No | No |  |  |  | 2026-07-31 | 2026-07-30 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 20:32:11 | Yes | Yes | 2026-08-09 15:13:40 |  | 2026-08-20 | 2026-08-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:57:18 | Yes | Yes | 2026-08-18 18:23:54 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-25 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:07 | No | No |  |  | 2026-07-31 | 2026-07-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-25 12:10:05 | Yes | Yes | 2026-07-24 20:11:23 |  |  | 2026-07-31 | 2026-07-28 | Teloneer Company Limited | N/A | Closed | 2026-07-28 09:43:31 | No | No |  |  |  |  | 2026-07-25 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-25 20:57:06 | No | No |  | Replace UBBPg3 to UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 330 + Remove RRU x 2_BKJNM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 100 + Remove RRU x 1_BKJNM_H_2 Remove Antenna + (New AAU5775) + Main Dir = 220 + Remove RRU x 2_BKJNM_H_3 (Co AAU5775) + Main Dir = 330 + Remove RRU x 2_BKJNM_H_6 Remove Antenna + (Co AAU5775) + Main Dir = 100 + Remove RRU x 2_BKJNM_H_7 (Co AAU5775) + Main Dir = 220 + Remove RRU x 2_BKJNM_H_8 New Sector G (Co AAU5775) + Main Dir = 330_BKJNM_H_G New Sector H (Co AAU5775) + Main Dir = 330_BKJNM_H_H New Sector J (Co AAU5775) + Main Dir = 100_BKJNM_H_J New Sector K (Co AAU5775) + Main Dir = 100_BKJNM_H_K New Sector M (Co AAU5775) + Main Dir = 220_BKJNM_H_M New Sector N (Co AAU5775) + Main Dir = 220_BKJNM_H_N |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BKMOM_2026 Capacity Expansion Ph1_EXP_SR | Ban Km.53 | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-23 | 2026-09-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-29 17:24:41 | Yes | Yes | 2026-09-29 17:26:41 | 1. Remove BBP 2pcs or 3pcs ? 2.Need to upload remove RRU 1pcs SN photo in EQ 3.Need to upload remove RRU 2pcs SN photo at before 4.Before /EQ Ant SN is not same . |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-23 | 2026-08-31 | 2026-09-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-16 21:50:52 | No | No |  |  |  |  | 2026-09-16 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-16 19:04:06 | No | No |  | 16 Sep 2026 Replace RRU5516 sector1 add 1UBBPh2 Replace BBU5900 add GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BKNGS_2026 Capacity Expansion Ph1_EXP_SR | Ban Khlong Ngoen school | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-25 | 2026-09-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-30 09:35:29 | Yes | Yes | 2026-09-30 09:36:35 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-31 | 2026-08-31 | 2026-08-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-30 15:25:14 | No | No |  |  |  |  | 2026-08-30 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-30 19:08:33 | No | No |  | S2 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BKSBM_2026 Capacity Expansion Ph2_EXP_ER | Ban Krasaebon |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BKTAM_2026 Capacity Expansion Ph1_EXP_SR | Ban Ko Ta | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-09 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-09 | 2026-08-31 | 2026-09-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-09 18:28:13 | No | No |  |  |  |  | 2026-09-08 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-08 19:39:33 | No | No |  | 8 Sep 2026 Add AAU5656 sector2#，3 S2 > AAU5656 S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BMERI_2026 Capacity Expansion Ph1_EXP_SR | Ban Merai | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-17 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-15 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-15 17:32:45 | No | No |  | Rep BBU5900#，add g3a*1#，-WBBPf4*1#，-WBBPf6*1#，add gps S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BMHTG_2026 Capacity Expansion NW Modernization_EXP_SR | Ban Mueang Thong | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-09-05 | 2026-08-22 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-21 | 2026-08-31 | 2026-08-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-22 14:34:29 | No | No |  |  |  |  | 2026-08-21 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-21 18:03:53 | No | No |  | S2 > Rep RRU3826*2 to RRU3962*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BMRRB_2025 Capacity Expansion NW Modernization_EXP_BKK | BAI MAI RA ROENG RESTAURANT FOR THE LAKES RATCHADAPISAK |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:50:46 | No | No |  |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-05-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-26 11:25:23 | Yes | Yes | 2026-05-26 11:28:07 |  | 2026-04-30 | 2026-04-30 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-07-30 12:45:05 | Yes | Yes | 2026-04-30 15:24:08 | 1.Page 46#，AIS passport have 3 pcs but team member have 2persons. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 21:16:54 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-27 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-27 17:01:17 | No | No |  | 27-Mar-26 Replace BBU5900 Add GPS #，Replace RRU3826>>RRU5507*2 SA Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BN29M_2025 Capacity Expansion Ph8_EXP_BKK | BANGNA-TRAD KM29 |  |  |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-09 18:10:08 | No | No |  |  |  | 2026-02-28 | 2026-04-16 | 2026-06-02 | V Contribute Co., Ltd | N/A | Closed | 2026-06-02 15:13:17 | Yes | Yes | 2026-06-02 15:13:18 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-19 16:33:46 | Yes | Yes | 2026-03-07 19:37:17 | 1.Page 7#，SOW & QC mismatch.(in QC have install UBBPg3a activity) 2.Page 53#，After:Position: Open POE/POR C2 uploaded photo wrong. 3.Need to upload change mount additional page. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-22 | 2026-03-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 11:58:52 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:16:39 | Yes | Yes | 2026-03-07 19:49:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-17 15:33:54 | No | No |  | 17-Feb-26 Add AAU5636w Sector 1#，6 Add g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BNACH_2026 Capacity Expansion Ph1_EXP_SR | Ban Na Chumhet | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-13 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | 1.EHS task need to upload photo 2.Before cabinet all information photo need to upload |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-14 | 2026-08-31 | 2026-09-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-13 21:03:42 | No | No |  |  |  |  | 2026-09-13 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-13 18:04:35 | No | No |  | Rep BBU5900#，add h2a*1#，-d6*1#，add gps Rep Ant MB S4 S4 > RRU5516*1 > Ant Combine MB S4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BNBKB_2026 Capacity Expansion Ph1_EXP_SR | Ban Ni Bong Ka Bang | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-07-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-15 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-15 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-15 17:32:45 | No | No |  | S1 > Rep RRU5508*1 to RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BNGYK_2026 Capacity Expansion Ph1_EXP_SR | Ba Ngo Ya Kang | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-22 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-11 | 2026-08-31 | 2026-09-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-25 14:36:02 | No | No |  |  |  |  | 2026-09-11 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-11 18:07:20 | No | No |  | Rep card d6*1 to h2a*1 S1 > Rep RRU3953*1 to RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BNIKM_2026 Capacity Expansion NW Modernization_EXP_SR | Ban Namthun | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-09-05 | 2026-08-23 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-25 | 2026-08-31 | 2026-08-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-26 12:05:16 | No | No |  |  |  |  | 2026-08-25 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-25 18:46:59 | No | No |  | S1 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S2 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S3 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S4 > Rep RRU3826*2 to RRU3962*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BNMFM_2026 Capacity Expansion Ph1_EXP_ER | Ban NongmuangMai Moo5 | 2026-06-03 | Team : thcp_anat.sri Tel : 0629861985 | Clear Pending | 2026-06-01 | 2026-06-30 | 2026-06-02 | 2026-06-02 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2026-06-04 15:48:22 | No | No |  |  |  | 2026-06-30 | 2026-06-04 | 2026-06-04 | Teloneer Company Limited | N/A | Closed | 2026-06-04 16:13:10 | Yes | Yes | 2026-06-04 18:00:12 |  | 2026-06-30 | 2026-06-08 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:17:37 | Yes | Yes | 2026-06-08 10:26:22 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-06-22 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-07 15:06:12 | No | No |  |  | 2026-06-30 | 2026-06-02 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:31 | Yes | Yes | 2026-06-02 13:35:10 |  | 2026-06-02 | 2026-06-30 | 2026-06-02 | Teloneer Company Limited | N/A | Closed | 2026-06-02 17:15:55 | No | No |  |  |  |  | 2026-06-02 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-02 18:45:24 | No | No |  | Replace 1RRU5508 to (RRU5516_900) + 4T4R_BNMFM_L_2 Replace 1RRU5508 to (RRU5516_900) + 4T4R_BNMFM_L_3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-03 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BNPCB_2026 Capacity Expansion NW Modernization_EXP_BKK | BANGNA PLACE CONDOMINIUM | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BNRIG_2026 Capacity Expansion Ph1_EXP_SR | Ban Na Riang | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-25 | 2026-08-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-25 20:50:42 | Yes | Yes | 2026-09-01 13:48:02 |  | 2026-09-01 | 2026-09-01 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-01 16:06:56 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-01 | 2026-09-01 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-01 21:14:49 |  | 2026-08-25 | 2026-08-31 | 2026-08-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-25 18:01:38 | No | No |  |  |  |  | 2026-08-25 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-25 18:46:59 | No | No |  | Add h2a*1 Rep Ant MB S4 S4 > Rep RRU3953*1 to RRU5516*1 > Ant Combime MB S4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOBKM_2025 Capacity Expansion Ph8_EXP_ER | BoBua KlongKhuen | 2026-02-18 | thcp_apichat.f | Install & Integrate |  | 2026-02-28 | 2026-02-18 | 2026-02-18 | Teloneer Company Limited | N/A | Closed | 2026-02-18 16:31:10 | No | No |  |  |  | 2026-02-28 | 2026-02-19 | 2026-02-19 | Teloneer Company Limited | N/A | Closed | 2026-02-19 17:16:50 | Yes | Yes | 2026-02-21 20:32:46 |  | 2026-02-28 | 2026-02-21 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:22:43 | Yes | Yes | 2026-02-21 22:04:32 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:58 | Yes | Yes | 2026-03-20 16:26:52 |  | 2026-02-28 | 2026-02-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-20 08:59:31 | Yes | Yes | 2026-02-18 15:52:32 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-18 17:48:02 | No | No |  | Replace UBBPg1 to UBBPg3a Replace RRU5508 to (RRU5516_900) + 4T4R_BOBKM_L_2 New L26F5 + NR26 (New RRU5818) + Co Antenna_BOBKM_N_1 New L26F5 + NR26 (Co RRU5818) + Co Antenna_BOBKM_N_3 |  | 2026-02-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-20 15:06:20 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BOKNT_2025 Coverage Expansion (Co NT)_New_SR | Ban Chong Khao_Co-NT | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-24 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-02-24 15:05:19 | Yes | Yes | 2026-02-24 13:39:16 |  |  |  |  | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
BPDBE_2026 Capacity Expansion Ph1_EXP_SR | Ban Pa Dang Be Sa _Co-DTAC | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-16 | 2026-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-18 10:42:46 | Yes | Yes | 2026-08-23 22:06:52 |  | 2026-08-24 | 2026-08-28 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-28 11:23:26 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-24 | 2026-08-24 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-24 00:37:54 |  | 2026-08-11 | 2026-08-31 | 2026-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-11 20:42:08 | No | No |  |  |  |  | 2026-08-11 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-11 17:32:03 | No | No |  | 11 Aug 2026 Add RRU5516 sector2 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPDSM_2026 Capacity Expansion Ph2_EXP_ER | Ban Pluakdaeng school |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPDYR_2026 Capacity Expansion Ph1_EXP_SR | Ban Pridi Yarang | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-26 | 2026-08-31 | 2026-09-01 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-01 21:21:43 | No | No |  |  |  |  | 2026-08-24 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-24 19:18:22 | No | No |  | S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPGSM_2026 Capacity Expansion Ph1_EXP_BKK | WAT BANGPLUENG SCHOOL | [5 empty] | 2026-07-30 | 2026-08-01 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-08-03 16:03:00 | No | Yes | 2026-07-10 22:22:38 |  |  | 2026-07-31 | 2026-07-23 | 2026-07-24 | Teloneer Company Limited | N/A | Closed | 2026-07-24 17:55:06 | Yes | Yes | 2026-07-27 11:07:01 |  | 2026-07-27 | 2026-07-27 | Teloneer Company Limited | Approved | Closed | 2026-08-28 22:13:51 | Yes | Yes | 2026-08-26 10:41:07 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-29 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-31 15:42:51 | No | No |  |  |  | 2026-07-10 | Teloneer Company Limited | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-10 22:27:39 |  |  | 2026-06-30 | 2026-07-25 | Teloneer Company Limited | N/A | Closed | 2026-07-25 10:42:18 | No | No |  |  |  |  | 2026-07-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-07-21 17:43:23 | No | No |  | 21-07-2026. Replace UMPTg2#， Add UBBPg3a#， AAU5656 Sec.2#， 3#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-04 16:07:52 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPGYM_2025 Capacity Expansion Ph8_EXP_ER | Bangkla-Plangyao soi3/2 | 2026-02-09 |  | Install & Integrate |  | 2026-02-28 | 2026-02-09 | 2026-02-09 | Teloneer Company Limited | N/A | Closed | 2026-02-09 15:06:36 | No | No |  |  |  | 2026-02-28 | 2026-02-10 | 2026-02-10 | Teloneer Company Limited | N/A | Closed | 2026-02-10 14:59:47 | Yes | Yes | 2026-02-12 00:00:19 | SQC Close | 2026-02-28 | 2026-02-13 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:22:43 | Yes | Yes | 2026-02-13 20:03:07 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:58 | Yes | Yes | 2026-03-20 16:27:11 |  | 2026-02-28 | 2026-02-10 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-13 15:14:42 | Yes | Yes | 2026-02-10 16:50:18 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-09 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-09 18:10:55 | No | No |  | Add UBBPg3a Replace Antenna (MB)_BPGYM_H_1 New L26F5 + NR26 (New RRU5818) + Co Antenna_BPGYM_N_1 New L26F5 + NR26 (Co RRU5818) + Co Antenna_BPGYM_N_3 |  | 2026-02-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-11 17:48:57 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPHAA_2026 Capacity Expansion Ph1_EXP_SR | Buppha Apartment | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-28 | 2026-09-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-29 10:57:44 | Yes | Yes | 2026-10-01 16:22:26 |  | 2026-10-01 | 2026-10-01 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-10-01 20:49:27 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 | 2026-10-01 | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-10-01 20:47:40 |  | 2026-09-28 | 2026-08-31 | 2026-09-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-28 20:37:11 | No | No |  |  |  |  | 2026-09-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-28 20:25:05 | No | No |  | Rep BBU5900#，add h3a*1#，add gps Rep MB S1>S4 S1 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPJNS_2026 Capacity Expansion Ph1_EXP_SR | Ban Prajan School | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-20 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-18 | 2026-08-31 | 2026-09-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-18 16:47:28 | No | No |  |  |  |  | 2026-09-17 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-17 18:34:57 | No | No |  | 17 Sep 2026 Add DMM add AAU5775 sector2 add 1UBBPh3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPKKD_2026 Capacity Expansion NW Modernization_EXP_SR | BPKKD | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-09-05 | 2026-08-23 | 2026-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-23 17:08:04 | Yes | Yes | 2026-09-08 00:02:02 |  | 2026-09-09 | 2026-09-09 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-09 01:06:41 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-09 | 2026-09-09 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-09 01:10:11 |  | 2026-08-20 | 2026-08-31 | 2026-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-20 15:39:01 | No | No |  |  |  |  | 2026-08-20 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-20 17:08:58 | No | No |  | 20 Aug 2026 Replace RRU3962 sector1#，2#，3#，4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPMJM_2026 Capacity Expansion Ph2_EXP_ER | Bang Pra Moo Jed |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPSPM_2026 Capacity Expansion Ph1_EXP_SR | Behind Prince of Songkhla University Pattani Campus | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-22 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-21 | 2026-08-31 | 2026-09-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-22 15:59:40 | No | No |  |  |  |  | 2026-09-21 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-21 19:01:00 | No | No |  | remove card g3*1 S6 > RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BPTHO_2026 Capacity Expansion Ph1_EXP_SR | Ban Pak Thao | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-18 | 2026-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-19 12:18:50 | Yes | Yes | 2026-08-21 01:57:20 |  | 2026-08-22 | 2026-08-27 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-27 13:29:54 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-22 | 2026-08-22 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-22 22:23:44 |  | 2026-08-19 | 2026-08-31 | 2026-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-18 17:46:42 | No | No |  |  |  |  | 2026-08-18 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-18 16:38:53 | No | No |  | 18 Aug 2026 Add AAU5656 sector2 add 1UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BR63M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI BOROMRATCHCHONNANI 63 | [5 empty] | 2026-08-18 | 2026-08-18 | Thossapan Chaloemrit | N/A | Closed | 2026-08-18 00:14:15 | No | No |  |  |  | 2026-08-31 | 2026-08-18 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-24 15:01:52 | Yes | Yes | 2026-09-29 18:30:28 | 1.Need to upload Breaker install overview and SN in EQ. 2.Need to upload dismantle breaker overview and SN i EQ. 3.Need to fill remark for dismantle breaker in EQ. 4.Need o upload DC-RRU indoor lable for S1 RRU1 and S2 RRU1 in QC. 5.Need to upload EPS install start point and end point in QC. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-19 | Teloneer Company Limited | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-06-19 18:05:59 |  |  | 2026-06-30 | 2026-08-29 | Teloneer Company Limited | N/A | Closed | 2026-08-29 16:11:59 | No | No |  |  |  |  | 2026-08-12 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-08-12 19:16:42 | No | No |  | 2026-08-12 s2 rmv RRU3962*1 add AAU5775 s3 rmv RRU5507*2 add AAU5775 s7 rmv RRU3962*1 s8 rmv RRU5507*2 2026-08-11_Replace UBBPg3 to UBBPh3a S1 Replace RRU3962*2 to AAU5775 S6 Remove RRU3962*2 ***Pending Alarm AAU S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:00:10 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRPEM_2026 Capacity Expansion Ph1_EXP_SR | BAN BU RA PE | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-23 |  | Somchai Thummachard(Future Telecom Co.,Ltd.) | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-13 | 2026-08-31 | 2026-09-25 | Somchai Thummachard(Future Telecom Co.,Ltd.) | N/A | Closed | 2026-09-25 20:48:12 | No | No |  |  |  |  | 2026-09-13 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-13 18:04:35 | No | No |  | Remove card g3a*1#，g3*1 Rep Ant MB S2// Ret > LB S2 S2 > Rep RRU3953*2 to RRU5516*1 > Ant Combine MB S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRTDN_2026 Capacity Expansion Ph1_EXP_SR | Ban Rai Tok Dan Nok | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-14 | 2026-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-15 21:01:23 | Yes | Yes | 2026-08-19 11:13:09 |  | 2026-08-19 | 2026-08-26 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-26 13:01:36 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-19 | 2026-08-19 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-19 13:59:37 |  | 2026-08-12 | 2026-08-31 | 2026-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-12 18:23:54 | No | No |  |  |  |  | 2026-08-12 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-12 19:31:12 | No | No |  | Add UBBPh2a*1 Rep Ant MB S3 to 8 Port S3 Rep RRU3953*1 to RRU5516*1 > Ant Combine MB S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BRTPM_2026 Capacity Expansion Ph1_EXP_SR | Ban Ran Tatphom | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-06 | 2026-08-06 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-06 20:28:06 | Yes | Yes | 2026-08-12 09:25:49 |  | 2026-08-14 | 2026-08-17 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-09-04 11:09:44 | Yes | Yes | 2026-08-17 13:24:55 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-01 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-03 17:02:36 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-06 | 2026-08-31 | 2026-08-06 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-06 15:27:49 | No | No |  |  |  |  | 2026-08-06 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-06 17:08:20 | No | No |  | 6 Aug 2026 Replace RRU5516 sector4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS11M_2026 Capacity Expansion NW Modernization_EXP_BKK | Bang Kruai - Sai Noi 11 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 16:34:19 |  |  | 2026-10-10 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BS11M_2026 Capacity Expansion Ph2_BKK | Bang Kruai - Sai Noi 11 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSAKU_2026 Capacity Expansion Ph1_EXP_SR | Ban Sakhu_DTAC | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-17 | 2026-08-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-26 09:38:54 | Yes | Yes | 2026-08-29 15:52:29 |  | 2026-08-30 | 2026-08-30 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-30 08:26:51 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-30 | 2026-08-30 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-30 08:29:14 |  | 2026-08-14 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-14 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-14 17:58:26 | No | No |  | Rep Card UBBPg3*1 to UBBPh2a*1 S1 > Rep RRU3953*2 to RRU5516*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSGPU_2026 Capacity Expansion Ph1_EXP_SR | Ban Sang Phlu | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-14 | 2026-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-15 12:04:09 | Yes | Yes | 2026-08-21 01:47:29 |  | 2026-08-21 | 2026-08-28 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-28 12:35:39 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-21 | 2026-08-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-21 03:27:19 |  | 2026-08-14 | 2026-08-31 | 2026-08-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-14 21:20:20 | No | No |  |  |  |  | 2026-08-14 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-14 17:59:53 | No | No |  | Rep Ant MB S4 S4 > Rep RRU3953*2 to RRU5516*1 > Ant Combine MB S4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSHSM_2026 Capacity Expansion Modernize_EXP_ER | Soi Bangsai 63 | 2026-08-31 | Team : Thcp_phet.sa Tel : 0924272237 | Clear Pending |  | 2026-08-15 | 2026-08-05 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 18:01:59 | No | No |  |  |  | 2026-08-20 | 2026-08-06 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 16:24:24 | Yes | Yes | 2026-08-09 22:04:08 |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:57:18 | Yes | Yes | 2026-08-12 21:15:00 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:25 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:14:49 |  |  | 2026-08-15 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 17:05:14 | No | No |  |  |  |  | 2026-08-05 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-05 17:51:51 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_BSHSM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_BSHSM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_BSHSM_H_C |  | 2026-08-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-10 17:48:21 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% , Day2 : Clear pending | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSKPG_2026 Capacity Expansion Ph1_EXP_SR | Ban San Kamphaeng | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-05 | 2026-08-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-08 20:34:38 | Yes | Yes | 2026-08-17 22:19:55 |  | 2026-08-17 | 2026-08-21 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-21 08:44:18 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-17 | 2026-08-17 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-17 23:35:41 |  | 2026-08-05 | 2026-08-31 | 2026-08-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-04 19:24:10 | No | No |  |  |  |  | 2026-08-04 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-04 18:00:01 | No | No |  | S1 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSLUI_2026 Capacity Expansion Ph1_EXP_SR | Ban Salui_DTAC | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-25 | 2026-09-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-26 23:42:10 | Yes | Yes | 2026-09-30 10:48:45 | 1.Can't see clearly UMPT SN in EQ 2.Need to fill UMPT on sit data 3.Breaker have activity ? . But After/before breaker is same . |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-30 | 2026-08-31 | 2026-09-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-26 18:02:13 | No | No |  |  |  |  | 2026-09-25 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-25 19:08:43 | No | No |  | Rep BBU5900#，add g3a*1#，add gps S1&S3 > RRU5872(1) > Ex Ant Combine MB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSWHM_2026 Capacity Expansion Ph1_EXP_ER | Ban Namsap Nawanghin | 2026-07-07 | Team :thcp_pooriwat.k Tel : 0925094222 | Install & Integrate | 2026-06-01 | 2026-07-15 | 2026-07-07 | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-08 09:34:14 | No | No |  |  |  | 2026-07-20 | 2026-07-11 | 2026-07-12 | Teloneer Company Limited | N/A | Closed | 2026-07-12 09:46:53 | Yes | Yes | 2026-07-13 01:41:38 |  | 2026-07-20 | 2026-07-14 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:15 | Yes | Yes | 2026-07-14 23:18:14 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-10 16:09:38 | No | No |  |  | 2026-07-31 | 2026-07-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:42 | Yes | Yes | 2026-07-04 09:08:22 |  | 2026-07-08 | 2026-07-15 | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-07 16:28:46 | No | No |  |  |  |  | 2026-07-07 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-07 15:35:31 | No | No |  | Replace RRU (RRU5516_900) + 4T4R_BSWHM_L_1 Replace RRU (RRU5516_900) + 4T4R_BSWHM_L_3 New L26F5 + NR26 (New AAU5656)_BSWHM_N_2 New L26F5 + NR26 (New AAU5656)_BSWHM_N_3 |  | 2026-07-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-08 18:20:18 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-07 | Boonchot Boriwut | N/A | Closed | 2026-07-15 06:19:08 | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSWNS_2026 Capacity Expansion Ph1_EXP_SR | Bang Sawan Subdistrict Municipality | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-20 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | 1.Need install RRU overvieew and SN photo and label show with red mark. 2. 2.Need clear photo at after c1. 3.Install BBP(H3a)not found at after. 4. 4.Is this card install#， so you need to fill at eq and additional. 5. 5.Need all ground bar of before condition photo at before on ground. 6.Wrong pandorama photo at 300 degree. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-20 | 2026-08-31 | 2026-09-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-20 17:47:19 | No | No |  |  |  |  | 2026-09-20 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-20 19:56:55 | No | No |  | Rep d5*1 to h3a*1 Re MB S2&S7 > S3&S8 S3> RRU3953*1 > Ant 4 Port // *( Plan 4T ) S2 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BSY1B_2025 Capacity Expansion Ph8_EXP_BKK | BAAN SIRI YENARKAT (BACK) | [5 empty] | 2026-04-23 | 2026-04-23 | Narongsak wanichachiwa | N/A | Closed | 2026-04-23 17:24:42 | No | No |  |  | 2026-03-02 | 2026-03-31 | 2026-03-27 | 2026-04-27 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-04-27 11:29:28 | Yes | Yes | 2026-04-27 11:32:09 |  | 2026-04-22 | 2026-04-22 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-07-23 21:16:27 | Yes | Yes | 2026-09-10 11:28:22 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-06 | 2026-03-06 | Pariyakorn Jearwarakul | Approved | Closed | 2026-04-28 09:47:53 | Yes | Yes | 2026-04-23 12:38:46 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-03-19 16:34:58 | No | No |  | 19-Mar-2026 Add RRU5818 Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTACH_2026 Capacity Expansion Ph1_EXP_SR | Ban Tha Chang | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-24 | 2026-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-24 19:43:05 | Yes | Yes | 2026-10-01 18:17:40 | 1.Need to fill remark for install breaker in EQ. 2.Need to red mark dismantle RRU tower view photos in Before. 3.Need to fill remark that one in AD work. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 |  | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | N/A | Assigned |  | Yes | No |  |  | 2026-09-25 | 2026-08-31 | 2026-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-24 16:07:53 | No | No |  |  |  |  | 2026-09-24 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-24 18:34:35 | No | No |  | 24 Sep 2026 Add DMM AAU5775 sector1 add AAU5656 sector3 add 1UBBPh3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTAKH_2026 Capacity Expansion Ph1_EXP_SR | Ban Ta Khun Hospital | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-08-17 | 2026-09-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-29 17:23:29 | Yes | Yes | 2026-09-29 17:24:57 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-15 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-15 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-15 17:12:39 | No | No |  | Rep d6*1 to h2a*1 S1 > RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTDMM_2026 Capacity Expansion Ph1_EXP_ER | Ban Tandam | 2026-07-16 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-07-20 | 2026-07-16 | 2026-07-16 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-16 15:52:20 | No | No |  |  |  | 2026-07-20 | 2026-07-18 | 2026-07-18 | Teloneer Company Limited | N/A | Closed | 2026-07-18 14:37:32 | Yes | Yes | 2026-07-20 14:03:46 |  | 2026-07-20 | 2026-07-23 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:01:43 | Yes | Yes | 2026-07-29 08:45:04 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-14 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:47 | No | No |  |  | 2026-07-31 | 2026-07-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:42 | Yes | Yes | 2026-07-04 11:52:06 |  |  | 2026-07-20 | 2026-07-16 | Teloneer Company Limited | N/A | Closed | 2026-07-16 15:23:29 | No | No |  |  |  |  | 2026-07-16 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-16 14:16:02 | No | No |  | Add UBBPg3a_BTDMM_H_1 ReSectorname S3 to S7_BTDMM_N_7 New L26F5 + NR26 (New AAU5656)_BTDMM_N_2 |  | 2026-07-17 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-17 17:06:01 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTGBN_2026 Capacity Expansion Ph1_EXP_SR | Ban Thung Bin | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-20 | 2026-08-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-21 11:39:36 | Yes | Yes | 2026-08-26 18:46:23 |  | 2026-08-26 | 2026-09-01 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-01 02:35:32 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-26 | 2026-08-26 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-26 20:34:15 |  | 2026-08-19 | 2026-08-31 | 2026-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-19 15:07:24 | No | No |  |  |  |  | 2026-08-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-19 18:30:56 | No | No |  | S3 > Rep RRU3953*2 to RRU5516 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTJMM_2025 Capacity Expansion Ph8_EXP_ER | Ban Thajam | 2026-02-24 | Thcp_adirek.kh | Take Photo & Clear Pending |  | 2026-02-28 | 2026-02-20 | 2026-02-20 | Teloneer Company Limited | N/A | Closed | 2026-02-20 17:33:04 | No | No |  |  |  | 2026-02-28 | 2026-02-21 | 2026-02-26 | Teloneer Company Limited | N/A | Closed | 2026-02-26 15:31:10 | Yes | Yes | 2026-02-27 08:15:26 |  | 2026-02-28 | 2026-03-02 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-12 11:06:39 | Yes | Yes | 2026-03-02 20:24:37 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:29 | Yes | Yes | 2026-03-20 16:30:18 |  | 2026-02-28 | 2026-02-20 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:21:34 | Yes | Yes | 2026-02-20 17:38:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-20 19:12:10 | No | No |  | Replace UBBPg1 to UBBPg3a_BTJMM_H_1 Remove Antenna + (New AAU5768) + Main Dir = 250 + Remove RRU5505 x 2_BTJMM_H_3 Remove Antenna + (New AAU5768) + Main Dir = 330 + Remove RRU5505 x 1_BTJMM_H_4 Remove Antenna + (Co AAU5768) + Main Dir = 250 + Remove RRU5505 x 2_BTJMM_H_8 (Co AAU5768) + Main Dir = 330 + Remove RRU5505 x 1_BTJMM_H_9 Replace RRU3953 to (RRU5508 x 2) + Co L07 + NR07 + 4T4R_BTJMM_L_8 New Sector M (Co AAU5768) + Main Dir = 250_BTJMM_H_M New Sector N (Co AAU5768) + Main Dir = 250_BTJMM_H_N New Sector I (Co AAU5768) + Main Dir = 330_BTJMM_H_I New Sector L (Co AAU5768) + Main Dir = 330_BTJMM_H_L |  | 2026-02-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-24 16:25:40 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTL1M_2026 Capacity Expansion Ph1_EXP_SR | BAN KHUN THALE 1 | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  | 2026-07-26 | 2026-07-26 | 2026-07-26 | 2026-07-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-26 14:19:50 | Yes | Yes | 2026-08-11 14:36:07 |  | 2026-08-13 | 2026-08-13 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-18 19:47:39 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-13 | 2026-08-13 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-13 08:29:26 |  | 2026-07-30 | 2026-08-31 | 2026-07-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-26 13:10:37 | No | No |  |  |  |  | 2026-07-26 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-26 18:05:51 | No | No |  | S1 > Add AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTMKG_2026 Capacity Expansion Ph1_EXP_SR | Ban Tham Kong | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-13 | 2026-08-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-14 15:09:50 | Yes | Yes | 2026-08-17 16:16:54 |  | 2026-08-18 | 2026-08-25 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-25 10:43:52 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-25 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-25 11:09:51 |  | 2026-08-13 | 2026-08-31 | 2026-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-13 14:43:46 | No | No |  |  |  |  | 2026-08-13 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-13 17:59:57 | No | No |  | 13 Aug 2026 Add RRU5516 sector3 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTMOM_2026 Capacity Expansion Ph1_EXP_SR | Ban Thung Mor | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-19 | 2026-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-20 11:54:57 | Yes | Yes | 2026-08-24 13:59:44 |  | 2026-08-24 | 2026-08-24 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-24 17:39:54 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-29 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-30 13:04:17 | No | No |  |  | 2026-08-24 | 2026-08-24 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-24 17:45:16 |  | 2026-08-21 | 2026-08-31 | 2026-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-19 15:41:29 | No | No |  |  |  |  | 2026-08-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-19 18:30:56 | No | No |  | S2 >AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTPYM_2026 Capacity Expansion Ph1_EXP_SR | Ban Ton Phayom | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-29 | 2026-07-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-29 18:56:46 | Yes | Yes | 2026-08-08 17:01:01 |  | 2026-08-11 | 2026-08-13 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 20:37:27 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-08-13 | 2026-08-13 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 20:41:10 |  | 2026-07-30 | 2026-08-31 | 2026-07-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-29 16:46:53 | No | No |  |  |  |  | 2026-07-29 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-29 17:07:11 | No | No |  | S1 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTSAN_2026 Capacity Expansion Ph1_EXP_SR | Ban Ton San | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-28 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 20:27:11 | Yes | Yes | 2026-08-06 22:31:18 |  | 2026-08-17 | 2026-08-21 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-21 10:44:51 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-08-17 | 2026-08-17 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-17 22:12:18 |  | 2026-07-30 | 2026-08-31 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 15:52:44 | No | No |  |  |  |  | 2026-07-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-28 16:00:45 | No | No |  | S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTUSM_2026 Capacity Expansion NW Modernization_EXP_SR | Ban Thung Tamsao | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-09-05 | 2026-08-23 | 2026-08-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-27 10:02:30 | Yes | Yes | 2026-09-05 20:30:48 |  | 2026-09-07 | 2026-09-07 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-09 12:14:06 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-07 | 2026-09-07 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-07 09:35:29 |  | 2026-08-23 | 2026-08-31 | 2026-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-23 21:32:07 | No | No |  |  |  |  | 2026-08-23 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-23 18:12:01 | No | No |  | S1 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S2 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S3 > Rep RRU3826*2 to RRU3962*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BTWWM_2026 Capacity Expansion Ph1_EXP_ER | Bothong Watsuwan | 2026-06-02 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-06-30 | 2026-06-02 | 2026-06-02 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2026-06-04 15:48:22 | No | No |  |  |  | 2026-06-30 | 2026-06-04 | 2026-06-08 | Teloneer Company Limited | N/A | Closed | 2026-06-08 12:38:34 | Yes | Yes | 2026-06-10 09:33:07 |  | 2026-06-30 | 2026-06-12 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:57:06 | Yes | Yes | 2026-06-12 15:01:16 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-06-22 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-07 15:06:00 | No | No |  |  | 2026-06-30 | 2026-06-02 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:31 | Yes | Yes | 2026-06-02 12:06:24 |  | 2026-06-02 | 2026-06-30 | 2026-06-02 | Teloneer Company Limited | N/A | Closed | 2026-06-02 14:38:28 | No | No |  |  |  |  | 2026-06-02 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-02 18:45:24 | No | No |  | Add RRU5505 x 1 + 4T4R_BTWWM_H_6 ReSectorname S3 to S4_BTWWM_L_4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-02 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BUNAM_2026 Capacity Expansion Modernize_EXP_ER | BunNakhon NikomAmata | 2026-06-25 | Team : thcp_apichat.f Tel : 0960126111 | Clear Pending |  | 2026-06-30 | 2026-06-24 | 2026-06-24 | Teloneer Company Limited | N/A | Closed | 2026-06-25 18:24:26 | No | No |  |  |  | 2026-06-30 | 2026-06-25 | 2026-06-27 | Teloneer Company Limited | N/A | Closed | 2026-06-27 14:58:22 | Yes | Yes | 2026-06-27 15:02:01 |  | 2026-06-30 | 2026-06-29 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:53:25 | Yes | Yes | 2026-06-29 10:14:16 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-23 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-24 14:49:46 | No | No |  |  | 2026-06-30 | 2026-06-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-28 22:11:00 | Yes | Yes | 2026-06-25 09:43:40 |  |  | 2026-06-30 | 2026-06-24 | Teloneer Company Limited | N/A | Closed | 2026-06-24 16:50:41 | No | No |  |  |  |  | 2026-06-24 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-24 19:58:05 | No | No |  | "Add UBBPh3a + Remove Antenna + (New AAU5775) + Main Dir = 340 + Remove RRU x 2_BUNAM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 80 + Remove RRU x 2_BUNAM_H_2 Remove Antenna + (New AAU5775) + Main Dir = 200 + Remove RRU x 2_BUNAM_H_3 (Co AAU5775) + Main Dir = 340 + Remove RRU x 2_BUNAM_H_6 (Co AAU5775) + Main Dir = 80 + Remove RRU x 2_BUNAM_H_7 (Co AAU5775) + Main Dir = 200 + Remove RRU x 1_BUNAM_H_8 New Antenna (LB)_BUNAM_L_1 New Antenna (LB) + Add RRU5508 x 1 + Co NR07 + 4T4R_BUNAM_L_2 New Antenna (LB) + Add RRU5508 x 1 + Co NR07 L07 + 4T4R_BUNAM_L_3 New Sector G (Co AAU5775) + Main Dir = 340_BUNAM_H_G New Sector H (Co AAU5775) + Main Dir = 340_BUNAM_H_H New Sector J (Co AAU5775) + Main Dir = 80_BUNAM_H_J New Sector K (Co AAU5775) + Main Dir = 80_BUNAM_H_K New Sector M (Co AAU5775) + Main Dir = 200_BUNAM_H_M New Sector N (Co AAU5775) + Main Dir = 200_BUNAM_H_N " |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-29 | Nattawoot Suwan | N/A | Closed | 2026-06-29 15:05:02 | No | No |  |  |  | Day1 : 60% , Day2 : 80% , Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BW77M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI BANG WAEK 77 | [5 empty] | 2026-09-09 | 2026-09-09 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 | 2026-09-15 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 16:35:19 |  |  | 2026-10-10 | 2026-09-09 | Teloneer Company Limited | N/A | Closed | 2026-09-09 20:16:25 | No | No |  |  |  |  | 2026-09-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-09 16:58:52 | No | No |  | 9-Sep-2026 Add UBBPh3a Rmv d5 Add AAU5775 S3 Rmv RRU5507 Add RRU5516 S1 Rmv RRU5508 Add RRU5516 S2 Rmv RRU3953 Rep.Ant 8port S2 Co 1800700 2026-09-08 Install only |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-09 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:29:30 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BWSNM_2026 Capacity Expansion Ph1_EXP_SR | BAN WISAI NUA (CHUMPHON 4) | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-13 | 2026-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-18 09:55:21 | Yes | Yes | 2026-08-19 21:32:31 |  | 2026-08-21 | 2026-08-21 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-21 08:41:25 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-14 | 2026-08-31 | 2026-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-13 18:40:37 | No | No |  |  |  |  | 2026-08-13 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-13 17:59:57 | No | No |  | 13 Aug 2026 Add AAU5656 sector3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BYGNG_2026 Capacity Expansion Ph1_EXP_SR | Ban Yang Ngam Community | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-22 | 2026-08-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-25 15:38:42 | Yes | Yes | 2026-08-29 13:24:07 |  | 2026-08-29 | 2026-08-29 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-29 19:30:35 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-29 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-30 13:04:17 | No | No |  |  |  | 2026-08-29 | Future Telecom Co.,Ltd. | Approving | Assigned |  | Yes | Yes | 2026-08-29 19:31:48 |  | 2026-08-24 | 2026-08-31 | 2026-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-23 12:29:52 | No | No |  |  |  |  | 2026-08-22 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-22 16:53:20 | No | No |  | Add g2*1 S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BYKKM_2026 Capacity Expansion Ph2_EXP_ER | Bypass Khao Khoew |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BYNGS_2026 Capacity Expansion Ph1_EXP_SR | Rongrian Ban Yue Nang | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-26 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-24 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-24 17:31:53 | No | No |  | 24 Aug 2026 Add AAU5656 sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BZBLM_2026 Capacity Expansion Modernize_EXP_ER | Benzbanggalow | 2026-09-08 | Team: THCP_Wachira.s Tel :0657649919 |  |  | 2026-09-15 | 2026-09-08 | 2026-09-08 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-09 06:33:01 | No | No |  |  |  | 2026-09-15 | 2026-09-08 | 2026-09-14 | Teloneer Company Limited | N/A | Closed | 2026-09-14 16:53:28 | Yes | Yes | 2026-09-14 17:07:42 | 1.Need remove DPU SN in before section. 2.Need BF AC box. 3.New install OPM? | 2026-09-15 | 2026-09-15 | Apichart Kampuang(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-22 08:31:44 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 | 2026-09-01 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-02 08:43:19 | Yes | Yes | 2026-09-01 14:05:03 |  |  | 2026-09-15 | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-08 17:05:10 | No | No |  |  |  |  | 2026-09-08 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-08 14:41:17 | No | No |  | Add UBBPg3a + Replace Antenna (MB) + Replace RRU5526 + 4T4R_BZBLM_H_A Replace Antenna (Dualband) + Replace RRU5526 + 4T4R_BZBLM_H_B Replace Antenna (MB) + Replace RRU5526 + 4T4R_BZBLM_H_C Replace Antenna (Co Antenna) + Replace RRU (RRU5516_900) + 4T4R_BZBLM_L_B Co L21F2 All Sector |  | 2026-09-10 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-10 16:12:45 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BZBLM_2026 Capacity Expansion Ph1_EXP_ER | Benzbanggalow | 2026-06-09 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-06-30 | 2026-06-09 | 2026-06-12 | Phet Saithong(Teloneer Company Limited) | N/A | Closed | 2026-06-12 17:35:59 | No | No |  |  |  | 2026-06-30 | 2026-06-12 | 2026-06-12 | Teloneer Company Limited | N/A | Closed | 2026-06-12 15:32:00 | Yes | Yes | 2026-06-15 08:53:41 |  | 2026-06-30 | 2026-06-16 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:14:58 | Yes | Yes | 2026-06-16 18:05:19 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-14 15:06:49 | No | No |  |  | 2026-06-30 | 2026-06-05 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:20 | Yes | Yes | 2026-06-05 16:28:16 |  | 2026-06-24 | 2026-06-30 | 2026-06-09 | Teloneer Company Limited | N/A | Closed | 2026-06-09 13:45:08 | No | No |  |  |  |  | 2026-06-09 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-06-09 17:26:19 | No | No |  | New NR26 (New RRU5818) + Co Antenna_BZBLM_N_B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-06 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C241B_2025 Capacity Expansion NW Modernization_EXP_BKK | The Crest Sukhumvit 24 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-14 | 2026-03-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-15 10:05:29 | Yes | Yes | 2026-03-18 09:50:08 |  | 2026-03-27 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:28:41 | Yes | Yes | 2026-04-01 16:43:52 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-04-07 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 19:52:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-20 20:41:40 | No | No |  | 20-Feb-2026 Replace BBU5900 UMPTg2 Add g2 =2 Add RRU5526 sector 1 Remove RRU3826 Replace 12 port No Ret ไม่สามารถ Add GPS ได้ไม่มีพื้นที่ |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C277A_2025 Capacity Expansion Ph8_EXP_BKK | THANYABURI CITY HALL SMALLCELL (TOT) | [5 empty] | 2026-07-20 | 2026-08-01 | Thossapan Chaloemrit | N/A | Closed | 2026-08-03 16:03:00 | No | No |  |  |  | 2026-08-08 | 2026-07-19 | 2026-07-19 | Teloneer Company Limited | N/A | Closed | 2026-07-19 20:26:08 | Yes | Yes | 2026-07-20 16:41:41 |  | 2026-07-21 | 2026-07-22 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-21 11:28:34 | Yes | Yes | 2026-08-11 11:30:24 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-17 | Thossapan Chaloemrit | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-17 12:43:43 |  |  | 2026-08-08 | 2026-07-17 | Teloneer Company Limited | N/A | Closed | 2026-07-17 17:23:00 | No | No |  |  |  |  | 2026-07-17 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-07-17 17:07:05 | No | No |  | 17-Jul-2026 add rru2600 5818 *1 2 sector A#，B Add UBBPg3a slot 5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-20 | Teloneer Company Limited | N/A | Closed | 2026-07-21 12:49:41 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C341B_2025 Capacity Expansion NW Modernization_EXP_BKK | The Crest Sukhumvit 34 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-10 | 2026-03-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-11 16:24:46 | Yes | Yes | 2026-03-17 11:21:08 |  | 2026-03-25 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:28:41 | Yes | Yes | 2026-04-01 12:12:46 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 21:17:22 |  |  | 2026-03-31 | 2026-03-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-12 15:58:34 | No | No |  |  |  |  | 2026-02-13 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-13 18:58:33 | No | No |  | 13-Feb-26 Replace BBU3900 To RRU5900 Replace RRU5526 S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-02-13 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-06-25 04:38:41 | Yes | Yes | 2026-02-17 10:17:19 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
C418M_2026 Capacity Expansion NW Modernization_EXP_BKK | CHOK CHAI 4 RD. SOI 18 |  |  |  | 2026-06-11 |  | 2026-06-09 | 2026-06-16 | Teloneer Company Limited | N/A | Closed | 2026-06-16 12:33:36 | No | No |  |  |  | 2026-08-31 | 2026-06-15 | 2026-06-18 | Teloneer Company Limited | N/A | Closed | 2026-06-18 17:08:33 | Yes | Yes | 2026-06-24 14:52:54 |  | 2026-06-19 | 2026-06-26 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-07-21 21:00:16 | Yes | Yes | 2026-06-25 12:57:39 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-07-06 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-06 12:52:09 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-09 | 2026-07-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-06-16 16:19:02 |  |  | 2026-06-30 | 2026-06-12 | Teloneer Company Limited | N/A | Closed | 2026-06-12 15:15:09 | No | No |  |  |  |  | 2026-06-12 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-06-12 18:27:30 | No | No |  | 2026-06-12_Clear Pending#， Replace to new Ant 8 port Sector 1 (Fix alarm VSWR) 11-Jun-2026 ***Pending Alarm VSWR subrack 100 port B ///Replace port to 10G Add UBBPh3a=2 Remove d5 =2 Add RRU5516 S1 S2 S3 Remove RRU3953 *3 Add AAU5775 S2 Remove RRU3962 Remove RRU3962 S7 Remove RRU5502 S8 Replace Ant 8port 900 1800 S1 S3 S2 900 Done 2026-06-10_Pre work |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-06-11 | 2026-06-11 | Teloneer Company Limited | N/A | Closed | 2026-06-17 11:21:09 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CAKCM_2026 Capacity Expansion Ph1_EXP_ER | Combat Assistance Command 1 , Koh Chan | 2026-06-12 | Team : Thcp_phet.sa Tel : 092427223 | Install & Integrate | 2026-06-01 | 2026-06-30 | 2026-06-12 | 2026-06-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-13 06:26:49 | No | No |  |  |  | 2026-06-30 | 2026-06-12 | 2026-06-13 | Teloneer Company Limited | N/A | Closed | 2026-06-13 15:47:23 | Yes | Yes | 2026-06-15 08:55:55 |  | 2026-06-30 | 2026-06-16 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:14:58 | Yes | Yes | 2026-06-17 18:10:12 |  | First Time Pass | 2026-07-20 | 2026-07-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-20 17:12:55 | No | Yes | 2026-07-20 17:12:43 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-14 15:06:49 | No | No |  |  | 2026-06-30 | 2026-06-11 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:37:15 | Yes | Yes | 2026-06-11 13:21:25 |  | 2026-06-12 | 2026-06-30 | 2026-06-12 | Teloneer Company Limited | N/A | Closed | 2026-06-12 15:43:40 | No | No |  |  |  |  | 2026-06-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-12 18:50:45 | No | No |  | Add UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 30 + Remove RRU5505 x 1_CAKCM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 180 + Remove RRU5505 x 1_CAKCM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_CAKCM_H_3 New Sector 6 (Co AAU5775) + Main Dir = 30_CAKCM_H_6 New Sector G (Co AAU5775) + Main Dir = 30_CAKCM_H_G New Sector H (Co AAU5775) + Main Dir = 30_CAKCM_H_H New Sector 7 (Co AAU5775) + Main Dir = 180_CAKCM_H_7 New Sector J (Co AAU5775) + Main Dir = 180_CAKCM_H_J New Sector K |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-12 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CASHM_2026 Capacity Expansion Ph2_EXP_ER | ChakAoiSoi 5 | 2026-10-02 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-09-30 | 2026-09-22 | 2026-09-22 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-23 06:46:22 | No | No |  |  |  | 2026-09-30 | 2026-09-23 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 17:18:49 | Yes | Yes | 2026-09-30 20:11:21 | 1.Need to upload complete reposition | 2026-09-30 | 2026-09-30 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-30 23:18:05 |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:42:32 | Yes | Yes | 2026-09-22 11:34:46 |  |  | 2026-09-30 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 16:27:43 | No | No |  |  |  |  | 2026-09-22 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-22 16:26:17 | No | No |  | Add UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 350 + Remove RRU x 1_CASHM_H_1 Replace Antenna (Dualbeam)_CASHM_H_3 (Co AAU5775) + Main Dir = 350 + Remove RRU x 1_CASHM_H_6 New Sector G (Co AAU5775) + Main Dir = 350_CASHM_H_G New Sector H (Co AAU5775) + Main Dir = 350_CASHM_H_H New L18L21 + 4T4R+ Add RRU5513 + Co Antenna_CASHM_H_8 New U21_S8//Co L21(F2) S2#，S3#，S8 |  | 2026-09-23 | Reungsak Junkong 00927496 | N/A | Closed | 2026-09-23 16:35:58 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CATBM_2026 Capacity Expansion Modernize_EXP_ER | CAT Telecom Chonburi |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CBTKM_2026 Coverage Expansion Ph1-existing_EXP_ER | Chum Chon Ban Klong Ta Kao | 2026-04-24 | Thcp_adirek.kh | Install & Integrate |  | 2026-04-30 | 2026-04-24 | 2026-04-24 | Teloneer Company Limited | N/A | Closed | 2026-04-24 16:01:53 | No | No |  |  |  | 2026-04-30 | 2026-04-24 | 2026-04-25 | Teloneer Company Limited | N/A | Closed | 2026-04-25 11:00:44 | Yes | Yes | 2026-04-26 09:54:30 |  | 2026-04-30 | 2026-04-29 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-05-11 09:18:35 | Yes | Yes | 2026-04-29 15:32:29 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-30 | 2026-04-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-04-27 09:13:25 | Yes | Yes | 2026-04-24 12:25:13 |  |  | 2026-08-20 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-04-27 |  | 2026-04-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-04-24 17:39:45 | No | No |  | Replace UBBPg1 to UBBPg3a New L26F5 + NR26 (New AAU5636w)_CBTKM_N_4 |  | 2026-04-30 | Reungsak Junkong 00927496 | N/A | Closed | 2026-04-30 17:06:14 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-05-31 | 2026-04-24 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-23 07:22:38 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CC43M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI CHOK CHAI 4 SOI 3 |  |  |  | 2026-06-11 |  | 2026-06-16 | 2026-06-16 | Teloneer Company Limited | N/A | Closed | 2026-06-16 12:33:36 | No | No |  |  |  | 2026-08-31 | 2026-06-13 | 2026-06-18 | Teloneer Company Limited | N/A | Closed | 2026-06-18 19:53:23 | Yes | Yes | 2026-06-23 09:31:55 |  | 2026-06-23 | 2026-07-22 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 13:09:30 | Page.5 remove antenna 5 pcs or 6pcs?(pls revise detail) page.27 need to upload Grounding kit photo. | Not Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-07-06 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-06 12:52:09 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-09 | 2026-07-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-06-16 16:19:23 |  |  | 2026-06-30 | 2026-06-12 | Teloneer Company Limited | N/A | Closed | 2026-06-12 17:51:48 | No | No |  |  |  |  | 2026-06-25 | Autumporn Masing WX1434753 | N/A | Closed | 2026-06-25 17:45:00 | No | No |  | 25 Jun 2026 Add 1UBBPh2 2026-06-11_Replace RRU3935 to RRU5516(LB) Sector 1#，2#，3#， Replace Ant to 8 port Sector 1#，2#， Replace RRU3962 to RRU5502 Sector 1#， Remove RRU3826 Sector G#， Replace RRU3962(4) to AAU5775 Sector 2#，J#， Replace UBBPd5 to UBBPh3a#， ***Pending UBBPh2a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-06-12 | 2026-06-12 | Teloneer Company Limited | N/A | Closed | 2026-06-17 11:23:46 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CCCHM_2026 Capacity Expansion Modernize_EXP_ER | Chonburi Cancer Hospital | 2026-08-19 | Team : thcp_pooriwat.k Tel : 0925094222 | Install & Integrate |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-20 09:21:43 | No | No |  |  |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-20 20:27:35 | Yes | Yes | 2026-08-21 23:18:28 |  | 2026-08-20 | 2026-09-03 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:47:28 | Yes | Yes | 2026-09-03 23:09:38 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-08-20 | 2026-08-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-18 09:04:51 |  |  | 2026-08-20 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 13:04:41 | No | No |  |  |  |  | 2026-08-19 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-19 17:01:56 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_CCCHM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_CCCHM_H_2 Add RRU5505 x 1 + 4T4R_CCCHM_H_3 replace RRU (RRU5513) + 4T4R_CCCHM_H_A Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_CCCHM_L_3 Co L21(F2) all sector |  | 2026-08-20 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-20 17:23:56 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 80% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CITYM_2026 Capacity Expansion Modernize_EXP_ER | City Tower Condominium | 2026-06-18 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-06-30 | 2026-06-18 | 2026-06-18 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-18 19:16:40 | No | No |  |  |  | 2026-06-30 | 2026-06-18 | 2026-06-18 | Teloneer Company Limited | N/A | Closed | 2026-06-18 15:52:25 | Yes | Yes | 2026-06-19 08:41:27 |  | 2026-06-30 | 2026-06-24 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-28 22:14:43 | Yes | Yes | 2026-06-24 18:11:58 |  | Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:39:05 | No | Yes | 2026-09-12 10:36:10 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-16 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-16 16:50:00 | No | No |  |  | 2026-06-30 | 2026-06-17 | Palagon Prommueangma(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:11:17 | Yes | Yes | 2026-06-19 10:18:03 |  | 2026-06-18 | 2026-07-20 | 2026-07-13 | Teloneer Company Limited | N/A | Closed | 2026-07-13 14:17:15 | No | No |  |  |  |  | 2026-06-18 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-06-18 17:04:42 | No | No |  | "Replace Antenna (MB) + Replace RRU5526 + 4T4R_CITYM_H_7 Co L21F2 All sector" |  | 2026-07-20 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-20 20:57:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-20 | Nattawoot Suwan | N/A | Closed | 2026-06-20 11:07:58 | No | No |  |  |  | Day1 : 70% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CITYM_2026 Capacity Expansion Ph1_EXP_ER | City Tower Condominium | 2026-07-18 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-07-20 | 2026-07-18 | 2026-07-18 | Teloneer Company Limited | N/A | Closed | 2026-07-18 20:30:31 | No | No |  |  |  | 2026-07-20 | 2026-07-19 | 2026-07-20 | Teloneer Company Limited | N/A | Closed | 2026-07-20 10:36:35 | Yes | Yes | 2026-07-20 14:25:13 |  | 2026-07-20 | 2026-07-21 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:15 | Yes | Yes | 2026-07-21 12:07:15 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-14 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:47 | No | No |  |  | 2026-07-20 | 2026-07-13 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-14 21:10:02 | Yes | Yes | 2026-07-13 08:06:49 |  |  | 2026-09-30 | 2026-09-21 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-21 13:32:23 | No | No |  |  |  |  | 2026-07-18 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-18 20:06:51 | No | No |  | Remove RRU5818 x 1 + Add New AAU5656 + change 4T4R to 64T64R_CITYM_N_2 New NR26 (New AAU5656)_CITYM_N_1 |  | 2026-07-20 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-20 20:57:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : ติดตั้งไม่ได้ , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CK42M_2025 Capacity Expansion NW Modernization_EXP_BKK | CHAROENKRUNG SOI 42 |  |  |  | 2026-01-24 | 2026-01-24 | 2026-01-28 | 2026-01-28 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-01-29 09:34:01 | No | No |  |  | 2026-01-24 | 2026-01-24 | 2026-01-24 | 2026-01-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-01-24 17:09:48 | Yes | Yes | 2026-04-13 13:14:42 |  | 2026-04-16 | 2026-04-16 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Ready To Approve | Assigned |  | Yes | Yes | 2026-07-27 15:12:09 | page 6= need to fill remove ANT & RRU #， page 8=need to fill remove RRU activity#， page 10= in SQC #， remove ANT activity have but not have in INV file #， page 41= need site cleanness photo#， Need EHS information page | Not Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | N/A | Closed | 2026-08-01 21:39:56 | Yes | Yes | 2026-08-01 21:18:24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-24 | Wandee Thongpoon WX1039557 | Ready To Approve | Assigned |  | No | No |  | 24-Jan-2026 Add AAU5768 Sector 2 Remove RRU5507*2 Add g3a =2 Remove d5=2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
CK78M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAROEN KRUNG 78 | [5 empty] | 2026-08-18 | 2026-08-18 | Thossapan Chaloemrit | N/A | Closed | 2026-08-18 00:14:15 | No | No |  |  |  | 2026-08-31 | 2026-08-22 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 18:29:28 | Yes | Yes | 2026-09-25 18:29:37 | 1.EQ checklist Install BBP card mismatch need to upload completely serial photo 2.EQ checklist Dismantle BBP card mismatch need to upload completely serial photo3.S1 AAU on tower label need to upload show clear 4.S2/S3 18/21 2RRU on tower label need to upload 5.new install 4RRU 18/21 BBU to RRU indoor label need to upload 6.new install 4RRU 18/21 BBU to DC indoor label need to upload 7.S2/S3 18/21 2RRU Out door label need to upload |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-18 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-08-18 17:24:02 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-19 | Teloneer Company Limited | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-06-19 18:06:41 |  |  | 2026-06-30 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-21 11:53:35 | No | No |  |  |  |  | 2026-08-09 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-08-09 16:57:49 | No | No |  | 9-Aug-2026 Add RRU5507*2 S2 Rmv RRU3962 Add RRU5507*2 S3 Rmv RRU3962 *2 Rmv RRU3962 *2 S7 S8 Downgrade S7 S8 Add RRU516 S2 S3 Rmv RRU3953*2 Replace Ant 8port Co18002100 S2 s3 07-08-2026. ***Pending Sec.2#， 3 //Replace RRU5507 to AAU5775#， RRU3953 to RRU5516 Sec.1#， UBBPd5 to UBBPh2a#， UBBPh3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:00:10 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CKBNM_2026 Capacity Expansion NW Modernization_EXP_BKK | CHIANG KONG BANGNA | [5 empty] | 2026-09-09 | 2026-09-09 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 | 2026-09-27 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  | 1.Breaker install or not? 2.AAU label wrong in S1#，S2#，S3 at after 3.Need to upload this RRU SN photo in S3 at before 4. All Label Outdoor wrong on ground 5.Need to upload LED Monitor #，Alarm Krone#，POE Outlet#，POE Inlet#，Ground Bar in Cabinet#，DCDU Overview on ground C2 at after |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 16:36:17 |  |  | 2026-10-10 | 2026-09-10 | Teloneer Company Limited | N/A | Closed | 2026-09-10 09:53:12 | No | No |  |  |  |  | 2026-09-09 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-09 17:08:40 | No | No |  | 2026-09-09_Replace UBBPd5 to UBBPh3a S1 Replace RRU5507*2 to AAU5775 S2 Replace RRU5507*2 to AAU5775 S3 Replace RRU5507*2 to AAU5775 S6 Remove RRU5507*2 S7 Remove RRU5507*2 S8 Remove RRU5507*2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-09 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:29:30 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CKNKM_2026 Capacity Expansion Modernize_EXP_ER | Chak Nok | 2026-07-28 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-07-31 | 2026-07-20 | 2026-07-20 | Teloneer Company Limited | N/A | Closed | 2026-07-28 16:37:50 | No | No |  |  |  | 2026-07-31 | 2026-07-30 | 2026-07-31 |  | N/A | Closed | 2026-07-31 10:53:02 | Yes | Yes | 2026-08-06 10:48:19 |  | 2026-08-20 | 2026-08-07 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:57:18 | Yes | Yes | 2026-08-13 07:43:36 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-18 16:56:59 | No | No |  |  | 2026-07-31 | 2026-07-27 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-27 17:30:54 |  |  | 2026-07-31 | 2026-07-28 | Teloneer Company Limited | N/A | Closed | 2026-07-28 14:56:02 | No | No |  |  |  |  | 2026-07-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-27 20:43:27 | No | No |  | Add RRU5505 x 1 + 4T4R_CKNKM_H_3 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_CKNKM_H_4 |  | 2026-07-27 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-27 20:48:17 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 80% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMPHM_2026 Capacity Expansion Ph1_EXP_ER | Chum Chon Map Phai Moo 1 | 2026-07-01 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-06-30 | 2026-07-02 | 2026-07-02 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-02 17:15:09 | No | No |  |  |  | 2026-06-30 | 2026-06-29 | 2026-07-02 | Teloneer Company Limited | N/A | Closed | 2026-07-02 15:48:25 | Yes | Yes | 2026-07-02 15:52:55 |  | 2026-06-30 | 2026-07-10 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-20 21:39:19 | Yes | Yes | 2026-07-15 10:56:13 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-05 11:49:56 | No | No |  |  | 2026-06-30 | 2026-06-29 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-30 21:27:44 | Yes | Yes | 2026-06-29 10:29:48 |  | 2026-07-03 | 2026-06-30 | 2026-07-01 | Teloneer Company Limited | N/A | Closed | 2026-07-01 16:27:24 | No | No |  |  |  |  | 2026-07-01 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-01 19:36:38 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_CMPHM_H_2 Replace Antenna (Dualband)_CMPHM_H_3 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_CMPHM_L_1 New L26F5 + NR26 (New AAU5656)_CMPHM_N_2 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_CMPHM_L_3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-01 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:47:15 | No | No |  |  |  | Day1 : 50% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMPIM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | Chum Chon Map Phai Moo 4 | 2026-06-20 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-05-31 | 2026-06-20 | 2026-06-20 | Teloneer Company Limited | N/A | Closed | 2026-06-20 14:12:07 | No | No |  |  |  | 2026-06-30 | 2026-06-20 | 2026-06-22 | Teloneer Company Limited | N/A | Closed | 2026-06-22 15:06:03 | Yes | Yes | 2026-06-24 11:10:02 |  | 2026-06-30 | 2026-06-25 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-28 22:14:43 | Yes | Yes | 2026-06-25 17:52:09 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-06-19 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:11:17 | Yes | Yes | 2026-06-19 14:46:29 |  |  | 2026-06-30 | 2026-06-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-28 18:02:15 | No | No |  |  |  |  | 2026-06-20 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-20 17:45:02 | No | No |  | Newsite 3 sector RRU5505 x3 |  | 2026-06-20 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-20 17:45:02 | No | No |  |  |  | 2026-05-13 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-05-18 18:11:22 | Yes | Yes | 2026-05-18 11:26:23 |  |  | 2026-06-20 | Nattawoot Suwan | N/A | Closed | 2026-06-20 11:07:58 | No | No |  |  |  | Day1 : 60% , Day2 : 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMSKM_2026 Capacity Expansion NW Modernization_EXP_BKK | CHALERMSUK | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-10 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMT3M_2026 Capacity Expansion NW Modernization_EXP_BKK | Chumchon Mahat Thai 3 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-10 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CMTNM_2026 Capacity Expansion Modernize_EXP_ER | Chom Tian | 2026-08-20 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-08-31 | 2026-08-20 | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-20 17:32:51 | No | No |  |  |  | 2026-07-31 | 2026-08-03 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 23:47:59 | Yes | Yes | 2026-08-08 23:51:19 |  | 2026-08-20 | 2026-08-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:54:54 | Yes | Yes | 2026-08-09 00:49:30 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-07-31 | 2026-07-29 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-29 09:25:20 |  |  | 2026-07-31 | 2026-07-29 | Teloneer Company Limited | N/A | Closed | 2026-07-29 20:18:46 | No | No |  |  |  |  | 2026-08-20 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-20 16:14:15 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_CMTNM_H_2 Add RRU5508 x 1 + 4T4R_CMTNM_L_9 Co L21F2 S4#，9#，I#，L |  | 2026-08-26 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-26 16:58:36 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 90% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN02M_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | MAKRO SATHORN | [5 empty] | 2026-08-22 | 2026-08-22 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  |  | 2026-09-30 | 2026-08-26 | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-08 18:28:38 | Yes | Yes | 2026-09-15 12:02:42 |  | 2026-10-03 | 2026-09-15 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-09-15 13:19:39 | The whole site DUID wrong. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-20 | Teloneer Company Limited | Approved | Closed | 2026-08-28 15:30:50 | Yes | Yes | 2026-08-20 21:45:52 |  |  | 2026-08-31 | 2026-08-22 | Teloneer Company Limited | N/A | Closed | 2026-08-22 11:05:47 | No | No |  |  |  |  | 2026-08-20 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-08-20 17:03:38 | No | No |  | 20-Aug-2026 Add UBBPg2 Rmv d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-22 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:03:37 | No | No |  |  | SQC closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CN24M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI CHAROEN NAKHON 24 | [5 empty] | 2026-08-18 | 2026-08-18 | Thossapan Chaloemrit | N/A | Closed | 2026-08-18 00:14:15 | No | No |  |  |  | 2026-08-31 | 2026-08-13 | 2026-08-19 | Teloneer Company Limited | N/A | Closed | 2026-08-19 18:50:43 | Yes | Yes | 2026-08-24 11:10:57 |  | 2026-08-26 | 2026-08-25 | Khathahat Sitthihong(Teloneer Company Limited) | Approved | Closed | 2026-08-31 10:59:07 | Yes | Yes | 2026-08-26 20:53:58 | 1.Page 5#，56#，SOW#，EQ & QQ mismatch#，In EQ Add filtter activity not have. 2.Page 5#，56#， In & EQ SOW install DPU must be 4pcs. 5.Page 5#，56#，In SOW& EQ need to fill remove activity completely. 6.Page 10#，In S3 DPU40D install 1pcs. 7.Page 34#，In Before: RRU 1st: SN no. Uploaded DPU SN are After install DPU SN. 8.Page 39#，41#，Need to upload S1#，S2#，S3 AAU socket left & right photo. 9.Page 47#，Need to upload DC label from DPU photo. 10.Page 48#，After: Position: UPEU #， Slot 18#， 19 uploaded photo wrong. 11.Page 50#，Uploaded before & after AC breaker photo mismatch. 12.Page 55#，Phase name wrong.(must be 2026 Capacity Expansion NW Modernization_EXP_BKK) 13.Page 34#，35#，36#，Need to upload actual install OPM 4pcs's SN photo. 14.Page 56#，In EQ upload AAU SN wrong. 15#，Page 59#，In Over all Dismantle need to upload dismantle eq completely. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:25:35 |  |  | 2026-06-30 | 2026-08-08 | Teloneer Company Limited | N/A | Closed | 2026-08-08 10:12:29 | No | No |  |  |  |  | 2026-08-07 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-08-07 17:36:42 | No | No |  | 2026-08-07 s1#，s2#，s3 add RRU3953*1 s1 rmv RRU3962*1 add AAU5775*1 s2 rmv RRU3962*2 add AAU5775*1 s3 rmv RRU3962*2 add AAU5775*1 s6 rmv RRU3962*1 s7 rmv RRU3962*2 s8 rmv RRU3962*2 Add UBBPh3a slot4 2026-08-06 Install only |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:00:10 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CNAPM_2026 Capacity Expansion Modernize_EXP_ER | Chum Chon Na Pa Moo 9 | 2026-08-01 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-08-15 | 2026-08-01 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 20:19:40 | No | No |  |  |  | 2026-08-15 | 2026-08-04 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 16:51:17 | Yes | Yes | 2026-08-17 17:49:54 |  | 2026-08-20 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:30 | Yes | Yes | 2026-08-17 23:25:03 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:07 | No | No |  |  | 2026-08-15 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-06 11:37:47 | Yes | Yes | 2026-08-06 08:43:53 |  |  | 2026-08-15 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 18:06:03 | No | No |  |  |  |  | 2026-08-01 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-01 19:06:52 | No | No |  | Add UBBPh2a Add RRU5508 x 1 + Co NR07 + 4T4R_CNAPM_L_1 Add RRU5508 x 1 + Co NR07 + 4T4R_CNAPM_L_2 Add RRU5508 x 1 + Co NR07 + 4T4R_CNAPM_L_3 |  | 2026-08-03 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-03 17:32:32 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CNPHM_2026 Capacity Expansion Ph1_EXP_ER | Chum Chon Wat Nong Phai Kaew | 2026-07-10 | Team :thcp_pooriwat.k Tel : 0925094222 |  | 2026-06-01 | 2026-07-20 | 2026-07-10 | 2026-07-10 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-11 10:10:51 | No | No |  |  |  | 2026-07-20 | 2026-07-09 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 18:03:25 | Yes | Yes | 2026-07-11 16:19:40 |  | 2026-07-20 | 2026-07-16 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:15 | Yes | Yes | 2026-07-16 18:24:22 |  | Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:34:22 | No | Yes | 2026-09-12 10:31:14 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:47 | No | No |  |  | 2026-07-20 | 2026-07-09 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-11 11:49:00 | Yes | Yes | 2026-07-09 12:56:01 |  |  | 2026-07-20 | 2026-07-09 | Teloneer Company Limited | N/A | Closed | 2026-07-09 17:52:04 | No | No |  |  |  |  | 2026-07-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-10 22:15:02 | No | No |  | Replace UBBPg1 to UBBPh3a Replace UBBPg1 to UBBPg3a Replace Antenna (Dualband Dualbeam)_CNPHM_H_2 Replace Antenna (Dualband Dualbeam)_CNPHM_H_3 Replace Antenna (Dualband Dualbeam)_CNPHM_L_2 Replace Antenna (Dualband Dualbeam)_CNPHM_L_3 New Antenna (LB)_CNPHM_L_4 ReDirection 20 to 0_CNPHM_N_1 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_CNPHM_H_7 -- not finish New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_CNPHM_H_8 ReSectorname S2 to S3_CNPHM_N_3 ReSectorname S3 to S4_CNPHM_N_4 Remove Antenna + (New AAU5775) + Main Dir = 260 + Remove RRU x 2_CNPHM_H_4 New Sector 9 (Co AAU5775) + Main Dir = 260_CNPHM_H_9 New Sector I (Co AAU5775) + Main Dir = 260_CNPHM_H_I New Sector L (Co AAU5775) + Main Dir = 260_CNPHM_H_L New L26F5 + NR26 (New AAU5656)_CNPHM_N_2 |  | 2026-08-03 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-03 18:37:40 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 80% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CNWNM_2026 Capacity Expansion Ph2_EXP_ER | Chumchon NongWa soi1 | 2026-10-01 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-10-15 | 2026-10-01 | 2026-10-01 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-10-01 19:48:58 | No | No |  |  |  | 2026-10-16 | 2026-10-01 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-10-15 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-29 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-29 13:52:40 |  |  | 2026-10-15 | 2026-10-01 | Teloneer Company Limited | N/A | Closed | 2026-10-01 18:02:32 | No | No |  |  |  |  | 2026-10-01 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-10-01 18:29:20 | No | No |  | Add UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 60 + Remove RRU x 1_CNWNM_H_2 New Sector 7 (Co AAU5775) + Main Dir = 60_CNWNM_H_7 New Sector J (Co AAU5775) + Main Dir = 60_CNWNM_H_J New Sector K (Co AAU5775) + Main Dir = 60_CNWNM_H_K Co L21(F2) S1#，6#，G#，H |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CONEP_2025 Capacity Expansion NW Modernization_EXP_BKK | Center One |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-24 15:31:14 | No | No |  |  | 2026-02-22 | 2026-02-22 | 2026-02-22 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:14:46 | Yes | Yes | 2026-03-23 15:26:16 |  | 2026-03-24 | 2026-03-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-04-27 09:55:50 | Yes | Yes | 2026-03-24 15:32:40 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:57:08 | Yes | Yes | 2026-08-01 21:19:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-13 19:56:03 | No | No |  | Replace BBU3900 To RRU5900 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CPRGM_2026 Capacity Expansion Ph2_EXP_ER | CP Rayong | 2026-09-23 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-09-30 | 2026-09-23 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-24 07:39:09 | No | No |  |  |  | 2026-09-30 | 2026-09-24 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 11:35:35 | Yes | Yes | 2026-09-30 23:14:28 |  | 2026-09-30 | 2026-10-01 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-10-02 00:30:27 |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-25 17:31:42 | Yes | Yes | 2026-09-23 13:11:58 |  |  | 2026-09-30 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 21:45:41 | No | No |  |  |  |  | 2026-09-23 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-23 16:44:30 | No | No |  | Replace Antenna (Dualband Dualband)_CPRGM_H_3 Replace Antenna (Co Antenna)_CPRGM_L_3 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_CPRGM_H_8 |  | 2026-09-24 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-24 16:02:28 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CPWHM_2026 Capacity Expansion Modernize_EXP_ER | Chai Phon Withee Huai Yai Moo 4 | 2026-08-02 | Team : Team_Pooriwat Tel : 0925094222 |  |  | 2026-07-31 | 2026-07-30 | 2026-07-30 | Teloneer Company Limited | N/A | Closed | 2026-07-30 19:33:36 | No | No |  |  |  | 2026-08-20 | 2026-08-05 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 16:19:43 | Yes | Yes | 2026-08-14 19:33:27 |  | 2026-08-20 | 2026-08-15 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:30 | Yes | Yes | 2026-08-15 19:50:33 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:07 | No | No |  |  | 2026-07-31 | 2026-07-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-30 08:01:37 |  |  | 2026-07-31 | 2026-07-30 | Teloneer Company Limited | N/A | Closed | 2026-07-30 14:52:56 | No | No |  |  |  |  | 2026-07-30 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-30 18:55:45 | No | No |  | Add UBBPh3a_CPWHM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_CPWHM_H_2 Remove Antenna + (New AAU5775) + Main Dir = 260 + Remove RRU x 2_CPWHM_H_3 (Co AAU5775) + Main Dir = 260 + Remove RRU x 2_CPWHM_H_8 Replace RRU (RRU5516_900) + 4T4R_CPWHM_L_1 Replace RRU (RRU5516_900) + 4T4R_CPWHM_L_2 Replace RRU (RRU5516_900) + 4T4R_CPWHM_L_3 Replace RRU (RRU5516_900) + 4T4R_CPWHM_L_4 New Sector M (Co AAU5775) + Main Dir = 260_CPWHM_H_M New Sector N (Co AAU5775) + Main Dir = 260_CPWHM_H_N |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 100% , Day2 : ไม่เข้าClear pending , Day3 : Clear pending | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CRMJA_2025 Capacity Expansion NW Modernization_EXP_BKK | CHARAT MUENG JUNCTION |  |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-27 13:27:45 | No | No |  |  |  | 2026-02-27 | 2026-02-25 | 2026-02-27 | V Contribute Co., Ltd | N/A | Closed | 2026-02-27 13:41:00 | Yes | Yes | 2026-02-27 13:41:00 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-04 09:57:31 | Yes | Yes | 2026-03-09 17:42:53 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:06:06 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-26 21:32:03 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-06 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-06 19:00:44 | No | No |  | 6 Feb 202Replace RRU5516 sectorB#，C 900/700 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CRWSM_2025 Capacity Expansion Ph8_EXP_BKK | CHAROEN WITTHYA SCHOOL |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:11:05 | No | No |  |  |  | 2026-02-28 | 2026-04-19 | 2026-05-29 | V Contribute Co., Ltd | N/A | Closed | 2026-05-29 20:31:06 | Yes | Yes | 2026-05-29 20:31:07 |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-03-12 09:25:25 | Yes | Yes | 2026-03-10 21:58:24 | Page no.14#， must be replace double mount to double mount. (not triple mount) Page no.31#， need to revise remark. (not RRU#， must be AAU) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-14 | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:06:44 |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-10 22:17:37 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-17 15:34:08 | No | No |  | 17-Feb-26 Add AAU5636w Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CSPKM_2025 Capacity Expansion NW Modernization_EXP_BKK | BIGC SAPHANKWAI |  |  |  |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-03-13 | 2026-03-24 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 16:57:11 | Yes | Yes | 2026-03-24 16:57:11 |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-04-27 09:56:22 | Yes | Yes | 2026-04-08 11:17:37 | pg no 82: - need to upload team member 3 person photo and Need back side view of Picture of full body safety harness with lanyard Not update (not yet revise) | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-04-28 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-08 11:25:12 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-26 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-26 17:47:08 | No | No |  | 26-Feb-26 Replace RRU5507 To AAU57688 DMM S1 S2 S3 Add UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CTLNM_2026 Capacity Expansion Ph1_EXP_ER | Chum ChonTalad Nongchak | 2026-07-09 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-07-20 | 2026-07-08 | 2026-07-08 | Teloneer Company Limited | N/A | Closed | 2026-07-08 21:49:21 | No | No |  |  |  | 2026-07-20 | 2026-07-08 | 2026-07-09 | Teloneer Company Limited | N/A | Closed | 2026-07-09 17:36:37 | Yes | Yes | 2026-07-10 09:54:16 |  | 2026-07-20 | 2026-07-23 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-25 12:08:01 | Yes | Yes | 2026-07-23 14:43:27 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-10 16:09:38 | No | No |  |  | 2026-07-31 | 2026-07-07 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-08 16:57:16 | Yes | Yes | 2026-07-07 17:12:59 |  |  | 2026-07-20 | 2026-07-09 | Teloneer Company Limited | N/A | Closed | 2026-07-09 10:55:57 | No | No |  |  |  |  | 2026-07-08 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-08 19:49:36 | No | No |  | ReDirection 180 to 130_CTLNM_N_2 New L26F5 + NR26 (New AAU5656)_CTLNM_N_7 Co L21F2 S2#，7#，J#，K |  | 2026-07-09 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-09 17:51:02 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-09 | Boonchot Boriwut | N/A | Closed | 2026-07-14 10:52:09 | No | No |  |  | SQC Closed | Day1 : 90% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CTRGM_2025 Coverage Expansion Ph1_New BBU-2nd_ER | Century Golf | 2026-06-09 | Team : THCP_Wachira.s Tel : 065-7649919 | Clear Pending |  | 2026-06-30 | 2026-06-06 | 2026-06-06 | Wachira saovaro(Teloneer Company Limited) | N/A | Closed | 2026-06-06 19:26:51 | No | No |  |  |  | 2026-06-30 | 2026-06-18 | 2026-06-18 | Teloneer Company Limited | N/A | Closed | 2026-06-18 10:35:54 | Yes | Yes | 2026-06-22 09:59:24 |  | 2026-06-30 | 2026-06-23 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-25 08:23:12 | Yes | Yes | 2026-06-23 16:34:06 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-06-30 | 2026-06-07 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:11:17 | Yes | Yes | 2026-06-18 09:06:12 |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-31 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-20 18:17:25 | No | No |  | New Site |  | 2026-05-31 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-20 18:17:25 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-20 | Nattawoot Suwan | N/A | Closed | 2026-06-20 11:07:58 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CTRGM_2026 Capacity Expansion Ph1_EXP_ER | Century Golf | 2026-06-10 | Activity : clear alarm pending Team : THCP_Wachira.s | Clear Alarm |  | 2026-06-30 | 2026-06-09 | 2026-06-12 | Wachira saovaro(Teloneer Company Limited) | N/A | Closed | 2026-06-15 07:45:24 | No | No |  |  |  | 2026-06-30 | 2026-06-12 | 2026-06-12 | Teloneer Company Limited | N/A | Closed | 2026-06-12 16:01:29 | Yes | Yes | 2026-06-20 14:19:49 |  | 2026-06-30 | 2026-06-23 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-25 08:23:12 | Yes | Yes | 2026-06-23 16:40:37 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-14 15:06:49 | No | No |  |  | 2026-06-30 | 2026-06-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:11:17 | Yes | Yes | 2026-06-18 09:00:01 |  | 2026-06-10 | 2026-06-30 | 2026-06-10 | Teloneer Company Limited | N/A | Closed | 2026-06-10 13:24:15 | No | No |  |  |  |  | 2026-06-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-15 19:40:34 | No | No |  | install new bbu 5900a |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-06-02 | Angsana Jituafua WX1434741 | Ready To Approve | Assigned |  | Yes | Yes | 2026-06-25 00:14:32 |  |  | 2026-06-20 | Nattawoot Suwan | N/A | Closed | 2026-06-20 11:07:58 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CTSVM_2026 Capacity Expansion Modernize_EXP_ER | Jomtien Seaview village | 2026-08-07 | Team : Thcp_phet.sa Tel : 0924272237 | Clear Alarm |  | 2026-08-20 | 2026-08-07 | 2026-08-07 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-07 21:41:11 | No | No |  |  |  | 2026-08-20 | 2026-08-11 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 11:58:44 | Yes | Yes | 2026-08-16 13:03:52 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:30 | Yes | Yes | 2026-08-16 16:54:21 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:23 | No | No |  |  | 2026-07-31 | 2026-07-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-25 12:10:05 | Yes | Yes | 2026-07-23 10:26:19 |  |  | 2026-07-31 | 2026-07-23 | Teloneer Company Limited | N/A | Closed | 2026-07-23 21:44:50 | No | No |  |  |  |  | 2026-08-07 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-07 19:33:44 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_CTSVM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_CTSVM_H_2 |  | 2026-08-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-10 17:48:21 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% รอเปลี่ยน Rec , Day2 : clear alarm not done , Day3 : Clear alarm | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CTUSM_2026 Capacity Expansion Modernize_EXP_ER | CETUS Condo Jomtien Pattaya | 2026-08-11 | Team : thcp_watcharin.k Tel :0925546852 |  |  | 2026-08-20 | 2026-08-11 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 18:23:36 | No | No |  |  |  | 2026-08-20 | 2026-08-15 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 14:09:42 | Yes | Yes | 2026-08-19 20:15:05 |  | 2026-08-20 | 2026-09-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:47:28 | Yes | Yes | 2026-09-04 20:10:01 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:23 | No | No |  |  | 2026-08-20 | 2026-08-13 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-13 08:32:03 |  |  | 2026-08-20 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 12:09:32 | No | No |  |  |  |  | 2026-08-11 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-11 17:05:49 | No | No |  | Change Remote RRU to Remote BBU Add RRU5505 x 1 + 4T4R_CTUSM_H_A Add RRU5505 x 1 + 4T4R_CTUSM_H_B Co BBU_CTUSM_N_A Co BBU_CTUSM_N_B |  | 2026-08-11 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-11 17:05:49 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CW15M_2026 Capacity Expansion NW Modernization_EXP_BKK | BAN TULAWARN | [5 empty] | 2026-09-11 | 2026-09-11 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 16:37:36 |  |  | 2026-10-10 | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-16 20:40:25 | No | No |  |  |  |  | 2026-09-11 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-09-11 17:10:28 | No | No |  | 2026-09-11 s1 replace RRU3962*2 to AAU5775 s2 replace RRU3962*2 to RRU5507*2 s3 replace RRU3962 to AAU5775 s6 remove RRU3962*2 s8 remove RRU3962 add UBBPh3a/rmv UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-11 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:30:25 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CW15M_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | BAN TULAWARN | [5 empty] | 2026-09-16 | 2026-09-16 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-31 | 2026-09-22 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 15:13:25 | Yes | Yes | 2026-09-29 09:38:47 |  | 2026-10-01 | 2026-10-01 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-10-01 13:17:35 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-16 20:44:57 | No | No |  |  |  |  | 2026-09-16 | Autumporn Masing WX1434753 | N/A | Closed | 2026-09-16 20:14:40 | No | No |  | 2026-09-16 REP BBU to 5900//add g3 Add gps |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:24:42 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CWKWM_2025 Capacity Expansion Ph8_EXP_ER | Chum Chon Wat Kaew Silaram | 2026-02-10 | thcp_apichat.f | Install & Integrate |  | 2026-02-28 | 2026-02-10 | 2026-02-10 | Teloneer Company Limited | N/A | Closed | 2026-02-10 17:41:17 | No | No |  |  |  | 2026-02-28 | 2026-02-10 | 2026-02-11 | Teloneer Company Limited | N/A | Closed | 2026-02-11 14:08:01 | Yes | Yes | 2026-02-15 12:46:32 |  | 2026-02-28 | 2026-02-15 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:22:43 | Yes | Yes | 2026-02-15 21:27:22 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:29 | Yes | Yes | 2026-03-20 16:40:57 |  | 2026-02-28 | 2026-02-10 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-13 15:14:42 | Yes | Yes | 2026-02-10 18:20:30 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-10 17:54:15 | No | No |  | Add UBBPg2 + Add UBBPg3a Replace Antenna (Dualband)_CWKWM_H_3 Replace 1RRU3953 to (RRU5516_900) + Co L07 + NR07 +4T4R_CWKWM_L_1 New L26F5 + NR26 (New RRU5818) + Co Antenna_CWKWM_N_1 New L26F5 + NR26 (Co RRU5818) + Co Antenna_CWKWM_N_3 |  | 2026-02-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-11 17:48:57 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CYACB_2026 Capacity Expansion Ph1_EXP_SR | Chaiya Court Behind | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-09 | 2026-08-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-09 14:56:43 | Yes | Yes | 2026-08-14 14:36:45 |  | 2026-08-16 | 2026-08-16 | Muhamadnase Chesamae | Approved | Closed | 2026-09-04 11:09:44 | Yes | Yes | 2026-08-16 14:30:01 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-01 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-03 17:02:36 | No | No |  |  | 2026-08-16 | 2026-08-16 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-16 14:31:10 |  | 2026-08-09 | 2026-08-31 | 2026-08-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-09 13:42:20 | No | No |  |  |  |  | 2026-08-09 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-09 19:15:26 | No | No |  | Add UBBPh2a*1 S3 > Rep RRU3953*1 toRRU5516LB*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D033A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi ANNOPNARUEMIT |  |  |  |  | 2026-02-27 | 2026-03-03 | 2026-03-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-18 16:37:14 | No | No |  |  |  | 2026-03-13 | 2026-03-01 | 2026-03-03 | V Contribute Co., Ltd | N/A | Closed | 2026-03-03 12:33:33 | Yes | Yes | 2026-03-03 12:33:33 |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-04-29 10:29:28 | Yes | Yes | 2026-04-08 11:18:05 | PAT first time pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-18 | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-08 11:25:37 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-27 18:43:27 | No | No |  | 27-Feb-2026 Replace BBU5900 UMPTg2 Add GPS Add g2 Add RRU5526 Sector A Remove RRU3962 Replac Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D052A_2025 Capacity Expansion NW Modernization_EXP_BKK | KHLONG TOEI MARKET_3 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:50:46 | No | No |  |  | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-06-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-11 19:50:18 | Yes | Yes | 2026-06-11 19:53:14 |  | 2026-06-11 | 2026-06-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-04 20:30:59 | Yes | Yes | 2026-06-12 11:29:59 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 19:52:38 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-18 18:21:19 | No | No |  | 18-Feb-26 Replace RRU3962 to RRU5526 SA 17-Feb-26 ///Pending Replace RRU3962 To RRU5526 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D085A_2026 Capacity Expansion NW Modernization_EXP_BKK | Soi Muban Chaiya Phruek Townhouse | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:26:03 |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D088A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI WO KHO PHETCHABURI Small Cell |  |  |  |  | 2026-03-24 | 2026-03-02 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-14 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:29:52 | Yes | Yes | 2026-03-23 15:29:53 |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-04-08 11:18:33 | PAT first time pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-08 11:26:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-02 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-02 19:23:27 | No | No |  | 2-Mar-2026 Add RRU5526 SA SB Remove RRU3962 *2 Replace ant 4port No Ret SA SB ยังไม่ต้อง Config 4t4r PE แจ้ง ผรม. |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D113A_2025 Capacity Expansion NW Modernization_EXP_BKK | SI RAT EXPRESSWAY (2 ND EXPRESSWAY) |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:50:46 | No | No |  |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-05-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-26 12:31:43 | Yes | Yes | 2026-05-26 12:34:24 |  | 2026-05-31 | 2026-05-31 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:30:59 | Yes | Yes | 2026-05-31 01:51:38 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 19:52:54 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-13 16:36:11 | No | No |  | 13-Feb-2026 Add RRU5516 (700900) S1 S2 Remove RRU3953 S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D132A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI ARAM SI Small Cell |  |  |  |  | 2026-06-02 | 2026-06-02 | 2026-06-02 | V Contribute Co., Ltd | N/A | Closed | 2026-06-02 15:56:00 | No | No |  |  |  | 2026-06-30 | 2026-06-13 | 2026-09-25 | V Contribute Co., Ltd | N/A | Closed | 2026-09-25 20:35:22 | Yes | Yes | 2026-09-25 20:35:27 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 2-Jun-2026 Add g3a=1 Remove d5 =1 Add RRU5526 S1 S2 Remove RRU3962 *2 Replace Ant 12port No Ret S1 S2 Done Confirm พี่แวง config 2T RRU5526 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 1.Q6-need to revise OPM list in EQ.(install OPM-2pcs)>>Done 2.Q3-Install RRU sector 1 label not standard.>>>CPRI Chain S1,S2​ mark to let know that this CPRI cable belongs to RRU S, 2 3.Q6-need to see Install OPM ground nut for sector |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D132A_2025 Capacity Expansion Ph8_EXP_BKK | SOI ARAM SI Small Cell |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-05-27 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-05-27 16:49:25 | No | No |  |  |  | 2026-03-20 | 2026-03-11 | 2026-03-31 | V Contribute Co., Ltd | N/A | Closed | 2026-03-31 19:55:09 | Yes | Yes | 2026-03-31 19:55:09 |  | 2026-04-10 | 2026-04-09 | Chonradee Suwapan | Approved | Closed | 2026-04-27 09:56:22 | Yes | Yes | 2026-04-10 00:01:39 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-28 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-10 | 2026-04-09 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-10 00:20:14 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-05 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-06-02 14:03:25 | No | No |  | 05-03-26 AAU5246 SB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D141A_2026 Capacity Expansion NW Modernization_EXP_BKK | Soi Phahon Yothin 26 Yaek 9 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D145A_2025 Capacity Expansion NW Modernization_EXP_BKK | KHLONG TOEI MARKET_2 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:50:46 | No | No |  |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-06-08 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-08 14:46:11 | Yes | Yes | 2026-06-09 08:47:28 |  | 2026-06-11 | 2026-06-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-04 20:30:59 | Yes | Yes | 2026-06-12 11:40:56 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 19:53:08 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-17 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-17 16:59:58 | No | No |  | 17-Feb-26 Replace BBU3900 TO BBU5900 Replace RRU3962 To RRU5526 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D168A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi nathong Yek 2 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-16 | 2026-02-16 | 2026-03-06 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:35:07 | Yes | Yes | 2026-04-01 13:07:12 |  | 2026-04-22 | 2026-04-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-02 09:35:21 | Yes | Yes | 2026-04-24 11:47:23 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-05 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 19:53:21 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-11 18:04:36 | No | No |  | 11-Feb-2026 Add RRU5526 Sector A B Remove RRU3962 *2 Replace Ant 4port S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D186A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI MUBAN PHIBUN WATTHANA 5 Small Cell 1 |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-17 16:22:25 | No | No |  |  |  | 2026-02-28 | 2026-02-11 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 10:45:40 | Yes | Yes | 2026-02-12 10:45:40 |  | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-18 18:08:12 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:07:40 |  | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-16 22:26:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-23 16:03:30 | No | No |  | 23-Jan-2026 Add g2 Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D205A_2025 Capacity Expansion NW Modernization_EXP_BKK | KHLONG TOEI MARKET_5 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:50:46 | No | No |  |  | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-06-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-10 15:06:09 | Yes | Yes | 2026-06-10 15:09:17 |  | 2026-06-12 | 2026-06-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-04 20:33:00 | Yes | Yes | 2026-06-16 18:10:12 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 19:53:33 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-19 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-19 17:09:54 | No | No |  | 19-Feb-26 Replace 3962 To RRU5526 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D206A_2025 Capacity Expansion NW Modernization_EXP_BKK | KHLONG TOEI MARKET_6 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:50:46 | No | No |  |  | 2026-03-04 | 2026-03-11 | 2026-03-11 | 2026-06-08 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-08 14:49:32 | Yes | Yes | 2026-06-09 09:30:35 |  | 2026-06-12 | 2026-06-12 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:33:00 | Yes | Yes | 2026-06-12 12:21:15 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 19:53:48 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-19 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-19 17:09:54 | No | No |  | 19-Feb-26 Replace 3962 To RRU5526 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D220A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Nathong Yek2 |  |  |  |  | 2026-01-27 | 2026-03-06 | 2026-03-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-18 16:37:14 | No | No |  |  |  | 2026-02-07 | 2026-03-05 | 2026-03-06 | V Contribute Co., Ltd | N/A | Closed | 2026-03-06 16:19:36 | Yes | Yes | 2026-03-06 16:19:36 |  | 2026-03-18 | 2026-03-18 | Chonradee Suwapan | Approved | Closed | 2026-07-01 10:25:08 | Yes | Yes | 2026-03-18 22:19:26 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-07-06 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-18 | 2026-03-18 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-18 22:23:43 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-27 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-27 18:19:35 | No | No |  | 27-01-2026. Replace BBU5900#， UMPTg2 10G#， UBBPd5 x2 to UBBPg3a#， Add GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D222A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHERM SIN |  |  |  |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:46:55 | No | No |  |  |  | 2026-02-07 | 2026-03-08 | 2026-03-08 | V Contribute Co., Ltd | N/A | Closed | 2026-03-08 18:14:30 | Yes | Yes | 2026-03-08 18:14:30 |  | 2026-03-18 | 2026-03-18 | Chonradee Suwapan | Approved | Closed | 2026-07-22 16:31:43 | Yes | Yes | 2026-04-01 10:57:29 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-23 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-18 | 2026-03-18 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-18 22:26:55 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 27 Jan 2026 ***Replace BBU5900 GPS only |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D227A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI Peamsombat |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-02-28 | 2026-03-21 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:15:16 | Yes | Yes | 2026-03-23 15:15:16 |  | 2026-03-25 | 2026-03-25 | Chonradee Suwapan | Approved | Closed | 2026-08-13 09:28:48 | Yes | Yes | 2026-03-25 21:51:56 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-03-25 | 2026-03-25 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-25 21:57:54 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-23 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-23 16:54:34 | No | No |  | 23-Feb-26 Replace Ant S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D228A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Prachasanti |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 16:26:40 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-10 | 2026-02-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-12 22:02:24 | Yes | Yes | 2026-02-18 10:29:53 |  | 2026-02-24 | 2026-02-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-26 10:52:14 | Yes | Yes | 2026-02-24 11:50:16 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:08:18 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 21:20:30 |  |  | 2026-03-12 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-10 11:00:57 | No | No |  | 7-Feb-2026 Add Replace BBU5900 UMPTg2 Add g3a =2 g2 =1 ติด GPS ไม่ได้ไม่มีพื้นที่ |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-02-07 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D229A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Maenieo Yek3_1 | 2026-01-29 |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-07 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 20:40:35 | Yes | Yes | 2026-02-11 20:40:36 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-09 09:23:58 | Yes | Yes | 2026-02-28 21:30:34 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-01 | 2026-03-10 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:08:37 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-28 22:48:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-29 14:54:27 | No | No |  | 29-Jan-2026 Add UBBPg3a Remove g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D270A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI MUBAN PHIBUN WATTHANA 5 Small Cell 2 |  |  |  |  | 2026-03-24 | 2026-03-04 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-21 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:17:11 | Yes | Yes | 2026-03-23 15:17:11 |  | 2026-04-10 | 2026-04-09 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-04-10 00:03:10 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-10 | 2026-04-09 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-10 00:20:54 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-04 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-04 17:37:40 | No | No |  | 4-Mar-2026 Add RRU5526 Sector A Remove RRU3962 Replace Ant 4port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D292B_2025 Capacity Expansion NW Modernization_EXP_BKK | SUKHUMVIT 22_5 serve condo | [5 empty] | 2026-05-20 | 2026-05-20 | Narongsak wanichachiwa | N/A | Closed | 2026-05-20 17:15:58 | No | No |  |  | 2026-05-18 | 2026-05-25 | 2026-05-21 | 2026-05-22 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-05-22 11:17:54 | Yes | Yes | 2026-05-25 16:56:25 |  |  | 2026-05-27 | OATTAPAN AUTTAHON | Approved | Closed | 2026-09-18 18:28:50 | Yes | Yes | 2026-05-27 18:24:44 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-31 |  | Turnkey Communication Services Public Company Limited. | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-15 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-05-15 16:57:59 | No | No |  | 15-May-26 Replace RRU5507>>RRU5526 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D377A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi kwanpattana |  |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-19 11:37:19 | No | No |  |  | 2026-02-16 | 2026-02-16 | 2026-02-17 | 2026-02-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-22 10:25:07 | Yes | Yes | 2026-02-22 10:27:39 |  | 2026-02-19 | 2026-02-19 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-02 09:35:21 | Yes | Yes | 2026-02-19 11:37:49 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-09 | 2026-06-05 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 21:20:51 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D444A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHAHON YOTHIN 3 (LUECHA 2) Small Cell 5 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-03-22 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:25:04 | Yes | Yes | 2026-03-24 13:59:12 |  | 2026-04-20 | 2026-04-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-03 09:26:53 | Yes | Yes | 2026-04-20 11:35:08 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 17:59:01 | Yes | Yes | 2026-08-01 21:21:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-05 17:48:24 | No | No |  | 5-Feb-2026 Add UBBPg3a Remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D523A_2026 Capacity Expansion Ph2_BKK | NIRAN RESIDENT SRINAKHARIN_9 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D525A_2026 Capacity Expansion Ph2_BKK | NIRAN RESIDENT SRINAKHARIN_11 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D689A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi kiattichai_TOT | 2026-01-29 |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-28 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 18:07:23 | Yes | Yes | 2026-02-11 18:07:24 |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approving | Assigned |  | Yes | Yes | 2026-03-11 21:35:36 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-01 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | No | No |  |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approving | Assigned |  | Yes | Yes | 2026-03-11 21:47:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-29 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-29 19:21:19 | No | No |  | 29-01-2026 add g3a Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D733A_2025 Capacity Expansion NW Modernization_EXP_BKK | RAMA 6 RD.Small Cell 1 TOT |  |  |  |  | 2026-02-14 | 2026-02-14 | 2026-02-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-28 | 2026-02-13 | 2026-02-14 | V Contribute Co., Ltd | N/A | Closed | 2026-02-14 10:12:18 | Yes | Yes | 2026-02-14 10:12:18 |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-03-16 09:29:19 | Yes | Yes | 2026-03-13 10:48:35 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-04 | 2026-03-16 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-10 22:18:50 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-12 17:47:45 | No | No |  | 12-Feb-26 Replace BBU3900 To RRU5900 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D819A_2026 Capacity Expansion Ph1_EXP_BKK | Soi Ruam Jai 14_1 | [5 empty] | 2026-09-05 | 2026-09-05 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-09-30 | 2026-09-12 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 16:30:43 | Yes | Yes | 2026-09-29 18:29:54 | Need GPS surge before & after photo at AD #， and fill remark. Need install 2600 RRU under label at after section. Need to upload install BBU model & SN photo at EQ. Need remove UFLPb model & SN photo at EQ. Need to upload install UPEU model & SN photo at EQ. Need install AAU label at after section. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-20 11:30:46 |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-05 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-09-05 17:12:33 | No | No |  | 5-Sep-2026 add UBBPg3a Add RRU5872 SA Add RRU5516 SA Add Ant 8port 4-Sep-2026 ***Pending UBBPg3a Add RRU5872 SA Add RRU5516 SA Add Ant 8port SA Co 2600700 ///Replace BBU5900 UMPTg2 Add GPS UBBPh2a Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-05 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:13:41 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D841A_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI VIBHAVADI RANGSIT 64 Yeak 7_1 | [5 empty] | 2026-09-23 | 2026-09-23 | Thossapan Chaloemrit | N/A | Closed | 2026-09-23 21:55:28 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-24 15:12:04 | No | No |  |  |  |  | 2026-09-23 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-23 15:09:08 | No | No |  | 2026-09-23 SA Replace RRU3962 to RRU5507 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D857A_2026 Capacity Expansion NW Modernization_EXP_BKK | TOT Pole SOI SAUN PHAK 4 (KHON SONG) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:26:30 |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D860A_2026 Capacity Expansion NW Modernization_EXP_BKK | TOT Pole Soi BOROMRATCHONNANI 67 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:26:58 |  |  | 2026-06-30 | 2026-09-30 | Teloneer Company Limited | N/A | Closed | 2026-09-30 10:41:16 | No | No |  |  |  |  | 2026-09-29 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-09-29 16:34:40 | No | No |  | 2026-09-29 sA replace RRU3962 to RRU5516 replace ant 12 port Replace by BBU5900#，add UBBPg3/add gps |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D934A_2026 Capacity Expansion Ph1_EXP_BKK | Ratchawithi Rd. Small Cell 1 | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:43:41 | No | No |  |  |  | 2026-07-31 | 2026-09-10 | 2026-09-17 | Teloneer Company Limited | N/A | Closed | 2026-09-17 19:27:51 | Yes | Yes | 2026-09-17 19:27:57 | "1.new install all Equipment photo need to upload in checklist 2.Before ODF information photo need to upload 3.Site information and onsite install mismatch need to revise correct information" |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-20 11:31:06 |  |  | 2026-06-30 | 2026-08-26 | Teloneer Company Limited | N/A | Closed | 2026-08-26 16:45:32 | No | No |  |  |  |  | 2026-08-26 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-08-26 19:01:49 | No | No |  | 2026-08-26 SB Add RRU5872 (26 4T)+ No Act. Ant ----------------------------------------------------------------------------------------- ----------------------------------------------------------------------------------------- 6-Aug-2026 ***Pending Add RRU5872 SB wait core optic ///Replace BBU5900 UMPTg2 Add GPS Add g2 g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:10:40 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D947A_2025 Capacity Expansion NW Modernization_EXP_BKK | G.I. Industry Co., Ltd Small Cell |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-11 | 2026-03-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-12 09:16:31 | Yes | Yes | 2026-03-18 09:30:31 |  | 2026-03-25 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-07 09:36:42 | Yes | Yes | 2026-04-01 12:20:07 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-08-07 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:21:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-14 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-14 17:45:28 | No | No |  | 14-02-2026. Replace BBU5900#， UMPTg2#， Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
D958A_2025 Capacity Expansion NW Modernization_EXP_BKK | Ratchawithi Rd. Small Cell 2 | 2026-02-11 |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-11 19:07:38 | No | No |  |  |  | 2026-02-07 | 2026-02-08 | 2026-02-08 | V Contribute Co., Ltd | N/A | Closed | 2026-02-08 20:28:03 | Yes | Yes | 2026-02-08 20:28:03 |  | 2026-02-11 | 2026-02-11 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-11 19:03:43 | Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:12:41 |  | 2026-02-11 | 2026-02-11 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-11 19:09:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-26 18:26:07 | No | No |  | 2026-01-26_Replace to BBU5900 by UMPTg2#， Add UBBPg2#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DDG2M_2025 Capacity Expansion NW Modernization_EXP_BKK | DIN DAENG STATION2 |  |  |  |  | 2026-02-10 | 2026-03-13 | 2026-03-13 | Annop Auyto | N/A | Closed | 2026-03-18 16:37:14 | No | No |  |  |  | 2026-02-21 | 2026-03-09 | 2026-03-13 | V Contribute Co., Ltd | N/A | Closed | 2026-03-13 11:39:53 | Yes | Yes | 2026-03-13 11:39:53 |  | 2026-02-19 | 2026-02-19 | Chonradee Suwapan | Approved | Closed | 2026-02-23 15:57:48 | Yes | Yes | 2026-04-01 15:28:36 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-01 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:13:56 |  | 2026-02-19 | 2026-02-19 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-19 22:08:36 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-28 18:23:24 | No | No |  | 28-01-2026. Replace RRU5507 to AAU5768 S.1#， 3#， RRU3962 to AAU5768 S.2#， UBBPd6 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DINCA_2025 Capacity Expansion NW Modernization_EXP_BKK | DIANA COURT |  |  |  |  | 2026-02-18 | 2026-03-08 | 2026-03-08 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-18 16:37:14 | No | No |  |  |  | 2026-02-28 | 2026-03-08 | 2026-03-08 | V Contribute Co., Ltd | N/A | Closed | 2026-03-08 15:23:39 | Yes | Yes | 2026-03-08 15:23:40 |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-04-19 17:51:55 | Yes | Yes | 2026-04-01 11:14:44 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-16 | 2026-04-19 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-03-17 20:41:12 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-23 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-23 16:17:19 | No | No |  | 23 Feb 2026 Clear pending change SFP s.B 18-Feb-2026 ***Pending Alarm RF Unit CPRI Interface Error //Add RRU5526 SB Remove RRU3962*2 Add g2 remove d6 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DKBKM_2025 Capacity Expansion Ph8_EXP_ER | Ban Donkrabak | 2026-02-06 | Thcp_phet.sa |  |  | 2026-02-28 | 2026-02-06 | 2026-02-06 | Teloneer Company Limited | N/A | Closed | 2026-02-06 17:43:08 | No | No |  |  |  | 2026-02-28 | 2026-02-06 | 2026-02-06 | Teloneer Company Limited | N/A | Closed | 2026-02-06 19:25:24 | Yes | Yes | 2026-02-10 16:28:45 | SQC CLose | 2026-02-28 | 2026-02-10 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-11 17:52:27 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:29 | Yes | Yes | 2026-03-20 16:41:54 |  | 2026-02-28 | 2026-02-07 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:16:52 | Yes | Yes | 2026-02-07 13:27:13 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-06 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-06 19:45:33 | No | No |  | Add UBBPg3a Replace Antenna (MB)_DKBKM_H_1 New L26F5 + NR26 (New RRU5818) + Co Antenna_DKBKM_N_1 |  | 2026-02-09 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-09 18:20:13 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DMMUG_2026 Capacity Expansion Ph1_EXP_SR | Don Mamuang | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-16 | 2026-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-18 20:58:56 | Yes | Yes | 2026-08-23 10:12:55 |  | 2026-08-24 | 2026-08-24 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-28 10:55:10 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-24 | 2026-08-24 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-24 11:52:46 |  | 2026-08-19 | 2026-08-31 | 2026-08-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-17 18:34:58 | No | No |  |  |  |  | 2026-08-17 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-17 17:19:15 | No | No |  | Rep BBU5900#，add h2a*1#，add gps S2 > RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DMSKH_2026 Capacity Expansion Ph1_EXP_SR | Dormitory of Songkhla Hospital | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-07-31 | 2026-07-29 | 2026-07-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-31 21:10:54 | Yes | Yes | 2026-08-06 22:29:15 |  | 2026-08-17 | 2026-08-24 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-24 13:06:32 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:20 | No | No |  |  | 2026-08-17 | 2026-08-17 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-17 13:16:53 |  | 2026-07-29 | 2026-08-31 | 2026-07-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-29 20:12:36 | No | No |  |  |  |  | 2026-07-29 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-29 17:06:33 | No | No |  | add UBBPh2a*1 Rep Ant MB S2 *2 to Ant 8 Port*1 S2 > Rep RRU&Ant 3953*1 to RRU5516LB*1 > Ant Combine MB S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DOHFM_2025 Coverage Expansion Ph1_New_BKK | DO HOME Head Office |  |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-23 14:25:10 | No | No |  |  |  | 2026-02-14 | 2026-03-30 | 2026-04-23 | V Contribute Co., Ltd | N/A | Closed | 2026-04-23 17:01:13 | Yes | Yes | 2026-04-23 17:01:13 |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-05-27 11:35:44 | Yes | Yes | 2026-05-15 16:16:51 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-17 |  | Jutatip Tiprean 84012709 | N/A | Not assigned |  | Yes | No |  |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:44:41 | Yes | Yes | 2026-02-18 22:57:17 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-07 16:34:48 | No | No |  | 7-Feb-2026 Add New BBU 3900 Add RRU3962 S1 S2 S3 Add Ant 4port S1 S2 S3 Add d5=3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-02-16 |  | N/A | Not assigned |  | No | No
DRCHM_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI DARACHAI | [5 empty] | 2026-08-18 | 2026-08-18 | Thossapan Chaloemrit | N/A | Closed | 2026-08-18 00:14:15 | No | No |  |  |  | 2026-08-31 | 2026-08-21 | 2026-08-23 | Teloneer Company Limited | N/A | Closed | 2026-08-23 15:11:34 | Yes | Yes | 2026-08-24 15:43:20 |  | 2026-08-25 | 2026-08-25 | Teloneer Company Limited | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-25 16:46:47 | 1.Need to fill additional work in pg-5. 2.Wrong disamantle antenna model in pg-5 . 3.SOW is duplicate in pg-5 and 11.(pg 11 is correcrt) 4.Wrong install BBP SN in pg-13. 5.Need After : Rectifier View Photo C2 photo in pg-49. 6.Wrong BBPh3a Sn in pg-58. 7.Need 2 more RRU SN#，BBP SN and DCDU SN photos in pg-61. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:27:30 |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-07-22 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-07-22 17:44:29 | No | No |  | 2026-07-22 s1 rmv RRU5507*2 add AAU5775 s1 rmv RRU5507*2 add AAU5775 s2 rmv RRU5507*2 add AAU5775 s6 rmv RRU5507*2 s7 rmv RRU5507*2 s8 rmv RRU5507*2 add UBBPh3a slot4#，#，rmv UBBPd5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:00:10 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DRCHM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | SOI DARACHAI | [5 empty] | 2026-07-10 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 22:30:58 | No | No |  |  |  | 2026-08-08 | 2026-07-11 | 2026-07-11 | Teloneer Company Limited | N/A | Closed | 2026-07-11 19:31:40 | Yes | Yes | 2026-07-13 09:03:51 |  | 2026-07-15 | 2026-08-04 | Payon Thappat(Teloneer Company Limited) | Approved | Closed | 2026-08-31 10:54:28 | Yes | Yes | 2026-08-26 18:57:35 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-18 16:56:59 | No | No |  |  |  | 2026-07-17 | Thossapan Chaloemrit | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-17 12:40:02 |  |  | 2026-08-08 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 13:41:42 | No | No |  |  |  |  | 2026-07-07 | Autumporn Masing WX1434753 | N/A | Closed | 2026-07-07 14:52:25 | No | No |  | 2026-07-07 add g3a at a lot 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:32:15 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
DSFPM_2026 Capacity Expansion Ph1_EXP_SR | Donsak Ferri Pier | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-09 | 2026-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-13 10:17:32 | Yes | Yes | 2026-08-15 16:04:18 |  | 2026-08-19 | 2026-08-31 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-31 08:49:11 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-19 | 2026-08-19 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-19 07:52:12 |  | 2026-08-09 | 2026-08-31 | 2026-08-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-09 18:48:03 | No | No |  |  |  |  | 2026-08-09 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-09 19:15:15 | No | No |  | Rep Card d6*1 to h2a*1 S4 > RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E041A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Ratchawithi Small Cell |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-03-22 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:29:18 | Yes | Yes | 2026-04-01 09:44:27 |  | 2026-04-16 | 2026-04-16 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-03 09:26:53 | Yes | Yes | 2026-04-23 10:57:12 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:22:26 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:57:17 | No | No |  | 2026-02-05_Replace UBBPeb to UBBPg3a(2) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E085A_2026 Capacity Expansion NW Modernization_EXP_BKK | Soi Pradu 55 Small Cell 1 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-08-07 17:42:20 | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E127A_2026 Capacity Expansion NW Modernization_EXP_BKK | Soi Bang Waek 69 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E170A_2025 Capacity Expansion NW Modernization_EXP_BKK | TOT Pole Soi RANG NAM |  |  |  |  | 2026-03-16 | 2026-03-05 | 2026-03-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:44:49 | No | No |  |  |  | 2026-03-20 | 2026-03-22 | 2026-03-22 | V Contribute Co., Ltd | N/A | Closed | 2026-03-22 16:44:26 | Yes | Yes | 2026-03-22 16:44:27 |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-04-08 18:18:41 | PAT first time pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-08 18:25:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-03-05 23:36:54 | No | No |  | 5 Mar 2026 Replace RRU5526 sectorA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E193A_2026 Capacity Expansion NW Modernization_EXP_BKK | TOT Pole RATCHAPHUREK RD. | [5 empty] | 2026-07-17 | 2026-07-17 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-07-17 14:53:45 | No | Yes | 2026-07-10 22:22:59 |  |  | 2026-08-31 | 2026-07-15 | 2026-07-18 | Teloneer Company Limited | N/A | Closed | 2026-07-18 12:15:49 | Yes | Yes | 2026-07-20 10:16:31 |  | 2026-07-20 | 2026-07-22 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-21 11:29:49 | Yes | Yes | 2026-08-05 17:49:18 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Teloneer Company Limited | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-10 22:27:19 |  |  | 2026-06-30 | 2026-07-16 | Teloneer Company Limited | N/A | Closed | 2026-07-16 10:04:12 | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 2026-07-13_Replace RRU3962 to RRU5516 Sector B **Pending UBBPg3a slot0 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-14 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:30:41 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E308A_2025 Capacity Expansion NW Modernization_EXP_BKK | National Housing Authority Huai Khwang PRACHA SONGKHRO 43_7 |  |  |  | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-18 14:30:29 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-12 | 2026-02-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-15 16:19:32 | Yes | Yes | 2026-02-17 13:40:31 |  | 2026-02-18 | 2026-02-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-26 10:52:14 | Yes | Yes | 2026-02-20 09:35:35 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:16:27 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:00:19 | Yes | Yes | 2026-08-01 21:23:55 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-30 18:57:58 | No | No |  | 30-Jan-2026 Add Replace BBU5900 UMPTg2 Add GPS Add UBBPg3a Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E333A_2026 Capacity Expansion NW Modernization_EXP_BKK | CHAI CHIMPHLI PLAZA FRESH MARKET | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 23:30:10 |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E367A_2026 Capacity Expansion NW Modernization_EXP_BKK | CHAI CHIMPHLI PLAZA FRESH MARKET_2 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E396A_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI VIBHAVADI RANGSIT 64 Yeak 1_1 | [5 empty] | 2026-09-24 | 2026-09-24 | Thossapan Chaloemrit | N/A | Closed | 2026-09-28 16:14:22 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-24 15:06:32 | No | No |  |  |  |  | 2026-09-24 | Autumporn Masing WX1434753 | N/A | Closed | 2026-09-24 14:24:06 | No | No |  | 2026-09-24 SA REP RRU3826*1 to RRU5507*1 2T |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E400A_2025 Capacity Expansion NW Modernization_EXP_BKK | TOT Pole SOI PHAHON YOTHIN 11 (SENA RUAM) |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-11 | 2026-03-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-12 09:44:17 | Yes | Yes | 2026-03-17 09:52:05 |  | 2026-03-25 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-31 18:22:22 | Yes | Yes | 2026-04-01 13:13:21 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 21:24:28 |  |  | 2026-02-28 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-16 17:59:46 | No | No |  | 16-02-2026. Replace BBU5900#， UMPTg2#， Add UBBPg2#， UBBPg3a x2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E405A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Phetchaburi 5 Small Cell 1 |  |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-13 10:47:09 | No | No |  |  |  | 2026-02-07 | 2026-02-07 | 2026-02-08 | V Contribute Co., Ltd | N/A | Closed | 2026-02-08 11:20:19 | Yes | Yes | 2026-02-08 11:20:20 | SQC Close | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-12 21:57:32 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:01 | Yes | Yes | 2026-04-09 12:17:23 |  | 2026-02-12 | 2026-02-12 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-12 22:36:00 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-26 17:44:22 | No | No |  | 26-01-2026. Replace BBU5900#， UMPTg2 10G#， Add UBBPg3a x2 #，GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E492A_2026 Capacity Expansion Ph1_EXP_BKK | SOI CHARAN SANIT WONG 49 (ATSAWA MIT) | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:43:41 | No | No |  |  |  | 2026-07-31 | 2026-09-04 | 2026-09-10 | Teloneer Company Limited | N/A | Closed | 2026-09-10 20:17:26 | Yes | Yes | 2026-09-16 10:47:39 | 1.Need to upload dismantle AAU 1 pcs removed process in Before. 2.Need to revise ODF-BBU label for 2600 RRU in QC. 3.Need to upload BBU-ODF label for RRU 2pcs in QC. | 2026-09-16 | 2026-09-16 | Boonchot Boriwut | Approving | Assigned |  | Yes | Yes | 2026-09-24 13:58:09 | Page 5 Add Circuit Breaker 16 A 1P not found in QC EQ. (Need to revise) Page 34 16A-1P 2pcs Breaker not found Activity . | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-20 11:31:25 |  |  | 2026-06-30 | 2026-08-26 | Teloneer Company Limited | N/A | Closed | 2026-08-26 12:01:50 | No | No |  |  |  |  | 2026-08-24 | Autumporn Masing WX1434753 | N/A | Closed | 2026-08-24 18:22:40 | No | No |  | 2026-08-24 S3 RMV AAU3940*2 S3 ADD RRU3962*1 2T Downgrade 4>2 S3 ADD RRU5872*1 4T S3 Add ANT 4 port //no ret ----------------------------------- 2026-08-07 add g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:10:40 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E717A_2025 Capacity Expansion Ph8_EXP_BKK | Soi Naradhiwas Rajanagarindra 10. Small Cell - TOT |  |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-27 13:27:45 | No | No |  |  |  | 2026-02-12 | 2026-02-17 | 2026-02-18 | V Contribute Co., Ltd | N/A | Closed | 2026-02-18 09:53:37 | Yes | Yes | 2026-02-18 09:53:37 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-05-06 18:21:02 | Yes | Yes | 2026-03-09 18:06:49 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-26 21:28:08 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 11-Feb-26 Add AAU5246 S1 **//Pending Clear Alarm Power to Low// |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E744A_2026 Capacity Expansion NW Modernization_EXP_BKK | Soi Sukhumvit 64 Small Cell (TOT Pole) |  |  |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-10 09:50:03 | No | No |  |  | 2026-06-25 | 2026-06-25 | 2026-06-28 | 2026-07-21 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-21 21:09:27 | Yes | Yes | 2026-07-21 21:12:34 |  | 2026-07-08 | 2026-07-08 | Mahadee Japakiya | Approved | Closed | 2026-10-01 00:37:25 | Yes | Yes | 2026-07-10 10:59:03 | 1.Page 44#，In MDB box ODF label wrong. 2.Page 46#，In EQ need to fill Splitter SN. | Not Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-08-07 17:42:20 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-08 | 2026-07-08 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-07-08 21:49:37 |  |  | 2026-06-25 | 2026-07-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-27 14:14:36 | No | No |  |  |  |  | 2026-06-25 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-06-25 20:03:51 | No | No |  | 25-06-2026. Replace RRU392 to RRU5526 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E795A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHETCHABURI 19 (CHUNLADIT) |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 16:26:40 | No | No |  |  |  | 2026-02-28 | 2026-02-21 | 2026-02-21 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-21 15:00:08 | Yes | Yes | 2026-02-24 16:25:07 |  | 2026-04-03 | 2026-04-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-05-25 16:00:25 | Yes | Yes | 2026-04-20 11:56:02 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-05-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 19:54:02 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-20 18:47:26 | No | No |  | 2026-02-20_Replace RRU3962 to RRU5526#， Replace to Ant 12 port Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E858A_2025 Capacity Expansion Ph8_EXP_BKK | Soi Chan 41/1 |  |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | Chonradee Suwapan(V Contribute Co., Ltd) | N/A | Closed | 2026-04-23 14:25:10 | No | No |  |  |  | 2026-02-12 | 2026-04-23 | 2026-04-23 | V Contribute Co., Ltd | N/A | Closed | 2026-04-23 16:03:46 | Yes | Yes | 2026-04-23 16:03:46 |  | 2026-04-24 | 2026-04-24 | Chonradee Suwapan | Approved | Closed | 2026-05-07 15:52:42 | Yes | Yes | 2026-04-24 02:28:26 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-16 | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-24 | 2026-04-24 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-24 17:40:54 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-12 17:47:45 | No | No |  | 12-Feb-26 Add AAU5246 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E864A_2025 Capacity Expansion NW Modernization_EXP_BKK | Small Cell Soi Pracha Songkhro 2 (Suthiporn) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-05 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:32:04 | Yes | Yes | 2026-03-24 10:59:23 |  | 2026-04-20 | 2026-04-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-03 09:26:53 | Yes | Yes | 2026-04-24 12:12:09 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 21:25:27 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Replace UBBPg3a to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E864A_2025 Capacity Expansion Ph8_EXP_BKK | Small Cell Soi Pracha Songkhro 2 (Suthiporn) | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-07-14 22:47:28 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E865A_2025 Capacity Expansion NW Modernization_EXP_BKK | Small Cell SOI SOM PRATTHANA YAEK 3 |  |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-06 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-07 07:32:17 | No | No |  |  |  | 2026-02-07 | 2026-03-08 | 2026-03-08 | V Contribute Co., Ltd | N/A | Closed | 2026-03-08 11:54:18 | Yes | Yes | 2026-03-08 11:54:18 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-02-17 17:18:26 | Yes | Yes | 2026-02-06 22:27:56 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:20:49 |  | 2026-02-06 | 2026-02-06 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-06 22:52:28 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-27 15:19:09 | No | No |  | 27-Jan-2025 Replace BBU5900 UMPTg2 Add UBBP g2 Add split GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E892A_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Ratchawithi 18 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-03-22 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:21:18 | Yes | Yes | 2026-03-24 11:34:01 |  | 2026-04-20 | 2026-04-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-03 09:26:53 | Yes | Yes | 2026-04-20 11:51:48 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 21:25:42 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-05 19:48:28 | No | No |  | 5 Feb 2025 add 1UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E898A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI PRADIPHAT 25 |  |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-13 10:47:09 | No | No |  |  |  | 2026-02-07 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 20:12:52 | Yes | Yes | 2026-02-11 20:12:53 |  | 2026-02-10 | 2026-02-10 | Chonradee Suwapan | Approved | Closed | 2026-02-17 17:18:26 | Yes | Yes | 2026-02-10 20:51:59 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:21:26 |  | 2026-02-10 | 2026-02-10 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-10 20:59:06 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-26 17:44:22 | No | No |  | 26-01-2026. Replace UBBPd5 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E931A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI SUTTHIPORN |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:50:46 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-06-02 | 2026-06-16 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-16 09:57:07 | Yes | Yes | 2026-06-16 09:59:49 |  | 2026-06-15 | 2026-06-15 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-03 09:26:53 | Yes | Yes | 2026-06-15 16:48:40 | Page no.20#， need to fill install BBP card SN in EQ. Page no.25#， 26#， need to upload EHS photo. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:01:31 | Yes | Yes | 2026-08-01 21:26:00 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-13 18:58:33 | No | No |  | 13-Feb-26 Replace BBU3900 To RRU5900 Replace RRU5526 S1 S2 S3 6 Feb 2026 Prework Rollback rep BBU |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-06-11 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E945A_2025 Capacity Expansion NW Modernization_EXP_BKK | Small Cell SOI PHETCHABURI 10 |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:10:15 | No | No |  |  |  | 2026-02-28 | 2026-02-11 | 2026-02-25 | V Contribute Co., Ltd | N/A | Closed | 2026-02-25 11:39:59 | Yes | Yes | 2026-02-25 11:40:00 |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-03-16 09:29:19 | Yes | Yes | 2026-05-17 10:56:43 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-14 | 2026-03-16 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-07-20 10:32:17 | Yes | Yes | 2026-03-11 21:50:25 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
E958A_2025 Capacity Expansion NW Modernization_EXP_BKK | Small Cell Kretkaew Apartment |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-13 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:36:48 | Yes | Yes | 2026-03-23 15:36:48 |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-06-26 09:39:44 | Yes | Yes | 2026-04-21 12:23:19 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-18 | 2026-06-29 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-08 11:29:03 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-28 13:58:21 | No | No |  | 28-Feb-2026 Replace Ant 12port No Ret Sector 2 Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EBSMM_2026 Capacity Expansion Ph1_EXP_ER | Electric Power Substation Bangsamak | 2026-09-19 | Team : Thcp_phet.sa Tel : 0924272237 | Clear Pending | 2026-06-01 | 2026-09-30 | 2026-09-19 | 2026-09-19 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-19 08:29:22 | No | No |  |  |  | 2026-09-30 | 2026-09-17 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 10:20:31 | Yes | Yes | 2026-09-23 20:17:15 | 1.This remove RRU SN not found at before on tower#， pls upload and show with red mark. 2.What about this activity#， need to fill at additional? 3.Need to upload EHS photo. | 2026-09-30 | 2026-09-26 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-28 20:11:45 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 | 2026-08-02 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-04 10:24:05 | Yes | Yes | 2026-08-02 11:25:34 |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-18 18:55:04 | No | No |  | Add UBBPh3a + Add UBBPh2a Remove Antenna + (New AAU5775) + Main Dir = 60 + Remove RRU x 1_EBSMM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 180 + Remove RRU x 1_EBSMM_H_2 Remove Antenna + (New AAU5775) + Main Dir = 290 + Remove RRU x 1_EBSMM_H_3 (Co AAU5775) + Main Dir = 60 + Remove RRU x 1_EBSMM_H_6 (Co AAU5775) + Main Dir = 180 + Remove RRU x 1_EBSMM_H_7 (Co AAU5775) + Main Dir = 290 + Remove RRU x 2_EBSMM_H_8 New Sector G (Co AAU5775) + Main Dir = 60_EBSMM_H_G New Sector H (Co AAU5775) + Main Dir = 60_EBSMM_H_H New Sector J (Co AAU5775) + Main Dir = 180_EBSMM_H_J New Sector K (Co AAU5775) + Main Dir = 180_EBSMM_H_K New Sector M (Co AAU5775) + Main Dir = 290_EBSMM_H_M New Sector N (Co AAU5775) + Main Dir = 290_EBSMM_H_N New Antenna (LB)_EBSMM_L_1 New Antenna (LB)_EBSMM_L_2 New Antenna (LB)_EBSMM_L_3 New L26F5 + NR26 (New AAU5656) (Update Ant Height)_EBSMM_N_1 New L26F5 + NR26 (New AAU5656) (Update Ant Height)_EBSMM_N_2 New L26F5 + NR26 (New AAU5656) (Update Ant Height)_EBSMM_N_3 |  | 2026-09-21 | Reungsak Junkong 00927496 | N/A | Closed | 2026-09-21 17:58:15 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 20% , Day2 : 80% , Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EM21M_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | EKAMAI SOI 21 | [5 empty] | 2026-09-04 | 2026-09-04 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-09-30 | 2026-09-12 | 2026-09-21 | Teloneer Company Limited | N/A | Closed | 2026-09-21 14:40:39 | Yes | Yes | 2026-09-29 09:29:05 | 1.Need to upload GPS check photo#， screenshot GPS status from OMC | 2026-10-01 | 2026-10-01 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-10-01 15:13:02 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 16:38:46 |  |  | 2026-09-30 | 2026-09-04 | Teloneer Company Limited | N/A | Closed | 2026-09-04 17:37:21 | No | No |  |  |  |  | 2026-09-04 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-09-04 20:18:28 | No | No |  | 2026-09-04 Replace by BBU5900 + Replace by UMPTg2 Add Card UBBPg2#， UBBPd6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-04 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:12:35 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
EM22M_2025 Capacity Expansion NW Modernization_EXP_BKK | EKAMAI SOI 22 |  |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-16 17:56:33 | No | No |  |  |  | 2026-02-07 | 2026-02-06 | 2026-02-09 | V Contribute Co., Ltd | N/A | Closed | 2026-02-09 12:10:36 | Yes | Yes | 2026-02-09 12:10:36 |  | 2026-02-13 | 2026-02-13 | Chonradee Suwapan | Approved | Closed | 2026-03-16 17:56:27 | Yes | Yes | 2026-03-01 23:10:58 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-02 | 2026-03-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-13 | 2026-02-13 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-13 23:07:50 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-30 16:56:57 | No | No |  | 30-Jan-2026 Add AAU5768 S1 S3 Remove RRU5502 *2 RRU3962 *2 add g3a Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ESPCP_2025 Capacity Expansion NW Modernization_EXP_BKK | ESPLANADE SHOPPING CENTER |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:10:15 | No | No |  |  |  | 2026-02-28 | 2026-03-18 | 2026-03-18 | V Contribute Co., Ltd | N/A | Closed | 2026-03-18 19:46:50 | Yes | Yes | 2026-03-18 19:46:50 |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-04-09 16:11:45 | Yes | Yes | 2026-03-11 21:36:49 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-15 | 2026-04-12 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-07-20 10:32:17 | Yes | Yes | 2026-03-11 21:51:54 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-12 17:47:45 | No | No |  | 12-Feb-26 Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ESPNM_2026 Capacity Expansion Modernize_EXP_ER | Espana Condo Resort Pattaya | 2026-07-24 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-07-31 | 2026-07-24 | 2026-07-24 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-25 11:41:04 | No | No |  |  |  | 2026-07-31 | 2026-07-28 | 2026-07-29 | Teloneer Company Limited | N/A | Closed | 2026-07-29 16:00:32 | Yes | Yes | 2026-07-29 21:04:06 |  | 2026-07-31 | 2026-07-31 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-06 11:40:37 | Yes | Yes | 2026-08-01 00:14:08 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-19 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:20 | No | No |  |  | 2026-07-31 | 2026-07-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-25 12:10:05 | Yes | Yes | 2026-07-24 22:00:58 |  |  | 2026-07-31 | 2026-07-24 | Teloneer Company Limited | N/A | Closed | 2026-07-24 21:24:48 | No | No |  |  |  |  | 2026-07-24 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-24 19:23:10 | No | No |  | Add RRU5505 x 1 + 4T4R_ESPNM_H_1 Add RRU5505 x 1 + 4T4R_ESPNM_H_2 Add RRU5505 x 1 + 4T4R_ESPNM_H_3 Co L21F2 All Sector |  | 2026-07-27 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-27 20:48:17 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ETLDM_2026 Capacity Expansion Ph2_EXP_ER | Easternland | 2026-10-02 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-10-15 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-10-15 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-10-15 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-29 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-29 13:53:16 |  |  | 2026-10-15 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FACOM_2026 Antenna Dualbeam_Replacement_BKK | FACCOM (แฟคคอม) |  |  |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-12 11:56:32 | No | No |  |  | 2026-05-15 | 2026-05-15 | 2026-05-07 | 2026-05-09 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-09 18:56:34 | Yes | Yes | 2026-05-11 11:48:52 |  | 2026-05-12 | 2026-05-12 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-17 16:24:50 | Yes | Yes | 2026-05-12 11:56:22 | PAT Pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 21:56:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-28 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-04-28 17:36:37 | No | No |  | 28-Apr-26 Replace Ant S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FATWB_2025 Capacity Expansion NW Modernization_EXP_BKK | FAIR TOWER |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-03-31 | 2026-03-31 | 2026-03-23 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 16:05:32 | Yes | Yes | 2026-04-03 14:08:42 |  | 2026-04-27 | 2026-04-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-21 16:43:57 | Yes | Yes | 2026-04-27 10:16:11 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-12-29 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 19:54:36 |  |  | 2026-03-31 | 2026-03-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-10 17:51:00 | No | No |  |  |  |  | 2026-03-10 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-10 17:14:42 | No | No |  | 10-Mar-26 Replace RRU3962 To RRU5507*2 S1 S2 Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FMSYM_2026 Capacity Expansion Modernize_EXP_ER | FAMILY TOWN SUKPRAYOON | 2026-08-03 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-08-15 | 2026-08-03 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 18:02:10 | No | No |  |  |  | 2026-08-15 | 2026-08-04 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 10:21:41 | Yes | Yes | 2026-08-06 10:48:28 |  | 2026-08-20 | 2026-08-07 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:57:42 | Yes | Yes | 2026-08-13 07:46:46 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:27 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:15:41 |  |  | 2026-08-15 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 17:05:45 | No | No |  |  |  |  | 2026-08-03 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-03 20:48:06 | No | No |  | Add RRU5508 x 1 + Co NR07 + 4T4R_FMSYM_L_1 Add RRU5508 x 1 + Co NR07 + 4T4R_FMSYM_L_2 Add RRU5508 x 1 + Co NR07 + 4T4R_FMSYM_L_3 Co L21(F2) all sector |  | 2026-08-04 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-04 17:05:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FS04M_2026 Capacity Expansion NW Modernization_EXP_BKK | FLAT SANYABAT 4 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 16:39:42 |  |  | 2026-10-10 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
FSKPL_2026 Capacity Expansion Ph1_EXP_SR | FLAT SONGKHLA POLICE | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-08 | 2026-08-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-16 13:36:37 | Yes | Yes | 2026-08-23 10:12:06 |  | 2026-08-23 | 2026-08-23 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-23 23:04:14 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-07-31 | 2026-08-23 | Aomchun Jittreemit(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-23 19:52:57 |  | 2026-08-08 | 2026-08-31 | 2026-08-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-08 16:27:56 | No | No |  |  |  |  | 2026-08-08 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-08 16:45:48 | No | No |  | Add UBBPh2a*1 Rep Ant MB S3 to Ant 8 Port S3 > RRU5516LB*1 > Ant Combine MB S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G090A_2025 Capacity Expansion NW Modernization_EXP_BKK | Small Cell Soi Sukhumvit 2 |  |  |  |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-07 | 2026-02-20 | 2026-02-20 | V Contribute Co., Ltd | N/A | Closed | 2026-02-20 14:10:32 | Yes | Yes | 2026-02-20 14:10:33 |  | 2026-03-18 | 2026-03-18 | Chonradee Suwapan | Approved | Closed | 2026-04-10 11:05:10 | Yes | Yes | 2026-03-18 22:20:50 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-10 | 2026-04-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-18 | 2026-03-18 | Chonradee Suwapan | Approved | Closed | 2026-07-20 10:32:17 | Yes | Yes | 2026-03-18 22:24:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-27 14:55:37 | No | No |  | 27-Jan-2025 Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G097A_2026 Capacity Expansion NW Modernization_EXP_BKK | Madee Apartment Srinakarin Road | [5 empty] | 2026-07-15 | 2026-07-15 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-07-17 14:53:45 | No | Yes | 2026-07-10 22:23:19 |  |  | 2026-08-31 | 2026-07-15 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 16:44:57 | Yes | Yes | 2026-07-17 10:04:39 |  | 2026-07-17 | 2026-07-23 | Thossapan Chaloemrit(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-04 13:56:17 | Page 1 Need to fil complete DUID. Page 6 #，7 Need to fill Site name . Page 22 Before BBU left Photo Need. Need to upload RRU plug in #， socket wire left and right photo. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Teloneer Company Limited | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-10 22:27:00 |  |  | 2026-06-30 | 2026-08-31 | Teloneer Company Limited | N/A | Closed | 2026-08-31 13:12:16 | No | No |  |  |  |  | 2026-07-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-07-11 16:13:02 | No | No |  | 31-08-2026. clear work 11-07-2026. Replace RRU3962 to RRU5526 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-11 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:30:41 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G117A_2025 Capacity Expansion Ph8_EXP_BKK | SMALL CELL SOI YEN AR KARD 1 |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto | N/A | Closed | 2026-03-16 17:10:15 | No | No |  |  |  | 2026-03-31 | 2026-03-31 | 2026-04-19 | V Contribute Co., Ltd | N/A | Closed | 2026-04-19 17:53:19 | Yes | Yes | 2026-04-19 17:53:19 |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-05-13 19:22:29 | Yes | Yes | 2026-04-26 15:52:48 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-05-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-11 22:04:42 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-16 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-16 19:13:00 | No | No |  | 16-Feb-26 Add RRU5818 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G139A_2025 Capacity Expansion NW Modernization_EXP_BKK | GOVERNMENT SAVING BANK(HQ) |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:54:42 | No | No |  |  | 2026-03-02 | 2026-03-06 | 2026-05-29 | 2026-05-30 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-30 15:34:08 | Yes | Yes | 2026-06-02 10:45:51 |  | 2026-06-09 | 2026-06-09 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-07-31 18:22:41 | Yes | Yes | 2026-06-09 09:20:40 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 19:56:02 |  |  | 2026-03-04 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-28 15:34:24 | No | No |  | 28-Feb-2026 R Replace BBU5900 UMPTg2 g2 g3a d5 GPS ติดไม่ได้พื้นที่อยาในห้อง |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-03-04 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G191A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL - CROSS 2 VIBE SUKUMVIT HOTEL |  |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-27 | 2026-02-11 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 09:47:59 | Yes | Yes | 2026-02-12 09:47:59 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-16 17:56:27 | Yes | Yes | 2026-02-28 21:32:00 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-02 | 2026-03-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-28 22:50:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-13 11:17:44 | No | No |  | 10-02-26 Add UBBPg2=1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G203A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PRADIPAT 13 SMALL CELL |  |  |  |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-10 16:17:32 | No | No |  |  |  | 2026-02-07 | 2026-02-25 | 2026-02-26 | V Contribute Co., Ltd | N/A | Closed | 2026-02-26 12:16:10 | Yes | Yes | 2026-02-26 12:16:10 |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:42:08 | Yes | Yes | 2026-02-09 21:19:12 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:24:33 |  | 2026-02-09 | 2026-02-09 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-09 21:28:47 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-27 16:24:02 | No | No |  | 27-Jan-2025 Replace BBU5900 UMPTg2 Add UBBP g2 Add split GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G256A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL INTHAMARA 51 |  |  |  |  | 2026-02-17 | 2026-03-15 | 2026-03-15 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-18 16:37:14 | No | No |  |  |  | 2026-02-28 | 2026-03-14 | 2026-03-15 | V Contribute Co., Ltd | N/A | Closed | 2026-03-15 12:09:22 | Yes | Yes | 2026-03-15 12:09:22 |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-04-19 17:51:55 | Yes | Yes | 2026-04-01 16:57:16 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-04-19 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:25:03 | Yes | Yes | 2026-03-17 20:42:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-17 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-17 15:35:23 | No | No |  | 17-Feb-26 Add RRU5526 SA SB SC Remove RRU5507 *3 Add g2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G299A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI PRACHA RAT BAMPHEN 1 (TOT) |  |  |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-16 13:39:08 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-12 | 2026-02-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-15 11:39:04 | Yes | Yes | 2026-02-16 11:01:49 |  | 2026-02-16 | 2026-02-16 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-20 10:54:17 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:25:29 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 21:26:52 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-30 18:57:36 | No | No |  | 30-Jan-2026 Add Replace BBU5900 UMPTg2 Add GPS Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G311A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL TOT SOI KOLIT |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-13 13:27:00 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-05 | 2026-02-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-18 11:55:37 | Yes | Yes | 2026-02-18 11:57:56 |  | 2026-02-13 | 2026-02-13 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-23 15:57:48 | Yes | Yes | 2026-02-19 15:45:32 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:25:48 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 21:27:07 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G317A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI INTHAMARA 47 (TOT) |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:29:00 | No | No |  |  | 2026-05-20 | 2026-06-03 | 2026-05-20 | 2026-05-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-27 13:58:58 | Yes | Yes | 2026-05-27 14:03:57 |  | 2026-06-25 | 2026-06-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-07-31 18:22:22 | Yes | Yes | 2026-06-25 16:16:27 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 19:56:35 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-08 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-05-08 17:07:46 | No | No |  | 8 Apr 2026 Add RRU5507 sectorA 2T>4T |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G319A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL TOT SOI PHETCHABURI 6 |  |  |  |  | 2026-02-18 | 2026-03-08 | 2026-03-08 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-18 16:37:14 | No | No |  |  |  | 2026-02-28 | 2026-03-08 | 2026-03-08 | V Contribute Co., Ltd | N/A | Closed | 2026-03-08 18:11:58 | Yes | Yes | 2026-03-08 18:11:59 |  | 2026-04-27 | 2026-04-27 | Chonradee Suwapan | Approved | Closed | 2026-09-04 20:34:46 | Yes | Yes | 2026-04-27 02:03:38 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-15 | 2026-04-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-27 | 2026-04-27 | Chonradee Suwapan | Approving | Assigned |  | Yes | Yes | 2026-04-27 02:08:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-18 12:25:12 | No | No |  | 18-Feb-2026 Upgrade to Single 4T Sector B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G323A_2026 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL PHROMSUWAN BUILDING | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G330A_2025 Capacity Expansion Ph8_EXP_BKK | THE ROOM CONDOMINIUM | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  | 2026-02-16 | 2026-02-28 | 2026-02-17 | 2026-02-17 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-17 16:51:30 | Yes | Yes | 2026-02-18 08:17:40 |  | 2026-02-18 | 2026-02-18 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-05-12 16:26:02 | Yes | Yes | 2026-05-05 13:33:30 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-20 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-02 | 2026-02-02 | Pariyakorn Jearwarakul | Approved | Closed | 2026-07-20 10:32:17 | Yes | Yes | 2026-03-25 16:42:30 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-16 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-16 17:59:46 | No | No |  | 16-02-2026. Add AAU5636w Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G335A_2025 Capacity Expansion NW Modernization_EXP_BKK | GRAND RESIDENCE |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-03-02 | 2026-03-06 | 2026-03-02 | 2026-03-02 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-02 19:47:33 | Yes | Yes | 2026-03-12 10:41:39 |  | 2026-03-30 | 2026-03-30 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-30 12:45:05 | Yes | Yes | 2026-03-30 16:53:00 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-07-29 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 19:56:50 |  |  | 2026-03-04 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-28 14:55:46 | No | No |  | 28-Feb-2026 Add UBBPg2 Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-03-04 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G356A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SUTHIPONG 1/3 |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-17 16:22:25 | No | No |  |  |  | 2026-02-28 | 2026-02-11 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:11:21 | Yes | Yes | 2026-03-23 15:11:22 |  | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-16 22:08:24 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:26:25 |  | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:03:32 | Yes | Yes | 2026-02-16 22:28:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-23 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-23 18:01:39 | No | No |  | 23-01-2026 Add card g2 slot 0 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G367A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI RATCHADA PHISEK 12 SMALL CELL TOT |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | 2026-03-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-24 11:49:43 | No | No |  |  | 2026-02-16 | 2026-02-16 | 2026-03-07 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:15:58 | Yes | Yes | 2026-03-23 15:31:15 |  | 2026-03-24 | 2026-03-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-31 10:10:51 | Yes | Yes | 2026-03-24 11:52:59 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:03:19 | Yes | Yes | 2026-08-01 21:27:21 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-10 19:46:59 | No | No |  | 10-02-2026. Replace RRU5507 to RRU5526 Sec.A#， B#， C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G368A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PRADIPAT 18/1 |  |  |  |  | 2026-02-13 | 2026-02-13 | 2026-02-13 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-13 10:47:09 | No | No |  |  |  | 2026-02-07 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 19:27:48 | Yes | Yes | 2026-02-11 19:27:49 |  | 2026-02-10 | 2026-02-10 | Chonradee Suwapan | Approved | Closed | 2026-02-17 17:18:26 | Yes | Yes | 2026-02-10 20:52:30 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-18 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:26:44 |  | 2026-02-10 | 2026-02-10 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-10 20:59:38 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-26 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-01-26 17:44:22 | No | No |  | 26-01-2026. Replace UBBPd5 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G380A_2026 Capacity Expansion NW Modernization_EXP_BKK | CHOK CHAI 4 SOI 18 SMALL CELL | [5 empty] | 2026-08-18 | 2026-08-18 | Thossapan Chaloemrit | N/A | Closed | 2026-08-18 00:14:15 | No | No |  |  |  | 2026-08-31 | 2026-08-17 | 2026-08-17 | Teloneer Company Limited | N/A | Closed | 2026-08-17 19:30:29 | Yes | Yes | 2026-08-19 14:14:25 |  | 2026-08-25 | 2026-08-25 | Teloneer Company Limited | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-26 09:14:44 | 1.new install is not UPEUc in pg-5.This must be UPEUe-2pcs. 2.Need to fill completely (not GPS) as GPS surge in pg-5. 3.Remove BBU is BBU3900.Revise in pg-5. 4.Need to fill Remove UPEUc in pg-5. 5.SOW is duplicate in pg-5 and 7.Delete pg7. 6.Need to fill Vender name in pg-9. 7.Wrong Vender name in pg-10#，11. 8.Wrong before BBU3900 SN in INV.(pg-12). 9.Wrong after BBPg3 and UMPTg2 SN in INV.(pg-12). 10.Need before DC-RRU#，CPRI indoor/outdoor photos in pg-40.Uploaded photo is wrong. 11.Wrong After: Position: UPEU #， Slot 18#， 19 photo in pg-41. 12.Not install GPS splitter.Revise in pg-51. 13.Need to fill install GPS surge in pg-51. 14.Delete one UPEU SN in pg-53. 15.Need to upload BBP SN in pg-53. 13.Need red mark at new install BBU in pg-32. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-09 | Teloneer Company Limited | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-07-09 10:28:14 |  |  | 2026-06-30 | 2026-08-29 | Teloneer Company Limited | N/A | Closed | 2026-08-29 12:07:57 | No | No |  |  |  |  | 2026-08-13 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-08-13 17:36:48 | No | No |  | 2026-08-13_Replace to BBU5900 by UMPTg2#， Add UBBPg3#， GPS SA Add RRU5507 SB Add RRU5507 2026-08-12 install 9 Jul 2026 Prework |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:00:10 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G392A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL EMMANUELLE |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 16:43:55 | Yes | Yes | 2026-03-04 11:57:38 |  | 2026-04-03 | 2026-04-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-30 12:45:05 | Yes | Yes | 2026-04-03 12:03:29 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 19:57:10 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-21 17:23:23 | No | No |  | 21-02-2026. Replace Ant.12 port Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G396A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI NA THONG, LANE 3 |  |  |  |  | 2026-03-24 | 2026-03-06 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-27 | 2026-03-23 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:12:09 | Yes | Yes | 2026-03-23 15:12:10 |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-09-04 20:34:46 | Yes | Yes | 2026-04-29 22:08:10 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-29 22:24:43 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-06 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-06 19:15:56 | No | No |  | 06-Mar-26 Replace RRU5507 To RRU5526 SA SB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G404A_2025 Capacity Expansion NW Modernization_EXP_BKK | TOT SOI INTAMARA 4 | 2026-01-29 |  |  |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-07 | 2026-02-19 | 2026-02-20 | V Contribute Co., Ltd | N/A | Closed | 2026-02-20 09:45:26 | Yes | Yes | 2026-02-20 09:45:27 |  | 2026-04-20 | 2026-04-19 | Chonradee Suwapan | Approved | Closed | 2026-07-22 16:31:43 | Yes | Yes | 2026-04-20 01:58:26 | Page no.3#，12#，13#，16 wrong site code in watermark.(must be STN2M) Page no.23#， site code and site name wrong. Not update | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-10 | 2026-07-23 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-20 | 2026-04-19 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-20 02:00:27 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-29 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-01-29 18:33:39 | No | No |  | 2026-01-29_Replace to BBU5900 by UMPTg2#， Add UBBPg2#， UBBPg3a(2)#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G404A_2025 Capacity Expansion Ph8_EXP_BKK | TOT SOI INTAMARA 4 |  |  |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | V Contribute Co., Ltd | N/A | Closed | 2026-03-06 15:12:46 | No | No |  |  |  | 2026-03-20 | 2026-03-10 | 2026-03-12 | V Contribute Co., Ltd | N/A | Closed | 2026-03-12 15:02:52 | Yes | Yes | 2026-03-12 15:02:52 |  | 2026-04-30 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-11 09:29:24 | Yes | Yes | 2026-04-30 00:00:07 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-24 | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-30 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-30 00:06:06 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-06 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-03-06 18:42:48 | No | No |  | 2026-03-06_Replace UBBPd5 to UBBPg3a#， Add AAU5246 Sector A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G410A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI SUTTHIPORN 3 |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:54:42 | No | No |  |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-05-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-26 15:17:37 | Yes | Yes | 2026-05-26 15:18:28 |  | 2026-05-31 | 2026-05-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-08 09:24:43 | Yes | Yes | 2026-06-01 00:08:46 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-08 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:28:08 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-07 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-04-07 18:42:27 | No | No |  | 07-Apr-26 Replace RRU3962 >>RRU5507*2 S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G411A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI RATCHADAPHISEK 13 |  |  |  |  | 2026-02-20 | 2026-02-20 | 2026-02-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-17 | 2026-02-20 | V Contribute Co., Ltd | N/A | Closed | 2026-02-20 10:01:03 | Yes | Yes | 2026-02-20 10:01:03 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-05-11 09:29:24 | Yes | Yes | 2026-05-06 01:06:07 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-10 | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-26 21:26:17 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-10 17:06:52 | No | No |  | 10-02-26 Swap BBU3900 To BBU5900 Add GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G431A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL ITTHIKORN MANSION |  |  |  |  | 2026-03-24 | 2026-02-27 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-13 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:21:38 | Yes | Yes | 2026-03-23 15:21:38 |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-04-08 11:19:40 | PAT first time pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-08 11:28:25 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-27 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-27 18:11:04 | No | No |  | 27-02-2026. Replace RRU3962 to RRU5526 Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G451A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI FU SAK |  |  |  |  | 2026-03-03 | 2026-03-03 | 2026-03-03 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-06 18:17:38 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:07:13 | Yes | Yes | 2026-03-23 15:07:14 |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-03-09 09:23:58 | Yes | Yes | 2026-03-05 20:35:56 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-21 | 2026-03-09 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:27:40 |  | 2026-03-05 | 2026-03-05 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:17:02 | Yes | Yes | 2026-03-05 21:06:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-13 16:14:21 | No | No |  | 13-Feb-2026 Add RRU5526 Sector A#， B Remove RRU3962 *2 Replace Ant 12 port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G473A_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI LATPRAO 111/1 SMALL CELL TOT | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G475A_2025 Capacity Expansion NW Modernization_EXP_BKK | ZENZONI GROUP |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:29:00 | No | No |  |  | 2026-04-08 | 2026-04-29 | 2026-04-08 | 2026-04-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-10 11:56:20 | Yes | Yes | 2026-04-17 09:18:31 |  | 2026-06-12 | 2026-06-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-05 09:28:56 | Yes | Yes | 2026-06-12 16:14:00 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 19:57:26 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-06 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-04-06 16:19:51 | No | No |  | 6-Apr-2026 Add RRU5507*2 Sector A Remove RRU3962 Chain |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G505A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL SOI PHARMACARE RATCHADAPHISEK 3 |  |  |  |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-28 | 2026-03-23 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 13:57:30 | Yes | Yes | 2026-03-24 13:57:30 |  | 2026-03-31 | 2026-03-31 | Chonradee Suwapan | Approved | Closed | 2026-04-22 09:39:37 | Yes | Yes | 2026-03-31 00:05:20 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-23 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-31 | 2026-03-31 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-31 00:18:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-25 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-25 18:36:39 | No | No |  | 25-02-2026. Replace RRU3962 to RRU5502 Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G534A_2025 Capacity Expansion NW Modernization_EXP_BKK | RAMA 6 SOI 21 |  |  |  |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:47:30 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:16:28 | Yes | Yes | 2026-03-23 15:16:28 |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-04-19 17:51:55 | Yes | Yes | 2026-03-17 20:23:51 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-17 20:44:20 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-18 18:21:19 | No | No |  | 18-Feb-26 Replace RRU3953 to RRU5516 S1 S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G547A_2025 Capacity Expansion NW Modernization_EXP_BKK | RAMA 6 SOI 23 |  |  |  |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:09:22 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:35:30 | Yes | Yes | 2026-03-23 15:35:30 |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-04-22 09:36:49 | Yes | Yes | 2026-03-14 22:11:14 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-04-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-14 22:24:38 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-18 17:48:09 | No | No |  | 18-02-2026. Replace RRU3962 to RRU5526#， 12 port Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G550A_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI INTHAMARA 47 |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 16:26:40 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-10 | 2026-02-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-13 10:26:53 | Yes | Yes | 2026-02-18 09:14:29 |  | 2026-02-24 | 2026-02-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-02-26 10:52:14 | Yes | Yes | 2026-02-24 11:06:08 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-26 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:29:14 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 21:28:38 |  |  | 2026-03-12 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-07 18:36:19 | No | No |  | 07-02-2026. Replace BBU5900#， UMPTg2#， Add UBBPg3a#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-02-07 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G553A_2025 Capacity Expansion NW Modernization_EXP_BKK | WAT PHRAYAYANG |  |  |  |  | 2026-02-21 | 2026-02-21 | 2026-02-21 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-28 | 2026-02-20 | 2026-02-21 | V Contribute Co., Ltd | N/A | Closed | 2026-02-21 10:34:08 | Yes | Yes | 2026-02-21 10:34:08 |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-04-19 17:51:55 | Yes | Yes | 2026-04-01 11:54:30 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-11 | 2026-04-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-14 22:25:32 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-18 16:03:00 | No | No |  | 18-Feb-2026 Add RRU5526 SA Remove RRU5507 Replace Ant 12port No Ret Add g3a=2 Remove eb d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G566A_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI LAT KRABANG 1 YEAK 2 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G577A_2026 Capacity Expansion NW Modernization_EXP_BKK | SUKHUMVIT 97/1 CAR PARK | [5 empty] | 2026-08-22 | 2026-08-22 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-08-24 21:24:24 | No | Yes | 2026-07-10 22:23:43 |  |  | 2026-08-31 | 2026-09-02 | 2026-09-07 | Teloneer Company Limited | N/A | Closed | 2026-09-07 14:58:32 | Yes | Yes | 2026-09-10 11:23:12 |  | 2026-09-13 | 2026-09-13 | Boonchot Boriwut | Approving | Assigned |  | Yes | Yes | 2026-09-27 08:54:40 | need to upload inventory page. page.5 need to revise GPS or GPS Surge?(pls revise detail) page.5 need to upload UFLPb card page.5 need to revise remove antenna 2pcs page.30 need to upload before and after Alarm Krone page.38 need to upload GPS Surge SN. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Teloneer Company Limited | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-10 22:26:41 |  |  | 2026-06-30 | 2026-08-31 | Teloneer Company Limited | N/A | Closed | 2026-08-31 21:14:25 | No | No |  |  |  |  | 2026-08-04 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-08-04 17:57:31 | No | No |  | 2026-08-06 Clear alarm RRU down done 2026-08-04 SA Add RRU5507 (18/21) SB Add RRU5507 (18/21) Replace by BBU5900 + Replace by UMPTg2 + Add Card UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-22 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:03:37 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G614A_2026 Capacity Expansion Ph1_EXP_BKK | JODD FAIRS DANNERAMIT 1 | [5 empty] | 2026-08-18 | 2026-08-18 | Thossapan Chaloemrit | N/A | Closed | 2026-08-18 00:14:15 | No | No |  |  |  | 2026-07-31 | 2026-08-11 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 16:22:57 | Yes | Yes | 2026-08-17 16:46:24 |  | 2026-08-18 | 2026-08-18 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-08-18 10:17:53 | Page 25 Need to Upload Grounding Kit warping tape . Page 26 Need to Upload Ground under RRU1 . Page 30 Need to upload DC-RRU photo. Need to upload Install OPM photo . | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-20 11:31:44 |  |  | 2026-06-30 | 2026-08-29 | Teloneer Company Limited | N/A | Closed | 2026-08-29 10:20:37 | No | No |  |  |  |  | 2026-08-04 | Autumporn Masing WX1434753 | N/A | Closed | 2026-08-04 14:37:50 | No | No |  | 2026-08-04 SC ADD new RRU5516//use exiting ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:00:10 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G659A_2026 Capacity Expansion NW Modernization_EXP_BKK | Soi On Nut 74/3 (Electric Pole) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
G844A_2025 Coverage Expansion Ph1_New_BKK | MEA soi Samaharn |  |  |  | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-06 | Akhom Srinara | N/A | Closed | 2026-06-06 14:03:41 | No | No |  |  | 2026-06-06 | 2026-06-06 | 2026-06-08 | 2026-06-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-06-09 15:45:55 | Yes | Yes | 2026-06-16 11:40:40 |  | 2026-06-16 | 2026-06-16 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-04 15:09:24 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-06-20 | 2026-06-20 | Future Telecom Co.,Ltd. | Approving | Assigned |  | Yes | Yes | 2026-06-20 00:27:21 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-06-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-06-06 17:38:03 | No | No |  | 06-06-2026. New Site Small Cell Add RRU5507#， Ant.4 port x2 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
GATEP_2025 Capacity Expansion NW Modernization_EXP_BKK | GATEWAY EKKAMAI |  |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-28 | 2026-02-11 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 10:00:53 | Yes | Yes | 2026-02-12 10:00:54 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-16 09:29:19 | Yes | Yes | 2026-02-28 21:32:53 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-02 | 2026-03-16 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-28 22:53:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-10 19:46:59 | No | No |  | 10-02-2026. Replace UBBPd5 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GBCEP_L3_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | Parking East Building B (The Government Complex) | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GCPKM_2026 Capacity Expansion Modernize_EXP_ER | GrandChon Park | 2026-08-03 | Team : thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-08-15 | 2026-08-03 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 18:02:10 | No | No |  |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 17:44:47 | Yes | Yes | 2026-08-05 08:57:23 |  | 2026-08-15 | 2026-08-11 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:57:42 | Yes | Yes | 2026-08-11 10:44:21 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:27 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:16:01 |  |  | 2026-08-15 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 10:34:04 | No | No |  |  |  |  | 2026-08-03 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-03 20:48:25 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_GCPKM_H_2 Co L21(F2) all sector |  | 2026-08-04 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-04 17:05:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1: 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GJTHM_2026 Capacity Expansion Modernize_EXP_ER | Grand Jomtian Hotel | 2026-08-31 | Team : Thcp_phet.sa Tel : 0924272237 | Clear Pending |  | 2026-07-31 | 2026-07-25 | 2026-07-25 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-25 11:41:04 | No | No |  |  |  | 2026-07-31 | 2026-07-31 | 2026-08-06 | Teloneer Company Limited | N/A | Closed | 2026-08-06 09:45:31 | Yes | Yes | 2026-08-07 19:00:54 |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:57:59 | Yes | Yes | 2026-08-12 15:26:59 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-20 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:20 | No | No |  |  | 2026-07-31 | 2026-07-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-25 12:10:05 | Yes | Yes | 2026-07-24 08:03:46 |  |  | 2026-07-31 | 2026-07-25 | Teloneer Company Limited | N/A | Closed | 2026-07-25 11:36:58 | No | No |  |  |  |  | 2026-07-24 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-24 21:28:56 | No | No |  | Add UBBPh3a + Remove Antenna + (New AAU5775) + Main Dir = 20 + Remove RRU x 1_GJTHM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 120 + Remove RRU x 2_GJTHM_H_2 Add RRU5505 x 1 + 4T4R_GJTHM_H_3 (Co AAU5775) + Main Dir = 20 + Remove RRU x 2_GJTHM_H_6 (Co AAU5775) + Main Dir = 120 + Remove RRU x 2_GJTHM_H_7 New Antenna (LB)_GJTHM_L_1 New Antenna (LB)_GJTHM_L_2 New Sector G (Co AAU5775) + Main Dir = 20_GJTHM_H_G New Sector H (Co AAU5775) + Main Dir = 20_GJTHM_H_H New Sector J (Co AAU5775) + Main Dir = 120_GJTHM_H_J New Sector K (Co AAU5775) + Main Dir = 120_GJTHM_H_K |  | 2026-07-24 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-24 21:28:56 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 100% , Day2 : Clear pending | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GMBSA_2026 Capacity Expansion NW Modernization_EXP_BKK | The Government Complex Commemorating His Majesty The Kings 80th (Building B)_South (Small Cell Rooftop) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GMBSP_L1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | The Government Complex Commemorating His Majesty The King's 80th (Building B)_South | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GMCNB_2026 Capacity Expansion NW Modernization_EXP_BKK | Chaeng Watthana Government Complex Building C (North)_Small Cell for Ministry of Digital Economy and Society) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GMCPP_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | Chaeng Watthana Government Complex Building C (Poddaung) | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GMNWT_2026 Capacity Expansion Ph1_EXP_SR | GOVERNMENT OF NARATHIWAT | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-24 | 2026-08-31 | 2026-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-23 21:07:37 | No | No |  |  |  |  | 2026-08-22 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-22 16:53:20 | No | No |  | S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GOCPM_2026 Capacity Expansion NW Modernization_EXP_BKK | Government Office Car Park | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GS32B_2025 Capacity Expansion NW Modernization_EXP_BKK | Government Savings Bank 32 floors (Small cell IBC Floor 8) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-02-16 | 2026-02-16 | 2026-03-23 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:20:55 | Yes | Yes | 2026-04-07 13:37:03 |  | 2026-05-05 | 2026-05-05 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-06 09:05:06 | Yes | Yes | 2026-05-05 09:17:29 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-06 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-07-14 22:49:23 |  |  | 2026-03-18 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-18 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-03-18 17:24:26 | No | No |  | 18-Mar-2026 Add RRU5507*2 Sector D |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
GS32B_2025 Capacity Expansion Ph7_EXP_BKK | Government Savings Bank, 32 floors |  |  |  | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-22 15:59:53 | No | No |  |  | 2026-05-26 | 2026-05-26 | 2026-05-26 | 2026-05-29 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-29 09:59:32 | Yes | Yes | 2026-05-29 10:40:10 |  | 2026-06-22 | 2026-06-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-17 09:29:09 | Yes | Yes | 2026-06-22 15:59:08 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-07-14 22:49:47 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-26 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-05-26 14:44:28 | No | No |  | 26-May-2026 Add RRU5818 Sector A co B Replace Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HAMHM_2025 Capacity Expansion Ph8_EXP_ER | Ban Huai Ang Moo 9 | 2026-02-14 | Thcp_adirek.kh | Install & Integrate |  | 2026-02-28 | 2026-02-14 | 2026-02-14 | Teloneer Company Limited | N/A | Closed | 2026-02-14 16:53:06 | No | No |  |  |  | 2026-02-28 | 2026-02-15 | 2026-02-15 | Teloneer Company Limited | N/A | Closed | 2026-02-15 16:46:13 | Yes | Yes | 2026-02-17 14:06:31 |  | 2026-02-28 | 2026-02-17 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:22:43 | Yes | Yes | 2026-02-17 20:33:06 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:28 | Yes | Yes | 2026-03-20 16:46:39 |  | 2026-02-28 | 2026-02-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-20 08:59:31 | Yes | Yes | 2026-02-17 11:13:46 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-14 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-14 17:38:01 | No | No |  | Add UBBPg3a Replace Antenna (MB)_HAMHM_H_1 New L26F5 + NR26 (New RRU5818) + Co Antenna_HAMHM_N_1 |  | 2026-02-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-18 17:46:06 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HBONM_2026 Capacity Expansion Ph2_EXP_ER | Hubbon |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HCPNM_2026 Capacity Expansion Ph1_EXP_ER | ห้วยชุมพร | 2026-06-15 | Team : thcp_apichat.f Tel : 0960126111 | Clear Pending | 2026-06-01 | 2026-06-30 | 2026-06-13 | 2026-06-13 | Teloneer Company Limited | N/A | Closed | 2026-06-14 13:37:30 | No | No |  |  |  | 2026-06-30 | 2026-06-16 | 2026-06-17 | Teloneer Company Limited | N/A | Closed | 2026-06-17 11:25:23 | Yes | Yes | 2026-06-17 17:26:40 |  | 2026-06-30 | 2026-06-22 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-25 08:23:12 | Yes | Yes | 2026-06-22 17:49:38 |  | First Time Pass | 2026-07-20 | 2026-07-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-20 17:15:56 | No | Yes | 2026-07-20 17:15:44 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-14 15:06:49 | No | No |  |  | 2026-06-30 | 2026-06-15 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:37:15 | Yes | Yes | 2026-06-15 08:08:00 |  | 2026-06-15 | 2026-06-30 | 2026-06-13 | Teloneer Company Limited | N/A | Closed | 2026-06-13 15:06:19 | No | No |  |  |  |  | 2026-06-13 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-06-13 20:36:03 | No | No |  | Add UBBPh3a + Remove Antenna + (New AAU5775) + Main Dir = 325 + Remove RRU x 2_HCPNM_H_1 Replace Antenna (Dualband)_HCPNM_H_2 ReSectorname S2 to S3_HCPNM_L_3 ReSectorname S3 to S4_HCPNM_L_4 New Sector 6 (Co AAU5775) + Main Dir = 325_HCPNM_H_6 New Sector G (Co AAU5775) + Main Dir = 325_HCPNM_H_G New Sector H (Co AAU5775) + Main Dir = 325_HCPNM_H_H New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_HCPNM_L_2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-15 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HCSHM_2026 Capacity Expansion Modernize_EXP_ER | Had Chomtiam Soi 15 | 2026-07-27 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-07-31 | 2026-07-28 | 2026-07-28 | Teloneer Company Limited | N/A | Closed | 2026-07-28 16:32:04 | No | No |  |  |  | 2026-08-20 | 2026-08-01 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 15:32:16 | Yes | Yes | 2026-08-12 20:15:41 |  | 2026-08-20 | 2026-08-13 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:54:54 | Yes | Yes | 2026-08-13 22:46:45 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-20 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:20 | No | No |  |  | 2026-07-31 | 2026-07-27 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-27 17:51:18 |  |  | 2026-07-31 | 2026-07-27 | Teloneer Company Limited | N/A | Closed | 2026-07-27 20:51:06 | No | No |  |  |  |  | 2026-07-27 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-27 21:33:36 | No | No |  | Replace UBBPg3 to UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 40 + Remove RRU x 2_HCSHM_H_1 (Co AAU5775) + Main Dir = 40 + Remove RRU x 2_HCSHM_H_6 New Sector G (Co AAU5775) + Main Dir = 40_HCSHM_H_G New Sector H (Co AAU5775) + Main Dir = 40_HCSHM_H_H Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_HCSHM_H_2 > 43 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_HCSHM_H_3 > 44 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_HCSHM_H_4 > 45 Replace RRU (RRU5516_900) + Co L07 + 4T4R_HCSHM_L_1 Co L21(F2) all sector |  | 2026-07-29 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-29 19:23:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HDTNM_2026 Capacity Expansion Ph1_EXP_SR | Ban Had Tun | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-04 | 2026-08-31 | 2026-09-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-04 11:15:02 | No | No |  |  |  |  | 2026-09-03 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-03 18:11:47 | No | No |  | 3 Sep 2026 Add AAU5656 sector1 add 1UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HJRNM_2026 Capacity Expansion Ph1_EXP_SR | Hong Jarern | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-17 | 2026-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-18 15:44:56 | Yes | Yes | 2026-08-23 17:10:20 |  | 2026-08-24 | 2026-08-24 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-24 13:21:46 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-24 | 2026-08-24 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-24 13:22:54 |  | 2026-08-19 | 2026-08-31 | 2026-08-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-17 15:34:45 | No | No |  |  |  |  | 2026-08-17 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-17 17:19:15 | No | No |  | S2 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HJTKM_2026 Capacity Expansion Ph2_EXP_ER | HadJomtien soi9 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HKG2M_2025 Capacity Expansion NW Modernization_EXP_BKK | HUAY KWANG 2_3G2100 |  |  |  |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-10 16:18:21 | No | No |  |  |  | 2026-01-31 | 2026-01-29 | 2026-01-31 | V Contribute Co., Ltd | N/A | Closed | 2026-01-31 16:01:48 | Yes | Yes | 2026-01-31 16:01:49 |  | 2026-02-07 | 2026-02-07 | Chonradee Suwapan | Approved | Closed | 2026-02-11 09:40:40 | Yes | Yes | 2026-03-09 17:40:49 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:31:08 |  | 2026-02-07 | 2026-02-07 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-07 22:14:00 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-28 20:18:48 | No | No |  | 28-Jan-2026 AAU5768 S1 S2 S3 Remove RRU5507*8 Add g3a Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HKMJM_2026 Capacity Expansion Ph2_EXP_ER | Ban Huaykru moo7 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HKPIM_2026 Capacity Expansion Modernize_EXP_ER | Huai Kapi | 2026-08-06 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-15 | 2026-08-05 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 19:59:26 | No | No |  | Add UBBPh2a Add RRU5505 x 1 + 4T4R_HKPIM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_HKPIM_H_3 Add RRU5505 x 1 + 4T4R_HKPIM_H_4 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_HKPIM_H_9 Replace RRU5508 to (RRU5516_900) + NR07 + 4T4R_HKPIM_L_1 Replace RRU5508 to (RRU5516_900) + Co L07 + NR07 + 4T4R_HKPIM_L_3 Replace RRU5508 to (RRU5516_900) + NR07 + 4T4R_HKPIM_L_4 Co L21F2 all sector |  | 2026-08-20 | 2026-08-06 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 16:45:49 | Yes | Yes | 2026-08-09 17:13:38 |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:57:42 | Yes | Yes | 2026-08-12 16:37:52 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:27 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:16:22 |  |  | 2026-08-20 | 2026-08-06 | Teloneer Company Limited | N/A | Closed | 2026-08-06 17:13:44 | No | No |  |  |  |  | 2026-08-05 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-05 20:19:56 | No | No |  | Add UBBPh2a Add RRU5505 x 1 + 4T4R_HKPIM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_HKPIM_H_3 Add RRU5505 x 1 + 4T4R_HKPIM_H_4 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_HKPIM_H_9 Replace RRU5508 to (RRU5516_900) + NR07 + 4T4R_HKPIM_L_1 Replace RRU5508 to (RRU5516_900) + Co L07 + NR07 + 4T4R_HKPIM_L_3 Replace RRU5508 to (RRU5516_900) + NR07 + 4T4R_HKPIM_L_4 Co L21F2 all sector |  | 2026-08-06 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-06 19:48:17 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% , Day2 : Clear Alarm | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HKTTM_2026 Capacity Expansion Ph2_EXP_ER | Tanonsai Huaikoo-Takiantia |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HMR1M_2026 Capacity Expansion NW Modernization_EXP_BKK | MUBAN HEMARAT1 | [5 empty] | 2026-09-15 | 2026-09-15 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 16:40:35 |  |  | 2026-10-10 | 2026-09-15 | Teloneer Company Limited | N/A | Closed | 2026-09-15 12:02:00 | No | No |  |  |  |  | 2026-09-14 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-14 18:52:20 | No | No |  | 2026-09-14 S1 Replace RRU5507*2 to AAU5775 S2 Replace RRU5507*2 to AAU5775 S3 Add RRU3953 S6 Remove RRU5507*2 S7 Remove RRU5507*2 2026-09-12_UBBPh3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-13 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:31:11 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HMTFM_2026 Capacity Expansion Ph1_EXP_ER | Madsayid Harunmustofa | 2026-07-20 | Team : thcp_apichat.f Tel : 0960126111 | Clear Pending | 2026-06-01 | 2026-07-20 | 2026-07-18 | 2026-07-18 | Teloneer Company Limited | N/A | Closed | 2026-07-18 20:30:31 | No | No |  |  |  | 2026-07-20 | 2026-07-21 | 2026-07-22 | Teloneer Company Limited | N/A | Closed | 2026-07-22 15:46:15 | Yes | Yes | 2026-07-22 15:48:10 |  | 2026-07-20 | 2026-07-22 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:40 | Yes | Yes | 2026-07-22 17:02:25 |  | First Time Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:34:22 | No | Yes | 2026-09-12 10:31:43 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-14 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:47 | No | No |  |  | 2026-07-20 | 2026-07-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-20 21:36:40 | Yes | Yes | 2026-07-16 10:21:22 |  |  | 2026-07-20 | 2026-07-20 | Teloneer Company Limited | N/A | Closed | 2026-07-20 14:05:30 | No | No |  |  |  |  | 2026-07-18 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-18 20:07:09 | No | No |  | Replace UBBPd5 to UBBPh2a + Add UBBPg3a ืnot finish (add g3a only) Replace Antenna (Dualband) + Add RRU5505 x 1 + 4T4R_HMTFM_H_1 Replace Antenna (Dualband) + Add RRU5505 x 1 + 4T4R_HMTFM_H_2 Replace Antenna (Dualband) + Add RRU5505 x 1 + 4T4R_HMTFM_H_3 Replace Antenna (Dualband) + Add RRU5505 x 1 + 4T4R_HMTFM_H_4 ReSectorname S1 to S2 + Replace Antenna (Co Antenna)_HMTFM_L_2 done ReSectorname S2 to S3 + Replace Antenna (Co Antenna)_HMTFM_L_3 done ReSectorname S3 to S4 + Replace Antenna (Co Antenna)_HMTFM_L_4 done New L26F5 + NR26 (New AAU5656)_HMTFM_N_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_HMTFM_L_1 |  | 2026-07-20 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-20 20:57:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 40% , Day2 : 100% , Day3 : Clear work | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HNRNM_2026 Capacity Expansion Ph2_EXP_ER | Hat Namrin |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HPHTB_2026 Capacity Expansion Ph1_EXP_SR | Health Promoting Hospital Tambon Ban Muang Ngam | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-08-25 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | 1.Need to upload Antenna M tilt#， Azimuth photos in Before. 2.Need to upload BBU left & right in Before. 3.Need to revise RRU-BBU indoor label in QC. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-15 | 2026-08-31 | 2026-08-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-17 20:30:50 | No | No |  |  |  |  | 2026-08-15 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-15 17:15:27 | No | No |  | Clear plan Add UBBPh2a*1 Rep Ant MB S1 S1 > RRU5516*1 > Ant Combine MB S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HPTNM_2026 Capacity Expansion Ph1_EXP_SR | Ban Houy Plu Tuen | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  | 2026-07-26 | 2026-07-26 | 2026-07-26 | 2026-07-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-26 17:09:37 | Yes | Yes | 2026-08-07 19:09:17 |  | 2026-08-08 | 2026-08-18 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 11:10:12 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-08 | 2026-08-08 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-08 14:16:28 |  | 2026-07-26 | 2026-08-31 | 2026-07-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-26 17:59:37 | No | No |  |  |  |  | 2026-07-26 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-26 18:06:09 | No | No |  | S2 > Rep RRU&Ant 3953*1 to 5516LB > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HRRYM_2026 Capacity Expansion Ph1_EXP_ER | Hemmaraj Rayong RIL | 2026-08-10 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-08-20 | 2026-08-10 | 2026-08-10 | Teloneer Company Limited | N/A | Closed | 2026-08-10 17:15:32 | No | No |  |  |  | 2026-08-20 | 2026-08-11 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 20:28:18 | Yes | Yes | 2026-08-13 12:35:10 |  | 2026-08-20 | 2026-08-13 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:54:54 | Yes | Yes | 2026-08-13 19:25:22 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:28 | No | No |  |  | 2026-08-20 | 2026-08-14 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:52:24 | Yes | Yes | 2026-08-14 15:12:38 |  |  | 2026-08-20 | 2026-08-10 | Teloneer Company Limited | N/A | Closed | 2026-08-10 17:04:59 | No | No |  |  |  |  | 2026-08-10 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-10 16:00:07 | No | No |  | Replace Antenna (Dualband)_HRRYM_H_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_HRRYM_L_1 |  | 2026-08-11 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-11 15:10:03 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HTPGM_2026 Capacity Expansion Modernize_EXP_ER | Hat Thampang | 2026-09-09 | Team : Thcp_phet.sa Tel : 0924272237 |  |  | 2026-09-20 | 2026-09-09 | 2026-09-09 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-09 17:43:17 | No | No |  |  |  | 2026-09-20 | 2026-09-10 | 2026-09-14 | Teloneer Company Limited | N/A | Closed | 2026-09-14 17:29:51 | Yes | Yes | 2026-09-15 10:19:16 | Need to upload Panorama. | 2026-09-20 | 2026-09-15 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:44:45 | Yes | Yes | 2026-09-17 12:51:47 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-16 | 2026-09-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:46:21 | Yes | Yes | 2026-09-08 13:48:43 |  |  | 2026-09-20 | 2026-09-09 | Teloneer Company Limited | N/A | Closed | 2026-09-09 19:54:29 | No | No |  |  |  |  | 2026-09-09 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-09 17:16:59 | No | No |  | Replace RRU (RRU5526) + 4T4R_HTPGM_H_A Replace RRU (RRU5526) + 4T4R_HTPGM_H_B |  | 2026-09-10 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-10 15:59:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HTRTM_2026 Capacity Expansion Ph2_BKK | HATHAIRAT RD. | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HTSLA_2026 Capacity Expansion Ph1_EXP_SR | Hat Thong Sala | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-24 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 |  | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | N/A | Assigned |  | Yes | No |  |  | 2026-09-24 | 2026-08-31 | 2026-09-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-25 14:56:03 | No | No |  |  |  |  | 2026-09-24 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-24 18:34:35 | No | No |  | 24 Sep 2026 Add DMM AAU5775 sector1 add1UBBPh3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HUALT_2026 Capacity Expansion Ph1_EXP_SR | Mu 3 Huai Lot | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-26 | 2026-08-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-27 10:20:16 | Yes | Yes | 2026-08-31 10:11:25 |  | 2026-08-31 | 2026-08-31 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-31 14:57:16 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-31 | 2026-08-31 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-31 14:58:29 |  | 2026-08-26 | 2026-08-31 | 2026-08-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-26 15:04:38 | No | No |  |  |  |  | 2026-08-26 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-26 17:45:51 | No | No |  | 26 Aug 2026 Replace RRU5516 sector2 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HUCBA_2025 Capacity Expansion NW Modernization_EXP_BKK | HUA CHANG BRIDGE |  |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-01-31 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 20:16:04 | Yes | Yes | 2026-02-11 20:16:04 |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-18 22:47:22 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:32:04 |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:03:32 | Yes | Yes | 2026-02-18 22:54:27 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-28 15:26:21 | No | No |  | 28-Jan-2026Add Add g3a Remove d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HUSRM_2026 Capacity Expansion Ph2_EXP_ER | Hua Samrong | 2026-09-22 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-09-30 | 2026-09-22 | 2026-09-22 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-23 06:46:22 | No | No |  |  |  | 2026-09-30 | 2026-09-23 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 17:11:24 | Yes | Yes | 2026-09-27 22:15:46 |  | 2026-09-30 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-10-02 00:53:37 | Already upload New PAT DOC Please check 01/10/2026 1.Page 24#， Need to upload DC-AAU indoor label photo. 2.Page 34#， Need to upload page completely. Not update | Not Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:42:32 | Yes | Yes | 2026-09-22 08:18:10 |  |  | 2026-09-30 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 16:58:20 | No | No |  |  |  |  | 2026-09-22 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-22 16:26:33 | No | No |  | Replace UBBPg1 to UBBPg3a New L26F5 + NR26 (New AAU5656)_HUSRM_N_6 |  | 2026-09-23 | Reungsak Junkong 00927496 | N/A | Closed | 2026-09-23 16:35:58 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
HVLXB_2025 Capacity Expansion NW Modernization_EXP_BKK | HAVEN LUXE |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-03-14 | 2026-03-14 | 2026-03-14 | 2026-03-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-15 10:32:06 | Yes | Yes | 2026-04-17 09:01:23 |  | 2026-05-05 | 2026-05-05 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-02 09:19:52 | Yes | Yes | 2026-05-12 19:46:53 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:04:30 | Yes | Yes | 2026-08-01 19:57:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-13 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-13 18:20:07 | No | No |  | 12 Mar 2026 Replace BBU5900 UMPTg2 Add g3a Add RRU5502 S1 Remove RRU3962 Replace Ant 12port No Ret ติดตั้ง GPS ไม่ได้ |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
INNEM_2026 Capacity Expansion Modernize_EXP_ER | Innex Chemical Co.,Ltd | 2026-08-07 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-20 | 2026-08-07 | 2026-08-07 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-07 21:41:11 | No | No |  |  |  | 2026-08-20 | 2026-08-08 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 14:47:05 | Yes | Yes | 2026-08-13 12:34:52 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:50 | Yes | Yes | 2026-08-16 17:15:32 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:28 | No | No |  |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-13 11:59:25 |  |  | 2026-08-20 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 12:33:14 | No | No |  |  |  |  | 2026-08-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-07 19:41:33 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_INNEM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_INNEM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_INNEM_H_3 (NO RET) have only L18 |  | 2026-08-07 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-07 19:31:01 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IT36M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI INTHAMARA 36 | 2026-01-29 |  |  |  | 2026-02-14 | 2026-02-14 | 2026-02-14 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-07 | 2026-02-12 | 2026-02-14 | V Contribute Co., Ltd | N/A | Closed | 2026-02-14 15:42:56 | Yes | Yes | 2026-02-14 15:42:57 |  | 2026-02-28 | 2026-02-28 | Chonradee Suwapan | Approved | Closed | 2026-03-06 15:45:14 | Yes | Yes | 2026-03-10 16:02:19 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:00 | Yes | Yes | 2026-04-09 12:33:38 |  | 2026-02-27 | 2026-02-27 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-27 01:32:50 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-30 11:19:35 | No | No |  | 30-Jan-2026 Config RET 700900 S2 subrack101 29-01-2026 ON DMM 1#，2#，3#， sector 2 add rru 3953 #2 07/09 Done. Pending Ret 07/09 not detect.wait fix |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ITBHP_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | Intercontinental Bangkok hotel | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:43:41 | No | No |  |  |  | 2026-09-30 | 2026-08-26 | 2026-08-27 | Teloneer Company Limited | N/A | Closed | 2026-08-27 09:40:22 | Yes | Yes | 2026-09-02 18:22:33 |  | 2026-10-03 | 2026-09-03 | Payon Thappat(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-03 10:11:26 | 1.Wrong After:Position:UPEU #， Slot 18#， 19 photo in pg-11. 2.Need INV file. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 16:42:04 |  |  | 2026-08-31 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-21 12:20:50 | No | No |  |  |  |  | 2026-08-20 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-08-20 19:16:48 | No | No |  | 2026-08-20 Replace Card UBBPd6 > UBBPh2a ----------------------------------------------------------------------------------------- ----------------------------------------------------------------------------------------- |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:10:40 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IW36M_2026 Capacity Expansion NW Modernization_EXP_BKK | INTRAWAT 36 | [5 empty] | 2026-09-07 | 2026-09-07 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-10-10 | 2026-09-14 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 21:18:05 | Yes | Yes | 2026-09-25 21:18:27 | 1. Need to upload After wire strip at DCDU in S1 at after 2.Need to upload M Tilt#，Zoom Compass of Azimuth 3.Can't see clearly Zoom Left Side of BBU at after |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 16:43:22 |  |  | 2026-10-10 | 2026-09-07 | Teloneer Company Limited | N/A | Closed | 2026-09-07 15:31:11 | No | No |  |  |  |  | 2026-09-05 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-05 17:38:06 | No | No |  | 5-Sep-2026 Add UBBPh3a Add RRU5526 S1 Rmv RRU3962 *2 Add AAU5775 S2 Rmv RRU3962 *2 Rmv RRU3962 *2 S7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-07 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:14:19 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IW36M_2026 Capacity Expansion Ph2_BKK | INTRAWAT 36 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IYRMM_2026 Capacity Expansion NW Modernization_EXP_BKK | IYARA MANAGEMENT | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-08 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-08 22:02:47 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-19 | Teloneer Company Limited | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-06-19 18:07:20 |  |  | 2026-06-30 | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-01 14:33:09 | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
IYRMM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | IYARA MANAGEMENT | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:52:00 | No | No |  |  |  | 2026-08-08 | 2026-09-03 | 2026-09-03 | Teloneer Company Limited | N/A | Closed | 2026-09-03 19:14:26 | Yes | Yes | 2026-09-04 12:10:29 |  | 2026-09-04 | 2026-09-04 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-09-04 16:29:34 | 1.This site not install GPS splitter.Delete this in pg-5#，17. 2.Need to fill install GPS surge-1pc#，UPEUe-2pcs in pg-5#，17. 3.Need to fill remove UPEUd-2pcs#，UFLPc-1pc in pg-5. 4.Need redmark at install BBU in pg-10. 5.Need install UPEUe-2pcs SN in pg-11. 6.Need remove UPEUd-2pcs#，UFLPc-1pc SN in pg-11. 7.Need install and remove BBU SN in pg-11. 8.Need After:DC-RRU#， CPRI photo in pg-12. 9.Install BBU is 5900.So fill BBU5900 and wrong BBU SN in pg-7. 10.No need to fill remove BBU and UMPTb1 in pg-17. | Not Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-07-08 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-08 22:02:47 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:28:08 |  |  | 2026-08-08 | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-01 14:38:16 | No | No |  |  |  |  | 2026-09-01 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-09-01 15:34:38 | No | No |  | 2026-09-01 Replace by BBU5900#，add UBBPg3#，add GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:10:40 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JKPAM_2026 Capacity Expansion Modernize_EXP_ER | J.K. Place Amata Chonburi | 2026-08-17 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-08-20 | 2026-08-17 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-18 08:59:40 | No | No |  |  |  | 2026-08-20 | 2026-08-18 | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-18 17:20:56 | Yes | Yes | 2026-08-21 10:32:55 |  | 2026-08-20 | 2026-08-27 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-28 23:19:56 | Yes | Yes | 2026-08-27 09:48:06 |  | First Time Pass |  |  | ABC THAI COMPANY LIMITED | N/A | Not assigned |  | No | No |  |  |  |  | ABC THAI COMPANY LIMITED | N/A | Not assigned |  | No | No |  |  |  | 2026-09-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-18 16:56:59 | No | No |  |  | 2026-08-20 | 2026-08-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-18 09:05:14 |  |  | 2026-08-20 | 2026-08-17 | Teloneer Company Limited | N/A | Closed | 2026-08-17 15:24:13 | No | No |  |  |  |  | 2026-08-17 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-17 16:57:31 | No | No |  | Replace RRU3962x2 to RRU5505 x 2_JKPAM_H_2 Replace RRU3962x2 to RRU5505 x 2_JKPAM_H_3 |  | 2026-08-17 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-17 17:01:03 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JMGRA_2025 Capacity Expansion NW Modernization_EXP_BKK | Jasmine Grande Residence Hotel |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-03-01 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-01 10:41:03 | Yes | Yes | 2026-03-04 10:57:08 |  | 2026-04-03 | 2026-04-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-24 09:38:39 | Yes | Yes | 2026-06-18 10:16:45 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-07-02 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 21:30:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-06 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-06 19:00:44 | No | No |  | 6 Feb 2026 Replace RRU5526 sector1#，2 Add 1Ug3a Ug2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOASM_D2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | JOAN OF ARC HIGH SCHOOL |  |  |  | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-06-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-26 18:54:47 | No | No |  |  | 2026-06-23 | 2026-06-23 | 2026-06-25 | 2026-06-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-26 16:47:51 | Yes | Yes | 2026-07-02 09:45:23 |  | 2026-07-02 | 2026-07-08 | Mahadee Japakiya(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-26 20:54:22 | Yes | Yes | 2026-07-08 22:01:32 | Pg-24-More EHS photos need to upalod. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-27 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-28 11:46:38 | No | No |  |  | 2026-07-08 | 2026-07-08 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-07-08 21:50:01 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-06-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-06-20 18:43:06 | No | No |  | 20-06-2026. Replace UBBPd5 to UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
JOMPM_RET_2025_RepSGR_NER | JOM POL |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-19 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 11:48:42 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-25 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 10:30:03 | No | No |  |  | DTH1202609100011 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
K7RNM_2026 Capacity Expansion Ph2_BKK | KLONG 7 RANGSIT NAKHORN NAYOK | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAKIM_2026 Capacity Expansion Ph1_EXP_SR | Ban Khao Kai | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-12 | 2026-08-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-14 12:32:35 | Yes | Yes | 2026-08-14 18:02:24 |  | 2026-08-19 | 2026-08-25 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-25 12:12:32 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-19 | 2026-08-19 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-19 03:35:49 |  | 2026-08-12 | 2026-08-31 | 2026-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-12 19:51:05 | No | No |  |  |  |  | 2026-08-12 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-12 19:27:23 | No | No |  | Rep Card g2*1 to h2a*1 Rep Ant MB S4 to 8 Port S4 > RRU5516LB*1 > Ant Combine MB S4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KANUM_2026 Capacity Expansion Ph1_EXP_SR | Ban Wat Khanun | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-29 | 2026-07-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-30 09:47:01 | Yes | Yes | 2026-08-06 16:00:08 |  | 2026-08-07 | 2026-08-13 | Charuwan Limsaihua | Approved | Closed | 2026-08-28 16:01:00 | Yes | Yes | 2026-08-13 10:06:29 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:05 | No | No |  |  | 2026-08-07 | 2026-08-07 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-07 14:03:56 |  | 2026-07-30 | 2026-08-31 | 2026-07-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-29 20:37:53 | No | No |  |  |  |  | 2026-07-29 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-29 17:07:11 | No | No |  | S4 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KAPOM_2026 Capacity Expansion Ph1_EXP_SR | Ka Pho | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-26 | 2026-09-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-29 17:27:43 | Yes | Yes | 2026-09-29 17:34:32 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-26 | 2026-08-31 | 2026-09-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-27 19:54:00 | No | No |  |  |  |  | 2026-09-26 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-26 16:31:07 | No | No |  | 26 Sep 2026 Add DMM add AAU5775 sector1 add 1UBBPh3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KATGM_2026 Capacity Expansion Ph1_EXP_SR | KANTANG | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-31 | 2026-07-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-31 17:40:50 | Yes | Yes | 2026-08-10 10:56:29 |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-11 15:51:43 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-11 15:54:04 |  | 2026-07-31 | 2026-08-31 | 2026-07-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-31 14:15:12 | No | No |  |  |  |  | 2026-07-31 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-07-31 17:28:56 | No | No |  | 31 July 2026 Add RRU5516 sector6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KBOIS_2026 Capacity Expansion Ph1_EXP_SR | Ku Bo Isalam Padang Be Sa | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-29 | 2026-08-01 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-01 18:21:45 | Yes | Yes | 2026-08-06 15:47:10 |  | 2026-08-07 | 2026-08-13 | Charuwan Limsaihua | Approved | Closed | 2026-08-28 16:01:00 | Yes | Yes | 2026-08-13 10:07:30 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:05 | No | No |  |  | 2026-08-07 | 2026-08-07 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-07 09:52:09 |  | 2026-07-30 | 2026-08-31 | 2026-07-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-29 17:52:11 | No | No |  |  |  |  | 2026-07-29 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-29 17:07:11 | No | No |  | S1 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KCGDM_2026 Capacity Expansion Modernize_EXP_ER | KC Grand Place BanSuan Chonburi | 2026-08-05 | Team : thcp_watcharin.k Tel :0925546852 |  |  | 2026-08-15 | 2026-08-05 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 18:01:59 | No | No |  |  |  | 2026-08-20 | 2026-08-06 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 12:28:42 | Yes | Yes | 2026-08-09 15:13:36 |  | 2026-08-20 | 2026-08-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:54:09 | Yes | Yes | 2026-08-09 19:24:21 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:28 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:17:03 |  |  | 2026-08-15 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 11:09:58 | No | No |  |  |  |  | 2026-08-05 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-05 10:41:59 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KCGDM_H_1 Co L21F2 All Sector |  | 2026-08-06 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-06 19:48:17 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KDINM_2026 Capacity Expansion Ph1_EXP_SR | Ban Khuan Din | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-24 | 2026-08-31 | 2026-09-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-30 12:24:02 | No | No |  |  |  |  | 2026-08-23 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-23 18:12:01 | No | No |  | S1 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KDRGM_KKN_2025_RepSGR_NER | KUD RUNG |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-17 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 20:06:38 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-23 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-17 | Teloneer Company Limited | N/A | Closed | 2026-09-17 09:20:02 | No | No |  |  | DTH1202609100016 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
KDSSM_2026 Capacity Expansion Modernize_EXP_ER | Ban KraDorn Soi2 | 2026-08-12 |  |  |  | 2026-08-20 | 2026-08-12 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-13 07:38:13 | No | No |  |  |  | 2026-08-20 | 2026-08-14 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 09:35:33 | Yes | Yes | 2026-08-20 18:17:28 |  | 2026-08-20 | 2026-08-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:47:28 | Yes | Yes | 2026-08-27 00:08:59 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:28 | No | No |  |  | 2026-08-15 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 17:58:32 |  |  | 2026-08-20 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 20:05:15 | No | No |  |  |  |  | 2026-08-12 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-12 20:01:46 | No | No |  | Add UBBPh2a Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KDSSM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KDSSM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KDSSM_H_3 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_KDSSM_L_2 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_KDSSM_L_8 Co L21(F2) all sector |  | 2026-08-13 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-13 17:40:44 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KGP1M_2026 Capacity Expansion NW Modernization_EXP_BKK | KHLONG PREM 1 | [5 empty] | 2026-09-15 | 2026-09-15 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:25:09 |  |  | 2026-10-10 | 2026-09-21 | Teloneer Company Limited | N/A | Closed | 2026-09-21 15:15:57 | No | No |  |  |  |  | 2026-09-15 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-15 18:35:11 | No | No |  | 2026-09-15_Replace UBBPd6 to UBBPh3a S1 Replace RRU3962*2 to AAU5775 S2 Replace RRU5507*2 to AAU5775 S3 Replace RRU3962*2 to RRU5507*2 S6 Remove RRU3962*2 S7 Remove RRU5507*2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-15 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:24:42 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KHASM_2025 Capacity Expansion Ph8_EXP_ER | Ban KhaoSaton | 2026-02-19 | Thcp_adirek.kh | Take Photo & Clear Pending |  | 2026-02-28 | 2026-02-18 | 2026-02-18 | Teloneer Company Limited | N/A | Closed | 2026-02-18 15:51:00 | No | No |  |  |  | 2026-02-28 | 2026-02-19 | 2026-02-19 | Teloneer Company Limited | N/A | Closed | 2026-02-19 17:43:59 | Yes | Yes | 2026-02-24 17:02:13 |  | 2026-02-28 | 2026-02-24 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-25 15:33:46 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:28 | Yes | Yes | 2026-03-24 12:06:29 |  | 2026-02-28 | 2026-02-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-20 08:59:31 | Yes | Yes | 2026-02-18 15:58:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-18 17:48:02 | No | No |  | Replace UBBPg1 to UBBPg2 New L26F5 + NR26 (New RRU5818) + Co Antenna_KHASM_N_1 New L26F5 + NR26 (New RRU5818) + Co Antenna_KHASM_N_2 New L26F5 + NR26 (Co RRU5818) + Co Antenna_KHASM_N_3 |  | 2026-02-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-20 15:06:20 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KHGPO_2026 Capacity Expansion Ph1_EXP_SR | Khlong Pom | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-28 | 2026-07-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-29 10:35:55 | Yes | Yes | 2026-08-10 10:57:01 |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-08-28 16:01:00 | Yes | Yes | 2026-08-11 02:23:09 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:05 | No | No |  |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-11 02:24:17 |  | 2026-07-30 | 2026-08-31 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 15:36:18 | No | No |  |  |  |  | 2026-07-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-28 16:00:24 | No | No |  | S1 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KHHAN_2026 Capacity Expansion Ph1_EXP_SR | Khao Han | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-30 | 2026-08-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-31 11:33:24 | Yes | Yes | 2026-09-02 21:38:58 |  | 2026-09-04 | 2026-09-04 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-04 03:42:23 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-04 | 2026-09-04 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-04 03:46:54 |  | 2026-08-30 | 2026-08-31 | 2026-08-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-30 18:42:25 | No | No |  |  |  |  | 2026-08-30 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-30 19:08:33 | No | No |  | Rep Card d6*1 to h2a*1 S1 > Rrep RRU3953*1 to RU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KHRHM_2026 Capacity Expansion Ph2_BKK | Khlong Rahaeng | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KHWKM_2026 Capacity Expansion Ph1_EXP_ER | Ban KhaoWangKaew | 2026-07-15 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-07-20 | 2026-07-15 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 15:41:01 | No | No |  |  |  | 2026-07-20 | 2026-07-15 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 16:42:03 | Yes | Yes | 2026-07-15 17:30:35 |  | 2026-07-20 | 2026-07-20 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:40 | Yes | Yes | 2026-07-20 16:49:00 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:48 | No | No |  |  | 2026-07-20 | 2026-07-14 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-14 21:10:02 | Yes | Yes | 2026-07-14 20:42:10 |  |  | 2026-07-20 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 12:26:41 | No | No |  |  |  |  | 2026-07-15 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-15 11:09:05 | No | No |  | Add UBBPg3a_KHWKM_H_1 New L26F5 + NR26 (New AAU5656)_KHWKM_N_2 New L26F5 + NR26 (New AAU5656)_KHWKM_N_3 |  | 2026-07-16 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-16 16:29:59 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 60% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KJUKM_2026 Capacity Expansion Ph2_EXP_ER | Khaojuk | 2026-09-30 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : น้ำท่วม | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KKCPM_2026 Capacity Expansion Modernize_EXP_ER | Khaomakok soi2 - Chaiyapruek road | 2026-07-29 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-07-31 | 2026-07-29 | 2026-07-29 | Teloneer Company Limited | N/A | Closed | 2026-07-29 20:34:20 | No | No |  |  |  | 2026-07-31 | 2026-08-03 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 18:05:05 | Yes | Yes | 2026-08-12 11:37:27 |  | 2026-08-20 | 2026-08-15 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:57:42 | Yes | Yes | 2026-08-15 13:33:30 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:08 | No | No |  |  | 2026-07-31 | 2026-07-29 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-29 11:00:15 |  |  | 2026-07-31 | 2026-07-29 | Teloneer Company Limited | N/A | Closed | 2026-07-29 16:39:16 | No | No |  |  |  |  | 2026-07-29 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-29 19:22:40 | No | No |  | Add UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 0 + Remove RRU x 1_KKCPM_H_1 Add RRU5505 x 1 + 4T4R_KKCPM_H_2 >43 Add RRU5505 x 1 + 4T4R_KKCPM_H_3 >44 (Co AAU5775) + Main Dir = 0 + Remove RRU x 1_KKCPM_H_6 New ant 4port + Add RRU5508 x 1 + 4T4R_KKCPM_L_1 Add RRU5508 x 1 + 4T4R_KKCPM_L_2 Add RRU5508 x 1 + 4T4R_KKCPM_L_3 New Sector G (Co AAU5775) + Main Dir = 0_KKCPM_H_G New Sector H (Co AAU5775) + Main Dir = 0_KKCPM_H_H Co L21(F2) S2#，S3#，S4 |  | 2026-07-30 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-30 19:06:52 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KKFJM_2025 Capacity Expansion Ph5_EXP_ER_Add | KYORITSU KIDEN FUJI (THAILAND) CO., LTD. | 2026-03-05 | Thcp_phet.sa | Cancel |  | 2026-03-05 | 2026-05-22 | 2026-05-22 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-05-22 17:58:19 | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2026-02-28 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-02-28 | 2026-02-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:21:34 | Yes | Yes | 2026-02-26 08:03:58 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-25 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-02-25 16:13:49 | Yes | Yes | 2026-02-25 15:38:55 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KKFJM_2026 Capacity Expansion Modernize_EXP_ER | KYORITSU KIDEN FUJI (THAILAND) CO., LTD. | 2026-09-29 | Team : Thcp_phet.sa Tel : 0924272237 | Clear Pending |  | 2026-08-31 | 2026-09-03 | 2026-09-03 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-04 07:44:37 | No | No |  |  |  | 2026-08-31 | 2026-09-03 | 2026-09-07 | Teloneer Company Limited | N/A | Closed | 2026-09-07 09:43:20 | Yes | Yes | 2026-09-07 09:44:52 |  | 2026-08-31 | 2026-09-07 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:37:52 | Yes | Yes | 2026-09-07 13:36:07 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-15 | 2026-08-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-25 16:53:49 | Yes | Yes | 2026-08-24 12:42:30 |  |  | 2026-08-31 | 2026-09-03 | Teloneer Company Limited | N/A | Closed | 2026-09-03 14:51:36 | No | No |  |  |  |  | 2026-09-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-03 18:02:05 | No | No |  | Replace RRU5505 to (RRU5513) + 4T4R_KKFJM_H_A Replace RRU5505 to (RRU5513) + 4T4R_KKFJM_H_B Replace RRU5508 to (RRU5516_900) + Co L07 + NR07 + 4T4R_KKFJM_L_A Replace RRU5508 to (RRU5516_900) + Co L07 + NR07 + 4T4R_KKFJM_L_B **need add cell LNR7 |  | 2026-09-29 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-29 15:21:21 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% , Day2 : ไม่เข้า , Day3 : Clear work | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KKHBM_KKN_2025_RepSGR_NER | KUDKEA HUAYBONG |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-25 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 15:45:21 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-26 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-24 22:20:01 | No | No |  |  | DTH1202609100017 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
KKLWN_2026 Capacity Expansion Ph1_EXP_SR | Ban Khai Ka Lu Wo Nuea | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-22 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-21 | 2026-08-31 | 2026-09-22 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-22 12:17:27 | No | No |  |  |  |  | 2026-09-21 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-21 19:01:00 | No | No |  | Rep d6*1 to h2a*1 Rep Ant MB S3 S3 > Rep RRU3953*1 to RRU5516*1 > Ant Combine MB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KLG9M_2026 Capacity Expansion NW Modernization_EXP_BKK | Soi Kalong 9 | [5 empty] | 2026-09-20 | 2026-09-20 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:26:27 |  |  | 2026-10-10 | 2026-09-20 | Teloneer Company Limited | N/A | Closed | 2026-09-20 20:01:46 | No | No |  |  |  |  | 2026-09-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-19 19:13:03 | No | No |  | 2026-09-20 Clear pending 19-Sep-2026 Add Replace BBU5900 UMPTg2 Add GPS UBBPh2a Add RRU5507 *2 S1 Rmv RRU3962*2 Add RRU5507 *2 S2 Rmv RRU3962*2 Add RRU5507 S3 Rmv RRU3962 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-20 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:27:23 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KLPMM_2026 Capacity Expansion Ph1_EXP_SR | Klongphanom National Park | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-28 | 2026-07-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-29 14:46:11 | Yes | Yes | 2026-08-07 18:43:49 |  | 2026-08-10 | 2026-08-13 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 10:22:34 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-13 | 2026-08-13 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 20:23:10 |  | 2026-07-30 | 2026-08-31 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 17:34:32 | No | No |  |  |  |  | 2026-07-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-28 16:02:22 | No | No |  | add UBBPg3a*1 S3 AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KLS1B_2025 Capacity Expansion NW Modernization_EXP_BKK | Klangkrung Resort (Back Left) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-03-02 | 2026-03-02 | 2026-03-03 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:27:22 | Yes | Yes | 2026-03-25 09:14:26 |  | 2026-04-23 | 2026-04-23 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-02 09:16:21 | Yes | Yes | 2026-04-23 14:04:38 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 21:30:55 |  |  | 2026-02-28 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-18 17:48:09 | No | No |  | 18-02-2026. Replace RRU3826 to RRU5526#， Ant.12port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-02-07 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KLS2B_2025 Capacity Expansion NW Modernization_EXP_BKK | Klangkrung Resort (Back Right) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:04:56 | Yes | Yes | 2026-03-23 15:11:32 |  | 2026-03-25 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-02 09:16:21 | Yes | Yes | 2026-04-20 16:01:26 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 21:31:10 |  |  | 2026-02-28 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-18 17:48:09 | No | No |  | 18-02-2026. Replace RRU3826 to RRU5526#， Ant.12port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KLS3B_2025 Capacity Expansion NW Modernization_EXP_BKK | Klangkrung Resort (Side Right) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:21:31 | No | No |  |  | 2026-03-04 | 2026-03-04 | 2026-03-19 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:48:51 | Yes | Yes | 2026-03-26 08:45:58 |  | 2026-04-24 | 2026-04-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-02 09:16:21 | Yes | Yes | 2026-05-04 17:00:51 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 21:31:24 |  |  | 2026-02-28 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-28 17:42:18 | No | No |  | 28-02-2026. Replace RRU3962 to RRU5526#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KLS4B_2025 Capacity Expansion NW Modernization_EXP_BKK | Klangkrung Resort (Front Right) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 13:24:51 | No | No |  |  | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:16:14 | Yes | Yes | 2026-03-23 15:27:38 |  | 2026-03-30 | 2026-03-30 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-02 09:16:21 | Yes | Yes | 2026-03-30 15:38:04 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 19:57:55 |  |  | 2026-02-28 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-28 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-28 17:42:18 | No | No |  | 28-02-2026. Replace RRU3962 to RRU5526#， Ant.12 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KLSIM_RET_2025_RepSGR_NER | KAMALASAI | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
KLTOM_2026 Capacity Expansion Ph1_EXP_SR | Ban Klong To | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-16 | 2026-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-18 20:53:55 | Yes | Yes | 2026-08-23 22:07:37 |  | 2026-08-24 | 2026-08-28 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-28 11:21:48 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-29 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-30 13:04:17 | No | No |  |  | 2026-08-24 | 2026-08-24 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-24 03:00:40 |  | 2026-08-10 | 2026-08-31 | 2026-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-10 13:45:30 | No | No |  |  |  |  | 2026-08-10 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-10 18:36:04 | No | No |  | 10 Aug 2026 Replace RRU5516 sector 1 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KMAFG_2026 Capacity Expansion Ph1_EXP_SR | Khok Mafueang | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-29 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-30 | 2026-08-31 | 2026-09-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-29 20:45:39 | No | No |  |  |  |  | 2026-09-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-28 20:25:05 | No | No |  | Rep Card g3*1 to h3a*1 S8 > RRU5516*1 > Ant 8 Port remove 5513*1+Ant S2 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KMCPM_2026 Capacity Expansion Modernize_EXP_ER | Krom Luang Chumphon Shrine , Laem Pu Chao | 2026-08-19 | Team : thcp_apichat.f Tel : 0960126111 | Clear Pending |  | 2026-08-20 | 2026-08-20 | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-20 09:21:43 | No | No |  |  |  | 2026-08-20 | 2026-08-19 | 2026-08-23 | Teloneer Company Limited | N/A | Closed | 2026-08-23 13:20:22 | Yes | Yes | 2026-08-26 16:54:55 |  | 2026-08-20 | 2026-08-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:47:28 | Yes | Yes | 2026-08-30 13:52:31 |  | Pass |  |  | ABC THAI COMPANY LIMITED | N/A | Not assigned |  | No | No |  |  |  |  | ABC THAI COMPANY LIMITED | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-08-20 | 2026-08-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-18 12:19:09 |  |  | 2026-08-20 | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-18 16:33:36 | No | No |  |  |  |  | 2026-08-19 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-19 11:44:05 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KMCPM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KMCPM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KMCPM_H_C Co L21F2 Sec.2 |  | 2026-08-20 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-20 17:23:56 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 100% , Day2 : Clear pending | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KMKWA_2026 Capacity Expansion Ph1_EXP_SR | Khum Kaew Apartment | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-27 | 2026-09-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-28 18:02:39 | Yes | Yes | 2026-09-28 18:09:23 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 |  | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 | 2026-08-31 | 2026-09-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-27 15:58:01 | No | No |  |  |  |  | 2026-09-27 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-27 15:45:09 | No | No |  | 27 Sep 2026 Add RRU5516 sectorB add 1UBBPh2 replace BBU5900 add GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KMLGM_2026 Capacity Expansion Ph1_EXP_SR | Kamlang Sap Road | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-08-27 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-31 | 2026-08-31 | 2026-08-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-29 11:11:03 | No | No |  |  |  |  | 2026-08-29 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-29 19:12:55 | No | No |  | S1 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KMOKM_2026 Capacity Expansion Modernize_EXP_ER | Ban KhaoMakok | 2026-07-31 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-07-31 | 2026-07-30 | 2026-07-30 | Teloneer Company Limited | N/A | Closed | 2026-07-30 19:33:36 | No | No |  |  |  | 2026-08-20 | 2026-08-05 | 2026-08-08 | Teloneer Company Limited | N/A | Closed | 2026-08-08 09:50:57 | Yes | Yes | 2026-08-09 23:24:58 |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:57:59 | Yes | Yes | 2026-08-12 20:58:19 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-20 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:20 | No | No |  |  | 2026-08-15 | 2026-07-31 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-31 14:35:51 |  |  | 2026-07-31 | 2026-07-30 | Teloneer Company Limited | N/A | Closed | 2026-07-30 18:25:59 | No | No |  |  |  |  | 2026-07-30 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-30 19:20:49 | No | No |  | Add RRU5505 x 1 + 4T4R_KMOKM_H_1 Add RRU5505 x 1 + 4T4R_KMOKM_H_6 Replace RRU5508 to (RRU5516_900) + 4T4R_KMOKM_L_1 Replace RRU5508 to (RRU5516_900) + 4T4R_KMOKM_L_2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% , Day2 : Clear pending | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KMYTL_RET_2025_RepSGR_NER | KHWAN MUANG-YANG TALAD |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-21 | Teloneer Company Limited | N/A | Closed | 2026-09-21 20:00:04 | No | No |  |  | DTH1202609100021 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
KN27M_2026 Capacity Expansion Ph1_EXP_BKK | SOI KRUNGTHEP_NONTHABURI27_3G2100 |  |  |  | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-20 20:29:20 | No | No |  |  | 2026-07-31 | 2026-07-31 | 2026-07-16 | 2026-07-17 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-17 21:09:16 | Yes | Yes | 2026-07-24 09:10:43 |  | 2026-08-03 | 2026-08-04 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-04 11:34:51 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 21:54:28 |  |  | 2026-07-31 | 2026-07-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-10 20:28:07 | No | No |  |  |  |  | 2026-07-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-07-10 17:48:16 | No | No |  | 10-Jul-2026 Add UBBPh2a Remove d5 Add AAU5636w S7 Add RRU5516 S7 Replace Ant 12port 1800 700 S2 S7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNSKK_KKN_2025_RepSGR_NER | KUD NAM SAI-KHON KAEN |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-23 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 15:21:03 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  | DTH1202609100010 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
KNT1M_2025 Capacity Expansion NW Modernization_EXP_BKK | KLUAYNAMTHAI 1_3G2100 |  |  |  | 2026-02-28 | 2026-02-28 | 2026-03-18 | 2026-03-18 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-18 16:03:05 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-08 | 2026-03-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-10 09:47:49 | Yes | Yes | 2026-03-11 11:44:01 |  | 2026-03-24 | 2026-03-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:35:56 | Yes | Yes | 2026-03-24 15:00:49 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-17 | 2026-03-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 21:31:41 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-12 18:19:34 | No | No |  | 12 Feb 2026 Add AAU5768 DMM sector1 add 1Ug3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNTRM_2025 Capacity Expansion NW Modernization_EXP_BKK | WAT KUNNATERUTTHARAM |  |  |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-03-21 | 2026-03-24 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 15:05:04 | Yes | Yes | 2026-03-24 15:05:05 |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-05-11 09:29:24 | Yes | Yes | 2026-04-08 18:19:54 | PAT first time pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-08 | 2026-04-08 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-08 18:26:01 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-04 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-03-04 18:08:45 | No | No |  | 4 Mar 2026 Add DMM AAU5768 sector1#，2 replace Ant remove RRU s3#，8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNWAM_2026 Capacity Expansion Modernize_EXP_ER | Khai Nawamin | 2026-07-31 | Team : Team_Pooriwat Tel : 0925094222 | Install & Integrate |  | 2026-07-31 | 2026-07-31 | 2026-07-31 | Teloneer Company Limited | N/A | Closed | 2026-07-31 14:30:56 | No | No |  |  |  | 2026-07-31 | 2026-08-01 | 2026-08-02 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-02 20:15:16 | Yes | Yes | 2026-08-05 18:13:02 |  | 2026-08-15 | 2026-08-05 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:05:52 | Yes | Yes | 2026-08-05 20:29:40 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:08 | No | No |  |  | 2026-08-15 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-06 11:37:47 | Yes | Yes | 2026-08-06 08:22:51 |  |  | 2026-07-31 | 2026-07-31 | Teloneer Company Limited | N/A | Closed | 2026-07-31 13:55:32 | No | No |  |  |  |  | 2026-07-31 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-31 14:29:05 | No | No |  | Add RRU5505 x 1 + 4T4R_KNWAM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_KNWAM_H_2 Add RRU5505 x 1 + 4T4R_KNWAM_H_3 |  | 2026-07-31 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-31 14:29:05 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KNWNE_2026 Capacity Expansion NW Modernization_EXP_SR | ควนนกหว้า | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-09-05 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-16 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-16 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-16 19:04:06 | No | No |  | 16 Sep 2026 Replace RRU3962 sector1#，2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOCNM_2026 Capacity Expansion Ph1_EXP_ER | Koh Chan | 2026-07-17 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate | 2026-06-01 | 2026-07-20 | 2026-07-17 | 2026-07-17 | Teloneer Company Limited | N/A | Closed | 2026-07-17 14:13:38 | No | No |  |  |  | 2026-07-20 | 2026-07-18 | 2026-07-18 | Teloneer Company Limited | N/A | Closed | 2026-07-18 16:49:24 | Yes | Yes | 2026-07-19 20:42:53 |  | 2026-07-20 | 2026-07-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:02:06 | Yes | Yes | 2026-07-23 00:01:12 |  | Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:34:22 | No | Yes | 2026-09-12 10:32:04 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-14 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:48 | No | No |  |  | 2026-07-20 | 2026-07-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-20 21:36:48 | Yes | Yes | 2026-07-16 08:52:49 |  |  | 2026-07-20 | 2026-07-17 | Teloneer Company Limited | N/A | Closed | 2026-07-17 15:12:39 | No | No |  |  |  |  | 2026-07-17 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-17 14:08:41 | No | No |  | Replace Antenna (Dualbeam)_KOCNM_H_1 ฝาก confirm Direction_KOCNM_H_3 [final Dir : 240] New L18L21 + 4T4R+ Add RRU5513 + Co Antenna_KOCNM_H_6 New L18L21 + 4T4R+ Add RRU5513 + New Antenna (MB)_KOCNM_H_4 Co L21(F2) all sector |  | 2026-07-20 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-20 20:57:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 60% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOPHM_2026 Capacity Expansion Ph1_EXP_SR | Koh Pha Ngan | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-25 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-28 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-26 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-26 16:31:07 | No | No |  | 26 Sep 2026 Add AAU5656 sector2 *Pending Re HB S6>S1#， S6>S1 S2 > AAU5656 ------------------ add h3a*1#，add g3a*1 Remove MB S6#，S9 S3 MB Re use RRU form S4 > RRU5507x2 to 4T S1 > AAU5775 S4 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOPOM_2026 Capacity Expansion Ph1_EXP_ER | Koh Pho | 2026-07-11 | Team :thcp_pooriwat.k Tel : 0925094222 |  | 2026-06-01 | 2026-07-20 | 2026-07-11 | 2026-07-11 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-11 19:47:52 | No | No |  |  |  | 2026-07-20 | 2026-07-13 | 2026-07-13 | Teloneer Company Limited | N/A | Closed | 2026-07-13 19:00:17 | Yes | Yes | 2026-07-14 20:13:35 |  | 2026-07-20 | 2026-07-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:40 | Yes | Yes | 2026-07-16 22:46:02 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:48 | No | No |  |  | 2026-07-31 | 2026-07-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:42 | Yes | Yes | 2026-07-04 10:35:14 |  | 2026-07-13 | 2026-07-20 | 2026-07-11 | Teloneer Company Limited | N/A | Closed | 2026-07-11 17:41:49 | No | No |  |  |  |  | 2026-07-11 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-11 18:59:08 | No | No |  | Replace UBBPg1 to UBBPg3a_KOPOM_H_1 ReDirection 10 to 340_KOPOM_N_1 ReSectorname S2 to S7_KOPOM_N_7 New L26F5 + NR26 (New AAU5656)_KOPOM_N_6 |  | 2026-07-13 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-13 17:18:11 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 30% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOSHM_2026 Capacity Expansion Modernize_EXP_ER | Ko Sichang Hospital | 2026-09-10 | Team: THCP_Wachira.s Tel :0657649919 |  |  | 2026-09-20 | 2026-09-09 | 2026-09-09 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-09 19:06:39 | No | No |  |  |  | 2026-09-20 | 2026-09-10 | 2026-09-11 | Teloneer Company Limited | N/A | Closed | 2026-09-11 15:39:44 | Yes | Yes | 2026-09-11 23:11:16 |  | 2026-09-20 | 2026-09-15 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:44:45 | Yes | Yes | 2026-09-15 21:38:27 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-20 | 2026-09-09 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:46:21 | Yes | Yes | 2026-09-09 15:45:34 |  |  | 2026-09-20 | 2026-09-10 | Teloneer Company Limited | N/A | Closed | 2026-09-10 11:56:39 | No | No |  |  |  |  | 2026-09-09 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-09 18:36:02 | No | No |  | Replace RRU (RRU5526) + 4T4R_KOSHM_H_1 Replace RRU (RRU5526) + 4T4R_KOSHM_H_2 Replace Antenna (MB) + Replace RRU5526 + 4T4R_KOSHM_H_3 Co L21F2 All Sector |  | 2026-09-10 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-10 16:01:28 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% , Day2 : Clear work | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOSKM_2026 Capacity Expansion Ph1_EXP_SR | Khao Sok | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-30 | 2026-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-11 14:00:03 | Yes | Yes | 2026-08-13 14:36:12 |  | 2026-08-14 | 2026-08-20 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-17 16:02:02 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-14 | 2026-08-14 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-14 16:15:05 |  | 2026-08-10 | 2026-08-31 | 2026-08-08 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-08 14:51:12 | No | No |  |  |  |  | 2026-08-08 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-08 16:44:14 | No | No |  | S2 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KOTEM_2026 Capacity Expansion Ph1_EXP_SR | Ban Ko Toei | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-07 | 2026-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-10 16:33:53 | Yes | Yes | 2026-08-14 17:31:54 |  | 2026-08-17 | 2026-09-08 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-08 20:53:59 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-17 | 2026-08-17 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-17 01:54:23 |  | 2026-08-05 | 2026-08-31 | 2026-08-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-04 19:44:28 | No | No |  |  |  |  | 2026-08-04 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-04 18:00:01 | No | No |  | Rep UBBPd6*1 to UBBPg3a*1 S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KP22M_2026 Capacity Expansion NW Modernization_EXP_BKK | Kamphaeng Phet 2 Station 2 | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:43:41 | No | No |  |  |  | 2026-09-30 | 2026-09-08 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 17:01:04 | Yes | Yes | 2026-09-25 17:01:42 | 1.Need indoor label at after c1. 2.Need Azimuth zoom out photo at after sec 1#，2#，3. 3.Need RRU socket wire strip left and right side view photo more at after sec 2. 4. 4.This breaker not found at after #，is this remove? 5.Need DCDU-Ground#， label at after c1. 6. 6.Site code wrong at eq. 7.Dismantle items not matched with on site data and list out dismantle equipment checklist. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:27:15 |  |  | 2026-09-30 | 2026-08-29 | Teloneer Company Limited | N/A | Closed | 2026-08-29 11:36:02 | No | No |  |  |  |  | 2026-08-29 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-08-29 19:06:34 | No | No |  | 2026-08-29 S1 Replace RRU3953 > RRU5516 (7/9 4T) S2 Replace RRU3953 > RRU5516 (7/9 4T) + Replace RRU3962 > RRU5507 (18/21 2T) S3 Replace RRU3953 > RRU5516 (7/9 4T) + Replace Ant to 8port Replace Card UBBPd5 > UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-04 16:14:27 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KPAKH_2026 Capacity Expansion Ph1_EXP_SR | K Park Hotel | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-14 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | Need before & after BBU right side view photo clearly at after section. Need indoor label for install RRU from DCDU side at after section. Need before OFF box at before section. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 |  | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | N/A | Assigned |  | Yes | No |  |  | 2026-09-17 | 2026-08-31 | 2026-09-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-14 20:34:14 | No | No |  |  |  |  | 2026-09-14 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-14 18:08:01 | No | No |  | Rep BBU5900#，add h2a*1#，add gps S3 > RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KPMTM_2026 Capacity Expansion NW Modernization_EXP_BKK | KHLONG PRAPA MUANG THONG THANI (LEARP KHLONG PRAPA, MUANGTHONG THANI 2) | [5 empty] | 2026-09-22 | 2026-09-22 | Thossapan Chaloemrit | N/A | Closed | 2026-09-23 21:55:28 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:28:09 |  |  | 2026-10-10 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 20:20:18 | No | No |  |  |  |  | 2026-09-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-22 19:36:59 | No | No |  | 22-Sep-2026 Add UBBPg3a Add RRU5507 S2 Rmv RRU3962 Add CPRI S1 S3 for AAU5726 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KPOEM_2026 Capacity Expansion Ph1_EXP_SR | KAPOE | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-23 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-23 | 2026-08-31 | 2026-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-24 17:46:53 | No | No |  |  |  |  | 2026-09-23 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-23 18:28:56 | No | No |  | 23 Sep 2026 Add DDM AAu5775 sector2 add UBBPh3 rmv sector4 re4>3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KPPRM_2026 Capacity Expansion Ph1_EXP_SR | Kampong Pa Re | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-06 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-06 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-06 20:05:46 | No | No |  | S8 > RRU5516LB*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KPSRM_2026 Capacity Expansion Ph1_EXP_SR | Kapangsurin | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-04 | 2026-08-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-05 17:18:58 | Yes | Yes | 2026-08-10 10:57:20 |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-14 01:35:00 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-11 13:22:26 |  | 2026-08-07 | 2026-08-31 | 2026-08-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-05 12:18:10 | No | No |  |  |  |  | 2026-08-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-05 17:34:32 | No | No |  | 5 Aug 2026 Add AAU5656 sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRN1M_2026 Capacity Expansion Ph1_EXP_SR | KHIRIRATTHA NIKHOM 1 | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-08-15 | 2026-09-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-25 18:39:03 | Yes | Yes | 2026-09-29 23:18:30 | Dis breaker not found at before. Need dcdu-grod#，rec-dcdu label at after c1. Need AC box pto at before and after on ground c1. | 2026-09-30 | 2026-09-30 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-09-30 13:50:34 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 | 2026-09-30 | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-30 13:52:05 |  | 2026-08-17 | 2026-08-31 | 2026-08-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-16 02:16:41 | No | No |  |  |  |  | 2026-08-15 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-15 17:12:39 | No | No |  | Rep AAU S3 S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KRSNK_2026 Capacity Expansion Ph1_EXP_SR | Khang Rongphayaban Song SoemSuk Pha Phana Kha | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-09 | 2026-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-11 14:44:05 | Yes | Yes | 2026-08-17 22:22:12 |  | 2026-08-18 | 2026-08-18 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-10 16:56:09 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-18 | 2026-08-18 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-18 20:29:46 |  | 2026-08-13 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-10 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-10 18:36:04 | No | No |  | 10 Aug 2026 Replace RRU5516 sector1 "*Pending S1 > Rep RRU3953*1 to 5516LB*1 > Ex Ant Rep BBU5900 addg3a*1#，add gps |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSCSM_2026 Capacity Expansion Modernize_EXP_ER | Koh Srichang School | 2026-09-08 | Team: THCP_Wachira.s Tel :0657649919 |  |  | 2026-09-15 | 2026-09-08 | 2026-09-08 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-09 06:33:01 | No | No |  |  |  | 2026-09-15 | 2026-09-11 | 2026-09-14 | Teloneer Company Limited | N/A | Closed | 2026-09-14 09:59:05 | Yes | Yes | 2026-09-16 10:05:25 |  | 2026-09-15 | 2026-09-16 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:44:45 | Yes | Yes | 2026-09-18 10:17:33 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-16 | 2026-09-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:46:21 | Yes | Yes | 2026-09-08 15:58:49 |  |  | 2026-09-15 | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-08 20:43:36 | No | No |  |  |  |  | 2026-09-08 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-08 17:17:07 | No | No |  | Replace Antenna (MB) + Replace RRU5526 + 4T4R_KSCSM_H_2 Replace Antenna (MB) + Replace RRU5526 + 4T4R_KSCSM_H_3 Co L21F2 All Sector |  | 2026-09-10 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-10 16:10:55 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSLSM_2026 Capacity Expansion NW Modernization_EXP_BKK | KONG SALAK - SANAMBINNAM | [5 empty] | 2026-09-12 | 2026-09-12 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 | 2026-09-22 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 17:44:46 | Yes | Yes | 2026-09-29 18:36:55 |  | 2026-10-01 | 2026-10-01 | Nattawoot Suwan | Approving | Assigned |  | Yes | Yes | 2026-10-01 17:08:25 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:28:58 |  |  | 2026-10-10 | 2026-09-12 | Teloneer Company Limited | N/A | Closed | 2026-09-12 21:23:23 | No | No |  |  |  |  | 2026-09-12 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-09-13 08:49:50 | No | No |  | 2026-09-12 S1 Replace RRU3962 > RRU5507*2 (18/21 2T) + Replace Ant to 8port S2 Remove RRU3962 > Add AAU5775 + Remove Ant S3 Replace RRU3962 > RRU5507 (18/21 2T) S7 Remove RRU3962 Replace Card UBBPg2#， UBBPh3a ----------------------------------------------------------------------------------------- ----------------------------------------------------------------------------------------- |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-11 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:30:25 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSLSM_2026 Capacity Expansion Ph2_BKK | KONG SALAK - SANAMBINNAM | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-10-01 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-10-01 14:38:45 | No | No |  | 1-Oct-2026 Add AAU5656 Sector 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSLYM_2026 Capacity Expansion NW Modernization_EXP_BKK | KHLONG SALA LOY | [5 empty] | 2026-09-15 | 2026-09-15 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 | 2026-09-22 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:29:46 |  |  | 2026-10-10 | 2026-09-15 | Teloneer Company Limited | N/A | Closed | 2026-09-15 12:05:51 | No | No |  |  |  |  | 2026-09-12 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-09-12 20:42:21 | No | No |  | 2026-09-14 Clear Pending ----------------------------------------------------------------------------------------- ----------------------------------------------------------------------------------------- 12-09-2026. Replace RRU3962 to AAU5775 Sec.1#， 3#， RRU3953#， RRU5508 to RRU5516 Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-14 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:31:11 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSNIM_2026 Capacity Expansion Ph1_EXP_SR | Ban Khuan Sanai | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-20 | 2026-08-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-21 17:06:36 | Yes | Yes | 2026-08-24 14:55:57 |  | 2026-09-02 | 2026-09-02 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-05 19:59:41 | 2.Page 8#，In SOW need to fill install & remove sector. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-02 | 2026-09-02 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-02 08:56:34 |  | 2026-08-20 | 2026-08-31 | 2026-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-20 21:53:52 | No | No |  |  |  |  | 2026-08-20 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-20 17:08:58 | No | No |  | 20 Aug 2026 Add RRU5516 sector1 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KSOHM_2026 Capacity Expansion Ph2_EXP_ER | Talad Khong Soi5 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTK8M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI KRUNGTHEP KRITHA 8 YEAK 12 |  |  |  | 2026-06-11 |  | 2026-06-16 | 2026-06-16 | Teloneer Company Limited | N/A | Closed | 2026-06-16 12:33:36 | No | No |  |  |  | 2026-08-31 | 2026-06-16 | 2026-06-22 | Teloneer Company Limited | N/A | Closed | 2026-06-22 17:03:48 | Yes | Yes | 2026-06-23 12:07:15 |  | 2026-06-23 | 2026-07-22 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-21 11:31:46 | Yes | Yes | 2026-08-05 17:47:58 |  | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-07-06 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-06 12:52:09 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-09 | 2026-07-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-06-16 16:19:46 |  |  | 2026-06-30 | 2026-06-16 | Teloneer Company Limited | N/A | Closed | 2026-06-16 17:02:34 | No | No |  |  |  |  | 2026-06-15 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-06-15 17:37:42 | No | No |  | 25-Jun-2026 Add UBBPg2 Remove UBBPh3a 15 Jun 2026 Add AAU5775 sector1#，3 rru5507 sector2#， replace RRU5516 sector1#，2#，3 add 1UBBPh3 v1.4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-06-16 | 2026-06-16 | Teloneer Company Limited | N/A | Closed | 2026-06-17 11:23:46 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTMTB_2025 Capacity Expansion NW Modernization_EXP_BKK | KHLONG TOEI MARKET SMALL CELL |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:54:42 | No | No |  |  | 2026-04-02 | 2026-04-02 | 2026-04-02 | 2026-05-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-24 11:01:28 | Yes | Yes | 2026-05-27 08:39:48 |  | 2026-05-31 | 2026-05-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-04 20:35:56 | Yes | Yes | 2026-06-02 16:31:52 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 20:06:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-21 17:23:23 | No | No |  | 21-02-2026. Replace RRU5507 to RRU5526 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTMTM_2025 Capacity Expansion NW Modernization_EXP_BKK | KHLONG TOEI MARKET |  |  |  | 2026-02-12 | 2026-02-12 | 2026-04-23 | 2026-04-23 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-04-23 14:54:42 | No | No |  |  | 2026-02-23 | 2026-02-23 | 2026-03-22 | 2026-06-08 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-08 11:51:26 | Yes | Yes | 2026-06-09 08:47:42 |  | 2026-06-10 | 2026-06-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-03 09:43:26 | Yes | Yes | 2026-06-10 16:51:13 | Page no.8#， need to revise install INV. (install AAU 2pcs#， RRU 1pc in QC but INV wrong) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-18 | 2026-09-03 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:05:39 | Yes | Yes | 2026-08-01 19:58:13 |  |  | 2026-06-03 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-12 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-12 20:33:13 | No | No |  | 12-Feb-2026 Add AAU5768 S2 S3 Remove RRU5507 *4 RRU3962 *4 Add RRU3953 Sector 1 Add g3a Remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-02-12 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTNAM_2026 Capacity Expansion Ph2_BKK | KANTANA | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTPZP_2025 Capacity Expansion NW Modernization_EXP_BKK | Krungthong Plaza |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 17:49:52 | No | No |  |  |  | 2026-01-31 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 19:17:39 | Yes | Yes | 2026-02-11 19:17:40 |  | 2026-02-21 | 2026-02-21 | Chonradee Suwapan | Approved | Closed | 2026-02-25 09:26:15 | Yes | Yes | 2026-02-21 21:01:04 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:42:24 |  | 2026-02-21 | 2026-02-21 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:45 | Yes | Yes | 2026-02-21 21:09:45 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 28-01-2026 Revise card UBBP follow plan card Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTSCM_2026 Capacity Expansion NW Modernization_EXP_BKK | KRUNGTHEP SUKSA COMMERCIAL COLLAGE | [5 empty] | 2026-09-24 | 2026-09-24 | Thossapan Chaloemrit | N/A | Closed | 2026-09-28 16:14:22 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-10 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 12:25:00 | No | No |  |  |  |  | 2026-09-24 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-24 17:46:25 | No | No |  | 2026-09-24_Replace UBBPeb to UBBPh3a S1 Replace RRU3962*2 to AAU5775 S3 Replace RRU3962*2 to AAU5775 SG Replace RRU3826 to RRU5507 S6 Remove RRU3962*2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTSUM_2026 Capacity Expansion Modernize_EXP_ER | Sapan Klong Ta Suk | 2026-07-31 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-07-31 | 2026-07-31 | 2026-07-31 | Teloneer Company Limited | N/A | Closed | 2026-07-31 17:16:04 | No | No |  |  |  | 2026-07-31 | 2026-08-02 | 2026-08-02 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-02 18:17:41 | Yes | Yes | 2026-08-03 23:06:30 |  | 2026-08-15 | 2026-08-05 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:05:52 | Yes | Yes | 2026-08-06 00:13:41 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:08 | No | No |  |  | 2026-08-15 | 2026-07-31 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-31 14:36:10 |  |  | 2026-07-31 | 2026-07-31 | Teloneer Company Limited | N/A | Closed | 2026-07-31 18:15:21 | No | No |  |  |  |  | 2026-07-31 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-31 16:38:25 | No | No |  | Add RRU5505 x 1 + 4T4R_KTSUM_H_2 Add RRU5505 x 1 + 4T4R_KTSUM_H_3 |  | 2026-07-31 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-31 16:38:25 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed. | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTSUM_2026 Capacity Expansion Ph2_EXP_ER | Sapan Klong Ta Suk |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-29 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-29 13:53:48 |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KTTRM_2026 Capacity Expansion Ph1_EXP_SR | Koto Tuera | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-21 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-19 18:30:56 | No | No |  | S2 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KW60M_2026 Capacity Expansion NW Modernization_EXP_BKK | King Kaeo Soi 60 | [5 empty] | 2026-09-07 | 2026-09-07 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-10-10 | 2026-09-10 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 21:13:44 | Yes | Yes | 2026-09-25 21:13:52 | Need 1 person AIS team member photo. Need to upload sec-1 remove antenna position view photo at before section. Need to upload remove RRU position view photo at before section. Need to upload sec-3 before ground bar photo at before section. Need to upload install EPS100D & module photo#， fill remark at AD. Fill quantity install DCDU at EQ. Install AAU under label must have name tag#， please change. Need install DCDU label for ground at body#， ground at cabinet#， rec: to DCDU & DCDU to rec: . Please upload photo clearly . Need this label for sec-3 install AAU at after section. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:30:34 |  |  | 2026-10-10 | 2026-09-07 | Teloneer Company Limited | N/A | Closed | 2026-09-07 16:51:25 | No | No |  |  |  |  | 2026-09-07 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-09-07 19:53:32 | No | No |  | 2026-09-07 S1 Remove RRU5507*2 > Add AAU5775 + Remove Ant S3 Remove RRU5507*2 > Add AAU5775 + Remove Ant S6 Remove RRU5507*2 S8 Remove RRU5507*2 Replace Card UBBPg3a > UBBPh3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-07 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:14:19 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KW60M_2026 Capacity Expansion Ph2_BKK | KING KAEO SOI 60 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KYBSM_2026 Capacity Expansion Modernize_EXP_ER | KYB STEERING (THAILAND) CO., LTD | 2026-06-22 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-06-30 | 2026-06-22 | 2026-06-22 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-23 15:32:53 | No | No |  |  |  | 2026-06-30 | 2026-06-23 | 2026-06-23 | Teloneer Company Limited | N/A | Closed | 2026-06-23 21:15:39 | Yes | Yes | 2026-06-24 11:10:49 |  | 2026-06-30 | 2026-06-25 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-28 22:14:43 | Yes | Yes | 2026-06-25 17:57:02 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-06-30 | 2026-06-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-25 08:21:58 | Yes | Yes | 2026-06-23 09:46:53 |  | 2026-06-24 | 2026-06-30 | 2026-06-22 | Teloneer Company Limited | N/A | Closed | 2026-06-22 13:39:01 | No | No |  |  |  |  | 2026-06-22 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-22 18:01:33 | No | No |  | "Replace RRU (RRU5513) + 4T4R_KYBSM_H_A Replace RRU (RRU5513) + 4T4R_KYBSM_H_B Replace RRU (RRU5513) + 4T4R_KYBSM_H_C New L21(F2) all sec.1#，2#，3" |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-22 | Boonchot Boriwut | N/A | Closed | 2026-06-25 22:57:05 | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KYUBK_2026 Capacity Expansion Ph1_EXP_SR | Ka Yu Bo Ko | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-16 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-16 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-16 19:04:06 | No | No |  | 16 Sep 2026 Replace RRU5516 sector3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
KZBPA_2026 Capacity Expansion Ph1_EXP_BKK | Micro Cell Kinza-Bus Port Opposite Future Park Rangsit | [5 empty] | 2026-09-04 | 2026-09-04 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-09-30 | 2026-09-17 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:31:40 |  |  | 2026-09-30 | 2026-09-20 | Teloneer Company Limited | N/A | Closed | 2026-09-20 17:22:00 | No | No |  |  |  |  | 2026-09-04 | Autumporn Masing WX1434753 | N/A | Closed | 2026-09-04 18:09:11 | No | No |  | 2026-09-04 SA#，SB Co-RRU5818 Swap BBU to 5900//add g3a add gps |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-04 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:12:35 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L107M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI LAT PHRAO 107 (DI SOM CHOK) |  |  |  | 2026-06-11 |  | 2026-06-16 | 2026-06-16 | Teloneer Company Limited | N/A | Closed | 2026-06-16 12:33:36 | No | No |  |  |  | 2026-08-31 | 2026-06-16 | 2026-06-24 | Teloneer Company Limited | N/A | Closed | 2026-06-24 14:29:13 | Yes | Yes | 2026-06-25 08:21:03 |  | 2026-06-26 | 2026-07-22 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 12:50:57 | page.57 need to upload Notch CPRI 2pcs photo | Not Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-07-06 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-06 12:52:09 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-09 | 2026-07-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-06-16 16:20:10 |  |  | 2026-06-30 | 2026-06-15 | Teloneer Company Limited | N/A | Closed | 2026-06-15 11:23:10 | No | No |  |  |  |  | 2026-06-11 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-06-11 18:18:40 | No | No |  | 2026-06-12_Clear Pending 2026-06-11_Change LAN to Optic 10G#， Replace RRU3935 to RRU5516 Sector 2#，3#， Replace RRU3953#， RRU5508 to RRU5516(LB) Sector 1#， Replace RRU5507(2)#， RRU3962(2) to AAU5775 Sector 1#，G#，2#，J#， Replace ant to 8 port Sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-06-12 | 2026-06-12 | Teloneer Company Limited | N/A | Closed | 2026-06-17 11:23:46 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L109M_2026 Capacity Expansion NW Modernization_EXP_BKK | Soi LAT PHRAO 109 Yaek 9 | [5 empty] | 2026-06-22 | 2026-06-22 | Teloneer Company Limited | N/A | Closed | 2026-06-26 15:01:08 | No | No |  |  |  | 2026-08-31 | 2026-06-23 | 2026-06-24 | Teloneer Company Limited | N/A | Closed | 2026-06-24 15:50:18 | Yes | Yes | 2026-06-25 08:38:54 |  | 2026-06-25 | 2026-07-22 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-21 11:33:14 | Yes | Yes | 2026-08-06 16:15:02 |  | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-10 17:22:38 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-09 | 2026-07-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-06-16 16:20:28 |  |  | 2026-06-30 | 2026-06-22 | Teloneer Company Limited | N/A | Closed | 2026-06-22 12:25:05 | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 20-06-2026. ***Waiting ODD Sec.J //Replace RRU3962 to AAU5775 Sec.2#， 3#， to RRU5507 x2#， Ant.8 port Sec.1#， J#， UBBPd5 to UBBPh3a //2026-06-17_Change LAN to Optic 10G#， Replace UBBPg3 to UBBPh3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-06-22 | 2026-06-22 | Teloneer Company Limited | N/A | Closed | 2026-06-23 12:49:43 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L110M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI LAT PHRAO 110 | [5 empty] | 2026-08-22 | 2026-08-22 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  |  | 2026-08-31 | 2026-08-31 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 20:15:38 | Yes | Yes | 2026-09-25 20:15:47 | Install AAU sn pto found 1 at eq. Need install aau snn pto at aft sec 1. Need dis bbp clear sn and overview pto at eq. Wrong label#，must be 18/21 at after on ground. Need master ground bar pto at bf and aft on ground. Need dcdu-ground label at aft c1. Overview pto is complicated #，plz show with red mark. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-10 17:22:38 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-19 | Teloneer Company Limited | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-06-19 18:07:38 |  |  | 2026-06-30 | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-07 11:16:07 | No | No |  |  |  |  | 2026-08-15 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-08-15 20:29:48 | No | No |  | 2026-08-22 clear pending 2026-08-15 S1 Replace RRU3953 > RRU5516 (7/9) + Remove RRU5502 > Add AAU5775 + Replace Ant to 4x4L/4x4H Single Beam Multi port S2 Replace RRU3953 > RRU5516 (7/9) + Remove RRU3962 > Add AAU5775 + Replace Ant to 4x4L/4x4H Single Beam Multi port S3 Replace RRU3953 > RRU5516 (7/9) + Replace RRU3962 > RRU5507*2 (18/21) + Replace Ant to 4x4L/4x4H Single Beam Multi port S6 Remove RRU3962 S7 Remove RRU5502 Replace Card UBBPd2#，UBBPd5 > UBBPg2#，UBBPh3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-22 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:03:37 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L110M_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | SOI LAT PHRAO 110 | [5 empty] | 2026-07-10 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 22:30:58 | No | No |  |  |  | 2026-08-08 | 2026-07-11 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 16:04:03 | Yes | Yes | 2026-07-17 10:07:46 |  | 2026-07-17 | 2026-07-23 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-07-23 20:52:53 | Yes | Yes | 2026-07-22 20:05:58 | No inventory | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-07-10 17:22:38 | No | No |  |  |  | 2026-08-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-03 17:02:36 | No | No |  |  |  | 2026-07-17 | Thossapan Chaloemrit | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-17 12:40:25 |  |  | 2026-08-08 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 16:01:05 | No | No |  |  |  |  | 2026-07-07 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-07-07 18:12:33 | No | No |  | 2026-07-07_Replace UBBPd5 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:32:15 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
L4ASA_2025 Capacity Expansion NW Modernization_EXP_BKK | Life Rama 4 - Asoke |  |  |  | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-05 09:31:04 | No | No |  |  | 2026-03-31 | 2026-03-31 | 2026-03-24 | 2026-03-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-25 15:20:18 | Yes | Yes | 2026-04-07 13:25:05 |  | 2026-05-05 | 2026-05-05 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-08-05 09:28:56 | Yes | Yes | 2026-05-05 09:30:18 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:06:34 | Yes | Yes | 2026-08-01 19:58:48 |  |  | 2026-03-31 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-03-20 17:38:59 | No | No |  | 20-03-2026. Replace BBU5900#， UMPTg2#， Add UBBPg2#， RRU5507 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LAR9B_2025 Capacity Expansion NW Modernization_EXP_BKK | LIFE ASOKE - RAMA 9 |  |  |  | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-06-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-26 18:54:47 | No | No |  |  | 2026-05-31 | 2026-05-31 | 2026-06-29 | 2026-06-30 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-30 20:44:01 | Yes | Yes | 2026-07-06 08:47:00 |  | 2026-07-17 | 2026-07-17 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-04 16:44:42 | Yes | Yes | 2026-07-17 16:27:43 | page.6 and page.41 mismatch with braker page.6 need to revise install AC braker page.29#，31 need to revise S1#，S2 RRU2 socket left and right photo | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-04 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:06:34 | Yes | Yes | 2026-08-01 19:59:13 |  |  | 2026-06-23 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-06-23 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-06-23 20:07:18 | No | No |  | 2026-06-23_Replace RRU3962 to RRU5507 Sector C#， 5-May-2026 ***Pending Add RRU5507*2 SC Remove RRU3962 ///Add RRU5507 *2 SA Remove RRU3962 Add RRU5507 *2 SB Remove RRU3962 chain Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 1.back Picture of full body safety harness with lanyard |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LB50M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI LATKABANG 50 | [5 empty] | 2026-09-05 | 2026-09-05 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-10-10 | 2026-09-14 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:32:41 |  |  | 2026-10-10 | 2026-09-05 | Teloneer Company Limited | N/A | Closed | 2026-09-05 21:04:34 | No | No |  |  |  |  | 2026-09-05 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-09-05 18:31:38 | No | No |  | 2026-09-05 s1 replace RRU5507*2 to AAU5775 s2 replace RRU5507*2 to AAU5775 s3 replace RRU5507*2 to AAU5775 s6 remove RRU5507*2 s7 remove RRU5507*2 s8 remove RRU5507*2 add UBBPh3a/rmv UBBPd5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-05 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:13:41 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LDPYM_2026 Capacity Expansion Ph2_EXP_ER | LukDod Pattaya |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LIE9A_2026 Capacity Expansion Ph1_EXP_BKK | LATKRABANG INDUSTRIAL ESTATE MICRO CELL STATION9 | [5 empty] | 2026-08-21 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  |  | 2026-07-31 | 2026-09-01 | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-08 18:50:55 | Yes | Yes | 2026-09-10 11:22:44 | 1. Need to up;load After wire strip at DCDU at after 2.Need to upload Ground end point at ground bar at after 3.Need to upload RRU label in door 4. BBU SN photo in EQ and after not same. 5.Need to upload GPS check photo#， screenshot GPS status from OMC at after | 2026-09-13 | 2026-09-13 | Boonchot Boriwut | Approving | Assigned |  | Yes | Yes | 2026-09-13 14:01:35 | need to upload inventory page. page.5 need to upload add GPS Surge#，UPEU#，Splitter page.23 need to upload GPS Surge#，OMC page.33 need to upload UPEU#，GPS Surge#，Splitter SN. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-20 11:32:02 |  |  | 2026-06-30 | 2026-08-31 | Teloneer Company Limited | N/A | Closed | 2026-08-31 11:00:24 | No | No |  |  |  |  | 2026-08-05 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-08-05 15:42:15 | No | No |  | 2026-08-05 add RRU5872 Sec.A#，add UBBPg3a slot 5#，rmv UBBPd5#， replace BBU5900#，add GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:02:43 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LLK4M_2026 Capacity Expansion Ph2_BKK | LAMLUKKA LIAB KHLONG 4 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LMBKP_2025 Capacity Expansion NW Modernization_EXP_BKK | MBK CENTER BANGKOK |  |  |  |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-11 | 2026-02-19 | V Contribute Co., Ltd | N/A | Closed | 2026-02-19 11:08:26 | Yes | Yes | 2026-02-19 11:08:27 |  | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-04 09:27:40 | Yes | Yes | 2026-02-25 21:57:10 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:46:47 |  | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-25 22:29:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Replace UBBPd2 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LMPYM_2026 Capacity Expansion Ph1_EXP_SR | ban lumphaya | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-25 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-25 | 2026-08-31 | 2026-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-24 16:50:24 | No | No |  |  |  |  | 2026-09-24 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-24 18:34:35 | No | No |  | 24 Sep 2026 Add AAU5656 sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LNIRB_2026 Capacity Expansion NW Modernization_EXP_BKK | HW_Lumpini Ville Nakhon In-Riverview | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 | 2026-10-01 | Teloneer Company Limited | N/A | Closed | 2026-10-01 10:43:35 | No | No |  |  |  |  | 2026-09-30 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-30 16:59:26 | No | No |  | 2026-10-01 3RNCBPL8H_LNIRB_2 Rep BBU to 5900 //h2a Add GPS SG REP RRU3826 to RRU5507 2T ______________________________ 2026-09-30 3RNCBPL8H_LNIRB SB Replace RRU3826 to RRU5507 SC Replace RRU3962 to RRU5507 SD Replace RRU3962 to RRU5507 2026-09-29 REP BBU to 5900//add h2a add gps |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LOWLB_2025 Capacity Expansion NW Modernization_EXP_BKK | LIFE ONE WIRELESS |  |  |  |  | 2026-03-16 | 2026-02-25 | 2026-03-16 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:44:49 | No | No |  |  |  | 2026-03-13 | 2026-03-20 | 2026-03-21 | V Contribute Co., Ltd | N/A | Closed | 2026-03-21 12:28:06 | Yes | Yes | 2026-03-21 12:28:07 |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-07-07 16:24:19 | Yes | Yes | 2026-04-29 22:11:01 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-29 | 2026-04-29 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:34:41 | Yes | Yes | 2026-04-29 22:23:58 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-25 20:33:44 | No | No |  | 25-Feb-2026 Add RRU5526 Sector A B C D Remove RRU3962 *1#，1#，1#，2 Replace Ant 4port No ret sector C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP25M_2026 Capacity Expansion NW Modernization_EXP_BKK | Ladphrao 25 | [5 empty] | 2026-08-21 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  | 2026-08-21 | 2026-08-24 | 2026-08-27 | 2026-09-01 | Nammon Manakiat(Teloneer Company Limited) | N/A | Closed | 2026-09-01 19:13:17 | Yes | Yes | 2026-09-02 12:17:21 |  | 2026-09-07 | 2026-09-07 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-09-07 11:54:53 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-20 | Teloneer Company Limited | Approved | Closed | 2026-08-28 15:30:50 | Yes | Yes | 2026-08-20 21:46:14 |  |  | 2026-08-24 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-21 20:46:30 | No | No |  |  |  |  | 2026-08-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-08-21 18:33:47 | No | No |  | 26-08-2026 Repalce SFP RRU5516 to 10G 21-08-2026. Replace RRU3953 to RRU5516#， Ant.8 port Sec.1#， 2#， 3#， UBBPd5 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:02:43 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LP4KB_2025 Capacity Expansion NW Modernization_EXP_BKK | LUMPINI PLACE RAMA4-KLUOYNAMTHAI |  |  |  |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:47:30 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:37:57 | Yes | Yes | 2026-03-23 15:37:57 |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-05-06 18:21:02 | Yes | Yes | 2026-03-17 20:25:59 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-17 | 2026-03-17 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-17 20:45:51 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-18 17:48:09 | No | No |  | 18-02-2026. Add UBBPg2#， Replace RRU3962 to RRU5526 Sec.A#， B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LPCTM_2026 Capacity Expansion Modernize_EXP_ER | Lumpini Condo Town | 2026-08-15 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-20 | 2026-08-15 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-16 07:49:19 | No | No |  |  |  | 2026-08-20 | 2026-08-17 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-21 21:29:28 | Yes | Yes | 2026-08-24 08:59:01 |  | 2026-08-20 | 2026-08-22 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:42:47 | Yes | Yes | 2026-09-07 08:56:17 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:28 | No | No |  |  | 2026-08-20 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 17:58:57 |  |  | 2026-08-20 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 18:31:43 | No | No |  |  |  |  | 2026-08-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-15 21:16:39 | No | No |  | Replace RRU (RRU5516_900) + 4T4R_LPCTM_L_8 |  | 2026-08-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-15 21:20:53 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LPHSB_2025 Capacity Expansion NW Modernization_EXP_BKK | The Lord Palace Hotel&Spa small cell |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:29:00 | No | No |  |  | 2026-05-22 | 2026-05-22 | 2026-05-24 | 2026-06-01 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-01 13:39:06 | Yes | Yes | 2026-06-01 13:41:58 |  | 2026-05-26 | 2026-05-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-02 09:19:52 | Yes | Yes | 2026-05-26 16:15:43 | page -38 and page-7 new MDB box new install or not | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-08 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:06:34 | Yes | Yes | 2026-08-01 21:31:59 |  |  | 2026-05-09 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-05-07 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-05-07 14:59:20 | No | No |  | 7-May-2026 Add RRU5507*2 Sector A remove RRU3962 Replace Ant 12port No Ret *2 SA Chain |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LPJTM_2026 Capacity Expansion Modernize_EXP_ER | Lumpini Park Beach Jomtien | 2026-09-23 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-09-30 | 2026-09-23 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-24 07:39:09 | No | No |  |  |  | 2026-09-30 | 2026-09-24 | 2026-09-27 | Teloneer Company Limited | N/A | Closed | 2026-09-27 23:45:55 | Yes | Yes | 2026-09-28 19:14:39 |  | 2026-09-30 | 2026-09-28 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-10-01 19:08:33 | Already upload New PAT DOC Please check 01/10/2026 Page no.32#， need to revise Bill of Quantity for AWN Pancake Project BKK into ER. not update | Not Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-25 17:31:42 | Yes | Yes | 2026-09-23 08:28:04 |  |  | 2026-07-31 | 2026-07-25 | Teloneer Company Limited | N/A | Closed | 2026-07-25 17:49:23 | No | No |  |  |  |  | 2026-09-23 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-23 17:46:38 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_LPJTM_H_1 --revise rep. to 5513 Replace Antenna (MB) + Change 2T2R to 4T4R_LPJTM_H_2 |  | 2026-09-23 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-23 17:46:38 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% , Day2 : 90% , Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LPNGM_2026 Capacity Expansion NW Modernization_EXP_BKK | LAO PENG NGUAN TOWER 1 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-10 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LPNIM_2026 Capacity Expansion Modernize_EXP_ER | Lumpini Seaview Jomtien | 2026-07-31 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-07-31 | 2026-07-31 | 2026-07-31 | Teloneer Company Limited | N/A | Closed | 2026-07-31 17:15:13 | No | No |  |  |  | 2026-07-31 | 2026-08-02 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 12:15:14 | Yes | Yes | 2026-08-03 23:03:08 |  | 2026-08-20 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:06:25 | Yes | Yes | 2026-08-06 23:09:37 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:08 | No | No |  |  | 2026-08-15 | 2026-07-31 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-31 14:36:30 |  |  | 2026-07-31 | 2026-07-31 | Teloneer Company Limited | N/A | Closed | 2026-07-31 13:42:58 | No | No |  |  |  |  | 2026-07-31 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-31 16:34:22 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_LPNIM_H_2 |  | 2026-07-31 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-31 16:34:22 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LPPAB_2026 Capacity Expansion NW Modernization_EXP_BKK | LPN Park Pinklao Building A | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LPPBB_2026 Capacity Expansion NW Modernization_EXP_BKK | LPN Park Pinklao | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LPS3M_2026 Capacity Expansion NW Modernization_EXP_BKK | LAT PHRAO RD. SOI 3 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRB1B_2026 Capacity Expansion NW Modernization_EXP_BKK | LPN Condotown Rattanathibet | [5 empty] | 2026-09-16 | 2026-09-16 | Thossapan Chaloemrit | N/A | Closed | 2026-09-22 12:04:45 | No | No |  |  |  | 2026-10-31 | 2026-09-24 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 16:21:58 | Yes | Yes | 2026-09-25 16:22:23 | > Mismatch with onsite data. > Need to upload OPM SN in equip checklist. >Need to upload Cabinet ground bar in BF and AF section. >Need to upload Cabinet Inlet/Outlet in BF and AF section. >Need to upload AC box in BF and AF section. >Need to upload Breaker overview in BF and AF section. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:33:25 |  |  | 2026-10-03 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 12:02:15 | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:24:42 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRB2B_2026 Capacity Expansion NW Modernization_EXP_BKK | LPN Condotown Rattanathibet | [5 empty] | 2026-09-16 | 2026-09-16 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-31 | 2026-09-30 | 2026-09-30 | Teloneer Company Limited | N/A | Closed | 2026-09-30 19:49:30 | Yes | Yes | 2026-09-30 19:49:47 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:34:13 |  |  | 2026-10-03 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 12:12:28 | No | No |  |  |  |  | 2026-09-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-16 17:35:09 | No | No |  | 16-Sep-2026 Add RRU5507 SA Rmv RRU3962 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:24:42 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRB3B_2026 Capacity Expansion NW Modernization_EXP_BKK | LPN Condotown Rattanathibet | [5 empty] | 2026-09-16 | 2026-09-16 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-31 | 2026-10-01 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:35:02 |  |  | 2026-10-03 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 12:14:31 | No | No |  |  |  |  | 2026-09-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-16 17:35:09 | No | No |  | 16-Sep-2026 Add RRU5507 SA Rmv RRU3962 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:24:42 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRB4B_2026 Capacity Expansion NW Modernization_EXP_BKK | LPN Condotown Rattanathibet | [5 empty] | 2026-09-17 | 2026-09-17 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-31 | 2026-10-01 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:35:47 |  |  | 2026-10-03 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 12:13:33 | No | No |  |  |  |  | 2026-09-18 | Autumporn Masing WX1434753 | N/A | Closed | 2026-09-18 20:36:48 | No | No |  | 2026-09-18 SA Replace RRU3962 to RRU5507 2T |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-18 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:27:23 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRB5B_2026 Capacity Expansion NW Modernization_EXP_BKK | LPN Condotown Rattanathibet | [5 empty] | 2026-09-16 | 2026-09-16 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:36:38 |  | 2026-09-17 | 2026-10-03 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 12:15:52 | No | No |  |  |  |  | 2026-09-17 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-09-17 19:21:14 | No | No |  | 17-Sep-2026 Replace 1RRU3962 to 1RRU5507 (LRB5B) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-17 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:27:23 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRB6B_2026 Capacity Expansion NW Modernization_EXP_BKK | LPN Condotown Rattanathibet | [5 empty] | 2026-09-17 | 2026-09-17 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:37:27 |  | 2026-09-17 | 2026-10-03 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 12:17:28 | No | No |  |  |  |  | 2026-09-17 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-09-17 19:21:14 | No | No |  | 17-Sep-2026 Replace 1RRU3962 to 1RRU5507 (LRB6B) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-17 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:27:23 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LRBSB_2026 Capacity Expansion NW Modernization_EXP_BKK | LPN CONDOTOWN RATTANATHIBET | [5 empty] | 2026-09-16 | 2026-09-16 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:39:17 |  |  | 2026-10-03 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 12:19:58 | No | No |  |  |  |  | 2026-09-16 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-16 17:35:22 | No | No |  | 16-Sep-2026 Add RRU5502 SA Rmv RRU3962 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:24:42 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LSGVM_2026 Capacity Expansion Ph1_EXP_SR | Langsuan Government | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-06 | 2026-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-15 09:36:26 | Yes | Yes | 2026-08-20 15:13:10 |  | 2026-08-23 | 2026-08-26 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-26 12:50:04 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-23 | 2026-08-23 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-23 11:33:10 |  | 2026-08-06 | 2026-08-31 | 2026-08-06 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-06 14:57:58 | No | No |  |  |  |  | 2026-08-06 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-06 17:08:20 | No | No |  | 6 Aug 2026 Add AAU5775 sector1 re s3>7#，S4>3 add 1UBBPh3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LSMKB_2025 Capacity Expansion Ph8_EXP_BKK | LUMPINI SUITE PHETCHABURI - MAKKASAN | [5 empty] | 2026-03-24 | 2026-03-24 | Akhom Srinara | N/A | Closed | 2026-03-24 11:11:26 | No | No |  |  | 2026-03-13 | 2026-04-11 | 2026-03-17 | 2026-03-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-03-19 10:16:37 | Yes | Yes | 2026-03-23 22:21:15 |  | 2026-03-28 | 2026-03-28 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-04-09 16:11:54 | Yes | Yes | 2026-03-28 00:32:25 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-06-21 | 2026-06-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-22 20:48:24 | Yes | Yes | 2026-06-21 05:24:27 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-03-10 18:13:30 | No | No |  | 10-03-2026. Replace BBU5900#， UMPTg2#， Add UBBPg2#， UBBPg3a#， RRU5818 Sec.A co Sec.B#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
LUPHM_RET_2025_RepSGR_NER | LUM PHUK |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-14 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 21:18:06 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-22 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-14 | Teloneer Company Limited | N/A | Closed | 2026-09-14 18:00:04 | No | No |  |  | DTH1202609100014 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
LWASE_2025 Coverage Expansion Ph1_New_SR | Lang Wat SueaMueang | [5 empty] | 2026-03-09 | 2026-03-10 | Khathahat Sitthihong(Teloneer Company Limited) | N/A | Closed | 2026-03-16 10:32:02 | No | No |  |  |  | 2026-03-09 | 2026-03-09 | 2026-03-10 | Teloneer Company Limited | N/A | Closed | 2026-03-10 16:05:08 | Yes | Yes | 2026-03-17 14:25:40 |  | 2026-03-17 | 2026-03-17 | Teloneer Company Limited | Approved | Closed | 2026-03-19 08:10:52 | Yes | Yes | 2026-03-18 15:49:15 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-03-25 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:23 | Yes | Yes | 2026-03-27 17:02:08 |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  | 2026-03-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-03-10 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-03-10 19:25:49 | No | No |  | Donor : 3RNCHYI6H_WTCAN_D1 BBU3910#，UBBPd5*3#，add PMU S1 > RRU3839 > Ant 4 Port S2 > RRU3839 > Ant 4 Port S3 > RRU3839 > Ant 4 Port On service |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-02-25 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-02-25 14:58:46 | Yes | Yes | 2026-02-25 14:40:54 |  |  | 2026-06-08 | Nattawoot Suwan | N/A | Closed | 2026-06-08 18:40:06 | No | No | [5 empty] | 2026-03-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:58 | No | No
MARTM_2026 Capacity Expansion Ph1_EXP_SR | Mab Amarit | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-18 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-18 | 2026-08-31 | 2026-09-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-18 20:56:21 | No | No |  |  |  |  | 2026-09-18 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-18 17:30:16 | No | No |  | 01 Oct 2026 Clear pending Rep d5*1 to h3a*1 Re HB S4>S8#， Re LB S4>S3 Remove MB S4 S3 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MB88P_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | POLICE GENERAL HOSPITAL_MAHA BHUMIBOL RACHANUSORN 88TH YEARS BUILDING | [5 empty] | 2026-08-20 | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  |  | 2026-08-08 | 2026-09-25 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 20:26:22 | Yes | Yes | 2026-09-25 20:26:38 | 1.I found h2a (2)card and g2(umpt)=2 card at install eq. 2.This bbp card with red mark not found at before#，need to upload completely. 3.Need install GPS screen shot pto at after c1. 4.Found BBU overview pto 2 #，U install 2 or 1? |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-27 13:53:55 |  |  | 2026-08-08 | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-18 20:57:13 | No | No |  |  |  |  | 2026-08-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-08-18 19:10:32 | No | No |  | 18-08-2026. Replace BBU5900#， UMPTg2#， Add UBBPh2a#， GPS 2026-08-17 Install only |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:01:06 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MB88P_2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | POLICE GENERAL HOSPITAL_MAHA BHUMIBOL RACHANUSORN 88TH YEARS BUILDING | [5 empty] | 2026-08-20 | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  |  | 2026-08-08 | 2026-08-28 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 20:20:50 | Yes | Yes | 2026-09-25 20:21:06 | Not complete eq#，I will check bf and aft later. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-07-27 13:54:15 |  |  | 2026-08-08 | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-18 21:00:23 | No | No |  |  |  |  | 2026-08-18 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-08-18 20:58:14 | No | No |  | 2026-08-18_Replace to BBU5900 by UMPTg2#， Add UBBPh2a#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:01:06 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBBVM_2026 Capacity Expansion Ph1_EXP_BKK | MUBAN BANG BON VILL |  |  |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-19 16:36:19 | No | No |  |  |  | 2026-06-17 | 2026-06-17 | 2026-06-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-26 13:37:56 | Yes | Yes | 2026-06-26 13:41:09 |  | 2026-06-19 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:06:34 | Yes | Yes | 2026-08-01 21:54:43 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-06-17 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-06-17 18:22:31 | No | No |  | 17-06-2026. Replace RRU5507 to AAU5775 Sec.2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBGAM_2025 Capacity Expansion Ph8_EXP_ER | Na Moo Ban The Grand Amata Chonburi | 2026-02-14 | Thcp_phet.sa | Clear Pending | 2026-02-11 | 2026-02-28 | 2026-02-14 | 2026-02-14 | Teloneer Company Limited | N/A | Closed | 2026-02-14 16:54:16 | No | No |  |  | 2026-02-11 | 2026-02-28 | 2026-02-11 | 2026-02-16 | Teloneer Company Limited | N/A | Closed | 2026-02-16 09:49:54 | Yes | Yes | 2026-02-17 14:11:23 |  | 2026-02-28 | 2026-02-19 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-19 11:31:58 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 12:18:43 |  | 2026-02-28 | 2026-02-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-13 15:14:42 | Yes | Yes | 2026-02-12 07:57:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-11 17:52:41 | No | No |  | Add UBBPg3a New L26F5 + NR26 (New RRU5818) + Co Antenna_MBGAM_N_2 |  | 2026-02-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-13 17:49:57 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBK3P_2025 Capacity Expansion NW Modernization_EXP_BKK | MABOONKRONGH 3 |  |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-11 | 2026-02-11 | V Contribute Co., Ltd | N/A | Closed | 2026-02-11 21:13:40 | Yes | Yes | 2026-02-11 21:13:41 |  | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-06 15:45:14 | Yes | Yes | 2026-02-25 21:59:40 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:48:41 |  | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:45 | Yes | Yes | 2026-02-25 22:35:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Replace UBBPd5(2) to UBBPg3a#， UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBK4P_2025 Capacity Expansion NW Modernization_EXP_BKK | MABOONKRONGH 4 |  |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-11 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 17:35:14 | Yes | Yes | 2026-02-12 17:35:15 |  | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-06 15:45:14 | Yes | Yes | 2026-02-25 22:00:20 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:49:00 |  | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:45 | Yes | Yes | 2026-02-25 22:36:01 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Replace UBBPd5(2) to UBBPg3a#， UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBK5P_2025 Capacity Expansion NW Modernization_EXP_BKK | MABOONKRONGH 5 |  |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-11 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 10:58:31 | Yes | Yes | 2026-02-12 10:58:31 |  | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-06 15:45:14 | Yes | Yes | 2026-02-25 22:07:04 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:49:19 |  | 2026-02-25 | 2026-02-25 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:45 | Yes | Yes | 2026-02-25 22:36:34 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Replace UBBPd5(2) to UBBPg3a#， UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBK6P_2025 Capacity Expansion NW Modernization_EXP_BKK | MABOONKRONGH 6 |  |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-21 | 2026-02-11 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 10:54:00 | Yes | Yes | 2026-02-12 10:54:00 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-06 15:45:14 | Yes | Yes | 2026-02-26 21:23:54 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-08 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:49:37 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-26 21:27:28 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Replace UBBPd6(2) to UBBPg3a#， UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MBLBM_2026 Capacity Expansion Ph1_EXP_ER | MabLumBid | 2026-07-06 | Team : Thcp_phet.sa Tel : 0924272237 |  | 2026-06-01 | 2026-07-15 | 2026-07-06 | 2026-07-06 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-06 19:03:40 | No | No |  |  |  | 2026-07-20 | 2026-07-08 | 2026-07-08 | Teloneer Company Limited | N/A | Closed | 2026-07-08 20:36:01 | Yes | Yes | 2026-07-08 20:39:37 |  | 2026-07-20 | 2026-07-11 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-20 21:39:41 | Yes | Yes | 2026-07-11 10:51:24 |  | Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:34:22 | No | Yes | 2026-09-12 10:32:26 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-10 16:09:38 | No | No |  |  | 2026-06-30 | 2026-07-01 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:43 | Yes | Yes | 2026-07-01 13:41:27 |  | 2026-07-07 | 2026-07-15 | 2026-07-06 | Teloneer Company Limited | N/A | Closed | 2026-07-06 17:20:08 | No | No |  |  |  |  | 2026-07-06 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-06 19:00:55 | No | No |  | Replace UBBPg1 to UBBPg2 Replace UBBPg1 to UBBPg3a Replace Antenna (Dualband)_MBLBM_H_3 Replace Antenna (Co Antenna)_MBLBM_L_3 New L26F5 + NR26 (New AAU5656)_MBLBM_N_2 New L26F5 + NR26 (New AAU5656)_MBLBM_N_4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-10 | Boonchot Boriwut | N/A | Closed | 2026-07-13 04:19:49 | No | No |  |  |  | Day1 : 80% , Day2: ไม่เข้า0% , Day3 : ฝนตก0% , Day4 : ฝนตก50% , Day5 : ฝนตก50% , Day6 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MEAKB_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL MEA KHLONG TOEI |  |  |  | 2026-05-05 | 2026-05-05 | 2026-05-05 | 2026-05-05 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-05 16:34:05 | No | No |  |  | 2026-03-25 | 2026-03-25 | 2026-03-30 | 2026-03-31 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-31 15:03:41 | Yes | Yes | 2026-04-17 09:14:20 |  | 2026-05-05 | 2026-05-05 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-31 18:23:03 | Yes | Yes | 2026-05-05 16:36:24 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 21:32:48 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-20 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-03-20 18:07:12 | No | No |  | 20 Mar 2026 Replace Ant clear work 19-03-2026. ***Need Replace BBU5900#， RRU5507 Sec.B //Replace RRU3962 to RRU5507 x2 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MECPM_2025 Capacity Expansion Ph8_EXP_ER | Mitsubishi Electric Consumer Products (Thailand) Co., Ltd._Phase10 | 2026-02-19 | Thcp_phet.sa | Install & Integrate |  | 2026-02-28 | 2026-02-19 | 2026-02-19 | Teloneer Company Limited | N/A | Closed | 2026-02-19 14:47:43 | No | No |  |  |  | 2026-02-28 | 2026-02-20 | 2026-02-25 | Teloneer Company Limited | N/A | Closed | 2026-02-25 16:17:08 | Yes | Yes | 2026-02-26 23:22:46 |  | 2026-02-28 | 2026-03-02 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-12 17:50:40 | Yes | Yes | 2026-03-04 10:07:26 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-09 | 2026-03-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 12:19:39 |  | 2026-02-28 | 2026-02-20 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:21:34 | Yes | Yes | 2026-02-20 17:39:00 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-19 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-19 17:05:07 | No | No |  | Add UBBPg3a New L26F5 + NR26 (New RRU5818) + Co Antenna_MECPM_N_P |  | 2026-02-20 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-20 15:06:20 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MGKLM_2026 Capacity Expansion Ph1_EXP_SR | Ban Muang Kluang | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-08 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-07 | 2026-08-31 | 2026-09-06 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-06 16:36:13 | No | No |  |  |  |  | 2026-09-06 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-06 20:05:46 | No | No |  | Add g3a*1 S2 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MGMHM_2026 Capacity Expansion Modernize_EXP_ER | Mueang Moo 4 | 2026-08-14 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-20 | 2026-08-14 | 2026-08-14 | Teloneer Company Limited | N/A | Closed | 2026-08-14 17:29:28 | No | No |  |  |  | 2026-08-20 | 2026-08-15 | 2026-08-17 | Teloneer Company Limited | N/A | Closed | 2026-08-17 15:44:01 | Yes | Yes | 2026-08-19 22:10:34 |  | 2026-08-20 | 2026-08-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:48:05 | Yes | Yes | 2026-09-04 19:28:50 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:30 | No | No |  |  | 2026-08-20 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 18:00:32 |  |  | 2026-08-20 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 09:19:44 | No | No |  |  |  |  | 2026-08-14 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-14 17:19:02 | No | No |  | Add UBBPh2a Add RRU5505 x 1 + 4T4R_MGMHM_H_1 Add RRU5505 x 1 + 4T4R_MGMHM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_MGMHM_H_3 Replace RRU (RRU5516_900) + Co NR07 + 4T4R_MGMHM_L_1 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_MGMHM_L_2 Co L21(F2) all sector |  | 2026-08-19 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-19 15:53:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MGVPM_2026 Capacity Expansion Ph2_EXP_ER | Moo Ban Groovy Park |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MHBTM_2026 Capacity Expansion Ph1_EXP_ER | Moo6 Ban NoenThung | 2026-07-16 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-07-20 | 2026-07-16 | 2026-07-16 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-16 12:03:39 | No | No |  |  |  | 2026-07-20 | 2026-07-16 | 2026-07-16 | Teloneer Company Limited | N/A | Closed | 2026-07-16 19:17:49 | Yes | Yes | 2026-07-16 19:20:34 |  | 2026-07-20 | 2026-07-20 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:40 | Yes | Yes | 2026-07-20 17:09:04 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-14 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:48 | No | No |  |  | 2026-07-20 | 2026-07-10 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-11 11:49:00 | Yes | Yes | 2026-07-10 18:09:26 |  |  | 2026-07-20 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 18:03:13 | No | No |  |  |  |  | 2026-07-16 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-16 10:26:06 | No | No |  | Add UBBPg3a_MHBTM_H_1 New L26F5 + NR26 (New AAU5656)_MHBTM_N_1 New L26F5 + NR26 (New AAU5656)_MHBTM_N_2 |  | 2026-07-17 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-17 17:06:01 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 70% , Day2 : 95% , Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MJA2B_2026 Capacity Expansion NW Modernization_EXP_BKK | MAJOR CINEPLEX RATCHAYOTHIN (IMAX) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MJA3B_2026 Capacity Expansion NW Modernization_EXP_BKK | MAJOR CINEPLEX RATCHAYOTHIN (IMAX) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MJANB_2026 Capacity Expansion NW Modernization_EXP_BKK | MAJOR CINEPLEX RATCHAYOTHIN (IMAX) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MJSKA_2026 Capacity Expansion Ph1_EXP_SR | Masjidklang Songkhla | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-28 | 2026-07-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-29 10:50:37 | Yes | Yes | 2026-08-06 22:22:38 |  | 2026-08-17 | 2026-08-21 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-21 10:58:21 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-08-10 | 2026-08-17 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-17 13:17:17 |  | 2026-07-30 | 2026-08-31 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 18:34:24 | No | No |  |  |  |  | 2026-07-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-28 16:00:35 | No | No |  | S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MK86M_2026 Capacity Expansion NW Modernization_EXP_BKK | MOTORWAY KM. 8.6 | [5 empty] | 2026-09-13 | 2026-09-13 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 | 2026-09-18 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 21:19:08 | Yes | Yes | 2026-09-25 21:19:16 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:40:23 |  |  | 2026-10-10 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 12:05:27 | No | No |  |  |  |  | 2026-09-13 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-13 17:11:55 | No | No |  | 13 Sep 2026 Add AAU57775 sector3 replace RRU5561 sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-14 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:31:11 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MKAOM_2025 Capacity Expansion Ph8_EXP_ER | Wat Nong Muang Kao | 2026-02-23 | Thcp_adirek.kh | Clear Pending |  | 2026-02-28 | 2026-02-04 | 2026-02-04 | Teloneer Company Limited | N/A | Closed | 2026-02-04 15:57:43 | No | No |  |  |  | 2026-02-28 | 2026-02-04 | 2026-02-09 | Teloneer Company Limited | N/A | Closed | 2026-02-09 17:13:22 | Yes | Yes | 2026-02-11 22:50:17 |  | 2026-02-28 | 2026-02-13 | Apichat fangsantthia(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-16 11:12:14 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 12:20:54 |  | 2026-02-28 | 2026-02-07 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:16:52 | Yes | Yes | 2026-02-07 14:32:58 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-24 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-26 16:47:27 | No | No |  | RET Motor Fault L18L21 S1 Tilt 30 / L9L7 S2 -- clear /// Add UBBPg2 Add RRU 5508 x 1 + Co NR07 + 4T4R_MKAOM_L_3 ( New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_MKAOM_L_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_MKAOM_L_2 |  | 2026-02-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-24 16:25:40 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MKERO_2026 Capacity Expansion Ph1_EXP_SR | Mu Jet Ke Ro | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-27 | 2026-09-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-30 13:40:26 | Yes | Yes | 2026-09-30 13:43:09 | 1.Antenna install or not ? |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-28 | 2026-08-31 | 2026-09-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-27 17:13:45 | No | No |  |  |  |  | 2026-09-27 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-27 15:45:09 | No | No |  | 27 Sep 2026 Add AAU5656 sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MKRBM_2026 Capacity Expansion Ph2_EXP_ER | Mahakij Rubber | 2026-09-23 | Team : thcp_jaran.s Tel : 0988500996 | Install & Integrate |  | 2026-09-30 | 2026-09-23 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-24 07:39:09 | No | No |  |  |  | 2026-09-30 | 2026-09-24 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-24 20:54:26 | Yes | Yes | 2026-09-26 14:25:00 | >Need to upload Panorama if you install new RRU. | 2026-09-30 | 2026-09-26 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-26 17:34:05 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-25 17:31:42 | Yes | Yes | 2026-09-23 14:52:17 |  |  | 2026-09-30 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-24 12:11:28 | No | No |  |  |  |  | 2026-09-23 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-23 17:47:00 | No | No |  | Add RRU5505 x 1 + 4T4R_MKRBM_H_3 Co L21(F2) S1#，S2#，S3 |  | 2026-09-24 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-24 16:06:18 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MKTTR_2026 Capacity Expansion Ph1_EXP_SR | Mu 2 Ko To Tue Ra | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-26 | 2026-09-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-27 11:57:08 | Yes | Yes | 2026-10-02 01:46:42 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-26 | 2026-08-31 | 2026-09-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-26 17:31:04 | No | No |  |  |  |  | 2026-09-26 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-26 16:31:07 | No | No |  | 26 Sep 2026 Replace RRU5516 sector1 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MKVLM_2026 Capacity Expansion Modernize_EXP_ER | Maneekaew Village | 2026-08-01 | Team : thcp_jaran.s Tel : 0988500996 | Install & Integrate |  | 2026-08-15 | 2026-08-01 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 20:19:39 | No | No |  |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 17:18:56 | Yes | Yes | 2026-08-06 10:47:21 |  | 2026-08-20 | 2026-08-07 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-16 19:01:41 | Yes | Yes | 2026-08-11 10:49:22 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:08 | No | No |  |  | 2026-08-15 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-06 11:37:47 | Yes | Yes | 2026-08-06 09:07:43 |  |  | 2026-08-15 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 10:57:06 | No | No |  |  |  |  | 2026-08-01 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-01 11:12:03 | No | No |  | Add RRU5508 x 1 + Co NR07 + 4T4R_MKVLM_L_3 |  | 2026-08-03 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-03 17:32:32 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MLLYM_2026 Capacity Expansion Ph1_EXP_BKK | MUBAN LULLY |  |  |  | 2026-07-11 | 2026-07-11 | 2026-07-02 | 2026-07-02 | Akarut Kittikasakun(CCS Comservice (Thailand) Ltd.) | N/A | Closed | 2026-07-02 16:03:17 | No | No |  |  | 2026-07-10 | 2026-07-10 | 2026-06-24 | 2026-06-25 | CCS Comservice (Thailand) Ltd. | N/A | Closed | 2026-06-25 16:41:40 | Yes | Yes | 2026-06-26 12:12:36 |  | 2026-06-26 | 2026-06-26 | CCS Comservice (Thailand) Ltd. | Approving | Assigned |  | Yes | Yes | 2026-09-01 14:21:26 | Page no.5#， need to fill install BBP card. Clear Done Need to delete extra page no.11#，12. Clear Done | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-06-08 | 2026-06-05 | Tanaporn Sungkrom | Approved | Closed | 2026-06-23 17:07:31 | Yes | Yes | 2026-06-08 09:27:09 |  |  | 2026-07-30 | 2026-06-18 | CCS Comservice (Thailand) Ltd. | N/A | Closed | 2026-06-18 15:49:03 | No | No |  |  |  |  | 2026-06-19 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-06-19 19:27:36 | No | No |  | 19-06-2026. Remove RRU Sec.M //18-Jun-2026 Add UBBPh2a Remove g3a Add AAU5775 S3 Remove RRU5507*2#，2 3#，8 Done No NB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Install 100 % | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MMT3M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI MUBAN MITTRAPHAB3 | [5 empty] | 2026-08-01 | 2026-08-01 | Thossapan Chaloemrit | N/A | Closed | 2026-08-03 16:03:00 | No | No |  |  |  | 2026-08-31 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 21:16:44 | Yes | Yes | 2026-08-07 11:18:00 |  | 2026-08-11 | 2026-08-11 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-08-11 23:11:31 | Page 46 After busbar C1 photo Need. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-27 10:26:45 |  |  | 2026-06-30 | 2026-07-30 | Teloneer Company Limited | N/A | Closed | 2026-07-30 14:07:18 | No | No |  |  |  |  | 2026-07-30 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-07-30 16:58:24 | No | No |  | 2026-07-30 S1 Remove RRU5507*2 > Add AAU5775 S2 Remove RRU3962 > Add AAU5775 S6 Remove RRU5507*2 S7 Remove RRU3962 Add Card UBBPh3a Cell RX Channel Interference Noise Power Unbalanced > alarm before |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-04 16:07:52 | No | No |  |  | SQC closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MNAKT_2026 Capacity Expansion Ph1_EXP_SR | Mu 7 Na Ket | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-07 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | Need to upload grounding kid photos in QC. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-07 | 2026-08-31 | 2026-09-07 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-07 18:19:37 | No | No |  |  |  |  | 2026-09-07 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-07 19:11:40 | No | No |  | Rep d5*1 to h2a*1 Rep Ant MB S3 S3 Rep RRU3953*1 to RRU5516*1 > Ant Combine MB S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MNATH_2026 Capacity Expansion Ph1_EXP_SR | Mu 4 Na Tham | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 |  | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | N/A | Assigned |  | Yes | No |  |  | 2026-09-21 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-21 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-21 19:01:00 | No | No |  | config ret LB S1 S3 > AAU5656 *Pending Ret LB S1 #，S3 > AAU5656 ------------------ add h3a*1#， remove eb*1#，g3a*1 Re MB S1>S3//add new ant LB S1 S1 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MNKWM_2026 Capacity Expansion Modernize_EXP_ER | Ban Maneekaew | 2026-08-03 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-15 | 2026-08-03 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 18:02:10 | No | No |  |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 16:35:28 | Yes | Yes | 2026-08-04 22:08:56 |  | 2026-08-15 | 2026-08-04 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:58:04 | Yes | Yes | 2026-08-07 21:06:13 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:30 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:17:22 |  |  | 2026-08-15 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 11:37:08 | No | No |  |  |  |  | 2026-08-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-03 19:41:49 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_MNKWM_H_1 Co L21F2 all sector |  | 2026-08-04 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-04 17:05:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1: 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MNMNM_2026 Capacity Expansion Ph1_EXP_ER | Microcell Nongmon | 2026-08-29 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-08-31 | 2026-08-29 | 2026-08-29 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-30 06:59:53 | No | No |  |  |  | 2026-08-31 | 2026-08-29 | 2026-08-31 | Teloneer Company Limited | N/A | Closed | 2026-08-31 23:33:55 | Yes | Yes | 2026-09-02 09:31:51 |  | 2026-08-31 | 2026-09-01 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:43:50 | Yes | Yes | 2026-09-01 23:06:26 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:28 | No | No |  |  | 2026-08-31 | 2026-09-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:42:57 | Yes | Yes | 2026-09-04 08:09:20 |  |  | 2026-08-31 | 2026-08-29 | Teloneer Company Limited | N/A | Closed | 2026-08-29 15:13:30 | No | No |  |  |  |  | 2026-08-29 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-29 17:50:19 | No | No |  | New NR26 (New RRU5818) + Co Antenna_MNMNM_N_1 New NR26 (Co RRU5818) + Co Antenna_MNMNM_N_2 |  | 2026-09-21 | Reungsak Junkong 00927496 | N/A | Closed | 2026-09-21 17:58:15 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MNTLM_2025 Capacity Expansion NW Modernization_EXP_BKK | MINISTRY OF LABOUR |  |  |  | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-29 11:41:53 | No | No |  |  | 2026-03-31 | 2026-03-31 | 2026-03-28 | 2026-03-28 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-28 18:18:48 | Yes | Yes | 2026-04-07 10:43:23 |  | 2026-04-29 | 2026-04-29 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 17:40:28 | Yes | Yes | 2026-04-29 11:45:26 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-07-14 22:52:23 |  |  | 2026-03-31 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-23 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-03-23 17:26:55 | No | No |  | 2026-03-23_Add RRU5507 Sector 2#， Replace RRU3962(2) to AAU5768 Sector 3#，8#， Add UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MONKM_2026 Capacity Expansion Ph1_EXP_ER | Moo4 Nongchak | 2026-06-12 | Team : THCP_Wachira.s Tel : 065-7649919 | Install & Integrate | 2026-06-01 | 2026-06-30 | 2026-06-12 | 2026-06-12 | Wachira saovaro(Teloneer Company Limited) | N/A | Closed | 2026-06-13 06:26:49 | No | No |  |  |  | 2026-06-30 | 2026-06-12 | 2026-06-13 | Teloneer Company Limited | N/A | Closed | 2026-06-13 16:19:39 | Yes | Yes | 2026-06-15 08:58:09 |  | 2026-06-30 | 2026-06-17 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:17:04 | Yes | Yes | 2026-06-17 12:46:51 |  | Pass | 2026-07-20 | 2026-07-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-20 17:17:35 | No | Yes | 2026-07-20 17:17:23 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-14 15:06:49 | No | No |  |  | 2026-06-30 | 2026-06-11 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:37:15 | Yes | Yes | 2026-06-11 13:21:47 |  | 2026-06-15 | 2026-06-30 | 2026-06-12 | Teloneer Company Limited | N/A | Closed | 2026-06-12 14:28:06 | No | No |  |  |  |  | 2026-06-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-12 18:50:45 | No | No |  | Replace UBBPd5 x 2 to UBBPh2a +Replace UBBPd5 to UBBPh3a done Remove Antenna + (New AAU5775) + Main Dir = 100 + Remove RRU5513 x 1_MONKM_H_2 Remove Antenna + (New AAU5775) + Main Dir = 220 + Remove RRU5513 x 1_MONKM_H_3 Replace 1RRU3953 to (RRU5508 x 2) + Co L07 + NR07 + 4T4R_MONKM_L_3 New Sector 7 (Co AAU5775) + Main Dir = 100_MONKM_H_7 New Sector J (Co AAU5775) + Main Dir = 100_MONKM_H_J New Sector K (Co AAU5775) + Main Dir = 100_MONKM_H_K New Sector 8 (Co AAU5775) + Main Dir = 220_MONKM_H_8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-12 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MPBST_2026 Capacity Expansion NW Modernization_EXP_SR | Mo 8 Ban Sai Tok | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-09-05 | 2026-08-20 | 2026-08-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-21 13:41:26 | Yes | Yes | 2026-08-24 15:43:06 |  | 2026-08-25 | 2026-09-03 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-09-03 09:06:20 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-25 | 2026-08-25 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-25 11:05:09 |  | 2026-08-20 | 2026-08-31 | 2026-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-20 21:45:56 | No | No |  |  |  |  | 2026-08-20 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-20 17:08:58 | No | No |  | 20 Aug 2026 Replace RRU3962 sector1#，2#，3#，4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MPHIM_2026 Capacity Expansion Ph1_EXP_ER | Mab Phai | 2026-06-30 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate | 2026-06-01 | 2026-06-30 | 2026-07-01 | 2026-07-01 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-02 13:14:25 | No | No |  |  |  | 2026-06-30 | 2026-06-30 | 2026-07-02 | Teloneer Company Limited | N/A | Closed | 2026-07-02 12:14:25 | Yes | Yes | 2026-07-02 13:30:20 |  | 2026-06-30 | 2026-07-07 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-11 11:51:06 | Yes | Yes | 2026-07-07 17:20:09 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-05 11:49:58 | No | No |  |  | 2026-06-30 | 2026-06-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-30 21:27:35 | Yes | Yes | 2026-06-30 10:02:49 |  | 2026-07-01 | 2026-06-30 | 2026-06-30 | Teloneer Company Limited | N/A | Closed | 2026-06-30 12:10:58 | No | No |  |  |  |  | 2026-06-30 | Autumporn Masing WX1434753 | N/A | Closed | 2026-07-24 09:41:26 | No | No |  | Add UBBPg3a ReDirection 130 to 90_MPHIM_N_2 New L26F5 + NR26 (New AAU5656)_MPHIM_N_7 |  | 2026-07-01 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-01 19:17:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-30 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:47:15 | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MPHKB_2025 Capacity Expansion NW Modernization_EXP_BKK | MINGPRACHA BUILDING (KLUAYNAMTHAI HOSPITAL)_MICRO CELL |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-27 | 2026-03-23 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:08:55 | Yes | Yes | 2026-03-23 15:08:56 |  | 2026-04-24 | 2026-04-24 | Chonradee Suwapan | Approved | Closed | 2026-06-30 20:16:37 | Yes | Yes | 2026-04-24 02:29:01 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-07 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-24 | 2026-04-24 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-24 17:42:40 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-06 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-03-06 18:42:48 | No | No |  | 2026-03-06_Replace RRU3962 to RRU5526#， Replace Ant to 12 port Sector A#， Replace UBBPd5 to UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MPIEM_2026 Capacity Expansion Ph2_EXP_ER | Maptaput Industrial Estate |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MPINM_2026 Capacity Expansion NW Modernization_EXP_BKK | MUBAN PAITOON | [5 empty] | 2026-09-17 | 2026-09-17 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-10 | 2026-10-01 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:41:09 |  |  | 2026-10-10 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 11:00:38 | No | No |  |  |  |  | 2026-09-16 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-16 20:11:11 | No | No |  | 2026-09-16_UBBPg3 to UBBPh3a S1 Replace RRU3962*2 to RRU5526 S2 Replace RRU3962*2 to AAU5775 S3 Replace RRU3962*2 to AAU5775 S7 Remove RRU3962 S8 Remove RRU3962*2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-17 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:27:23 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MPJSM_2026 Capacity Expansion Modernize_EXP_ER | MuangPattaya7 school | 2026-08-01 | Team : Thcp_phet.sa Tel : 0924272237 |  |  | 2026-08-15 | 2026-08-01 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 20:19:40 | No | No |  |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 11:46:55 | Yes | Yes | 2026-08-04 14:16:24 |  | 2026-08-15 | 2026-08-04 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-16 19:01:41 | Yes | Yes | 2026-08-07 21:17:24 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:08 | No | No |  |  | 2026-08-15 | 2026-08-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:04:40 | Yes | Yes | 2026-08-08 08:26:02 |  |  | 2026-08-15 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 14:17:08 | No | No |  |  |  |  | 2026-08-01 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-01 13:16:10 | No | No |  | Replace RRU (RRU5516_900) + Co L07 + 4T4R_MPJSM_L_3 Co L21F2 All Sector |  | 2026-08-03 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-03 17:32:32 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MPTNP_2025 Capacity Expansion NW Modernization_EXP_BKK | THE MARKET BY PLATINUM |  |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-16 17:56:33 | No | No |  |  |  | 2026-02-06 | 2026-02-11 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 11:33:59 | Yes | Yes | 2026-02-12 11:33:59 |  | 2026-02-13 | 2026-02-13 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-13 22:57:02 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:52:27 |  | 2026-02-13 | 2026-02-13 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-13 23:12:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-02 17:52:51 | No | No |  | 2 Feb 2026 Add 1UBBPg2 1UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MS22M_2026 Capacity Expansion Ph2_BKK | SOI MU BAN SETTHAKIT 22 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MSDPM_2026 Capacity Expansion Ph2_BKK | MUBAN SUAN DUANG PHON | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MSKHH_2025 Coverage Expansion Ph1_New_SR | Mu 3 Khuan Hin | [5 empty] | 2026-03-06 | 2026-03-06 | Nattawoot Suwan | N/A | Closed | 2026-03-13 18:40:38 | No | No |  |  |  | 2026-02-27 | 2026-03-06 | 2026-03-06 | Teloneer Company Limited | N/A | Closed | 2026-03-06 15:37:26 | Yes | Yes | 2026-03-09 15:38:51 |  | 2026-03-09 | 2026-03-09 | Teloneer Company Limited | Approved | Closed | 2026-03-11 15:48:40 | Yes | Yes | 2026-03-12 10:11:34 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-03-17 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-03-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-03-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-03-05 23:32:02 | No | No |  | 5 Mar 2026 Repace UMPT slot18 ***Pending RRU S3 -------------- 26 Feb 2026 Donor : 3RNCHYI6H_KKSUM_D1 BBU3910#，UBBPd6*3 S1 > RRU3839 > Ant 4 port S2 > RRU3839 > Ant 4 port S3 > RRU3839 > Ant 4 port |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-02-23 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-02-23 13:56:14 | Yes | Yes | 2026-02-23 13:47:32 |  |  | 2026-06-08 | Nattawoot Suwan | N/A | Closed | 2026-06-08 18:40:06 | No | No | [5 empty] | 2026-03-05 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-02 09:47:58 | No | No
MSSPA_2026 Capacity Expansion Ph1_EXP_SR | Mu 6 Sai Sopha | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-10 | 2026-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-11 14:39:23 | Yes | Yes | 2026-08-15 12:23:44 |  | 2026-08-16 | 2026-08-20 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-20 09:40:01 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-16 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-20 09:42:31 |  | 2026-08-13 | 2026-08-31 | 2026-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-10 15:57:41 | No | No |  |  |  |  | 2026-08-10 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-10 18:36:04 | No | No |  | 10 Aug 2026 Add AAU5656 sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MSSRM_2026 Capacity Expansion Modernize_EXP_ER | Marine Service Support Regiment | 2026-08-08 | Team : thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-08-20 | 2026-08-09 | 2026-08-09 | Teloneer Company Limited | N/A | Closed | 2026-08-09 11:10:45 | No | No |  |  |  | 2026-08-20 | 2026-08-11 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 13:57:31 | Yes | Yes | 2026-08-17 17:50:09 |  | 2026-08-20 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:50 | Yes | Yes | 2026-08-17 23:43:41 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:23 | No | No |  |  | 2026-08-20 | 2026-08-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:04:40 | Yes | Yes | 2026-08-08 10:45:20 |  |  | 2026-08-20 | 2026-08-08 | Teloneer Company Limited | N/A | Closed | 2026-08-08 13:58:34 | No | No |  |  |  |  | 2026-08-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-08 18:10:26 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_MSSRM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_MSSRM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_MSSRM_H_C New L21(F2) Sec. A#，B#，C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MSUPM_2026 Capacity Expansion Ph2_BKK | SOI MUBAN SUPNAKHON | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MSYYM_2026 Capacity Expansion Ph2_EXP_ER | Moo2 BanYuYenLen |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MTARY_2026 Capacity Expansion Ph1_EXP_SR | 42 Military Circle (Telecommunication) | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-07-31 | 2026-07-28 | 2026-07-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-29 14:54:52 | Yes | Yes | 2026-08-10 11:07:56 |  | 2026-08-13 | 2026-08-13 | Muhamadnase Chesamae | Approved | Closed | 2026-08-28 16:01:52 | Yes | Yes | 2026-08-14 10:21:08 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:05 | No | No |  |  | 2026-08-13 | 2026-08-13 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-13 08:09:11 |  | 2026-07-28 | 2026-08-31 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 18:13:02 | No | No |  |  |  |  | 2026-07-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-28 16:00:17 | No | No |  | Add UBBPh2a*1 Rep Ant MB S3 to Ant 8 Port S3 > RRU5516LB*1 > Ant Combine S3 MB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MTJCM_2026 Capacity Expansion Modernize_EXP_ER | Metro Jomtein Condo | 2026-07-23 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-07-31 | 2026-07-23 | 2026-07-23 | Teloneer Company Limited | N/A | Closed | 2026-07-24 09:31:29 | No | No |  |  |  | 2026-07-31 | 2026-07-24 | 2026-07-27 | Teloneer Company Limited | N/A | Closed | 2026-07-27 23:35:06 | Yes | Yes | 2026-07-28 14:58:41 |  | 2026-07-31 | 2026-07-28 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:02:06 | Yes | Yes | 2026-07-29 00:53:06 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-19 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:22 | No | No |  |  | 2026-07-31 | 2026-07-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-25 12:10:05 | Yes | Yes | 2026-07-23 15:24:41 |  |  | 2026-07-31 | 2026-07-23 | Teloneer Company Limited | N/A | Closed | 2026-07-23 20:26:38 | No | No |  |  |  |  | 2026-07-23 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-23 20:28:32 | No | No |  | Replace RRU5505 to (RRU5513) + 4T4R_MTJCM_H_2 Replace RRU5505 to (RRU5513) + 4T4R_MTJCM_H_3 Co L21F2 all sector |  | 2026-07-30 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-30 19:06:52 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MTLCH_2026 Capacity Expansion Ph1_EXP_SR | Mu 8 Taling Chan | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-25 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-25 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-25 19:08:43 | No | No |  | add h2a*1 Rep Ant MB S1 S1 > RRU5516*1 > Ant Combine MB S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MUDDM_2025 Capacity Expansion NW Modernization_EXP_BKK | MAHIDOL UNIVERSITY DIN DAENG |  |  |  |  | 2026-02-26 | 2026-02-26 | 2026-02-26 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-03-13 | 2026-03-23 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 13:16:38 | Yes | Yes | 2026-03-24 13:16:38 |  | 2026-04-10 | 2026-04-09 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-04-21 17:29:48 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-10 | 2026-04-09 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-10 00:21:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-26 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-26 18:46:57 | No | No |  | 2026-02-26_Replace RRU5507(4) to AAU5768 Sector 1#，6#，2#，7#，3#，8#， |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MWATM_2025 Capacity Expansion Ph5_EXP_ER_Add | Motorway Amata | 2026-03-30 | Thcp_adirek.kh | Install & Integrate |  | 2026-04-03 | 2026-03-30 | 2026-03-31 | Teloneer Company Limited | N/A | Closed | 2026-03-31 09:30:37 | No | No |  |  |  | 2026-04-10 | 2026-03-30 | 2026-04-02 | Teloneer Company Limited | N/A | Closed | 2026-04-02 20:48:49 | Yes | Yes | 2026-04-05 23:22:52 |  | 2026-04-10 | 2026-04-17 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-04-27 09:18:13 | Yes | Yes | 2026-04-17 17:57:25 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-23 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-31 | 2026-03-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-04-01 00:13:26 | Yes | Yes | 2026-03-30 11:51:00 |  | 2026-03-30 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-30 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-03-30 16:58:29 | No | No |  | "Add UBBPg2 Add RRU5508 x 1 + Co L07 + NR07 + 4T4RMWATM_L_1 Co NR07MWATM_L_2 Co NR07MWATM_L_3" |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MWHTM_2026 Capacity Expansion Ph2_EXP_ER | Mabpawa-Hintaen Road | 2026-09-30 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-09-30 | 2026-09-30 | 2026-09-30 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-30 21:10:28 | No | No |  |  |  | 2026-09-30 | 2026-09-28 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  | 1.Not same ground bar in S1 at after/before 2.Need to upload on ground completely photo at after 3.Need to upload install mount in additional work | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-30 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-30 11:23:47 |  |  | 2026-09-30 | 2026-09-30 | Teloneer Company Limited | N/A | Closed | 2026-09-30 16:20:21 | No | No |  |  |  |  | 2026-09-30 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-30 18:34:56 | No | No |  | New L26F5 + NR26 (New AAU5656)_MWHTM_N_3 |  | 2026-10-01 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-10-01 17:36:08 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
MYGMM_2026 Capacity Expansion Ph2_EXP_ER | Map Yang Porn Moo 6 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NABLA_2026 Capacity Expansion NW Modernization_EXP_SR | NA BIN LA | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-09-05 | 2026-08-23 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-23 | 2026-08-31 | 2026-08-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-25 11:44:21 | No | No |  |  |  |  | 2026-08-23 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-23 18:12:01 | No | No |  | S1 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S2 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S3 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S4 > Rep RRU3826*2 to RRU3962*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NAIR7_2026 Capacity Expansion Ph1_EXP_SR | Network Centric Air Base 7 Suratthani | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-09 | 2026-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-10 20:37:03 | Yes | Yes | 2026-08-20 09:47:33 |  | 2026-08-20 | 2026-08-20 | Charuwan Limsaihua | Approved | Closed | 2026-09-04 11:09:44 | Yes | Yes | 2026-08-20 13:34:02 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-01 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-03 17:02:36 | No | No |  |  | 2026-08-20 | 2026-08-20 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-20 13:35:33 |  | 2026-08-10 | 2026-08-31 | 2026-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-10 13:39:25 | No | No |  |  |  |  | 2026-08-10 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-10 18:36:04 | No | No |  | 10 Aug 2026 Add AAU5516 sector4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NANJM_2026 Capacity Expansion Modernize_BBU_EXP_ER | Nikom Amata Nakorn J | 2026-09-29 | Team : Thcp_phet.sa Tel : 0924272237 | Clear Alarm |  | 2026-09-30 | 2026-09-29 | 2026-09-29 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-30 07:17:06 | No | No |  |  |  | 2026-09-30 | 2026-09-28 | 2026-09-30 | Teloneer Company Limited | N/A | Closed | 2026-09-30 09:46:41 | Yes | Yes | 2026-10-01 12:36:13 |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-28 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-28 08:19:40 |  |  | 2026-09-30 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 20:13:56 | No | No |  |  |  |  | 2026-09-29 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-29 16:47:59 | No | No |  | KKFJM Remote RRU DSCTP Remote RRU MXMIP Remote RRU SMFSP Remote RRU no external alarm |  | 2026-09-28 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-28 17:52:03 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 90% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NARIG_2026 Capacity Expansion NW Modernization_EXP_SR | NA RING | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-09-05 | 2026-08-18 | 2026-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-19 20:24:22 | Yes | Yes | 2026-08-26 18:48:01 |  | 2026-09-01 | 2026-09-01 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-01 02:23:18 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-01 | 2026-09-01 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-01 02:25:29 |  | 2026-08-17 | 2026-08-31 | 2026-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-18 17:58:57 | No | No |  |  |  |  | 2026-08-17 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-17 17:19:15 | No | No |  | S1 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S2 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S3 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S8 > Rep RRU3826*2 to RRU3962*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NBGCM_2026 Capacity Expansion Ph2_BKK | NIKOM BANGCHAN | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NBKDM_2026 Capacity Expansion Ph2_BKK | NIKHOM BANGKRADI | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NBLEM_2026 Capacity Expansion Modernize_EXP_ER | Nong Bua Leak | 2026-06-17 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-06-30 | 2026-06-17 | 2026-06-17 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-17 21:12:35 | No | No |  |  |  | 2026-06-30 | 2026-06-17 | 2026-06-17 | Teloneer Company Limited | N/A | Closed | 2026-06-17 19:27:33 | Yes | Yes | 2026-06-19 08:44:59 |  | 2026-06-30 | 2026-06-23 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-25 08:23:12 | Yes | Yes | 2026-06-23 16:44:18 |  | First Time Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:39:05 | No | Yes | 2026-09-12 10:37:24 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-16 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-16 16:50:00 | No | No |  |  | 2026-06-30 | 2026-06-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:11:17 | Yes | Yes | 2026-06-17 10:29:23 |  | 2026-06-18 | 2026-06-30 | 2026-06-17 | Teloneer Company Limited | N/A | Closed | 2026-06-17 15:40:47 | No | No |  |  |  |  | 2026-06-17 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-17 19:50:29 | No | No |  | Add UBBPh3a + Remove Antenna + (New AAU5775) + Main Dir = 0 + Remove RRU5505 x 1_NBLEM_H_1 (Co AAU5775) + Main Dir = 0 + Remove RRU5505 x 1_NBLEM_H_6 Add RRU5508 x 1 + 4T4R_NBLEM_L_1 Replace Antenna (LB) + Replace 1RRU3953 to RRU5508 x 2 + Co L07 + NR07 + 4T4R_NBLEM_L_2 Add RRU5508 x 1 + Co NR07 + 4T4R_NBLEM_L_3 New Sector G (Co AAU5775) + Main Dir = 0_NBLEM_H_G New Sector H (Co AAU5775) + Main Dir = 0_NBLEM_H_H Co L21F2 all sector |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-20 | Nattawoot Suwan | N/A | Closed | 2026-06-20 11:07:58 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NBRPM_2026 Capacity Expansion Modernize_EXP_ER | Na Burapa University | 2026-08-06 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-20 | 2026-08-06 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-07 08:46:35 | No | No |  |  |  | 2026-08-20 | 2026-08-07 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 15:34:01 | Yes | Yes | 2026-08-12 11:51:13 |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:54:54 | Yes | Yes | 2026-08-12 23:05:53 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:30 | No | No |  |  | 2026-08-20 | 2026-08-13 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:17:51 |  |  | 2026-08-20 | 2026-08-06 | Teloneer Company Limited | N/A | Closed | 2026-08-06 11:04:54 | No | No |  |  |  |  | 2026-08-06 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-06 20:08:36 | No | No |  | Co NR07_NBRPM_L_1 Replace RRU5508 TO (RRU5516_900) + Co L07 + NR07 + 4T4R_NBRPM_L_3 |  | 2026-08-07 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-07 19:31:01 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NCHKM_2026 Capacity Expansion Ph1_EXP_ER | Nong Chak | 2026-06-15 | Team : thcp_anat.sri Tel : 0629861985 | Clear Pending | 2026-06-01 | 2026-06-30 | 2026-06-13 | 2026-06-13 | Teloneer Company Limited | N/A | Closed | 2026-06-14 13:37:30 | No | No |  |  |  | 2026-06-30 | 2026-06-12 | 2026-06-17 | Teloneer Company Limited | N/A | Closed | 2026-06-17 11:58:10 | Yes | Yes | 2026-06-17 17:33:24 |  | 2026-06-30 | 2026-06-19 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-25 08:23:12 | Yes | Yes | 2026-06-19 17:43:53 |  | First Time Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:34:22 | No | Yes | 2026-09-12 10:32:45 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-14 15:06:49 | No | No |  |  | 2026-06-30 | 2026-06-11 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:37:15 | Yes | Yes | 2026-06-11 14:50:05 |  | 2026-06-13 | 2026-06-30 | 2026-06-13 | Teloneer Company Limited | N/A | Closed | 2026-06-13 16:33:52 | No | No |  |  |  |  | 2026-06-13 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-06-13 20:36:03 | No | No |  | Replace UBBPg1 to UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 130 + Remove RRU x 2_NCHKM_H_2 Remove Antenna + (Co AAU5775) + Main Dir = 130 + Remove RRU x 2 + ReSector S3 to S7_NCHKM_H_7 Remove Antenna + (New AAU5775) + Main Dir = 260 + Remove RRU x 2 + ReSector S4 to S3_NCHKM_H_3 Remove Antenna + (Co AAU5775) + Main Dir = 260 + Remove RRU x 2_NCHKM_H_8 ReSector S3 to S2_NCHKM_L_2 ReSector S4 to S8_NCHKM_L_8 ReSector S8 to S3_NCHKM_L_3 ReSector S3 to S7_NCHKM_N_7 ReSector S4 to S8_NCHKM |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-15 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NCHSG_2026 Capacity Expansion Ph1_EXP_SR | Mu 8 Nong Chumsaeng | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-07 | 2026-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-10 16:49:58 | Yes | Yes | 2026-08-15 12:37:27 |  | 2026-08-16 | 2026-08-25 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-25 17:34:35 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-16 | 2026-08-16 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-16 18:36:09 |  | 2026-08-03 | 2026-08-31 | 2026-08-01 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-01 15:04:52 | No | No |  |  |  |  | 2026-08-01 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-01 17:51:33 | No | No |  | Block Clear Work add UBBPg3a*1 S1 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NCTSM_2026 Capacity Expansion Modernize_EXP_ER | San Chao Na Cha Sa Tai Sue | 2026-08-04 | Team : thcp_watcharin.k Tel :0925546852 |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 17:34:48 | No | No |  |  |  | 2026-08-20 | 2026-08-06 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 15:58:09 | Yes | Yes | 2026-08-09 15:15:06 |  | 2026-08-20 | 2026-08-18 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:58:04 | Yes | Yes | 2026-08-18 18:24:31 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:30 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:18:09 |  |  | 2026-08-15 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 18:07:29 | No | No |  |  |  |  | 2026-08-04 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-04 12:25:54 | No | No |  | Add RRU5505 x 1 + 4T4R_NCTSM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NCTSM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NCTSM_H_3 Co L21F2 All Sector |  | 2026-08-05 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-05 17:32:31 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NGBUA_2026 Capacity Expansion Ph1_EXP_SR | Nong Bua Na Sak | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-27 | 2026-08-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-29 22:14:08 | Yes | Yes | 2026-09-05 20:36:10 |  | 2026-09-07 | 2026-09-07 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-09 15:33:44 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-07 | 2026-09-07 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-07 19:34:55 |  | 2026-08-29 | 2026-08-31 | 2026-08-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-29 15:46:34 | No | No |  |  |  |  | 2026-08-29 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-29 19:12:43 | No | No |  | Rep d6*1 to h2a*1 S2 > Rep RRU3953*1 to RRU5516*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NGKOK_2026 Capacity Expansion Ph1_EXP_SR | Nong Kok | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-03 | 2026-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-13 15:29:36 | Yes | Yes | 2026-08-14 14:55:41 |  | 2026-08-18 | 2026-08-18 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-31 10:45:55 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-18 | 2026-08-18 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-18 15:39:55 |  | 2026-08-05 | 2026-08-31 | 2026-08-03 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-03 17:38:21 | No | No |  |  |  |  | 2026-08-03 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-03 19:39:02 | No | No |  | S2 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NGKTM_2026 Capacity Expansion Ph1_EXP_ER | Ban Nongkate | 2026-06-09 | Team : thcp_anat.sri Tel : 0629861985 | Take Photo & Clear Pending | 2026-06-01 | 2026-06-30 | 2026-06-03 | 2026-06-06 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-06 19:20:52 | No | No |  |  |  | 2026-06-30 | 2026-06-08 | 2026-06-08 | Teloneer Company Limited | N/A | Closed | 2026-06-08 20:42:12 | Yes | Yes | 2026-06-09 09:03:20 |  | 2026-06-30 | 2026-06-15 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:17:04 | Yes | Yes | 2026-06-15 17:14:07 |  | Pass | 2026-07-20 | 2026-07-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-20 17:18:41 | No | Yes | 2026-07-20 17:18:26 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-03 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-07 15:06:00 | No | No |  |  | 2026-06-30 | 2026-06-03 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:31 | Yes | Yes | 2026-06-03 12:53:42 |  | 2026-06-05 | 2026-06-30 | 2026-06-05 | Teloneer Company Limited | N/A | Closed | 2026-06-05 16:09:53 | No | No |  |  |  |  | 2026-06-05 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-05 18:19:54 | No | No |  | Replace UBBPd5 to UBBPg2_NGKTM_H_1 Replace Antenna (Dualbeam)_NGKTM_H_2 done Replace Antenna (Dualbeam)_NGKTM_H_3 done Replace Antenna (Dualbeam) + ReSectorname S8 to S4_NGKTM_H_4 done ReSectorname S8 to S4_NGKTM_N_4 done New L18L21 + 4T4R+ Add RRU5513 + Co Antenna_NGKTM_H_7 slot 4/5 New L18L21 + 4T4R+ Add RRU5513 + Co Antenna_NGKTM_H_8 slot 2/5 New L18L21 + 4T4R+ Add RRU5513 + Co Antenna_NGKTM_H_9 slot 1/5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-09 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NGLKD_2026 Capacity Expansion Ph1_EXP_SR | Nonglak Dormitory | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-05 | 2026-08-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-14 18:15:58 | Yes | Yes | 2026-08-19 11:11:26 |  | 2026-08-20 | 2026-08-26 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-26 14:20:50 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-29 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-30 13:04:17 | No | No |  |  | 2026-08-20 | 2026-08-20 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-20 20:30:58 |  | 2026-08-05 | 2026-08-31 | 2026-08-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-05 14:59:46 | No | No |  |  |  |  | 2026-08-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-05 17:34:32 | No | No |  | 5 Aug 2026 Add RRU5516 sector2 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NGSUM_2026 Capacity Expansion Ph1_EXP_ER | Nong Suang | 2026-08-31 | User isdp : thcp_apichat.f Tel : 0960126111 | Clear Pending | 2026-06-01 | 2026-08-31 | 2026-08-29 | 2026-08-29 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-30 06:59:53 | No | No |  |  |  | 2026-08-31 | 2026-08-29 | 2026-08-31 | Teloneer Company Limited | N/A | Closed | 2026-08-31 17:32:14 | Yes | Yes | 2026-09-02 09:32:56 |  | 2026-08-31 | 2026-09-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:48:05 | Yes | Yes | 2026-09-04 07:57:43 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:20 | No | No |  |  | 2026-07-31 | 2026-08-02 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-04 10:24:05 | Yes | Yes | 2026-08-02 09:14:16 |  |  | 2026-08-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-29 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-29 17:48:41 | No | No |  | Replace UBBPg1 to UBBPh2a Replace Antenna (Dualbeam)_NGSUM_H_1 Replace Antenna (Dualbeam)_NGSUM_H_2 Replace Antenna (Dualbeam)_NGSUM_H_3 Replace Antenna (Dualbeam)_NGSUM_H_4 ReSectorname S6 to SH_NGSUM_H_H New L18L21 + 4T4R+ Add RRU5526 + Co Antenna_NGSUM_H_6 New L18L21 + 4T4R+ Add RRU5526 + Co Antenna_NGSUM_H_7 New L18L21 + 4T4R+ Add RRU5526 + Co Antenna_NGSUM_H_8 New L18L21 + 4T4R+ Add RRU5526 + Co Antenna_NGSUM_H_9 New cell U21/L21/L18 : S6#，7#，8#，9 |  | 2026-09-01 | Reungsak Junkong 00927496 | N/A | Closed | 2026-09-01 15:58:06 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า , Day2 : ไม่เข้า , Day3 : 50% , Day4 : 80% , Day5 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NHINM_2026 Capacity Expansion Ph1_EXP_ER | Ban Noenhin | 2026-10-01 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-10-15 | 2026-10-01 | 2026-10-01 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-10-01 19:48:58 | No | No |  |  |  | 2026-10-16 | 2026-10-01 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-10-15 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 | 2026-07-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:42 | Yes | Yes | 2026-07-04 09:53:17 |  |  | 2026-10-15 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-10-01 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-10-01 18:27:40 | No | No |  | Add UBBPg3a New L26F5 + NR26 (New AAU5656)_NHINM_N_3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NIRNM_2025 Coverage Expansion Ph2_New Site_Remote-BBU_ER | Nong Irun Moo 10 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NISTA_2026 Capacity Expansion Ph2_BKK | NIST INTERNATIONAL SCHOOL_HUB BUILDING | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKBPM_2026 Capacity Expansion Ph2_BKK | NIKHOM BANG PU | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKMHM_2026 Capacity Expansion Ph1_EXP_ER | NongPaiKaew Moo5 | 2026-07-10 | Team :thcp_pooriwat.k Tel : 0925094222 | Install & Integrate | 2026-06-01 | 2026-07-20 | 2026-07-10 | 2026-07-10 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-10 21:43:32 | No | No |  |  |  | 2026-07-20 | 2026-07-13 | 2026-07-13 | Teloneer Company Limited | N/A | Closed | 2026-07-13 16:29:53 | Yes | Yes | 2026-07-14 13:35:55 |  | 2026-07-20 | 2026-07-25 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-27 16:14:05 | Yes | Yes | 2026-07-25 09:42:06 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:48 | No | No |  |  | 2026-07-31 | 2026-07-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-08 16:57:16 | Yes | Yes | 2026-07-08 12:27:49 |  | 2026-07-13 | 2026-07-20 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 14:32:06 | No | No |  |  |  |  | 2026-07-10 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-10 21:20:30 | No | No |  | Add UBBPh3a_NKMHM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 140 + Remove RRU x 1_NKMHM_H_2 (Co AAU5775) + Main Dir = 140 + Remove RRU x 1_NKMHM_H_7 (Co AAU5775) + Main Dir = 140 + Remove RRU x 1_NKMHM_H_J ReDirection 20 to 330_NKMHM_N_1 New L26F5 + NR26 (New AAU5656)_NKMHM_N_6 New Sector K (Co AAU5775) + Main Dir = 250_NKMHM_H_K |  | 2026-07-13 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-13 17:18:11 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKMHM_2026 Capacity Expansion Ph2_EXP_ER | NongPaiKaew Moo5 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKNVM_2026 Capacity Expansion Modernize_EXP_ER | Na khaiLuksuea NavySamut Sattahip school | 2026-08-20 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-08-31 | 2026-08-20 | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-20 17:32:51 | No | No |  |  |  | 2026-08-31 | 2026-08-21 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-21 17:09:29 | Yes | Yes | 2026-08-24 08:59:48 |  | 2026-08-31 | 2026-08-22 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:42:47 | Yes | Yes | 2026-09-07 08:56:38 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-08-31 | 2026-08-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:30 | Yes | Yes | 2026-08-22 09:38:57 |  |  | 2026-08-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-20 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-20 16:14:39 | No | No |  | Change Remote RRU to Remote BBU Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NKNVM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NKNVM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NKNVM_H_C |  | 2026-08-20 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-20 16:14:39 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 60% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKOWM_2026 Capacity Expansion Modernize_EXP_ER | Nong Khang Khok - Nantawan | 2026-08-03 | Team : thcp_watcharin.k Tel :0925546852 |  |  | 2026-08-15 | 2026-08-03 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 18:02:10 | No | No |  |  |  | 2026-08-20 | 2026-08-04 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 15:26:51 | Yes | Yes | 2026-08-09 15:14:54 |  | 2026-08-20 | 2026-08-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:54:09 | Yes | Yes | 2026-08-09 22:52:21 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:30 | No | No |  |  | 2026-08-15 | 2026-08-05 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:18:31 |  |  | 2026-08-15 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 15:19:30 | No | No |  |  |  |  | 2026-08-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-03 19:41:49 | No | No |  | Add RRU5505 x 1 + 4T4R_NKOWM_H_1 Add RRU5505 x 1 + 4T4R_NKOWM_H_2 Replace RRU5508 to (RRU5516_900) + NR07 + 4T4R_NKOWM_L_1 Replace RRU5508 to (RRU5516_900) + Co L07 + NR07 + 4T4R_NKOWM_L_2 Replace RRU5508 to (RRU5516_900) + NR07 + 4T4R_NKOWM_L_3 |  | 2026-08-04 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-04 17:05:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1: 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKPYN_KKN_2025_RepSGR_NER | BAN NONG KHU-PRA YUEN |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-16 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 11:26:11 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-23 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-16 09:10:02 | No | No |  |  | DTH1202609100019 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
NKRFM_2026 Capacity Expansion NW Modernization_EXP_BKK | NIKHOM ROTFAI (THANON KAMPHAENGPHET 2 ) | [5 empty] | 2026-08-20 | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  | 2026-08-18 | 2026-08-31 | 2026-08-28 | 2026-09-10 | Teloneer Company Limited | N/A | Closed | 2026-09-10 20:24:50 | Yes | Yes | 2026-09-16 10:51:19 |  | 2026-09-18 | 2026-09-18 | Nattawoot Suwan | Approving | Assigned |  | Yes | Yes | 2026-09-24 13:57:46 | 1.Page 5#，In SOW remove Fillter unit must be set. 2.Page 5#，In SOW need to fill remove pipe or mounting activity. 3.Page 16#，Need to upload new ANT m-tilt photo. 4.Page 27#，Need to upload BBU left & right side clear photo.(need to see BBP model clearly) 5.Page 56#，AIS passport have 3pcs but team member photo have 2persons. 6.Need to upload install & dismantle eq INV page. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:30:50 | Yes | Yes | 2026-08-18 00:04:47 |  |  | 2026-08-19 | 2026-08-19 | Teloneer Company Limited | N/A | Closed | 2026-08-19 17:53:01 | No | No |  |  |  |  | 2026-08-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-08-19 16:29:55 | No | No |  | 19-Aug-2026 Add UBBPh3a Add AAU5775 S1 S2 S3 Rmv RRU3962*12 S1 S2 S3 S6 S7 S8 Add RRU5516 S1 S2 S3 Rmv RRU3952 *4 Rep.Ant 8port S2 S3 700 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-20 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:01:06 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKRFM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | NIKHOM ROTFAI (THANON KAMPHAENGPHET 2 ) | [5 empty] | 2026-07-10 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 22:30:58 | No | No |  |  |  | 2026-08-08 | 2026-07-12 | 2026-07-13 | Teloneer Company Limited | N/A | Closed | 2026-07-13 10:59:41 | Yes | Yes | 2026-07-15 15:35:57 |  | 2026-07-17 | 2026-07-23 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-07-23 20:54:27 | Yes | Yes | 2026-07-22 20:06:18 | No inventory | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:30 | No | No |  |  |  | 2026-07-17 | Thossapan Chaloemrit | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-17 12:40:49 |  |  | 2026-08-08 | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-07 19:39:44 | No | No |  |  |  |  | 2026-07-07 | Autumporn Masing WX1434753 | N/A | Closed | 2026-07-07 19:27:59 | No | No |  | 2026-07-07 add g3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:30:41 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NKSOM_2026 Capacity Expansion Ph1_EXP_ER | Nong KlongSao | 2026-07-07 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate | 2026-06-01 | 2026-07-15 | 2026-07-07 | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-08 09:34:14 | No | No |  |  |  | 2026-07-20 | 2026-07-09 | 2026-07-09 | Teloneer Company Limited | N/A | Closed | 2026-07-09 17:52:21 | Yes | Yes | 2026-07-10 09:54:45 |  | 2026-07-20 | 2026-07-10 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-14 21:11:14 | Yes | Yes | 2026-07-10 17:44:10 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-10 16:09:40 | No | No |  |  | 2026-07-31 | 2026-07-03 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:42 | Yes | Yes | 2026-07-03 10:20:26 |  | 2026-07-08 | 2026-07-15 | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-07 15:50:55 | No | No |  |  |  |  | 2026-07-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-07 18:37:28 | No | No |  | Replace UBBPg1 to UBBPh3a Replace UBBPg1 to UBBPg3a ReDirection 300 to 290_NKSOM_N_1 ReDirection 20 to 350_NKSOM_N_2 New L26F5 + NR26 (New AAU5656)_NKSOM_N_7 |  | 2026-07-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-08 18:20:19 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NMBRM_2026 Capacity Expansion Ph2_BKK | NAWAMINTHRACHINUTHIT BENJAMARACHALAI SCHOOL | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NMDGM_2026 Capacity Expansion Ph2_BKK | NHAM DAENG | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NODBM_2026 Capacity Expansion Modernize_EXP_ER | Naval Ordnance Department Building P.2 | 2026-08-08 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-20 | 2026-08-09 | 2026-08-09 | Teloneer Company Limited | N/A | Closed | 2026-08-09 11:10:45 | No | No |  |  |  | 2026-08-20 | 2026-08-11 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 18:33:18 | Yes | Yes | 2026-08-12 16:42:36 |  | 2026-08-20 | 2026-08-14 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:58:04 | Yes | Yes | 2026-08-14 18:47:44 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:23 | No | No |  |  | 2026-08-20 | 2026-08-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:04:40 | Yes | Yes | 2026-08-08 10:46:00 |  |  | 2026-08-20 | 2026-08-08 | Teloneer Company Limited | N/A | Closed | 2026-08-08 13:45:44 | No | No |  |  |  |  | 2026-08-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-08 18:10:26 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NODBM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NODBM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NODBM_H_C New L21(F2) Sec. A#，B#，C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NOGKM_2026 Capacity Expansion Modernize_EXP_ER | Nongkae | 2026-06-26 | Team : thcp_apichat.f Tel : 0960126111 | Clear Pending |  | 2026-06-30 | 2026-07-01 | 2026-07-01 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-01 09:37:17 | No | No |  |  |  | 2026-06-30 | 2026-06-19 | 2026-06-20 | Teloneer Company Limited | N/A | Closed | 2026-06-20 13:37:29 | Yes | Yes | 2026-06-25 09:10:37 |  | 2026-06-30 | 2026-07-02 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:53:25 | Yes | Yes | 2026-07-02 17:27:32 |  | Pass |  | 2026-08-19 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-19 16:15:21 | No | Yes | 2026-08-19 16:14:20 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-05 11:50:01 | No | No |  |  | 2026-06-30 | 2026-06-19 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:11:17 | Yes | Yes | 2026-06-19 14:21:36 |  | 2026-06-22 | 2026-06-30 | 2026-06-26 | Teloneer Company Limited | N/A | Closed | 2026-06-26 12:07:49 | No | No |  |  |  |  | 2026-06-19 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-19 19:37:23 | No | No |  | Remove Antenna + (New AAU5775) + Main Dir = 150 + Remove RRU5513 x 1_NOGKM_H_3 (Co AAU5775) + Main Dir = 150 + Remove RRU5513 x 1_NOGKM_H_8 New Antenna (LB)_NOGKM_L_3 New Sector M (Co AAU5775) + Main Dir = 150_NOGKM_H_M New Sector N (Co AAU5775) + Main Dir = 150_NOGKM_H_N add Ubbph3a for onservice dmm (2026capexph1 no need to add h3a) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-20 | Nattawoot Suwan | N/A | Closed | 2026-06-20 11:07:58 | No | No |  |  |  | Day1 : 100% : Day2 : Clear work | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NOGKM_2026 Capacity Expansion Ph1_EXP_ER | Nongkae | 2026-06-27 | Team : thcp_apichat.f Tel : 0960126111 |  | 2026-06-01 | 2026-06-30 | 2026-07-01 | 2026-07-01 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-01 14:20:14 | No | No |  |  |  | 2026-06-30 | 2026-06-27 | 2026-07-02 | Teloneer Company Limited | N/A | Closed | 2026-07-02 12:32:16 | Yes | Yes | 2026-07-08 09:48:50 |  | 2026-06-30 | 2026-07-10 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-20 21:40:10 | Yes | Yes | 2026-07-10 17:55:22 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-05 11:49:58 | No | No |  |  | 2026-06-30 | 2026-06-27 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-28 22:11:00 | Yes | Yes | 2026-06-27 11:41:21 |  |  | 2026-06-30 | 2026-06-19 | Teloneer Company Limited | N/A | Closed | 2026-06-19 14:46:49 | No | No |  |  |  |  | 2026-06-27 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-27 17:30:00 | No | No |  | Replace UBBPg1 to UBBPh3a + Replace AAU5726 to AAU5775_NOGKM_H_1 Remove Antenna + Remove RRU x 1_MB Sec.1 Replace AAU5726 to AAU5775 (Co AAU)_NOGKM_H_6 Replace AAU5726 to AAU5775 (Co AAU)_NOGKM_H_G Replace AAU5726 to AAU5775 (Co AAU)_NOGKM_H_H ReSectorname S2 to S3_NOGKM_N_3 ReSectorname S3 to S4 + ReDirection 245 to 270_NOGKM_N_4 New L26F5 + NR26 (New AAU5656)_NOGKM_N_8 |  | 2026-06-29 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-29 17:43:40 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-29 | Nattawoot Suwan | N/A | Closed | 2026-06-29 15:05:02 | No | No |  |  | SQC Closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPHAM_2026 Capacity Expansion Modernize_EXP_ER | D Varee Jomtien Beach Pattaya | 2026-08-11 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPHBM_2026 Capacity Expansion Ph2_EXP_ER | Ban Nong Phlab |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NPHWM_2026 Capacity Expansion Ph1_EXP_ER | Nong Phaikaew | 2026-06-02 |  | Install & Integrate |  | 2026-06-30 | 2026-06-02 | 2026-06-02 | Wachira saovaro(Teloneer Company Limited) | N/A | Closed | 2026-06-04 15:48:22 | No | No |  |  |  | 2026-06-30 | 2026-06-04 | 2026-06-07 | Teloneer Company Limited | N/A | Closed | 2026-06-07 15:40:01 | Yes | Yes | 2026-06-08 12:08:57 |  | 2026-06-30 | 2026-06-11 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:57:06 | Yes | Yes | 2026-06-11 15:38:53 |  | Pass | 2026-07-20 | 2026-07-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-20 17:19:43 | No | Yes | 2026-07-20 17:19:21 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-06-22 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-07 15:06:12 | No | No |  |  | 2026-06-30 | 2026-06-02 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:31 | Yes | Yes | 2026-06-02 17:00:28 |  | 2026-06-04 | 2026-06-30 | 2026-06-02 | Teloneer Company Limited | N/A | Closed | 2026-06-02 19:03:04 | No | No |  |  |  |  | 2026-06-02 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-06-02 17:32:02 | No | No |  | Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_NPHWM_L_4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-02 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NREKM_2025 Capacity Expansion Ph8_EXP_ER | Ban Na Roek | 2026-02-23 | thcp_apichat.f | Install & Integrate |  | 2026-02-28 | 2026-02-23 | 2026-02-23 | Teloneer Company Limited | N/A | Closed | 2026-02-23 16:29:15 | No | No |  |  |  | 2026-02-28 | 2026-02-24 | 2026-02-25 | Teloneer Company Limited | N/A | Closed | 2026-02-25 11:41:38 | Yes | Yes | 2026-02-26 19:43:50 |  | 2026-02-28 | 2026-02-26 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:23:12 | Yes | Yes | 2026-02-26 20:41:24 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 14:29:47 |  | 2026-02-28 | 2026-02-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:21:34 | Yes | Yes | 2026-02-23 16:21:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-23 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-23 18:20:20 | No | No |  | Add UBBPg3a New L26F5 + NR26 (New RRU5818) + Co Antenna_NREKM_N_2 New L26F5 + NR26 (Co RRU5818) + Co Antenna_NREKM_N_3 |  | 2026-02-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-24 16:25:40 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NSCGM_2025 Capacity Expansion Ph8_EXP_ER | Nong Suea Chang Moo 5 | 2026-02-16 | Thcp_adirek.kh | Take Photo |  | 2026-02-28 | 2026-02-09 | 2026-03-09 | Teloneer Company Limited | N/A | Closed | 2026-03-09 10:57:27 | No | No |  |  |  | 2026-02-28 | 2026-02-09 | 2026-02-09 | Teloneer Company Limited | N/A | Closed | 2026-02-09 21:07:03 | Yes | Yes | 2026-02-16 16:41:46 |  | 2026-02-28 | 2026-02-16 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-17 15:42:05 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 14:30:25 |  | 2026-02-28 | 2026-02-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-13 15:14:42 | Yes | Yes | 2026-02-12 08:14:29 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-09 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-09 18:22:26 | No | No |  | Replace UBBPg2 to UBBPg3a + Add UBBPg3a_NSCGM_H_1 New L26F5 + NR26 (New AAU5636w)_NSCGM_N_1 New L26F5 + NR26 (New AAU5636w)_NSCGM_N_2 New L26F5 + NR26 (New AAU5636w)_NSCGM_N_3 New L26F5 + NR26 (New AAU5636w)_NSCGM_N_4 |  | 2026-02-11 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-11 17:48:57 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NSHMM_KKN_2025_RepSGR_NER | NON SA ART-HUAI MUANG |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-25 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 16:33:45 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-26 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 10:20:02 | No | No |  |  | DTH1202609100015 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
NSN1M_2026 Capacity Expansion Ph2_BKK | NISSAN MOTOR (THAILAND) 1 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NSSKM_2026 Capacity Expansion Ph1_EXP_ER | Nong Samsak | 2026-07-05 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-07-15 | 2026-07-05 | 2026-07-05 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-06 08:07:58 | No | No |  |  |  | 2026-07-15 | 2026-07-06 | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-07 16:01:42 | Yes | Yes | 2026-07-07 16:48:39 |  | 2026-07-15 | 2026-07-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-23 14:07:43 | Yes | Yes | 2026-07-16 09:34:55 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-05 11:49:58 | No | No |  |  | 2026-06-30 | 2026-07-01 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:43 | Yes | Yes | 2026-07-01 13:41:47 |  | 2026-07-08 | 2026-07-15 | 2026-07-05 | Teloneer Company Limited | N/A | Closed | 2026-07-05 13:57:01 | No | No |  |  |  |  | 2026-07-05 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-05 18:40:59 | No | No |  | Add UBBPg3a Replace Antenna (Dualband)_NSSKM_H_1 Replace Antenna (Dualband)_NSSKM_H_3 Replace Antenna (Co Antenna)_NSSKM_L_1 Replace Antenna (Co Antenna)_NSSKM_L_3 ReSectorname S2 to S3_NSSKM_N_3 ReSectorname S3 to S4 + ReDirection 220 to 200_NSSKM_N_4 New L26F5 + NR26 (New AAU5656)_NSSKM_N_9 |  | 2026-07-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-08 18:20:19 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-09 | Boonchot Boriwut | N/A | Closed | 2026-07-13 04:19:49 | No | No |  |  | SQC Closed. | Day1 : 50% , Day2 : 70% , Day3 : ไม่ได้เข้า70% , Day4 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NTGPO_2026 Capacity Expansion Ph1_EXP_SR | Na Thung Pho | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-10 | 2026-09-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-28 12:12:47 | Yes | Yes | 2026-09-28 12:14:59 | 1. Antenna install or not ? |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-10 | 2026-08-31 | 2026-09-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-10 20:23:36 | No | No |  |  |  |  | 2026-09-10 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-10 20:14:29 | No | No |  | Rep d6*1 to h2a*1 S2 > Rep RRU3953*2 to RRU5516*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NUMRM_2026 Capacity Expansion Modernize_EXP_ER | Nurse supportMar | 2026-08-22 | User isdp : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-08-31 | 2026-08-22 | 2026-08-22 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-23 11:39:08 | No | No |  |  |  | 2026-08-31 | 2026-08-22 | 2026-08-23 | Teloneer Company Limited | N/A | Closed | 2026-08-23 11:38:13 | Yes | Yes | 2026-08-26 16:55:48 |  | 2026-08-31 | 2026-08-31 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:48:05 | Yes | Yes | 2026-08-31 22:17:24 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-08-31 | 2026-08-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:30 | Yes | Yes | 2026-08-22 09:38:39 |  |  | 2026-08-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-22 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-22 19:05:40 | No | No |  | Change Remote RRU to Remote BBU Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NUMRM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NUMRM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NUMRM_H_C |  | 2026-08-22 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-22 19:05:40 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 60% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NUTAM_2026 Capacity Expansion Ph1_EXP_SR | Ban Nua Tha | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  | 2026-07-26 | 2026-07-26 | 2026-07-26 | 2026-07-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-27 16:10:42 | Yes | Yes | 2026-08-14 10:45:04 |  | 2026-08-17 | 2026-08-21 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-21 11:36:51 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-17 | 2026-08-17 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-17 18:26:15 |  | 2026-07-30 | 2026-08-31 | 2026-07-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-26 19:35:29 | No | No |  |  |  |  | 2026-07-26 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-26 18:06:43 | No | No |  | S3 > Add AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NVEWM_2026 Capacity Expansion Modernize_EXP_ER | SATTAHIP ELECTRICITY AUTHORITY THE ROYAL THAI NAVY WELFARE CONCESSION | 2026-08-09 | Team : thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-08-20 | 2026-08-09 | 2026-08-09 | Teloneer Company Limited | N/A | Closed | 2026-08-09 21:13:22 | No | No |  |  |  | 2026-08-20 | 2026-08-12 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 17:22:25 | Yes | Yes | 2026-08-16 22:45:17 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:50 | Yes | Yes | 2026-08-16 23:42:06 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:23 | No | No |  |  | 2026-08-20 | 2026-08-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:04:40 | Yes | Yes | 2026-08-08 20:53:40 |  |  | 2026-08-20 | 2026-08-09 | Teloneer Company Limited | N/A | Closed | 2026-08-09 12:40:33 | No | No |  |  |  |  | 2026-08-09 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-09 19:12:46 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NVEWM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NVEWM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NVEWM_H_C (NO RET) |  | 2026-08-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-10 17:48:21 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% , Day2: 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NVOTM_2026 Capacity Expansion Modernize_EXP_ER | Novotel Koh Sichang Marina Bay | 2026-09-10 | Team : Thcp_phet.sa Tel : 0924272237 |  |  | 2026-09-20 | 2026-09-10 | 2026-09-10 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-10 15:23:06 | No | No |  |  |  | 2026-09-20 | 2026-09-14 | 2026-09-15 | Teloneer Company Limited | N/A | Closed | 2026-09-15 17:45:40 | Yes | Yes | 2026-09-16 20:23:29 | >>Need to upload before remove RRU overview photo in before section A and before Section B. >>Need to upload before BBU BBU left and right side view clearly photos in before on ground section. >>Need to upload OPM Labels in after section. | 2026-09-20 | 2026-09-22 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-22 23:36:25 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 | 2026-09-01 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-02 08:43:19 | Yes | Yes | 2026-09-01 14:05:43 |  |  | 2026-09-20 | 2026-09-09 | Teloneer Company Limited | N/A | Closed | 2026-09-09 19:40:09 | No | No |  |  |  |  | 2026-09-10 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-10 11:32:28 | No | No |  | Replace Antenna (MB) + Replace RRU5526 + 4T4R_NVOTM_H_A Replace Antenna (MB) + Replace RRU5526 + 4T4R_NVOTM_H_B Replace Antenna (MB) + Replace RRU5526 + 4T4R_NVOTM_H_C Co L21(F2) SA#，SB#，SC |  | 2026-09-11 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-11 14:58:18 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 95% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NVPAB_2025 Capacity Expansion NW Modernization_EXP_BKK | NA VEERA PHAHOL-ARI |  |  |  | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-13 11:43:07 | No | No |  |  | 2026-03-20 | 2026-03-20 | 2026-03-24 | 2026-03-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-26 14:54:46 | Yes | Yes | 2026-04-17 08:55:03 |  | 2026-05-13 | 2026-05-13 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-07-31 10:10:31 | Yes | Yes | 2026-05-13 11:42:21 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 20:00:00 |  |  | 2026-03-18 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-24 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-03-24 13:55:29 | No | No |  | 24-Mar-2026 Add RRU5507 *2 SA Remove RRU3962 20 Mar 2026 Prework |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NVPSM_2026 Capacity Expansion Modernize_EXP_ER | Naval Port of Sattahip | 2026-08-07 | Team : thcp_pooriwat.k Tel : 0925094222 | Install & Integrate |  | 2026-08-20 | 2026-08-23 | 2026-08-23 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-25 09:38:38 | No | No |  |  |  | 2026-08-20 | 2026-08-24 | 2026-08-24 | Teloneer Company Limited | N/A | Closed | 2026-08-24 19:33:03 | Yes | Yes | 2026-08-25 14:45:40 |  | 2026-08-20 | 2026-08-25 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:42:47 | Yes | Yes | 2026-09-07 08:56:58 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-20 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:04:41 | Yes | Yes | 2026-08-08 08:35:46 |  |  | 2026-08-20 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 15:53:42 | No | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-10 17:25:44 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NWCBM_2026 Capacity Expansion NW Modernization_EXP_BKK | NAWACHAMNEAN BRIDGE | [5 empty] | 2026-09-21 | 2026-09-21 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-30 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 10:29:50 | No | No |  |  |  |  | 2026-09-20 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-09-21 02:53:45 | No | No |  | 2026-09-21_Clear Pending 2026-09-20 7/9 > S1#，2#，3 Rep to RRU5516 18/21 > S1#，2#，3 Rep to RRU5507*2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NWCBM_2026 Capacity Expansion Ph2_BKK | NAWACHAMNEAN BRIDGE | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NWKYM_2025 Capacity Expansion Ph8_EXP_ER | Na Wat Khlong Yai | 2026-02-23 | Thcp_phet.sa | Install & Integrate |  | 2026-02-28 | 2026-02-23 | 2026-02-23 | Teloneer Company Limited | N/A | Closed | 2026-02-23 14:36:52 | No | No |  |  |  | 2026-02-28 | 2026-02-23 | 2026-02-23 | Teloneer Company Limited | N/A | Closed | 2026-02-23 20:17:27 | Yes | Yes | 2026-02-26 11:04:15 |  | 2026-02-28 | 2026-03-02 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-12 17:50:40 | Yes | Yes | 2026-03-04 10:25:04 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:27 | Yes | Yes | 2026-03-24 14:31:40 |  | 2026-02-28 | 2026-02-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:21:34 | Yes | Yes | 2026-02-23 15:16:11 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-23 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-23 18:20:20 | No | No |  | Replace Antenna (MB)_NWKYM_H_2 New L26F5 + NR26 (New RRU5818) + Co Antenna_NWKYM_N_2 |  | 2026-02-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-24 16:25:40 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NWLDM_2026 Capacity Expansion Ph2_BKK | MUBAN NEW WORLD VILL | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NWRIM_KKN_2025_RepSGR_NER | BAN NONG WAENG RAI |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-20 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 14:37:27 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-25 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-20 | Teloneer Company Limited | N/A | Closed | 2026-09-20 14:40:02 | No | No |  |  | DTH1202609100020 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
NWTPT_2026 Capacity Expansion Ph1_EXP_SR | Narathiwat Polytechnic College | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-10-01 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-12 | 2026-08-31 | 2026-09-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-25 20:43:52 | No | No |  |  |  |  | 2026-09-12 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-12 16:56:25 | No | No |  | Rep d6*1 to h2a*1 S1 > Rep RRU3953*1 to RRU5516*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NYNGM_2026 Capacity Expansion Ph2_EXP_ER | Noen Yong |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NYOAM_2026 Capacity Expansion Modernize_EXP_ER | Banpak NorYor pointA | 2026-09-14 | Team : Thcp_phet.sa Tel : 0924272237 |  |  | 2026-08-20 | 2026-08-25 | 2026-08-25 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-25 18:59:07 | No | No |  |  |  | 2026-08-20 | 2026-08-24 | 2026-08-25 | Teloneer Company Limited | N/A | Closed | 2026-08-25 15:34:12 | Yes | Yes | 2026-08-26 09:24:49 |  | 2026-08-20 | 2026-08-25 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:42:47 | Yes | Yes | 2026-09-25 09:00:33 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-20 | 2026-08-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-25 16:53:49 | Yes | Yes | 2026-08-25 07:29:13 |  |  | 2026-09-30 | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-16 14:19:50 | No | No |  |  |  |  | 2026-09-14 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-14 16:42:55 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NYOAM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NYOAM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NYOAM_H_C Change solution remote RRU to remote BBU |  | 2026-09-14 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-14 16:42:55 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% , Day2 : Clear work | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NYOBM_2026 Capacity Expansion Modernize_EXP_ER | Banpak NorYor pointB | 2026-09-15 | isdp : thcp_apichat.f Tel : 0960126111 |  |  | 2026-09-30 | 2026-09-15 | 2026-09-15 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-16 16:32:36 | No | No |  |  |  | 2026-09-30 | 2026-09-16 | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-16 18:08:30 | Yes | Yes | 2026-09-16 20:23:31 |  | 2026-09-30 | 2026-09-24 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-24 22:43:42 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-14 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-16 21:51:05 | Yes | Yes | 2026-09-14 16:26:40 |  |  | 2026-09-30 | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-16 14:53:29 | No | No |  |  |  |  | 2026-09-15 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-15 16:54:39 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NYOBM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NYOBM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_NYOBM_H_C Change solution remote RRU to remote BBU |  | 2026-09-15 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-15 16:54:39 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% , Day2 : 50% , Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OBTNM_2026 Capacity Expansion Modernize_EXP_ER | Or Bor Tor Nongmaidaeng | 2026-08-12 |  |  |  | 2026-08-20 | 2026-08-12 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 18:06:16 | No | No |  |  |  | 2026-08-20 | 2026-08-12 | 2026-08-13 | Teloneer Company Limited | N/A | Closed | 2026-08-13 10:00:40 | Yes | Yes | 2026-08-17 18:53:55 |  | 2026-08-20 | 2026-08-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:48:05 | Yes | Yes | 2026-08-26 09:55:36 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:30 | No | No |  |  | 2026-08-15 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 18:00:58 |  |  | 2026-08-20 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 13:32:19 | No | No |  |  |  |  | 2026-08-12 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-08-12 20:02:52 | No | No |  | Add UBBPh2a Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_OBTNM_H_4 >23 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_OBTNM_L_1 Replace RRU (RRU5516_900) + NR07 + 4T4R_OBTNM_L_2 Co NR07_OBTNM_L_3 Co NR07_OBTNM_L_4 recell ID//Co L21(F2) all sector |  | 2026-08-13 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-13 17:40:45 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTCPM_2026 Capacity Expansion Modernize_EXP_ER | Oriental Copper | 2026-06-25 | Team : THCP_Wachira.s Tel : 065-7649919 | Clear Pending |  | 2026-06-30 | 2026-06-23 | 2026-06-23 | Wachira saovaro(Teloneer Company Limited) | N/A | Closed | 2026-06-23 17:39:51 | No | No |  |  |  | 2026-06-30 | 2026-06-24 | 2026-06-25 | Teloneer Company Limited | N/A | Closed | 2026-06-25 10:06:03 | Yes | Yes | 2026-06-25 21:15:25 |  | 2026-06-30 | 2026-06-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:53:25 | Yes | Yes | 2026-06-30 12:25:11 |  | Pass |  | 2026-08-19 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-19 16:15:21 | No | Yes | 2026-08-19 16:14:43 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-06-30 | 2026-06-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-25 08:21:58 | Yes | Yes | 2026-06-23 09:47:13 |  | 2026-06-23 | 2026-06-30 | 2026-06-23 | Teloneer Company Limited | N/A | Closed | 2026-06-23 17:35:07 | No | No |  |  |  |  | 2026-06-23 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-06-23 19:36:23 | No | No |  | Add UBBPg2 + Replace Antenna (Dualband)_OTCPM_H_A Replace Antenna (Dualband) + Replace RRU5513 x 1 + 4T4R_OTCPM_H_B Replace Antenna (Co Antenna)_OTCPM_N_A Replace Antenna (Co Antenna)_OTCPM_N_B New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_OTCPM_L_A New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_OTCPM_L_B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-25 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  | Day1 : Antไม่ตรง , Day2 : 100% , Day3 : Clear alarm | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OTSVM_2026 Capacity Expansion Ph1_EXP_ER | OTS Village | 2026-07-13 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate | 2026-07-01 | 2026-07-20 | 2026-07-13 | 2026-07-13 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-13 21:50:31 | No | No |  |  |  | 2026-07-20 | 2026-07-14 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 16:54:27 | Yes | Yes | 2026-07-15 16:55:51 |  | 2026-07-20 | 2026-07-17 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:40 | Yes | Yes | 2026-07-20 10:01:14 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:48 | No | No |  |  | 2026-07-20 | 2026-07-13 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-14 21:10:02 | Yes | Yes | 2026-07-13 13:48:48 |  | 2026-07-14 | 2026-07-20 | 2026-07-13 | Teloneer Company Limited | N/A | Closed | 2026-07-13 14:41:38 | No | No |  |  |  |  | 2026-07-13 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-13 19:30:32 | No | No |  | Replace Antenna (Dualband) + Add RRU5505 x 1 + 4T4R_OTSVM_H_3 Replace RRU (RRU5516_900) + 4T4R_OTSVM_L_1 Replace RRU3953*2 >> (RRU5516_900) + Co L07 + Co NR07 + 4T4R_OTSVM_L_2 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_OTSVM_L_3 New L26F5 + NR26 (New AAU5656)_OTSVM_N_2 ์New L21 F2 all sector |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า , Day2 : 60% , Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P110M_2026 Capacity Expansion Ph2_BKK | SOI PHETKASEM 110 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P117M_2026 Capacity Expansion Ph2_BKK | TESSABAN BANGPU 117 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P21MA_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHETCHABURI 21 MICRO CELL |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:23:44 | Yes | Yes | 2026-03-27 11:09:47 |  | 2026-04-28 | 2026-04-28 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:37:13 | Yes | Yes | 2026-05-04 11:44:27 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:07:42 | Yes | Yes | 2026-08-01 20:00:32 |  |  | 2026-06-20 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-05 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-05 18:04:46 | No | No |  | 05-03-26 Replace RRU5507 to RRU5526 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P2M2M_2026 Capacity Expansion Ph2_BKK | PUTTHAMONTHOL SAI 2 STATION 2 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P3BWM_2026 Capacity Expansion Ph2_BKK | Phutthamonthon Sai 3 - Bang Waek | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
P634M_2026 Capacity Expansion Ph2_BKK | SOI PHET KASEM 63/4 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PAPUM_KKN_2025_RepSGR_NER | PAPU |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-24 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 21:50:01 | No | No |  |  | DTH1202609100006 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
PARHM_2026 Capacity Expansion Modernize_EXP_ER | Paree Hut Resort Koh Sichang | 2026-08-17 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-20 | 2026-09-01 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-02 08:43:19 | Yes | Yes | 2026-09-01 14:06:20 |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PB19A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHETCHABURI 19 |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-02-16 | 2026-02-16 | 2026-03-21 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 09:48:13 | Yes | Yes | 2026-03-24 13:44:52 |  | 2026-04-20 | 2026-04-20 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-05-25 16:00:25 | Yes | Yes | 2026-04-20 13:24:25 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 20:14:24 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-09 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-09 18:03:32 | No | No |  | 2026-02-09_Replace RRU3962#， RRU5507 to RRU5526(18-21) |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PBR5M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHETCHABURI 5 |  |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:45:35 | No | No |  |  |  | 2026-02-28 | 2026-03-24 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 13:14:36 | Yes | Yes | 2026-03-24 13:14:37 |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-04-02 13:44:02 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-24 21:45:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-20 18:20:36 | No | No |  | 20-02-2026. Replace RRU5507 to AAU5768 Sec.1#， 3#， RRU3962 to 5507 Sec.2#， UBBPd6 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PBSTM_2026 Capacity Expansion Modernize_EXP_ER | P.27 Building Sattahip | 2026-08-11 | Team : thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-08-20 | 2026-08-11 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 16:55:51 | No | No |  |  |  | 2026-08-20 | 2026-08-13 | 2026-08-17 | Teloneer Company Limited | N/A | Closed | 2026-08-17 21:12:36 | Yes | Yes | 2026-08-21 10:32:32 |  | 2026-08-20 | 2026-08-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:48:05 | Yes | Yes | 2026-08-31 10:08:43 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:23 | No | No |  |  | 2026-08-20 | 2026-08-13 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:52:24 | Yes | Yes | 2026-08-13 09:30:53 |  |  | 2026-08-20 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 16:05:20 | No | No |  |  |  |  | 2026-08-11 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-11 13:38:01 | No | No |  | Add UBBPh3a_PBSTM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 145 + Remove RRU x 1_PBSTM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_PBSTM_H_3 (Co AAU5775) + Main Dir = 145 + Remove RRU x 1_PBSTM_H_7 New Sector J (Co AAU5775) + Main Dir = 145_PBSTM_H_J New Sector K (Co AAU5775) + Main Dir = 145_PBSTM_H_K Co L21F2 Sec1#，3 |  | 2026-08-13 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-13 17:40:44 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PBTMM_2026 Capacity Expansion Ph1_EXP_SR | Ban Pabontum | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-05 | 2026-08-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-05 17:05:25 | Yes | Yes | 2026-08-07 18:56:40 |  | 2026-08-11 | 2026-08-14 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-14 10:56:58 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:24 | No | No |  |  | 2026-08-13 | 2026-08-14 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-14 10:57:52 |  | 2026-08-07 | 2026-08-31 | 2026-08-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-05 14:46:57 | No | No |  |  |  |  | 2026-08-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-05 17:34:32 | No | No |  | 5 Aug 2026 Add AAU5656 sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PCOPM_2026 Capacity Expansion Ph2_EXP_ER | PTT Global Chemical Pubilc Company Limited Olefin Plant I-1 Branch 2 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PCR3M_2026 Capacity Expansion Ph2_BKK | SOI POON CHAROEN 3/1 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PCTUM_2026 Capacity Expansion Ph1_EXP_BKK | SOI PERMCHAI TUMRU ROAD | [5 empty] | 2026-07-10 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 22:30:58 | No | No |  |  |  | 2026-07-31 | 2026-07-11 | 2026-07-12 | Teloneer Company Limited | N/A | Closed | 2026-07-12 18:30:21 | Yes | Yes | 2026-07-13 10:05:16 |  | 2026-07-15 | 2026-07-22 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-31 10:54:55 | Yes | Yes | 2026-08-26 11:01:33 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-09 | Teloneer Company Limited | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-07-09 10:28:42 |  |  | 2026-07-30 | 2026-07-02 | Teloneer Company Limited | N/A | Closed | 2026-07-02 20:25:24 | No | No |  |  |  |  | 2026-07-02 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-07-02 18:26:35 | No | No |  | 2 Jul 2026 Add AAU5656 sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-08 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:30:41 | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PCTUM_2026 Capacity Expansion Ph2_BKK | SOI PERMCHAI TUMRU ROAD | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PDAGM_2026 Capacity Expansion Ph1_EXP_ER | PA DANG | 2026-07-15 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-07-20 | 2026-07-15 | 2026-07-15 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-16 08:54:57 | No | No |  |  |  | 2026-07-20 | 2026-07-17 | 2026-07-19 | Teloneer Company Limited | N/A | Closed | 2026-07-19 21:38:25 | Yes | Yes | 2026-07-19 21:41:16 |  | 2026-07-20 | 2026-07-22 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:40 | Yes | Yes | 2026-07-22 09:56:32 |  | Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:34:22 | No | Yes | 2026-09-12 10:33:07 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:48 | No | No |  |  | 2026-07-20 | 2026-07-14 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-14 21:10:02 | Yes | Yes | 2026-07-14 20:42:29 |  |  | 2026-07-20 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 17:05:17 | No | No |  |  |  |  | 2026-07-15 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-15 17:36:08 | No | No |  | Replace Antenna (Dualband Dualbeam)_PDAGM_H_2 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_PDAGM_L_1 Replace Antenna (Co Antenna)_PDAGM_L_2 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_PDAGM_H_7 |  | 2026-07-16 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-16 16:29:59 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PEAMM_2026 Capacity Expansion Ph1_EXP_ER | PEA Mabtaput Office | 2026-08-26 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-08-31 | 2026-08-27 | 2026-08-27 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-28 10:31:21 | No | No |  |  |  | 2026-08-31 | 2026-08-28 | 2026-08-28 | Teloneer Company Limited | N/A | Closed | 2026-08-28 14:10:44 | Yes | Yes | 2026-08-30 21:37:37 |  | 2026-08-31 | 2026-08-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:43:50 | Yes | Yes | 2026-08-31 00:09:39 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:28 | No | No |  |  | 2026-08-31 | 2026-08-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-25 16:53:49 | Yes | Yes | 2026-08-25 13:38:29 |  |  | 2026-08-31 | 2026-08-25 | Teloneer Company Limited | N/A | Closed | 2026-08-25 19:41:53 | No | No |  |  |  |  | 2026-08-26 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-26 16:03:00 | No | No |  | Replace Antenna (Dualband)_PEAMM_H_1 Replace Antenna (Dualband)_PEAMM_H_2 Replace Antenna (Dualband)_PEAMM_H_3 Replace Antenna (Co Antenna) + Replace RRU (RRU5516_900) + 4T4R_PEAMM_L_1 Replace Antenna (Co Antenna) + Replace RRU (RRU5516_900) + 4T4R_PEAMM_L_2 Replace Antenna (Co Antenna) + Replace RRU (RRU5516_900) + 4T4R_PEAMM_L_3 Co L21(F2) S1#，S2#，S3 |  | 2026-08-27 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-27 16:20:02 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 60% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PEBKM_2026 Capacity Expansion Ph1_EXP_ER | PEA Bang Pakong1 | 2026-09-29 | Team: THCP_Wachira.s Tel :0657649919 | Clear Alarm |  | 2026-09-30 | 2026-09-20 | 2026-09-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-20 19:05:29 | No | No |  |  |  | 2026-09-30 | 2026-09-21 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 14:41:57 | Yes | Yes | 2026-09-24 21:10:25 | Need install RRU SN photo for sec 3 at after sec3. Need tower name plate. | 2026-09-30 | 2026-09-25 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-29 21:16:19 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:42:33 | Yes | Yes | 2026-09-18 12:25:10 |  |  | 2026-09-30 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 16:43:21 | No | No |  |  |  |  | 2026-09-29 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-29 16:43:27 | No | No |  | Add UBBPh2a Replace Antenna (Dualband)_PEBKM_H_1 Replace Antenna (Dualband) + Replace RRU (RRU5513) + 4T4R_PEBKM_H_2 Replace Antenna (Dualband)_PEBKM_H_3 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_PEBKM_L_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_PEBKM_L_2 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_PEBKM_L_3 Co L21(F2) S1#，S2#，S3 |  | 2026-09-30 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-30 16:45:59 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า , Day2 : 70% , Day3 : 100% , Day4 : ฝนตก , Day5 : Clear Work | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PGASM_2026 Capacity Expansion Ph1_EXP_ER | Near PT Gas Nong Phai Kaew | 2026-06-08 | Team : THCP_Wachira.s Tel : 065-7649919 | Clear Pending |  | 2026-06-30 | 2026-06-04 | 2026-06-04 | Teloneer Company Limited | N/A | Closed | 2026-06-04 15:50:33 | No | No |  |  |  | 2026-06-30 | 2026-06-08 | 2026-06-08 | Teloneer Company Limited | N/A | Closed | 2026-06-08 20:26:34 | Yes | Yes | 2026-06-09 09:02:50 |  | 2026-06-30 | 2026-06-12 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:57:06 | Yes | Yes | 2026-06-12 10:46:04 |  | Pass | 2026-07-20 | 2026-07-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-20 17:23:11 | No | Yes | 2026-07-20 17:23:01 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-03 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-07 15:06:14 | No | No |  |  | 2026-06-30 | 2026-06-03 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:31 | Yes | Yes | 2026-06-03 11:10:18 |  | 2026-06-08 | 2026-06-30 | 2026-06-04 | Teloneer Company Limited | N/A | Closed | 2026-06-04 16:17:32 | No | No |  |  |  |  | 2026-06-04 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-04 18:34:33 | No | No |  | **need baseline L21 F2 S1#，2 #，MIMO L18/L21 S2#， L9/LNR7 S1#，2 Add UBBPh2a + Replace Antenna (Dualband)_PGASM_H_1 Replace Antenna (Dualband) + Add RRU5505 x 1 + 4T4R_PGASM_H_2 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_PGASM_L_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_PGASM_L_2 |  | 2026-06-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-08 19:38:43 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-08 | Boonchot Boriwut | N/A | Closed | 2026-07-10 05:49:47 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PHCNM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHRACHAN |  |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-27 13:27:45 | No | No |  |  |  | 2026-02-14 | 2026-03-17 | 2026-03-19 | V Contribute Co., Ltd | N/A | Closed | 2026-03-19 12:30:40 | Yes | Yes | 2026-03-19 12:30:40 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-12 11:43:46 | Yes | Yes | 2026-04-02 12:07:31 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-12 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 12:59:23 |  | 2026-02-26 | 2026-02-26 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:00:22 | Yes | Yes | 2026-02-26 21:34:10 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-10 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-10 19:46:59 | No | No |  | 10-02-2026. Replace RRU3962 to AAU5768 Sec.1#， 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PHIKM_2026 Capacity Expansion Ph1_EXP_ER | Ban Nong Phai Kaeo Moo 3 | 2026-07-14 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-07-31 | 2026-07-14 | 2026-07-14 | Teloneer Company Limited | N/A | Closed | 2026-07-14 17:56:57 | No | No |  |  |  | 2026-07-20 | 2026-07-15 | 2026-07-15 | Teloneer Company Limited | N/A | Closed | 2026-07-15 17:08:35 | Yes | Yes | 2026-07-17 15:37:34 |  | 2026-07-20 | 2026-07-20 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:40 | Yes | Yes | 2026-07-20 17:29:34 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-13 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:48 | No | No |  |  | 2026-07-31 | 2026-07-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:42 | Yes | Yes | 2026-07-04 12:53:10 |  |  | 2026-07-20 | 2026-07-14 | Teloneer Company Limited | N/A | Closed | 2026-07-14 17:16:04 | No | No |  |  |  |  | 2026-07-14 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-14 16:18:50 | No | No |  | Add UBBPg3a_PHIKM_H_1 ReDirection 200 to 170_PHIKM_N_3 New L26F5 + NR26 (New AAU5656)_PHIKM_N_8 |  | 2026-07-15 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-15 17:55:28 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PHIKM_2026 Capacity Expansion Ph2_EXP_ER | Ban Nong Phai Kaeo Moo 3 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PHKWM_NMA_2025_RepSGR_NER | PHU KHIAO |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-29 | 2026-09-29 | Teloneer Company Limited | N/A | Closed | 2026-09-29 11:12:25 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-29 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 18:20:02 | No | No |  |  | DTH1202609100004 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
PHNXM_KKN_2025_RepSGR_NER | PHOENIX |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-24 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 15:24:04 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-26 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 20:10:02 | No | No |  |  | DTH1202609100012 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
PHTCB_2025 Capacity Expansion NW Modernization_EXP_BKK | Soi Phahonyothin Place Center (Electric Pole) |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-03-31 | 2026-03-31 | 2026-03-13 | 2026-03-14 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-14 09:51:46 | Yes | Yes | 2026-03-18 09:53:58 |  | 2026-03-26 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-30 12:45:28 | Yes | Yes | 2026-03-27 13:56:58 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-04-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 20:15:14 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-18 18:21:19 | No | No |  | 18-Feb-26 Replace BBU3900 To BBU5900 Replace RRU3962 to RRU5526 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PIANM_2025 Capacity Expansion Ph8_EXP_BKK | SOI PIANON |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-24 14:48:20 | No | No |  |  |  | 2026-02-14 | 2026-03-02 | 2026-03-02 | V Contribute Co., Ltd | N/A | Closed | 2026-03-02 19:07:39 | Yes | Yes | 2026-03-02 19:07:39 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-03-04 09:57:31 | Yes | Yes | 2026-03-09 20:27:43 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-06 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 13:00:01 |  | 2026-02-23 | 2026-02-23 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-23 22:57:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-07 18:36:19 | No | No |  | 07-02-2026. Add AAU5636w Sec.3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PJNTM_2026 Capacity Expansion NW Modernization_EXP_BKK | POTJANART APARTMENT | [5 empty] | 2026-07-08 | 2026-07-08 | Thossapan Chaloemrit | N/A | Closed | 2026-07-08 08:50:21 | No | No |  |  |  | 2026-08-31 | 2026-07-08 | 2026-07-11 | Teloneer Company Limited | N/A | Closed | 2026-07-11 15:21:02 | Yes | Yes | 2026-07-13 09:00:12 |  | 2026-07-13 | 2026-07-23 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-07-31 18:22:41 | Yes | Yes | 2026-07-23 20:12:14 | 1.ไม่มี M2000 ของ Ant 2.SN อุปกรณ์ไม่ชัดเจน ให้ขยายแล้ว Capture 3.รูป BF-AT BBU ไม่ชัดเจน 4.ไม่ BOQ 5.จุดที่ Grounding kit ที่บาร์ไม่ชัดเจนว่าใช้เส้นไหนและไม่ได้รื้อสายที่ไม่ได้ใช้งาน 6.ตรวจสอบสายเก่าที่ไม่ได้ใช้งานได้รื้อถอนหรือไม่ (Before-after CPRI loop มีเพิ่มลูปอย่างเดียว) 7.Recheck DCDU ที่ Replace เป็น 16D แต่มีสาย BBU ต่อใช้งาน ให้ตรวจสอบว่าสามารถเพิ่ม CB แล้ว add 12B เพื่อใช้งานกับ BBU ได้หรือไม่ | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-05 11:50:00 | No | No |  |  |  | 2026-07-09 | Teloneer Company Limited | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-07-09 10:29:02 |  |  | 2026-07-30 | 2026-07-03 | Teloneer Company Limited | N/A | Closed | 2026-07-03 18:28:00 | No | No |  |  |  |  | 2026-07-02 | Autumporn Masing WX1434753 | N/A | Closed | 2026-07-02 21:02:25 | No | No |  | 2026-07-02 S1 REP 5507*1 to AAU5775*1 S3 REP 3962*1 to AAU5775*1 S6 RMV RRU5507*2 S8 RMV 3953*1 rmv card d6/add h3a Alarm :RF Unit CPRI Interface Error 7/9 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-06 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:30:41 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PJNTM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | POTJANART APARTMENT | [5 empty] | 2026-07-08 | 2026-07-08 | Thossapan Chaloemrit | N/A | Closed | 2026-07-08 08:50:21 | No | No |  |  |  | 2026-08-08 | 2026-07-10 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 18:55:02 | Yes | Yes | 2026-07-13 10:07:52 |  | 2026-07-13 | 2026-07-21 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 12:51:36 | Need redmark at install BBU#，BBP and UMPT in pg-10. Need Before:SN remove CE Card1 (UMPT) in pg-11. Need After:SN add new CE Card2 (BBP) in pg-11. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-09 | Teloneer Company Limited | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-07-09 10:32:18 |  |  | 2026-08-08 | 2026-07-03 | Teloneer Company Limited | N/A | Closed | 2026-07-03 18:24:06 | No | No |  |  |  |  | 2026-07-03 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-07-03 18:01:13 | No | No |  | 03-07-2026. Replace BBU5900#， UMPTg2#， Add UBBPh2a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-03 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:30:41 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PK11M_2026 Capacity Expansion NW Modernization_EXP_BKK | CHAENGWATTANA 14 STATION | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-30 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-30 11:32:55 | No | No |  | 30-Sep-2026 Add UBBPh3a Rmv g3 Add AAU5775 S1 Rmv RRU5507 Add AAU5775 S3 Rmv RRU5526 Rmv RRU5516 S8 ย้าย RET S3 700 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKFAM_2026 Capacity Expansion Ph1_EXP_ER | Prok Fa | 2026-08-09 | Team : thcp_watcharin.k Tel :0925546852 | Install & Integrate |  | 2026-08-20 | 2026-08-09 | 2026-08-09 | Teloneer Company Limited | N/A | Closed | 2026-08-10 17:52:02 | No | No |  |  |  | 2026-08-20 | 2026-08-13 | 2026-08-17 | Teloneer Company Limited | N/A | Closed | 2026-08-17 13:56:19 | Yes | Yes | 2026-08-21 10:36:23 |  | 2026-08-20 | 2026-08-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:42:47 | Yes | Yes | 2026-09-10 09:37:07 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:20 | No | No |  |  | 2026-07-31 | 2026-08-02 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-04 10:24:05 | Yes | Yes | 2026-08-02 08:05:32 |  |  | 2026-08-20 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-09 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-09 19:12:46 | No | No |  | Remove UBBPd5 x 3 +Add UBBPh2a + Add UBBPg3a Replace Antenna (MB) + Change 2T2R to 4T4R_PKFAM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_PKFAM_H_2 Replace Antenna (MB) + Change 2T2R to 4T4R_PKFAM_H_3 Replace Antenna (MB) + Change 2T2R to 4T4R_PKFAM_H_4 ReSectorname S2 to S3_PKFAM_L_3 ReSectorname S3 to S4_PKFAM_L_4 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_PKFAM_L_2 New L26F5 + NR26 (New AAU5656)_PKFAM_N_2 New L26F5 + NR26 (New AAU5656)_PKFAM_N_1 Co L21F2 S1#，2#，4 |  | 2026-08-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-10 17:25:44 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 0%รังแตน , Day2 : 80% , Day3: 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PKTNG_2026 Capacity Expansion Ph1_EXP_SR | PLAK THONG | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-07-31 | 2026-07-25 | 2026-07-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-27 17:23:13 | Yes | Yes | 2026-08-10 10:11:06 |  | 2026-08-13 | 2026-08-13 | Muhamadnase Chesamae | Approved | Closed | 2026-08-28 16:01:52 | Yes | Yes | 2026-08-14 08:48:38 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:05 | No | No |  |  | 2026-08-13 | 2026-08-13 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-13 08:16:49 |  | 2026-07-25 | 2026-07-30 | 2026-07-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-25 19:12:14 | No | No |  |  |  |  | 2026-07-25 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-25 17:34:46 | No | No |  | add UBBPh2a*1 Rep Ant MB S2 S2 > RRU5516LB*1 > Ant Combine MB S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLATM_2026 Capacity Expansion Ph1_EXP_SR | PALAT | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-24 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-24 | 2026-08-31 | 2026-09-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-26 10:50:18 | No | No |  |  |  |  | 2026-09-24 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-24 18:34:35 | No | No |  | 24 Sep 2026 Add DMM AAU5775 sector1 add1UBBPh3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLIKR_2026 Capacity Expansion NW Modernization_EXP_SR | Plai Grim | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-09-05 | 2026-08-25 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-22 | 2026-08-31 | 2026-08-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-24 13:46:24 | No | No |  |  |  |  | 2026-08-22 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-22 16:53:20 | No | No |  | S1 > RRU3826*2 to RRU3962*1 > Ex Ant S2 > RRU3826*2 to RRU3962*1 > Ex Ant S3 > RRU3826*2 to RRU3962*1 > Ex Ant S4 > RRU3826*2 to RRU3962*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLOCM_2026 Capacity Expansion Modernize_EXP_ER | Plaloc Asia (Thailand) CO.,LTD. | 2026-06-25 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-06-30 | 2026-06-25 | 2026-06-25 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-25 14:38:46 | No | No |  |  |  | 2026-06-30 | 2026-06-25 | 2026-06-25 | Teloneer Company Limited | N/A | Closed | 2026-06-25 18:18:03 | Yes | Yes | 2026-06-26 00:18:47 |  | 2026-06-30 | 2026-06-27 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:53:25 | Yes | Yes | 2026-06-27 14:35:40 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-23 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-24 14:49:49 | No | No |  |  | 2026-06-30 | 2026-06-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-28 22:11:00 | Yes | Yes | 2026-06-25 12:45:04 |  |  | 2026-06-30 | 2026-06-25 | Teloneer Company Limited | N/A | Closed | 2026-06-25 13:26:18 | No | No |  |  |  |  | 2026-06-25 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-25 18:09:38 | No | No |  | Replace RRU5505 to (RRU5513) + 4T4R_PLOCM_H_B Replace RRU5505 to (RRU5513) + 4T4R_PLOCM_H_C Co L21F2 all sector" |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-29 | Nattawoot Suwan | N/A | Closed | 2026-06-29 15:05:02 | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PLRKM_2026 Capacity Expansion Ph1_EXP_SR | Ban Plai Rik | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-07 | 2026-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-11 20:31:22 | Yes | Yes | 2026-08-14 14:55:11 |  | 2026-08-18 | 2026-08-21 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-28 13:29:28 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-18 | 2026-08-18 | Aomchun Jittreemit | Ready To Approve | Assigned |  | Yes | No |  |  | 2026-07-31 | 2026-08-31 | 2026-07-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-31 20:30:21 | No | No |  |  |  |  | 2026-07-31 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-07-31 17:28:56 | No | No |  | 31 July 2026 Replace RRU5516 sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PMCDM_2026 Capacity Expansion Modernize_EXP_ER | Phra Maha Chedsadharajchao Camp | 2026-08-18 | Team : thcp_pooriwat.k Tel : 0925094222 | Install & Integrate |  | 2026-08-20 | 2026-08-18 | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-18 18:24:58 | No | No |  |  |  | 2026-08-20 | 2026-08-19 | 2026-08-23 | Teloneer Company Limited | N/A | Closed | 2026-08-23 17:24:55 | Yes | Yes | 2026-08-25 09:29:49 |  | 2026-08-20 | 2026-08-25 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:42:47 | Yes | Yes | 2026-09-07 08:57:40 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-08-20 | 2026-08-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-18 10:05:24 |  |  | 2026-08-20 | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-18 11:46:52 | No | No |  |  |  |  | 2026-08-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-18 18:46:50 | No | No |  | Add UBBPh2a_PMCDM Add RRU5505 x 1 + 4T4R_PMCDM_H_2 -- revise plan to rep.RRU5505 to RRU5516 Add RRU5508 x 1 + Co NR07 + 4T4R_PMCDM_L_2 -- revise plan to rep.RRU5508 to RRU5516 Co NR07_PMCDM_L_3 Co NR07_PMCDM_L_1 Co L21F2 S1#，2#，6 **before RET MB/LB (co ant) not config #， RET not found |  | 2026-08-19 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-19 15:53:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : ไม่เข้า0% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PN27M_2025 Capacity Expansion Ph8_EXP_BKK | SOI PUNNAWITHI 27 |  |  |  |  | 2026-02-02 | 2026-03-24 | 2026-03-24 | Akhom Srinara | N/A | Closed | 2026-03-24 11:11:26 | No | No |  |  |  | 2026-02-24 | 2026-03-07 | 2026-03-07 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-03-07 14:53:36 | Yes | Yes | 2026-03-23 22:18:35 |  | 2026-03-27 | 2026-03-27 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-04-29 16:49:13 | Yes | Yes | 2026-03-27 02:08:38 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-06-21 | 2026-06-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-06-22 20:48:24 | Yes | Yes | 2026-06-21 05:18:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-03 12:00:35 | No | No |  | 3-Feb-2026 Add AAU5636w Sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PNDDA_2025 Capacity Expansion NW Modernization_EXP_BKK | DIN DAENG POST OFFICE |  |  |  |  | 2026-02-25 | 2026-02-25 | 2026-02-25 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-03-13 | 2026-03-24 | 2026-03-25 | V Contribute Co., Ltd | N/A | Closed | 2026-03-25 09:35:06 | Yes | Yes | 2026-03-25 09:35:06 |  | 2026-04-01 | 2026-04-01 | Chonradee Suwapan | Approved | Closed | 2026-07-06 09:43:51 | Yes | Yes | 2026-04-20 15:37:19 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-06 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-01 | 2026-04-01 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-01 00:49:25 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-25 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-25 16:43:36 | No | No |  | 25-Feb-26 Replace RRU3962 To RRU5526 SA SB SC |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PNIMM_2026 Capacity Expansion Ph2_EXP_ER | Pana Nikom |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PNK1A_2025 Capacity Expansion NW Modernization_EXP_BKK | PRATUNAM MARKET (SMALL CELL) No.1 |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:30:39 | No | No |  |  | 2026-04-30 | 2026-04-30 | 2026-05-07 | 2026-05-07 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-07 20:38:31 | Yes | Yes | 2026-05-19 13:50:25 |  | 2026-06-24 | 2026-06-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-04 16:44:42 | Yes | Yes | 2026-06-24 16:59:08 | Page no.7#， remove Breaker model wrong. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-04 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 20:15:29 |  |  | 2026-04-30 | 2026-04-25 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-25 16:43:54 | No | No |  |  |  |  | 2026-04-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-04-25 16:09:54 | No | No |  | 25-Apr-2026 Add RRU5507*2 Sector A Remove RRU3962 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PNK2A_2025 Capacity Expansion NW Modernization_EXP_BKK | PRATUNAM MARKET (SMALL CELL) No.2 |  |  |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-16 12:01:10 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-12 | 2026-02-15 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-15 09:42:03 | Yes | Yes | 2026-02-16 11:03:23 |  | 2026-02-16 | 2026-02-16 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-03-19 10:27:35 | Yes | Yes | 2026-03-11 18:16:00 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-06 | 2026-03-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:59 | Yes | Yes | 2026-04-09 13:02:15 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 20:15:45 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-30 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-02-18 14:36:00 | No | No |  | 2026-01-30_Replace to BBU5900 by UMPTg2#， Add UBBPg3a#， GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PNK3M_2026 Capacity Expansion Ph2_BKK | SOI PHATTHANA SUK 3 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PNP3M_2026 Capacity Expansion Ph2_BKK | PREAKSA-NAMPHUENG 3 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PNPMS_2026 Capacity Expansion Ph1_EXP_SR | P N P Mansion | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-15 | 2026-08-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-16 19:46:08 | Yes | Yes | 2026-08-21 01:51:36 |  | 2026-08-23 | 2026-08-28 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-28 13:11:08 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-29 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-30 13:04:17 | No | No |  |  | 2026-08-23 | 2026-08-23 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-23 03:50:04 |  | 2026-08-06 | 2026-08-31 | 2026-08-06 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-06 18:21:31 | No | No |  |  |  |  | 2026-08-06 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-06 17:08:20 | No | No |  | 6 Aug 2026 Add RRU5516 sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PP13M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI PRACHA RAT BAMPHEN 13 | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:43:41 | No | No |  |  |  | 2026-09-30 | 2026-09-04 | 2026-09-05 | Teloneer Company Limited | N/A | Closed | 2026-09-05 13:44:23 | Yes | Yes | 2026-09-10 11:26:30 |  | 2026-09-12 | 2026-09-12 | Boonchot Boriwut | Approving | Assigned |  | Yes | Yes | 2026-09-24 14:00:53 | need to revise inventory page. page.16 need to upload install antenna and AAU SN.photo | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:42:21 |  |  | 2026-09-30 | 2026-08-27 | Teloneer Company Limited | N/A | Closed | 2026-08-27 16:04:05 | No | No |  |  |  |  | 2026-08-27 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-08-27 15:02:57 | No | No |  | 2026-08-27 s1#，s2#，s3 replace RRU3953 to RRU5516#，replace ant 8 port 3 sector s3 replace RRU5502 to AAU5775 s6 rmv RRU5502 s7 rmv RRU5507*2 s8 rmv RRU5502 add UBBPg2#，UBBPh3a#，rmv UBBPeb |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-04 16:14:27 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PP15M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PRADIPHAT 15 |  |  |  |  | 2026-03-17 | 2026-03-17 | 2026-03-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:46:20 | No | No |  |  |  | 2026-02-28 | 2026-03-23 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 10:22:52 | Yes | Yes | 2026-03-24 10:22:53 |  | 2026-03-20 | 2026-03-20 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-03-20 21:29:17 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-20 | 2026-03-20 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-20 21:39:16 |  | 2026-02-19 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-19 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-19 17:09:54 | No | No |  | 19-Feb-26 Replace AAU5768 DMM S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PPKSM_2026 Capacity Expansion Modernize_EXP_ER | Pa Pa Koh SriChang | 2026-09-08 | Team : Thcp_phet.sa Tel : 0924272237 |  |  | 2026-09-15 | 2026-09-08 | 2026-09-08 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-09 06:33:01 | No | No |  |  |  | 2026-09-15 | 2026-09-08 | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-08 17:32:54 | Yes | Yes | 2026-09-10 23:14:43 |  | 2026-09-15 | 2026-09-11 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:44:45 | Yes | Yes | 2026-09-15 21:37:22 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-16 | 2026-09-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:46:21 | Yes | Yes | 2026-09-08 09:41:20 |  |  | 2026-09-15 | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:15:07 | No | No |  |  |  |  | 2026-09-08 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-08 12:29:56 | No | No |  | Replace RRU (RRU5526) + 4T4R_PPKSM_H_1 Replace RRU (RRU5526) + 4T4R_PPKSM_H_3 Co L21F2 All Sector |  | 2026-09-09 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-09 17:36:24 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PR20A_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PRACHA SONGKHRO 20 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-01 15:35:58 | Yes | Yes | 2026-03-25 14:14:32 |  | 2026-04-24 | 2026-04-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-31 10:10:31 | Yes | Yes | 2026-04-24 11:24:03 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-07-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 20:00:48 |  |  | 2026-02-27 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-02-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-27 18:44:36 | No | No |  | 27-Feb-2026 Replace Ant 12port No Ret S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PR25M_2025 Capacity Expansion NW Modernization_EXP_BKK | PRACHA SONGKHRAO SOI 25 |  |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-28 | 2026-03-24 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 17:45:31 | Yes | Yes | 2026-03-24 17:45:32 |  | 2026-03-31 | 2026-03-31 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-05-19 17:58:03 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-05-10 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-31 | 2026-03-31 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-31 00:19:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-23 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-23 17:25:38 | No | No |  | 23-02-2026. Replace RRU5507 to AAU5768 Sec.1#， 2#， 3#， UBBPd5 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRARM_2026 Capacity Expansion NW Modernization_EXP_BKK | Pracharat Road | [5 empty] | 2026-09-21 | 2026-09-21 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-10 | 2026-09-25 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 20:35:02 | Yes | Yes | 2026-09-26 20:35:57 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:43:15 |  |  | 2026-10-10 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 16:59:02 | No | No |  |  |  |  | 2026-09-15 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-15 18:22:05 | No | No |  | 2026-09-21 Clear pending 15-Sep-2026 Add UBBPh3a Add AAU5775 S1 S2 S3 Rmv RRU3826*2 Rmv AAU5726 S1 Rmv RRU5507*4 S2 S7 Rmv RRU5507*4 S3 S8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRDSM_2025 Coverage Expansion Ph2_New Site_Remote-BBU_ER | Paradise Park Pattaya | 2026-09-15 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-09-30 | 2026-09-15 | 2026-09-15 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-16 16:32:36 | No | No |  |  |  | 2026-09-30 | 2026-09-17 | 2026-09-17 | Teloneer Company Limited | N/A | Closed | 2026-09-17 17:53:13 | Yes | Yes | 2026-09-18 18:18:41 |  | 2026-09-30 | 2026-09-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:43:20 | Yes | Yes | 2026-09-18 20:36:07 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:42:32 | Yes | Yes | 2026-09-22 09:44:04 |  |  | 2026-09-30 | 2026-09-16 | Teloneer Company Limited | N/A | Closed | 2026-09-16 15:15:54 | No | No |  |  |  |  | 2026-09-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-15 17:56:41 | No | No |  | New site Relocate |  | 2026-09-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-15 17:56:41 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRDSM_2026 Capacity Expansion Modernize_EXP_ER | Paradise Park Pattaya | 2026-08-22 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-08-31 | 2026-08-22 | 2026-08-22 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-23 11:39:08 | No | No |  |  |  | 2026-08-31 | 2026-08-22 | 2026-08-23 | Teloneer Company Limited | N/A | Closed | 2026-08-23 17:18:29 | Yes | Yes | 2026-08-26 12:42:36 |  | 2026-08-31 | 2026-09-01 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:48:39 | Yes | Yes | 2026-09-01 21:52:55 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-08-31 | 2026-08-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:30 | Yes | Yes | 2026-08-22 08:36:08 |  |  | 2026-08-31 | 2026-08-22 | Teloneer Company Limited | N/A | Closed | 2026-08-22 21:26:46 | No | No |  |  |  |  | 2026-08-22 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-22 14:52:46 | No | No |  | replace RRU5513 x 1 + 4T4R_PRDSM_H_C Co L21F2 All Sector |  | 2026-08-24 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-24 19:13:26 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRDVM_2026 Capacity Expansion Ph1_EXP_ER | PARINDA VILLAGE | 2026-08-07 | Team : thcp_watcharin.k Tel :0925546852 |  |  | 2026-08-20 | 2026-08-07 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 17:34:59 | No | No |  |  |  | 2026-08-20 | 2026-08-08 | 2026-08-10 | Teloneer Company Limited | N/A | Closed | 2026-08-10 17:31:30 | Yes | Yes | 2026-08-16 13:04:42 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:50 | Yes | Yes | 2026-08-16 17:55:50 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:31 | No | No |  |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:12:17 |  |  | 2026-08-20 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 15:00:14 | No | No |  |  |  |  | 2026-08-07 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-07 13:49:07 | No | No |  | Add UBBPg3a_PRDVM_H_1 New NR26 (New AAU5639w)_PRDVM_N_3 New NR26 (New AAU5639w)_PRDVM_N_6 |  | 2026-08-19 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-19 15:53:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PRILM_2026 Capacity Expansion Ph1_EXP_ER | PEA NongLalork RIL | 2026-08-27 | User isdp : thcp_apichat.f Tel : 0960126111 | Take Photo & Clear Pending |  | 2026-08-31 | 2026-08-27 | 2026-08-27 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-28 10:31:21 | No | No |  |  |  | 2026-08-31 | 2026-08-27 | 2026-08-28 | Teloneer Company Limited | N/A | Closed | 2026-08-28 20:20:12 | Yes | Yes | 2026-08-30 19:56:36 |  | 2026-08-31 | 2026-08-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:43:50 | Yes | Yes | 2026-08-30 22:56:53 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:28 | No | No |  |  | 2026-08-31 | 2026-08-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-25 16:53:49 | Yes | Yes | 2026-08-25 12:07:36 |  |  | 2026-08-31 | 2026-08-27 | Teloneer Company Limited | N/A | Closed | 2026-08-27 15:22:56 | No | No |  |  |  |  | 2026-08-26 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-26 18:15:12 | No | No |  | Add UBBPh3a Replace Antenna (Dualband)_PRILM_H_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_PRILM_L_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_PRILM_L_2 New L0709 + NR07 + 4T4R + (RRU5516_900) + (New Antenna LB)_PRILM_L_3 Remove Antenna + (New AAU5775) + Main Dir = 140 + Remove RRU x 1_PRILM_H_2 Remove Antenna + (New AAU5775) + Main Dir = 260 + Remove RRU x 1_PRILM_H_3 (Co AAU5775) + Main Dir = 140 + Remove RRU x 1_PRILM_H_7 (Co AAU5775) + Main Dir = 260 + Remove RRU x 1_PRILM_H_8 New Sector J (Co AAU5775) + Main Dir = 140_PRILM_H_J New Sector K (Co AAU5775) + Main Dir = 140_PRILM_H_K New Sector M (Co AAU5775) + Main Dir = 260_PRILM_H_M New Sector N (Co AAU5775) + Main Dir = 260_PRILM_H_N |  | 2026-08-27 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-27 16:20:02 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 60% , Day2 : 100% , Day3 : Clear pending | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PS08M_2026 Capacity Expansion Ph2_BKK | SOI. PHRAEK SA 8 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PS38B_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SOI PRACHASONGKHRO38 for The Niche Ratchada - Huay Kwang |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  |  | 2026-02-28 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 21:12:05 | Yes | Yes | 2026-03-12 10:39:12 |  | 2026-04-03 | 2026-04-03 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-04 16:44:42 | Yes | Yes | 2026-04-03 13:18:52 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 20:01:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-23 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-23 16:54:34 | No | No |  | 23-Feb-26 Replace RRU3862 To RRU5507*2 SA #， |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PS81M_2026 Capacity Expansion Ph2_BKK | PHETKASAEM SOI 81 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PS88M_2026 Capacity Expansion Ph2_BKK | SOI PHETCHAKASEM 88 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PSB5M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PREMSOMBAT 5 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-03-08 | 2026-03-09 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-09 13:38:43 | Yes | Yes | 2026-03-11 10:08:27 |  | 2026-03-24 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 17:40:28 | Yes | Yes | 2026-03-27 13:49:47 | PAT Pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 18:09:00 | Yes | Yes | 2026-08-01 20:16:01 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-11 17:29:02 | No | No |  | 11-02-2026. Replace RRU5507 to AAU5768 Sec.1#， 2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PSN2M_2026 Antenna Dualbeam_Replacement_BKK | PATHUMTHANI-SAI NAI ROAD STATION 2 |  |  |  | 2026-05-19 | 2026-05-19 | 2026-05-19 | 2026-05-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-19 10:14:33 | No | No |  |  | 2026-05-12 | 2026-05-12 | 2026-05-13 | 2026-06-30 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-30 18:04:46 | Yes | Yes | 2026-06-30 18:06:52 |  | 2026-05-19 | 2026-05-19 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-17 16:24:50 | Yes | Yes | 2026-05-19 10:14:17 | Page no.6#， install antenna QTY must be 3 pcs/ unit must be pcs in SOW. Page no.28#， need to fill install antenna SN-1pc. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:27:19 | Yes | Yes | 2026-08-01 21:57:02 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-02 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-05-02 17:19:56 | No | No |  | 02-05-2026. Replace Ant.12 port Sec.1#， 2#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | Review ongoing and subcons not inform yet |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PSNMS_2025_Imp_UPS_SR | Pisan Mansion |  |  |  | 2026-06-11 | 2026-06-16 | 2026-06-11 | 2026-06-11 | Teloneer Company Limited | N/A | Closed | 2026-06-11 14:36:36 | No | No |  | MR cross project | 2026-06-11 | 2026-06-16 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-05 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-29 | 2026-06-05 |  | N/A | Closed | 2026-06-05 10:20:02 | No | No |  |  | DTH1202605200010 | Shipped | To X-Docking(Subcon pick up to site) | 2026/05/21 18:49:03 | 2026/05/22 10:00:00
PST1M_2026 Capacity Expansion NW Modernization_EXP_BKK | P.S. TALING CHAN 1 | [5 empty] | 2026-09-12 | 2026-09-12 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 | 2026-09-21 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:44:10 |  |  | 2026-10-10 | 2026-09-14 | Teloneer Company Limited | N/A | Closed | 2026-09-14 10:46:02 | No | No |  |  |  |  | 2026-09-11 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-09-12 01:51:52 | No | No |  | 2026-09-11 S1 Replace RRU3953 > RRU5516 (7/9 4T) + Remove RRU3962*2 > Add AAU5775 + Replace Ant to 8port S2 Replace RRU3953 > RRU5516 (7/9 4T) + Replace RRU3962*2 > RRU5526 (18/21 4T) + Replace Ant to 8port S3 Replace RRU3953 > RRU5516 (7/9 4T) + Replace Ant to 8port S6 Remove RRU3962*2 Replace + Add Card UBBPg2#， UBBPh3a ----------------------------------------------------------------------------------------- ----------------------------------------------------------------------------------------- |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-12 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:30:25 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PSTAM_2026 Capacity Expansion Ph1_EXP_SR | Pong Sata | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-20 | 2026-08-31 | 2026-09-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-25 10:43:54 | No | No |  |  |  |  | 2026-09-20 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-20 19:56:55 | No | No |  | Rep d5*1 to h3a*1 Remove MB S1&S6// Add new ant LB S1 S1 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PSYWO_2026 Capacity Expansion Ph1_EXP_SR | Pa Se Ya Wo | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-23 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-23 | 2026-08-31 | 2026-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-24 12:16:29 | No | No |  |  |  |  | 2026-09-23 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-23 18:30:47 | No | No |  | 23 Sep 2026 Add DDM AAu5775 sector2 add UBBPh3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PTHAM_2025 Capacity Expansion Ph8_EXP_ER | PT House Apartment | 2026-02-12 | Thcp_adirek.kh | Install & Integrate |  | 2026-02-28 | 2026-02-12 | 2026-02-12 | Teloneer Company Limited | N/A | Closed | 2026-02-12 13:30:46 | No | No |  |  |  | 2026-02-28 | 2026-02-13 | 2026-02-13 | Teloneer Company Limited | N/A | Closed | 2026-02-13 11:35:17 | Yes | Yes | 2026-02-16 19:26:53 |  | 2026-02-28 | 2026-02-16 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:23:12 | Yes | Yes | 2026-02-16 21:11:45 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 14:44:57 |  | 2026-02-28 | 2026-02-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-13 15:14:42 | Yes | Yes | 2026-02-12 08:32:57 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-12 18:07:15 | No | No |  | Add UBBPg3a New L26F5 + NR26 (New RRU5818) + Co Antenna_PTHAM_N_1 New L26F5 + NR26 (Co RRU5818 --> revise to 1RRU5818) + Co Antenna_PTHAM_N_2 |  | 2026-02-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-13 17:49:57 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PTIMM_2026 Capacity Expansion Ph2_EXP_ER | Plong Ta-iam | 2026-09-25 | Team : thcp_jaran.s Tel : 0988500996 | Install & Integrate |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:42:32 | Yes | Yes | 2026-09-22 13:55:36 |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 0% , Day2 : ฝนตก | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PTPDP_2025 Capacity Expansion NW Modernization_EXP_BKK | PANTIP PLAZA DEPARTMENT STORE |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:10:15 | No | No |  |  |  | 2026-02-28 | 2026-03-18 | 2026-03-18 | V Contribute Co., Ltd | N/A | Closed | 2026-03-18 16:08:43 | Yes | Yes | 2026-03-18 16:08:44 |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-04-10 11:05:10 | Yes | Yes | 2026-03-11 21:38:09 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-04-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-11 | 2026-03-11 | Chonradee Suwapan | Approved | Closed | 2026-07-20 10:33:26 | Yes | Yes | 2026-03-11 21:52:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-12 18:19:34 | No | No |  | 12 Feb 2026 Add 1UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PTPKM_2026 Capacity Expansion NW Modernization_EXP_BKK | PATA PINKLAO | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:45:12 |  |  | 2026-10-10 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PURGM_2026 Capacity Expansion Ph1_EXP_SR | Pu Rong | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-28 | 2026-09-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-29 12:09:41 | Yes | Yes | 2026-10-01 18:38:21 |  | 2026-10-01 | 2026-10-01 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-10-01 20:54:47 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 | 2026-10-01 | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-10-01 20:56:15 |  | 2026-09-30 | 2026-08-31 | 2026-09-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-28 20:08:12 | No | No |  |  |  |  | 2026-09-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-28 20:25:05 | No | No |  | S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PY16M_2026 Capacity Expansion Ph2_BKK | SOI PHRAYA SUREN 16 YAK 1 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PY24M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI PHAHON YOTHIN 24 | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:52:00 | No | No |  |  |  | 2026-09-30 | 2026-09-05 | 2026-09-11 | Teloneer Company Limited | N/A | Closed | 2026-09-11 09:25:36 | Yes | Yes | 2026-09-16 10:45:49 |  | 2026-10-03 | 2026-09-18 | Nattawoot Suwan(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-24 14:21:02 | 1.Page 5#，39#，In SOW & EQ add ANT model wrong. 2.Page 5#，In SOW remove card must be UBBPeb. 3.Page 19#，Need to upload BBU left & right side clear photo.(need to see BBP model clearly) 4.Need to upload install & dismantle eq INV page. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:45:59 |  |  | 2026-08-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-09-01 12:00:11 | No | No |  | 01-09-2026. Add CPRI AAU5726 Sec.3 2026-08-26 S1 REP RRU3962*1 to RRU5516*1 4T S2 REP RRU3962*2 to RRU5526*1 4T S7 REP RRU3826*1 to RRU5507*1 S6 RMV RRU3962*1 S1 REP ANT RMV eb//add h3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-04 16:14:27 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PY24M_D2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | SOI PHAHON YOTHIN 24 | [5 empty] | 2026-07-10 | 2026-07-10 | Teloneer Company Limited | N/A | Closed | 2026-07-10 22:30:58 | No | No |  |  |  | 2026-08-08 | 2026-07-12 | 2026-07-12 | Teloneer Company Limited | N/A | Closed | 2026-07-12 15:26:58 | Yes | Yes | 2026-07-13 10:06:39 |  | 2026-07-15 | 2026-07-23 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-07-23 22:08:02 | Yes | Yes | 2026-07-22 20:05:23 | No inventory | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-17 | Thossapan Chaloemrit | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-17 12:41:16 |  |  | 2026-08-08 | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-07 20:18:50 | No | No |  |  |  |  | 2026-07-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-07-07 19:04:18 | No | No |  | 07-07-2026. Replace UBBPd6 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-07 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:30:41 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PYMRP_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | Pattaya Marriott Resort & Spa | 2026-05-26 | thcp_adirek.kh | Install & Integrate |  | 2026-05-31 | 2026-05-26 | 2026-05-26 | Teloneer Company Limited | N/A | Closed | 2026-05-26 15:55:46 | No | No |  |  |  | 2026-05-31 | 2026-05-28 | 2026-06-02 | Teloneer Company Limited | N/A | Closed | 2026-06-02 12:14:27 | Yes | Yes | 2026-06-02 18:27:19 |  | 2026-05-31 | 2026-06-08 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:45:35 | Yes | Yes | 2026-06-08 10:31:20 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-05-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-05-28 08:46:34 | Yes | Yes | 2026-05-26 14:13:57 |  | 2026-05-26 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-26 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-05-27 18:04:21 | No | No |  | new site change remote RRU to remote BBU (NO gps) |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-05-20 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-05-25 09:17:43 | Yes | Yes | 2026-05-24 17:18:02 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
PZAAM_2026 Capacity Expansion Modernize_EXP_ER | Pure Park Plaza Amta Chonburi | 2026-08-12 |  |  |  | 2026-08-20 | 2026-08-12 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 18:06:16 | No | No |  |  |  | 2026-08-20 | 2026-08-14 | 2026-08-14 | Teloneer Company Limited | N/A | Closed | 2026-08-14 10:16:22 | Yes | Yes | 2026-08-16 13:51:16 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:50 | Yes | Yes | 2026-08-16 17:15:54 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:31 | No | No |  |  | 2026-08-15 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 18:01:19 |  |  | 2026-08-20 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 20:23:15 | No | No |  |  |  |  | 2026-08-12 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-12 15:00:12 | No | No |  | Add UBBPh2a_PZAAM_H_1 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_PZAAM_L_2 Co L21F2 All sector |  | 2026-08-13 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-13 17:40:45 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
QPHTM_2025 Coverage Expansion Ph1_New Site_Change SFP bidi_ER | Queen Pattaya Hotel | 2026-05-26 | Thcp_phet.sa | Install & Integrate |  | 2026-05-31 | 2026-05-26 | 2026-05-26 | Teloneer Company Limited | N/A | Closed | 2026-05-26 17:09:42 | No | No |  |  |  | 2026-05-31 | 2026-05-28 | 2026-05-28 | Teloneer Company Limited | N/A | Closed | 2026-05-28 12:30:55 | Yes | Yes | 2026-05-28 14:04:53 |  | 2026-05-31 | 2026-05-29 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:45:35 | Yes | Yes | 2026-06-01 11:57:50 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-05-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-05-28 08:46:34 | Yes | Yes | 2026-05-26 14:47:18 |  | 2026-05-26 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-26 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-05-27 18:04:21 | No | No |  | Change SFP bidi #，config ethport 10g |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RAKCM_2026 Capacity Expansion Ph1_EXP_SR | Rak Chan Rd. | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-03 | 2026-08-03 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-03 17:56:15 | Yes | Yes | 2026-08-06 22:32:47 |  | 2026-08-17 | 2026-08-21 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-21 11:59:29 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:22 | No | No |  |  | 2026-08-17 | 2026-08-17 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-17 20:57:05 |  | 2026-08-03 | 2026-08-31 | 2026-08-03 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-03 12:08:03 | No | No |  |  |  |  | 2026-08-03 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-03 19:39:38 | No | No |  | S2 >Rep RRU3953*2 to RRU5516LB*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RB11M_2026 Capacity Expansion NW Modernization_EXP_BKK | 11th Infantry Regiment King' Bodyguard | [5 empty] | 2026-09-17 | 2026-09-17 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:52 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:47:20 |  |  | 2026-10-10 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 15:09:07 | No | No |  |  |  |  | 2026-09-17 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-17 12:03:36 | No | No |  | 2026-09-17 S1 Replace RRU3962 to RRU5507 S2 Replace RRU3962 to RRU5507 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-17 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:27:23 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RCH1M_2026 Capacity Expansion Ph2_BKK | SOI RUAM CHAI 1 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RCTNM_2026 Capacity Expansion Modernize_EXP_ER | Recruit Training Center , Naval Education Department | 2026-08-08 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-20 | 2026-08-09 | 2026-08-09 | Teloneer Company Limited | N/A | Closed | 2026-08-09 11:10:45 | No | No |  |  |  | 2026-08-20 | 2026-08-11 | 2026-08-13 | Teloneer Company Limited | N/A | Closed | 2026-08-13 11:07:39 | Yes | Yes | 2026-08-17 18:53:22 |  | 2026-08-20 | 2026-08-21 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:48:39 | Yes | Yes | 2026-08-28 09:48:24 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:23 | No | No |  |  | 2026-08-20 | 2026-08-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:04:40 | Yes | Yes | 2026-08-08 20:54:00 |  |  | 2026-08-20 | 2026-08-08 | Teloneer Company Limited | N/A | Closed | 2026-08-08 18:37:13 | No | No |  |  |  |  | 2026-08-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-08 18:10:26 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_RCTNM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_RCTNM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_RCTNM_H_C New L21(F2) Sec. A#，B#，C No RET |  | 2026-08-11 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-11 15:10:03 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RCTRM_2026 Capacity Expansion Modernize_EXP_ER | Rongrian Chumpol Thaharnrue | 2026-08-07 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-08-20 | 2026-08-07 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 17:34:59 | No | No |  |  |  | 2026-08-20 | 2026-08-08 | 2026-08-08 | Teloneer Company Limited | N/A | Closed | 2026-08-08 11:23:22 | Yes | Yes | 2026-08-09 08:11:23 |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:57:00 | Yes | Yes | 2026-08-12 16:01:02 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:23 | No | No |  |  | 2026-07-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-08 08:47:08 |  |  | 2026-08-20 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 17:28:37 | No | No |  |  |  |  | 2026-08-07 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-07 17:07:53 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_RCTRM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_RCTRM_H_3 Add RRU5508 x 1 + 4T4R_RCTRM_L_2 Add RRU5508 x 1 + Co NR07 + 4T4R_RCTRM_L_3 Co L21F2 All sector |  | 2026-08-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-10 17:25:44 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RD13M_2025 Capacity Expansion NW Modernization_EXP_BKK | RACHADAPISEK 13 |  |  |  |  | 2026-02-10 | 2026-02-10 | 2026-02-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-10 16:18:21 | No | No |  |  |  | 2026-02-21 | 2026-03-09 | 2026-03-13 | V Contribute Co., Ltd | N/A | Closed | 2026-03-13 16:40:15 | Yes | Yes | 2026-03-13 16:40:16 |  | 2026-02-07 | 2026-02-07 | Chonradee Suwapan | Approved | Closed | 2026-02-11 09:27:15 | Yes | Yes | 2026-04-01 15:56:42 | Page no 8#， 81#， install BBPG3a card SN210305982310RC100514 mismatch with QC in INV. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:10:45 |  | 2026-02-07 | 2026-02-07 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-07 22:14:44 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-28 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-28 20:25:14 | No | No |  | 28-01-2026 On DMM sector 1#，2#，3 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RGANG_2026 Capacity Expansion Ph1_EXP_SR | Rong Ang Road | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-22 | 2026-09-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-27 20:54:04 | Yes | Yes | 2026-09-30 09:56:17 | Need to upload remove BBP card model & SN photo at EQ. Need this after photo. | 2026-10-01 | 2026-10-01 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-10-01 09:54:07 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-10-01 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-10-01 09:55:04 |  | 2026-09-18 | 2026-08-31 | 2026-09-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-19 15:32:30 | No | No |  |  |  |  | 2026-09-18 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-18 17:30:16 | No | No |  | Rep eb*1 to h2a*1 S1 > Rep RRU3953*2 to RRU5516*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RGDNM_2026 Capacity Expansion Ph2_EXP_ER | Na Mooban Rock Garden Rayong | 2026-09-29 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-09-30 | 2026-09-29 | 2026-09-29 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-30 07:17:06 | No | No |  |  |  | 2026-09-30 | 2026-09-29 | 2026-10-01 | Teloneer Company Limited | N/A | Closed | 2026-10-01 11:42:37 | Yes | Yes | 2026-10-01 11:43:36 |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-29 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-29 15:29:46 |  |  | 2026-09-30 | 2026-09-29 | Teloneer Company Limited | N/A | Closed | 2026-09-29 20:30:41 | No | No |  |  |  |  | 2026-09-29 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-29 16:47:00 | No | No |  | Add UBBPg3a New L26F5 + NR26 (New AAU5656)_RGDNM_N_2 |  | 2026-10-01 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-10-01 17:36:08 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RGPPP_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | Royal Garden Hotel | 2026-06-08 | Thcp_phet.sa | Clear Pending |  | 2026-05-31 | 2026-05-25 | 2026-05-25 | Teloneer Company Limited | N/A | Closed | 2026-05-25 13:51:30 | No | No |  |  |  | 2026-05-31 | 2026-05-26 | 2026-05-26 | Teloneer Company Limited | N/A | Closed | 2026-05-26 15:11:46 | Yes | Yes | 2026-05-27 13:15:28 |  | 2026-05-31 | 2026-06-08 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:45:35 | Yes | Yes | 2026-06-02 19:03:54 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-05-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-05-28 08:46:34 | Yes | Yes | 2026-05-24 16:33:32 |  | 2026-05-25 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-25 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-05-25 17:12:32 | No | No |  | new site change remote RRU to remote BBU #， Clear external alarm |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-05-20 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-05-25 09:17:43 | Yes | Yes | 2026-05-24 17:18:25 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RGRNM_2026 Capacity Expansion Modernize_EXP_ER | Rungcharoen Apartment | 2026-09-17 | Team : thcp_apichat.f Tel : 0960126111 | Clear Pending |  | 2026-08-20 | 2026-08-12 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 18:06:16 | No | No |  |  |  | 2026-08-20 | 2026-08-14 | 2026-08-14 | Teloneer Company Limited | N/A | Closed | 2026-08-14 10:32:26 | Yes | Yes | 2026-08-16 13:51:10 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:50 | Yes | Yes | 2026-08-16 17:16:36 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:31 | No | No |  |  | 2026-08-15 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 18:02:26 |  |  | 2026-08-20 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 12:21:24 | No | No |  |  |  |  | 2026-08-12 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-12 13:00:28 | No | No |  | >> change solution : replace RRU5516 to 2*RRU5508 : RGRNM_L_2 [complete : 2026/09/17] Co NR07_RGRNM_L_1 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_RGRNM_L_2 Co L21F2 All Sector |  | 2026-08-13 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-13 17:40:44 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 80% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RJLBM_2025 Coverage Expansion Ph2_New Site_NodeB_ER | Rojana Industrial Estate , Laem Chabang | 2026-08-19 | Team : Thcp_phet.sa Tel : 0924272237 | Clear Pending |  | 2026-08-20 | 2026-08-16 | 2026-08-16 | Teloneer Company Limited | N/A | Closed | 2026-08-16 08:30:11 | No | No |  |  |  | 2026-08-20 | 2026-08-18 | 2026-08-19 | Teloneer Company Limited | N/A | Closed | 2026-08-19 15:01:17 | Yes | Yes | 2026-08-21 20:19:36 |  | 2026-08-20 | 2026-08-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:48:39 | Yes | Yes | 2026-08-30 10:47:22 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-20 | 2026-08-19 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:30 | Yes | Yes | 2026-08-19 12:34:56 |  |  | 2026-08-20 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 17:15:16 | No | No |  |  |  |  | 2026-08-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-15 21:39:40 | No | No |  | new L18/UL21 S1#，2#，3#，4 3RRU5505 |  | 2026-08-15 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-15 21:39:40 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1: 70% , Day2 : 100% , Day3 : ไม่เข้า | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RKHBP_KKN_2025_RepSGR_NER | RAM KHAM HAENG UNIVERSITY BAN PHAI |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-25 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 15:48:09 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-26 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 05:10:03 | No | No |  |  | DTH1202609100013 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
RM65M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI RAMKHAMHAENG65 |  |  |  | 2026-07-10 | 2026-07-10 | 2026-07-10 | 2026-07-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-10 09:53:58 | No | No |  |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-29 19:19:58 | Yes | Yes | 2026-07-10 10:10:00 |  | 2026-07-08 | 2026-07-08 | Mahadee Japakiya | Approving | Assigned |  | Yes | Yes | 2026-07-10 10:16:39 | page.6 Add RRU or resecter ? (pls revise ADD) page.6 Remove RRU5507 4 pcs or 6pcs? (Pls revise) page.36 need to upload socket left and after page.55 need to RRU SN. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-08 | 2026-07-08 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:27:19 | Yes | Yes | 2026-07-08 21:50:24 |  |  | 2026-06-27 | 2026-06-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-27 20:16:33 | No | No |  |  |  |  | 2026-06-27 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-06-27 19:55:19 | No | No |  | 27-06-2026. Replace RRU5507 to AAU5775 Sec.1#， Add RRU5507x2 Site RM65B Sec.B //26-Jun-2026 Add UBBPh3a d6 Remove g3=2 Add AAU5775 S2 Remove AAU5726 Add AAU5775 S3 Remvoe RRU507*2 Remove RRU3826*2 S2 S7 Remvoe RRU5507 *2 S8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RMA6M_2025 Capacity Expansion Ph8_EXP_BKK | RAMA 6 ROAD 1 | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  |  | 2026-02-06 | 2026-02-06 | 2026-02-09 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-09 12:18:21 | Yes | Yes | 2026-02-16 23:36:44 |  | 2026-02-22 | 2026-02-22 | Pornpichai Dankum | Approved | Closed | 2026-02-25 09:26:15 | Yes | Yes | 2026-03-08 10:40:44 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-27 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:12:58 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-02 19:22:16 | No | No |  | 2026-02-02_ Add AAU5636w Sector 6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RMBTM_2025 Capacity Expansion Ph8_EXP_ER | Rongrian Nanachart Ruambandit | 2026-02-18 | THCP_Wachira.s | Install & Integrate |  | 2026-02-28 | 2026-02-18 | 2026-02-18 | Teloneer Company Limited | N/A | Closed | 2026-02-18 15:54:20 | No | No |  |  |  | 2026-02-28 | 2026-02-19 | 2026-02-19 | Teloneer Company Limited | N/A | Closed | 2026-02-19 16:01:37 | Yes | Yes | 2026-02-26 21:16:05 |  | 2026-02-28 | 2026-02-27 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:24:09 | Yes | Yes | 2026-02-27 10:32:58 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 14:48:25 |  | 2026-02-28 | 2026-02-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-20 08:59:31 | Yes | Yes | 2026-02-18 17:22:11 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-18 17:48:02 | No | No |  | Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 135 + Remove RRU5505 x 2_RMBTM_H_3 (Co AAU5768) + Main Dir = 135 + Remove RRU5505 x 2_RMBTM_H_8 New Sector M (Co AAU5768) + Main Dir = 135_RMBTM_H_M New Sector N (Co AAU5768) + Main Dir = 135_RMBTM_H_N |  | 2026-02-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-03-17 11:57:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RNRNM_NMA_2025_RepSGR_NER | RUNGNIRUN 6 |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-29 | 2026-09-29 | Teloneer Company Limited | N/A | Closed | 2026-09-29 10:53:18 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-29 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-25 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 23:40:02 | No | No |  |  | DTH1202609160027 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/17 16:16:51 | 2026/09/18 09:00:00
RPR1M_2025 Capacity Expansion NW Modernization_EXP_BKK | RATCHAPRAROP1 |  |  |  |  | 2026-03-12 | 2026-03-12 | 2026-03-12 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:46:55 | No | No |  |  |  | 2026-02-28 | 2026-02-25 | 2026-03-06 | V Contribute Co., Ltd | N/A | Closed | 2026-03-06 10:04:17 | Yes | Yes | 2026-03-06 10:04:18 |  | 2026-03-18 | 2026-03-18 | Chonradee Suwapan | Approved | Closed | 2026-06-02 09:35:21 | Yes | Yes | 2026-04-01 16:41:49 | PAT pass. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-05 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-18 | 2026-03-18 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-18 22:27:33 | [5 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 21-02-2026. ***Need Condig 4T4R S.2 //Replace RRU5507 to AAU5768 S.1#， 3#， RRU3962 to 5507x2 S.2#， UBBPd6#， eb to UBBPg3a //Config Sec.2 to 2T2R รอแก้ VSWR |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RPTST_2026 Capacity Expansion Ph1_EXP_SR | Rajaphat Sai Tho | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-07-31 | 2026-08-07 | 2026-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-10 22:39:35 | Yes | Yes | 2026-08-16 09:53:04 |  | 2026-08-16 | 2026-08-16 | Muhamadnase Chesamae | Approved | Closed | 2026-09-04 11:11:26 | Yes | Yes | 2026-08-16 14:33:01 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-01 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-03 17:02:36 | No | No |  |  | 2026-08-16 | 2026-08-16 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-16 14:34:36 |  | 2026-08-02 | 2026-08-31 | 2026-08-02 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-02 15:01:40 | No | No |  |  |  |  | 2026-08-02 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-02 17:56:52 | No | No |  | Add UBBPh2a*1 S6 > RRU5516LB*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RRPMM_2026 Capacity Expansion NW Modernization_EXP_BKK | RAUNG-RAPEE MANSION | [5 empty] | 2026-09-09 | 2026-09-09 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:48:07 |  |  | 2026-10-10 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-08 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-08 18:31:11 | No | No |  | 8-Sep-2026 Add UBBPh3a Add AAU5775 S1 Rmv RRU5507 *2 Rmv RRU5507 *2 S6 Add AAU5775 S2 Rmv RRU5507 *2 Rmv RRU5507 *2 S7 Add AAU5775 S3 Rmv RRU5507 *2 Rmv RRU5507 *2 S8 Add RRU5516 S1 S2 S3 Rmv RRU5508 *3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-09 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:29:30 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RRPMM_2026 Capacity Expansion Ph2_BKK | RAUNG-RAPEE MANSION | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RRWKM_2026 Capacity Expansion Modernize_EXP_ER | Ban Wang Ta Ko School | 2026-07-31 | Team : thcp_jaran.s Tel : 0988500996 | Install & Integrate |  | 2026-07-31 | 2026-08-01 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-02 01:17:06 | No | No |  |  |  | 2026-08-20 | 2026-08-03 | 2026-08-06 | Teloneer Company Limited | N/A | Closed | 2026-08-06 17:38:42 | Yes | Yes | 2026-08-09 15:13:28 |  | 2026-08-20 | 2026-08-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:57:00 | Yes | Yes | 2026-08-19 09:52:06 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-25 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:08 | No | No |  |  | 2026-08-15 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-06 11:37:47 | Yes | Yes | 2026-08-06 08:23:56 |  |  | 2026-07-31 | 2026-07-31 | Teloneer Company Limited | N/A | Closed | 2026-07-31 18:01:14 | No | No |  |  |  |  | 2026-07-31 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-31 19:51:39 | No | No |  | Add UBBPh2a Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_RRWKM_H_1 Add RRU5505 x 1 + 4T4R_RRWKM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_RRWKM_H_3 Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_RRWKM_L_2 Co L21(F2) S1#，S2#，S3 |  | 2026-08-19 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-19 15:53:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RSJNM_2026 Capacity Expansion Ph2_EXP_ER | Romsuk7 Noenkraprok |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RSKBM_2025 Capacity Expansion Ph8_EXP_ER | RongRien Chonburi Sukkhabot | 2026-02-13 | Thcp_adirek.kh | Install & Integrate |  | 2026-02-28 | 2026-02-13 | 2026-02-13 | Teloneer Company Limited | N/A | Closed | 2026-02-13 14:02:21 | No | No |  |  |  | 2026-02-28 | 2026-02-13 | 2026-02-16 | Teloneer Company Limited | N/A | Closed | 2026-02-16 21:13:14 | Yes | Yes | 2026-02-18 22:00:01 |  | 2026-02-28 | 2026-02-19 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:23:12 | Yes | Yes | 2026-02-19 16:12:53 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 15:07:45 |  | 2026-02-28 | 2026-02-13 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-13 15:14:42 | Yes | Yes | 2026-02-13 15:01:06 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-13 18:21:52 | No | No |  | Add UBBPg3a_RSKBM_H_A New L26F5 + NR26 (New RRU5818) + Co Antenna_RSKBM_N_A New L26F5 + NR26 (Co RRU5818) + Co Antenna_RSKBM_N_B |  | 2026-02-16 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-16 17:47:01 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-03-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RTDAD_2026 Capacity Expansion Ph1_EXP_SR | District Office Ratsada | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-04 | 2026-08-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-05 11:46:15 | Yes | Yes | 2026-08-06 15:53:39 |  | 2026-08-07 | 2026-08-13 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-13 10:33:21 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-08-07 | 2026-08-07 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-07 11:11:47 |  | 2026-08-05 | 2026-08-31 | 2026-08-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-04 17:38:34 | No | No |  |  |  |  | 2026-08-04 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-04 18:00:01 | No | No |  | S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RTS1B_2025 Capacity Expansion NW Modernization_EXP_BKK | RHYTHM ASOKE 1 |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:30:39 | No | No |  |  | 2026-04-30 | 2026-04-30 | 2026-04-30 | 2026-05-03 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-03 15:27:16 | Yes | Yes | 2026-07-07 08:36:07 |  | 2026-07-14 | 2026-07-14 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-02 16:18:36 | Yes | Yes | 2026-07-14 15:12:02 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-02 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 20:01:19 |  |  | 2026-04-30 | 2026-04-24 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-24 14:33:49 | No | No |  |  |  |  | 2026-04-24 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-04-24 14:55:20 | No | No |  | 24-Apr-2026 Add d5 Remove g3a Add RRU5507 *2 SA Remove RRU3962 Replace Ant 12port No Ret |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
RVE1M_2025 Capacity Expansion NW Modernization_EXP_BKK | RATCHATHEVEE 1 |  |  |  |  | 2026-02-09 | 2026-02-09 | 2026-02-09 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-23 16:11:24 | No | No |  |  |  | 2026-02-07 | 2026-02-08 | 2026-02-09 | V Contribute Co., Ltd | N/A | Closed | 2026-02-09 09:46:35 | Yes | Yes | 2026-02-09 09:46:36 | SQC Close | 2026-02-21 | 2026-02-21 | Chonradee Suwapan | Approved | Closed | 2026-05-11 09:29:24 | Yes | Yes | 2026-02-21 21:00:22 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-30 | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-21 | 2026-02-21 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-21 21:16:26 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-31 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-31 20:44:44 | No | No |  | 31-Jan-2026 Add AAU5768 S2 S3 Remove RRU5507 *8 Add g3a remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
S241B_2025 Capacity Expansion NW Modernization_EXP_BKK | Baan Siri Twenty Four |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-03-31 | 2026-03-31 | 2026-03-23 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:51:23 | Yes | Yes | 2026-04-03 09:42:04 |  | 2026-04-29 | 2026-04-30 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-28 22:13:13 | Yes | Yes | 2026-05-04 14:50:09 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-12-29 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 20:01:36 |  |  | 2026-03-31 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-07 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-07 16:45:45 | No | No |  | 07-Mar-26 Replace BBU5900 Replace RRU3826 To RRU5507*2 SA |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAFNM_2026 Capacity Expansion NW Modernization_EXP_BKK | SAIFON SCHOOL LATPHRAO | [5 empty] | 2026-09-19 | 2026-09-19 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:52 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:48:55 |  |  | 2026-10-10 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-24 21:22:50 | No | No |  |  |  |  | 2026-09-19 | Autumporn Masing WX1434753 | N/A | Closed | 2026-09-19 19:12:42 | No | No |  | 2026-09-19 S1 ADD RRU3953 ตัวที่ 2 S1 REP RRU3962*2 to AAU5775 S2 REP RRU5507*2 to AAU5775 S3 REP RRU5507*2 to AAU5775 S6 RRU3962*2 S7 RRU5507*2 S8 RRU5507*2 rmv d5//add h3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:27:23 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAKLM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SAM SAKUN |  |  |  | 2026-02-11 | 2026-02-11 | 2026-02-11 | 2026-02-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-11 16:31:24 | No | No |  |  | 2026-02-28 | 2026-02-28 | 2026-02-05 | 2026-02-08 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-08 13:47:40 | Yes | Yes | 2026-02-11 10:49:30 | SQC Close | 2026-02-11 | 2026-02-11 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-03-18 16:34:27 | Yes | Yes | 2026-02-11 16:54:03 | (Pass) Approved by Nopparat Jaiwongsa 84166092 | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-01 | 2026-03-24 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:18:20 |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 20:17:39 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-29 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-01-29 19:07:00 | No | No |  | 29-Jan-2026 Add AAU5768 S1 S3 Remove RRU5507*2 #，4 Add RRU5507 *2 Sector 2 Remove RRU3962 *2 Add g3a Remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAMPM_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI AMON PHAN | [5 empty] | 2026-09-22 | 2026-09-22 | Thossapan Chaloemrit | N/A | Closed | 2026-09-23 21:55:28 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:50:31 |  |  | 2026-10-10 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 15:30:51 | No | No |  |  |  |  | 2026-09-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-09-18 19:32:26 | No | No |  | 2026-09-21 S1 Replace RRU3953 to RRU5516(LB)#， Replace RRU3962*2 to AAU5775#， Replace to Ant BZ44G651618 S2 Replace RRU3953 to RRU5516(LB)#， Replace RRU3962 to RRU5507#， Replace to Ant BZ44G651618 S6 Remove RRU3962*2 SAMBP_A RRU5507 18-09-2026. Replace RRU3962 to AAU5775#， RRU3953 to RRU5516#， Ant.8 port Sec.3#， UBBPd5 to UBBPg3#， UBBPh3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAPIM_2026 Capacity Expansion Ph1_EXP_SR | BAN SA PHLI | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-13 | 2026-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-13 16:03:34 | Yes | Yes | 2026-08-16 16:18:37 |  | 2026-08-19 | 2026-08-25 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-25 08:26:08 | PAT pass wait revise INV | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-19 | 2026-08-19 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-19 08:01:57 |  | 2026-08-12 | 2026-08-31 | 2026-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-12 18:22:22 | No | No |  |  |  |  | 2026-08-12 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-12 19:27:23 | No | No |  | Rep Card g2*1 to h2a*1 Rep Ant MB S4 to 8 Port S4 > RRU5516LB*1 > Ant Combine MB S4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAPRM_2026 Capacity Expansion Ph2_BKK | SOI SAPPRASERT | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAS1B_2025 Capacity Expansion NW Modernization_EXP_BKK | Supalai Park Asoke-Ratchada (Front) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  |  | 2026-03-31 | 2026-03-23 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:08:13 | Yes | Yes | 2026-03-30 08:32:17 |  | 2026-04-27 | 2026-04-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-06 09:05:06 | Yes | Yes | 2026-04-27 11:17:45 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-06 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-08-01 20:01:51 |  |  | 2026-03-11 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-03-11 16:55:34 | No | No |  | 11-03-2026. Replace BBU5900#， UMPTg2#， RRU3962 to RRU5507 x2 Sec.A#， Add UBBPg2 //ติด GPS ไม่ได้ |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SAS2B_2025 Capacity Expansion NW Modernization_EXP_BKK | SUPALAI PARK ASOKE-RATCHADA (BACK) |  |  |  | 2026-03-25 | 2026-03-25 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  |  | 2026-03-24 | 2026-03-17 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:06:18 | Yes | Yes | 2026-03-30 10:06:51 |  | 2026-04-27 | 2026-04-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-04-27 10:47:58 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-12-29 |  |  | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:28:22 | Yes | Yes | 2026-07-14 22:56:03 |  |  | 2026-03-11 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-03-11 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-03-11 16:55:34 | No | No |  | 11-03-2026. Replace RRU3962 to RRU5507 x2 Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SBKWM_2026 Capacity Expansion Ph2_BKK | SOI. BUA KEAW | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SBWMM_2025 Capacity Expansion Ph8_EXP_ER | Soi MoobanBowinMuengThong2 | 2026-02-18 | Thcp_phet.sa | Take Photo & Clear Pending |  | 2026-02-28 | 2026-02-18 | 2026-02-18 | Teloneer Company Limited | N/A | Closed | 2026-02-18 13:44:51 | No | No |  |  |  | 2026-02-28 | 2026-02-19 | 2026-02-20 | Teloneer Company Limited | N/A | Closed | 2026-02-20 13:31:48 | Yes | Yes | 2026-02-25 16:14:17 |  | 2026-02-28 | 2026-02-25 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:24:09 | Yes | Yes | 2026-02-25 21:54:03 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 15:09:18 |  | 2026-02-28 | 2026-02-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-20 08:59:31 | Yes | Yes | 2026-02-17 17:03:25 |  | 2026-02-17 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-17 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-17 17:34:27 | No | No |  | "Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 260 + Remove RRU x 2_SBWMM_H_1 (Co AAU5768) + Main Dir = 260 + Remove RRU x 2_SBWMM_H_6 New Antenna (LB)_SBWMM_L_1 New Sector G (Co AAU5768) + Main Dir = 260_SBWMM_H_G New Sector H (Co AAU5768) + Main Dir = 260_SBWMM_H_H" |  | 2026-02-17 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-03-17 11:57:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCHOM_2026 Capacity Expansion Modernize_BBU_EXP_ER | Soi Chanchao | 2026-09-28 | Team: THCP_Wachira.s Tel :0657649919 | Install & Integrate |  | 2026-09-30 | 2026-09-28 | 2026-09-28 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-29 07:57:32 | No | No |  |  |  | 2026-09-30 | 2026-09-28 | 2026-09-30 | Teloneer Company Limited | N/A | Closed | 2026-09-30 11:20:25 | Yes | Yes | 2026-10-01 12:36:24 |  | 2026-09-30 | 2026-10-01 | Apichart Kampuang(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-10-01 17:03:34 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-25 17:31:42 | Yes | Yes | 2026-09-25 14:35:46 |  |  | 2026-09-30 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 20:04:55 | No | No |  |  |  |  | 2026-09-28 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-28 17:05:33 | No | No |  | SFCCM Remote RRU SFDBM Remote RRU BUSSM Remote RRU BUHPM Remote RRU BUNUM Remote RRU no external alarm |  | 2026-09-28 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-28 17:05:33 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ฝนตก , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM1B_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | Saichol Mansion | [5 empty] | 2026-08-22 | 2026-08-22 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  |  | 2026-08-08 | 2026-08-26 | 2026-08-26 | Teloneer Company Limited | N/A | Closed | 2026-08-26 14:56:44 | Yes | Yes | 2026-09-04 16:33:20 |  | 2026-09-01 | 2026-09-01 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-09-01 12:41:27 | 1.Need red mark at install BBPg3 in pg-9. 2.Delete red mark at BBPd5 in pg-9.This is not new intall. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:30:26 |  |  | 2026-08-08 | 2026-08-26 | Teloneer Company Limited | N/A | Closed | 2026-08-26 11:52:13 | No | No |  |  |  |  | 2026-08-22 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-08-22 13:50:13 | No | No |  | 22-Aug-2026 Add UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-22 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:03:37 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCM2B_2026 Capacity Expansion NW Modernization_EXP_BKK | Saichol Mansion | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:43:41 | No | No |  |  |  | 2026-09-30 | 2026-09-04 | 2026-09-05 | Teloneer Company Limited | N/A | Closed | 2026-09-05 13:32:33 | Yes | Yes | 2026-09-10 11:23:21 |  | 2026-10-03 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-24 14:29:04 | need to upload inventory page. page.16 need to upload indoor DC-RRU label clearly | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:51:33 |  |  | 2026-08-31 | 2026-08-25 | Teloneer Company Limited | N/A | Closed | 2026-08-25 20:49:53 | No | No |  |  |  |  | 2026-08-25 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-08-25 18:22:36 | No | No |  | 2026-08-25 SA Replace RRU3962 > RRU5507 (18/21 2T) Add Card UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:10:40 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCYNB_2025 Capacity Expansion NW Modernization_EXP_BKK | SACHAYAN COURT (FOR CONDO) |  |  |  |  | 2026-02-11 | 2026-03-07 | 2026-03-07 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-08 23:00:59 | No | No |  |  |  | 2026-02-21 | 2026-02-08 | 2026-03-08 | V Contribute Co., Ltd | N/A | Closed | 2026-03-08 17:49:01 | Yes | Yes | 2026-03-08 17:49:02 |  | 2026-02-19 | 2026-02-19 | Chonradee Suwapan | Approved | Closed | 2026-03-16 17:56:27 | Yes | Yes | 2026-05-19 10:17:36 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-25 | 2026-03-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-19 | 2026-02-19 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-19 22:09:16 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-05 20:56:25 | No | No |  | 2026-02-05_Replace RRU3962 to RRU5526#， Replace Ant to 4 port(NoRET) Sector A#， Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SCYNM_2025 Capacity Expansion NW Modernization_EXP_BKK | SACHAYAN COURT | 2026-01-29 |  |  |  | 2026-01-29 | 2026-01-29 | 2026-01-29 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-04-21 17:10:13 | No | No |  |  |  | 2026-02-07 | 2026-03-24 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 13:35:24 | Yes | Yes | 2026-03-24 13:35:24 |  | 2026-02-11 | 2026-02-11 | Chonradee Suwapan | Approved | Closed | 2026-03-16 17:56:27 | Yes | Yes | 2026-03-01 23:22:10 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-01 | 2026-03-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-11 | 2026-02-11 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:43:22 | Yes | Yes | 2026-02-11 19:10:13 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-01-29 | Supatong Juntorn WX1461874 | N/A | Closed | 2026-01-29 19:23:22 | No | No |  | 29-01-2026 On DMM 1#，2#，3#， and add card g3a 2 card Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SEAHM_2026 Capacity Expansion Modernize_EXP_ER | SEAH Precision Metal | 2026-06-22 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-06-30 | 2026-06-22 | 2026-06-22 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-23 15:32:53 | No | No |  |  |  | 2026-06-30 | 2026-06-23 | 2026-06-23 | Teloneer Company Limited | N/A | Closed | 2026-06-23 12:59:33 | Yes | Yes | 2026-06-24 11:09:40 |  | 2026-06-30 | 2026-06-29 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:53:25 | Yes | Yes | 2026-06-26 16:56:15 |  | Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:39:05 | No | Yes | 2026-09-12 10:40:37 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-06-30 | 2026-06-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-25 08:21:58 | Yes | Yes | 2026-06-23 09:47:32 |  | 2026-06-24 | 2026-06-30 | 2026-06-22 | Teloneer Company Limited | N/A | Closed | 2026-06-22 13:34:52 | No | No |  |  |  |  | 2026-06-22 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-22 20:38:40 | No | No |  | Replace Antenna (MB) + Replace 1RRU5505 to RRU5513 + 4T4R_SEAHM_H_A Replace Antenna (MB) + Replace 1RRU5505 to RRU5513 + 4T4R_SEAHM_H_B CO L21F2 ALL SECTOR |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-22 | Boonchot Boriwut | N/A | Closed | 2026-06-25 22:57:05 | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SECOM_2026 Capacity Expansion Ph2_EXP_ER | New Sheico Soi Wat Huai Prap |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SENFP_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | Sena Fest Community | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SESWM_2026 Capacity Expansion Ph2_EXP_ER | Sermsuwan Road |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SFCPM_2026 Capacity Expansion Modernize_EXP_ER | SoaFaiFa Pak SoiChaiyapruek | 2026-07-28 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 | 2026-07-27 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-27 22:38:40 |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SFDCM_2026 Capacity Expansion Ph1_EXP_ER | Near Siam Food Company 331 Road | 2026-07-11 | Team :thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-07-15 | 2026-07-11 | 2026-07-11 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-11 19:47:52 | No | No |  |  |  | 2026-07-20 | 2026-07-14 | 2026-07-14 | Teloneer Company Limited | N/A | Closed | 2026-07-14 19:42:50 | Yes | Yes | 2026-07-14 23:24:57 |  | 2026-07-20 | 2026-07-14 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:40 | Yes | Yes | 2026-07-14 17:54:23 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-17 10:46:48 | No | No |  |  | 2026-07-31 | 2026-07-04 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:42 | Yes | Yes | 2026-07-04 12:28:10 |  | 2026-07-13 | 2026-07-20 | 2026-07-11 | Teloneer Company Limited | N/A | Closed | 2026-07-11 10:41:53 | No | No |  |  |  |  | 2026-07-11 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-11 18:59:08 | No | No |  | New L26F5 + NR26 (New AAU5656)_SFDCM_N_1 |  | 2026-07-13 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-13 17:18:12 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SFHSM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | SoaFaiFa Paksoi Had Pattaya10 | 2026-05-26 | thcp_apichat.f | Install & Integrate |  | 2026-05-31 | 2026-05-26 | 2026-05-26 | Teloneer Company Limited | N/A | Closed | 2026-05-26 15:59:47 | No | No |  |  |  | 2026-05-31 | 2026-05-27 | 2026-05-28 | Teloneer Company Limited | N/A | Closed | 2026-05-28 15:40:34 | Yes | Yes | 2026-05-29 12:45:22 |  | 2026-05-31 | 2026-06-08 | Apichat fangsantthia(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:45:35 | Yes | Yes | 2026-06-02 19:00:44 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-05-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-05-28 08:46:34 | Yes | Yes | 2026-05-26 15:41:42 |  | 2026-05-26 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-26 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-05-27 18:04:21 | No | No |  | new site change remote RRU to remote BBU |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-05-20 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-05-25 09:17:43 | Yes | Yes | 2026-05-24 17:18:58 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SFSMM_2026 Capacity Expansion Modernize_EXP_ER | SoaFaiFa Na Sigma Hotel | 2026-08-07 | Team : Thcp_phet.sa Tel : 0924272237 |  |  | 2026-08-20 | 2026-08-07 | 2026-08-07 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-07 21:41:11 | No | No |  |  |  | 2026-08-20 | 2026-08-08 | 2026-08-10 | Teloneer Company Limited | N/A | Closed | 2026-08-10 17:14:22 | Yes | Yes | 2026-08-12 11:54:10 |  | 2026-08-20 | 2026-08-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-28 23:21:34 | Yes | Yes | 2026-08-24 21:41:19 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:23 | No | No |  |  | 2026-08-20 | 2026-08-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:04:40 | Yes | Yes | 2026-08-08 07:53:42 |  |  | 2026-08-20 | 2026-08-06 | Teloneer Company Limited | N/A | Closed | 2026-08-06 17:31:35 | No | No |  |  |  |  | 2026-08-07 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-07 19:45:27 | No | No |  | Change Remote RRU to Remote BBU + Add RRU5505 x 1 + 4T4R_SFSMM_H_A Add RRU5505 x 1 + 4T4R_SFSMM_H_B Add RRU5505 x 1 + 4T4R_SFSMM_H_C Co BBU_SFSMM_N_A Co BBU_SFSMM_N_B Co BBU_SFSMM_N_C ** set mnt and need to fix power too low slot 6/1 (umpt) on tomorrow -- fix alarm done (20260807) |  | 2026-08-06 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-06 20:08:59 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 100% , Day2 : Clear alarm | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SFTPM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | SoaFaiFa Na Tourist Police4 | 2026-05-27 | thcp_apichat.f | Install & Integrate |  | 2026-05-31 | 2026-05-27 | 2026-05-27 | Teloneer Company Limited | N/A | Closed | 2026-05-27 12:12:49 | No | No |  |  |  | 2026-05-31 | 2026-05-28 | 2026-05-29 | Teloneer Company Limited | N/A | Closed | 2026-05-29 17:50:00 | Yes | Yes | 2026-06-08 11:22:23 |  | 2026-05-31 | 2026-06-08 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:45:35 | Yes | Yes | 2026-06-08 17:34:59 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-05-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-05-28 08:46:34 | Yes | Yes | 2026-05-26 13:51:51 |  | 2026-05-27 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-27 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-05-27 18:05:03 | No | No |  | new site change remote RRU to remote BBU |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-05-20 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-05-25 09:17:43 | Yes | Yes | 2026-05-24 17:19:19 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHKVB_2025 Capacity Expansion NW Modernization_EXP_BKK | SMALL CELL SHAMA SUKHUMVIT HOTEL |  |  |  |  | 2026-03-10 | 2026-03-10 | 2026-03-10 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:09:22 | No | No |  |  |  | 2026-02-28 | 2026-02-19 | 2026-03-08 | V Contribute Co., Ltd | N/A | Closed | 2026-03-08 17:42:53 | Yes | Yes | 2026-03-08 17:42:53 |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-05-25 16:00:25 | Yes | Yes | 2026-03-14 22:13:25 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-05-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-14 | 2026-03-14 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-14 22:28:03 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-18 17:48:09 | No | No |  | 18-02-2026. เปลี่ยน Combiner แก้ VSWR Config to 4T4R Sec.A#， C //17-02-2026. Replace RRU3962 to RRU5526 Sec.A#， B#， C |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SHSSM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | SoaFaiFa Paksoi Had Pattaya12 | 2026-05-28 | thcp_anat.sri | Clear Pending |  | 2026-05-31 | 2026-05-27 | 2026-05-27 | Teloneer Company Limited | N/A | Closed | 2026-05-27 18:28:04 | No | No |  |  |  | 2026-05-31 | 2026-05-28 | 2026-05-29 | Teloneer Company Limited | N/A | Closed | 2026-05-29 11:47:47 | Yes | Yes | 2026-05-29 12:45:26 |  | 2026-05-31 | 2026-06-10 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:45:35 | Yes | Yes | 2026-06-08 10:55:21 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-05-28 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-05-29 18:48:20 | Yes | Yes | 2026-05-28 14:52:23 |  | 2026-05-27 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-27 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-05-27 18:05:03 | No | No |  | new site change remote RRU to remote BBU |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-05-20 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-05-25 09:17:43 | Yes | Yes | 2026-05-24 17:19:53 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SIBTM_2026 Capacity Expansion Ph2_EXP_ER | Moo4 Ban Takiantia |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SIHCP_L1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | Singha Complex | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-08 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-07-27 13:54:35 |  |  | 2026-08-08 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SIHCP_L2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | Singha Complex | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-08 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-07-27 13:54:54 |  |  | 2026-08-08 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SIHCP_L3_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | Singha Complex | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-08 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-07-27 13:55:17 |  |  | 2026-08-08 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SK33M_2025 Capacity Expansion Ph8_EXP_BKK | SUKHUMWIT SOI 33 | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-13 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-13 10:19:28 | Yes | Yes | 2026-02-13 11:27:26 |  | 2026-02-13 | 2026-02-13 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-03-23 16:15:41 | Yes | Yes | 2026-03-07 12:25:11 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-24 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-01-29 | 2026-01-29 | Pariyakorn Jearwarakul | Approved | Closed | 2026-07-20 10:36:04 | Yes | Yes | 2026-03-25 15:52:56 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-09 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-09 18:25:38 | No | No |  | 09-02-26 Add AAU5636w S6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKBTM_2026 Capacity Expansion Modernize_EXP_ER | Sukkhabot | 2026-08-13 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-08-20 | 2026-08-13 | 2026-08-13 | Teloneer Company Limited | N/A | Closed | 2026-08-13 17:37:42 | No | No |  |  |  | 2026-08-20 | 2026-08-15 | 2026-08-16 | Teloneer Company Limited | N/A | Closed | 2026-08-16 20:06:28 | Yes | Yes | 2026-08-19 23:40:23 |  | 2026-08-20 | 2026-08-19 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:43:43 | Yes | Yes | 2026-09-04 20:45:15 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:31 | No | No |  |  | 2026-08-15 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 18:02:50 |  |  | 2026-08-20 | 2026-08-13 | Teloneer Company Limited | N/A | Closed | 2026-08-13 16:32:19 | No | No |  |  |  |  | 2026-08-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-13 18:22:28 | No | No |  | Add UBBPh2a + Replace UBBPd5 to UBBPg1_SKBTM Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_SKBTM_H_6 Add RRU5505 x 1 + 4T4R_SKBTM_H_7 Replace RRU5508 to (RRU5516_900) + Co NR07 + 4T4R_SKBTM_L_2 |  | 2026-08-13 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-13 18:22:56 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKHNM_2026 Capacity Expansion Ph1_EXP_SR | Ban Sakom Hua non | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-30 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-29 | 2026-08-31 | 2026-09-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-05 10:42:27 | No | No |  |  |  |  | 2026-08-29 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-29 19:12:10 | No | No |  | Rep eb*1 to h3a*1 S1 > MB remove ANT 4*4 +RRU5505x2 Re LB S3 > S1 (final 5508*2/5516LB) Re MB S3>S8#， S1>S6 S3 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKKYM_2026 Capacity Expansion Ph2_EXP_ER | Soi Khao Kayai |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKN4M_2026 Capacity Expansion Ph2_BKK | SURAO KHLONG NUENG SOI 4 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKRKM_2026 Capacity Expansion Modernize_EXP_ER | Soi Khiri Nakhon | 2026-08-01 | Team : thcp_jaran.s Tel : 0988500996 | Install & Integrate |  | 2026-08-15 | 2026-08-01 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 20:19:39 | No | No |  |  |  | 2026-08-15 | 2026-08-04 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 11:43:16 | Yes | Yes | 2026-08-06 10:47:53 |  | 2026-08-20 | 2026-08-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:54:09 | Yes | Yes | 2026-08-09 15:05:46 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:09 | No | No |  |  | 2026-08-15 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-06 11:37:47 | Yes | Yes | 2026-08-06 09:27:09 |  |  | 2026-08-15 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 14:01:39 | No | No |  |  |  |  | 2026-08-01 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-01 14:33:21 | No | No |  | Add RRU5505 x 1 + 4T4R_SKRKM_H_3 Co L21F2 All sector |  | 2026-08-03 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-03 17:32:32 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKROM_2026 Capacity Expansion Ph2_BKK | SI KHAO RD. | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SKV1M_2025 Capacity Expansion Ph8_EXP_BKK | SUKHUMVIT SOI 1 | [5 empty] | 2026-02-23 | 2026-02-23 | Narongsak wanichachiwa | N/A | Closed | 2026-02-23 16:08:47 | No | No |  |  |  | 2026-02-12 | 2026-02-12 | 2026-02-16 | Turnkey Communication Services Public Company Limited. | N/A | Closed | 2026-02-16 10:15:13 | Yes | Yes | 2026-02-16 10:17:46 |  | 2026-02-13 | 2026-02-13 | Turnkey Communication Services Public Company Limited. | Approved | Closed | 2026-02-17 16:38:08 | Yes | Yes | 2026-03-05 16:19:06 | PAT Pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-23 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:58 | Yes | Yes | 2026-04-09 13:23:05 |  | 2026-01-26 | 2026-01-26 | Pariyakorn Jearwarakul | Approved | Closed | 2026-07-20 10:36:04 | Yes | Yes | 2026-03-25 15:45:23 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-07 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-02-07 18:36:19 | No | No |  | 07-02-2026. Add UBBPg3a#， AAU5636w Sec.7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SLA2M_2026 Capacity Expansion Ph2_BKK | SAI LUAT RD. STAION 2 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SLDSM_2025 Capacity Expansion NW Modernization_EXP_BKK | SCIENCE LIBRARY - DEPARTMENT OF SCIENCE SERVICE |  |  |  | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-23 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-04-23 14:58:26 | No | No |  |  | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-27 10:28:12 | Yes | Yes | 2026-05-19 11:33:16 |  | 2026-06-24 | 2026-06-24 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-06-24 15:44:01 | Page no.6#， in SOW S1 Remove antenna 1pc model must be MB3F-65-18DE10-TA. (not MB3F-65-18DE10-TH). Add antenna unit must be sets (not sector). | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-07-14 22:57:04 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-21 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-04-21 17:02:10 | No | No |  | 2026-04-21_Replace RRU5508 to RRU5516(LB) Sector 1#，2#， Add RRU5507 Sector 1#， Replace Ant to 8 port Sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SLLSD_2026 Capacity Expansion Ph1_EXP_SR | Soi Loi Luean Sadao | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-14 | 2026-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-18 13:30:55 | Yes | Yes | 2026-08-21 02:00:55 |  | 2026-08-23 | 2026-08-27 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-27 13:39:16 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-08-23 | 2026-08-23 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-23 02:14:49 |  | 2026-08-13 | 2026-08-31 | 2026-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-13 17:54:56 | No | No |  |  |  |  | 2026-08-13 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-13 17:59:57 | No | No |  | 13 Aug 2026 Add RRU5516 sector1 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SLRSM_2026 Capacity Expansion Ph2_EXP_ER | Sealey Resort Koh Larn |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMANT_2025 Coverage Expansion (Co NT)_New_SR | Samui International Airport_Co-NT | [5 empty] | 2026-05-13 | 2026-05-13 | Teloneer Company Limited | N/A | Closed | 2026-05-15 12:15:02 | No | No |  |  | 2026-04-09 | 2026-04-10 | 2026-04-09 | 2026-04-10 | Teloneer Company Limited | N/A | Closed | 2026-04-10 11:07:13 | Yes | Yes | 2026-04-17 14:30:06 |  | 2026-05-13 | 2026-05-13 | Nattawoot Suwan | Approved | Closed | 2026-05-31 21:45:31 | Yes | Yes | 2026-05-18 08:57:43 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 2026-05-27 | Jutatip Tiprean 84012709 | Ready To Approve | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-04-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-04-09 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-04-09 18:35:07 | No | No |  | BBU3910#，UBBPd5*4 S1 > RRU5516MB > Ant 4 port S2 > RRU5516MB > Ant 4 port S3 > RRU5516MB > Ant 4 port test done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | 2026-06-05 | Nattawoot Suwan | N/A | Closed | 2026-06-05 10:35:10 | No | No
SMATM_2026 Capacity Expansion Modernize_EXP_ER | Siam AT Industrial |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-15 | 2026-09-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-16 21:51:05 | Yes | Yes | 2026-09-16 12:01:53 |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMBLM_2026 Capacity Expansion Ph2_BKK | SOI MOOBAAN BUALUANG | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMHKW_2026 Capacity Expansion Ph1_EXP_SR | Samnaksong Huai Kaeo | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-04 | 2026-09-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-28 20:13:33 | Yes | Yes | 2026-09-28 20:16:40 | 1.Install and dis breaker not found#，pls show with red mark. 2.Need to delete extra dis breaker at equipment checklist. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-07 | 2026-08-31 | 2026-09-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-04 20:03:58 | No | No |  |  |  |  | 2026-09-04 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-04 17:55:38 | No | No |  | add g3a*1 S1 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMPAM_2026 Capacity Expansion Ph2_BKK | SAMAN MIT PHATTHANA RD. | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMPNG_2026 Capacity Expansion Ph1_EXP_SR | Sam Pang | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-14 | 2026-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-15 20:48:22 | Yes | Yes | 2026-08-17 16:18:35 |  | 2026-08-18 | 2026-08-20 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-20 12:10:19 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-18 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-18 15:18:10 |  | 2026-08-14 | 2026-08-31 | 2026-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-15 09:46:23 | No | No |  |  |  |  | 2026-08-14 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-14 17:58:26 | No | No |  | Rep Card UBBPeb*1 to UBBPh2a*1 Rep Ant MB S2 S2 > Rep RRU3953*2 to RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SMR1M_2026 Capacity Expansion Ph1_EXP_BKK | SOI SOR MANEERATH1 THEPHARAK 1 | [5 empty] | 2026-07-08 | 2026-07-08 | Thossapan Chaloemrit | N/A | Closed | 2026-07-08 08:50:21 | No | No |  |  |  | 2026-07-31 | 2026-07-08 | 2026-07-08 | Teloneer Company Limited | N/A | Closed | 2026-07-08 18:12:03 | Yes | Yes | 2026-07-13 09:02:35 |  | 2026-07-13 | 2026-07-21 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 12:52:07 | Need red mark at install BBP in pg-20. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-09 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-07-09 10:29:25 |  |  | 2026-06-30 | 2026-07-06 | Teloneer Company Limited | N/A | Closed | 2026-07-06 20:56:33 | No | No |  |  |  |  | 2026-07-06 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-07-06 18:12:23 | No | No |  | 06-07-2026. Add AAU5656 Sec.2#， Replace UBBPg3 to UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-09 | Teloneer Company Limited | N/A | Closed | 2026-07-09 10:14:19 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SNDPS_2026 Capacity Expansion Ph1_EXP_SR | Soi Na Dapphloeng Singhanakhon | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-19 | 2026-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-20 20:50:45 | Yes | Yes | 2026-08-26 17:14:38 |  | 2026-08-30 | 2026-08-30 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-30 15:32:59 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:22 | No | No |  |  | 2026-08-30 | 2026-08-30 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-30 15:34:14 |  | 2026-08-19 | 2026-08-31 | 2026-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-19 16:48:59 | No | No |  |  |  |  | 2026-08-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-19 18:30:56 | No | No |  | Add UBBPh2a*1 Rep Ant MB S2 S2 > RRU5516*1 > Ant Combine S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SNIWM_2026 Capacity Expansion Ph2_BKK | MUBAN SIAM NIWET | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SNNCM_2026 Capacity Expansion Ph2_EXP_ER | Suan Nongnuch Car park |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPAJB_2026 Capacity Expansion NW Modernization_EXP_SR | Soi Prajuab | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-09-05 | 2026-08-24 | 2026-08-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-26 20:46:49 | Yes | Yes | 2026-09-04 09:22:15 |  | 2026-09-07 | 2026-09-07 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-09-07 07:50:18 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-07 | 2026-09-07 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-09-07 07:51:38 |  | 2026-08-23 | 2026-08-31 | 2026-08-23 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-23 23:21:00 | No | No |  |  |  |  | 2026-08-23 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-23 18:12:01 | No | No |  | S2 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S3 > Rep RRU3826*2 to RRU3962*1 > Ex Ant S4 > Rep RRU3826*2 to RRU3962*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPBBM_2026 Capacity Expansion Ph2_BKK | SUKHAPIBAN BANGBON | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPGKM_2026 Capacity Expansion Ph2_EXP_ER | Soi Pong Saket |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPGTM_2026 Capacity Expansion Modernize_EXP_ER | Sattapong Tai | 2026-06-18 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-06-30 | 2026-06-18 | 2026-06-18 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-18 19:25:37 | No | No |  |  |  | 2026-06-30 | 2026-06-18 | 2026-06-19 | Teloneer Company Limited | N/A | Closed | 2026-06-19 16:35:11 | Yes | Yes | 2026-06-24 14:03:08 |  | 2026-06-30 | 2026-06-25 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-28 22:14:43 | Yes | Yes | 2026-06-25 15:30:37 |  | Pass |  | 2026-08-19 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-19 16:15:21 | No | Yes | 2026-08-19 16:15:03 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-16 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-16 16:50:00 | No | No |  |  | 2026-06-30 | 2026-06-17 | Palagon Prommueangma(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:11:17 | Yes | Yes | 2026-06-19 09:44:50 |  | 2026-06-19 | 2026-06-30 | 2026-06-18 | Teloneer Company Limited | N/A | Closed | 2026-06-18 14:08:53 | No | No |  |  |  |  | 2026-06-18 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-18 19:34:06 | No | No |  | Replae UBBPg3 to UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 320 + Remove RRU5505 x 2_SPGTM_H_1 (Co AAU5775) + Main Dir = 320 + Remove RRU5505 x 2_SPGTM_H_6 New Sector G (Co AAU5775) + Main Dir = 320_SPGTM_H_G New Sector H (Co AAU5775) + Main Dir = 320_SPGTM_H_H Co L21F2 all sector |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-20 | Nattawoot Suwan | N/A | Closed | 2026-06-20 11:07:58 | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPGTM_2026 Capacity Expansion Ph2_EXP_ER | Sattapong Tai |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPKPM_2026 Capacity Expansion Ph2_BKK | SAMUT PRAKAN CENTRAL PRISON | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPKWA_2025 Capacity Expansion NW Modernization_EXP_BKK | SAPHANKWAI SMALL CELL |  |  |  | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-06-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-26 18:54:47 | No | No |  |  | 2026-06-25 | 2026-06-25 | 2026-06-27 | 2026-06-29 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-29 14:20:11 | Yes | Yes | 2026-07-06 08:34:15 |  | 2026-07-17 | 2026-07-17 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-07-20 09:20:54 | Yes | Yes | 2026-07-17 15:21:13 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-07-20 10:36:04 | Yes | Yes | 2026-07-14 22:57:30 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-06-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-06-19 19:05:35 | No | No |  | 19-Jun-2026 Replace Ant 12port *2 No RET |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPOCM_2026 Capacity Expansion Modernize_EXP_ER | Soi Posayanon Chonburi | 2026-08-06 | Team : thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-08-20 | 2026-08-06 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-07 08:46:35 | No | No |  |  |  | 2026-08-20 | 2026-08-07 | 2026-08-14 | Teloneer Company Limited | N/A | Closed | 2026-08-14 16:18:59 | Yes | Yes | 2026-08-19 21:57:10 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:43:43 | Yes | Yes | 2026-09-04 20:30:58 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:31 | No | No |  |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:22 | Yes | Yes | 2026-08-12 17:07:03 |  |  | 2026-08-20 | 2026-08-06 | Teloneer Company Limited | N/A | Closed | 2026-08-06 14:49:03 | No | No |  |  |  |  | 2026-08-06 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-06 20:08:36 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_SPOCM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_SPOCM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_SPOCM_H_3 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_SPOCM_H_4 Co L21F2 all sector |  | 2026-08-07 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-07 19:31:01 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPPNM_2026 Capacity Expansion Ph1_EXP_SR | Sam Yaek PhunPhin | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-13 | 2026-08-31 | 2026-09-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-21 21:28:23 | No | No |  |  |  |  | 2026-09-13 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-13 18:04:35 | No | No |  | S1 MB remove ANT+RRU5505x1 Re MB S3&8 > S1&S6 S3 > AAU5775 *Pending add cell UL1800/2100 S6 *Pending S1 MB remove ANT+RRU5505x1 Re MB S3&8 > S1&S6 S3 > AAU5775 ---------------------- 12 Sep 2026 Rep Card d6*1 to h3a*1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPROM_2025 Capacity Expansion Ph5_EXP_ER_Add | Star Petroleum Refining Company Limited , Plant Operation | 2026-03-09 | Thcp_phet.sa | Cancel |  | 2026-02-28 | 2026-05-22 | 2026-05-22 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-05-22 17:58:19 | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2026-02-28 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-03-31 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPRYM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | Soi Thap Praya 9 | 2026-05-29 | THCP_Wachira.s | Clear Pending |  | 2026-05-31 | 2026-05-26 | 2026-05-26 | Teloneer Company Limited | N/A | Closed | 2026-05-26 13:37:25 | No | No |  |  |  | 2026-05-31 | 2026-05-27 | 2026-05-29 | Teloneer Company Limited | N/A | Closed | 2026-05-29 11:22:56 | Yes | Yes | 2026-05-29 12:46:47 |  | 2026-05-31 | 2026-06-08 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:45:35 | Yes | Yes | 2026-06-08 11:00:09 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-05-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-05-28 08:46:34 | Yes | Yes | 2026-05-24 16:03:07 |  | 2026-05-29 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-29 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-05-29 15:49:13 | No | No |  | new site UL21/L18 S1#，2#，3 3RRU5505 |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-05-08 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-05-18 18:11:22 | Yes | Yes | 2026-05-18 11:34:26 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPSNM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI PHERM SIN |  |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:45:35 | No | No |  |  |  | 2026-02-28 | 2026-03-25 | 2026-03-25 | V Contribute Co., Ltd | N/A | Closed | 2026-03-25 15:34:27 | Yes | Yes | 2026-03-25 15:34:27 |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-03-26 11:17:24 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-24 21:46:50 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-20 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-02-20 18:47:26 | No | No |  | 2026-02-20_Replace RRU3962(4) to AAU5768 Sector 1#，6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPT1M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI PHANIT THONBURI 1 | [5 empty] | 2026-09-28 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-29 13:25:23 | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-19 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-08-19 15:13:02 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:29:53 |  |  | 2026-06-30 | 2026-09-29 | Teloneer Company Limited | N/A | Closed | 2026-09-29 09:50:26 | No | No |  |  |  |  | 2026-09-28 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-28 16:48:14 | No | No |  | 2026-09-28_Replace UBBPd5 to UBBPh3a S1 Add RRU3953#， Replace to Ant BZ44G651618 S2 Replace RRU5508 to RRU5516(LB)#， Add SFP 25G + CRPI + Replace to Ant BZ44G651618 S3 Replace RRU5508 to RRU5516(LB)#， Replace RRU3962 to AAU5726 S6 Remove RRU5507*2 S7 Remove RRU3826 S8 Remove RRU3962 pre work |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SPT1M_2026 Capacity Expansion Ph2_BKK | SOI PANICHTHON 1 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SRRYM_2026 Capacity Expansion Ph2_EXP_ER | Soonratchakarn Rayong | 2026-09-23 | Team : thcp_jaran.s Tel : 0988500996 | Install & Integrate |  | 2026-09-30 | 2026-09-23 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-24 07:39:09 | No | No |  |  |  | 2026-09-30 | 2026-09-24 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 11:51:18 | Yes | Yes | 2026-09-27 11:55:13 | 1.Need to upload AAU ground cable in S1 at after 2.Photo wrong | 2026-09-30 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-30 23:49:15 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-23 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-25 17:31:42 | Yes | Yes | 2026-09-23 10:26:14 |  |  | 2026-09-30 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 15:40:53 | No | No |  |  |  |  | 2026-09-23 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-23 16:44:30 | No | No |  | Add UBBPh3a Remove Antenna + (New AAU5775) + Main Dir = 0 + Remove RRU x 1_SRRYM_H_1 New Sector 6 (Co AAU5775) + Main Dir = 0_SRRYM_H_6 New Sector G (Co AAU5775) + Main Dir = 0_SRRYM_H_G New Sector H (Co AAU5775) + Main Dir = 0_SRRYM_H_H ReSectorname S6 to S7_SRRYM_H_7 |  | 2026-09-23 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-23 16:44:30 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SS43M_2026 Capacity Expansion Ph2_BKK | SOI SUKSAWAT43 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SS99M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI SUKHUMVIT 99 | [5 empty] | 2026-07-07 | 2026-07-07 | Thossapan Chaloemrit | N/A | Closed | 2026-07-08 08:50:21 | No | No |  |  |  | 2026-08-31 | 2026-07-09 | 2026-07-11 | Teloneer Company Limited | N/A | Closed | 2026-07-11 17:52:07 | Yes | Yes | 2026-07-13 09:02:59 |  | 2026-07-15 | 2026-07-23 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 12:52:34 | Page 5 Need to fill Add antenna and Need to fill remark. page 6#，7 Need to fil site name . Page 32 Need to Upload photo DC-RRU. | Not Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-08-19 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-08-19 15:13:02 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-09 | Teloneer Company Limited | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-07-09 10:29:51 |  |  | 2026-06-30 | 2026-07-04 | Teloneer Company Limited | N/A | Closed | 2026-07-04 19:50:16 | No | No |  |  |  |  | 2026-07-04 | Autumporn Masing WX1434753 | N/A | Closed | 2026-07-04 17:09:58 | No | No |  | 2026-07-04 S1#，S2#，S3 Rep ant Done -config RET S2#，S3 700/900 -S1 ADD RRU07/09*1 -S2 REP RRU3953 to RRU5516*1 -S3 REP RRU3953 to RRU5516*1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-04 | Teloneer Company Limited | N/A | Closed | 2026-07-14 13:30:41 | No | No |  |  | SQC closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSD4M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI SAWADEE 4 | [5 empty] | 2026-09-15 | 2026-09-15 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:31:13 |  |  | 2026-06-30 | 2026-09-21 | Teloneer Company Limited | N/A | Closed | 2026-09-21 11:53:11 | No | No |  |  |  |  | 2026-09-15 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-09-15 17:37:14 | No | No |  | 20260921 **Clear work 2026-09-15 s1#，s2#，s3 add RRU3953 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-15 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:24:42 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSGKM_2026 Capacity Expansion Ph2_EXP_ER | SamnakSong Saisukhon |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSIAA_2026 Capacity Expansion Ph1_EXP_BKK | Small Cell Sai Mai School (Thatsanarom Anusorn) |  |  |  | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-20 20:37:16 | No | No |  |  | 2026-07-31 | 2026-07-31 | 2026-07-18 | 2026-07-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-18 20:47:15 | Yes | Yes | 2026-07-23 09:26:45 |  | 2026-08-04 | 2026-08-04 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approving | Assigned |  | Yes | Yes | 2026-08-04 14:44:38 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 21:54:58 |  |  | 2026-07-31 | 2026-07-14 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-14 20:22:52 | No | No |  |  |  |  | 2026-07-14 | Autumporn Masing WX1434753 | N/A | Closed | 2026-07-14 18:07:09 | No | No |  | 2026-07-14 S1#，S2 ADD AAU5636w REP BBU to 5900 add gps add g2/g3a // rmv d5*2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSKSM_2026 Capacity Expansion Modernize_EXP_ER | Soi Sang Ka Sri | 2026-08-12 |  |  |  | 2026-08-20 | 2026-08-12 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 18:06:16 | No | No |  |  |  | 2026-08-20 | 2026-08-14 | 2026-08-17 | Teloneer Company Limited | N/A | Closed | 2026-08-17 13:21:15 | Yes | Yes | 2026-08-21 10:33:08 |  | 2026-08-20 | 2026-08-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-28 23:20:17 | Yes | Yes | 2026-08-26 14:46:22 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-15 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 14:26:23 |  |  | 2026-08-20 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 19:27:18 | No | No |  |  |  |  | 2026-08-12 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-12 16:07:41 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_SSKSM_H_2 Replace Antenna (LB) + Replace RRU5516_900 + Co L07 + NR07 + 4T4R_SSKSM_L_2 Replace RRU (RRU5516_900) + 4T4R_SSKSM_L_4 Co L21F2 All Sector |  | 2026-08-13 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-13 17:40:44 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSPPN_2026 Capacity Expansion Ph1_EXP_SR | Soi Suan Pa Pha-ngan | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-24 | 2026-09-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-29 16:03:26 | Yes | Yes | 2026-09-29 16:10:26 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 |  | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | N/A | Assigned |  | Yes | No |  |  | 2026-09-24 | 2026-08-31 | 2026-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-24 18:33:01 | No | No |  |  |  |  | 2026-09-24 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-24 18:34:35 | No | No |  | 24 Sep 2026 Add DMM AAU5775 sector1 add1UBBPh3 re |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSRTM_2026 Capacity Expansion Ph2_BKK | WAT SANGSIRITHAM THA IT | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSSLM_2026 Capacity Expansion Ph2_EXP_ER | Soi Sao Sung Alai |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSSNM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | Soi Sibsam Tub Nung | 2026-05-28 | THCP_Wachira.s | Install & Integrate |  | 2026-05-31 | 2026-05-28 | 2026-05-28 | Teloneer Company Limited | N/A | Closed | 2026-05-28 14:34:13 | No | No |  |  |  | 2026-05-31 | 2026-05-29 | 2026-06-03 | Teloneer Company Limited | N/A | Closed | 2026-06-03 16:22:02 | Yes | Yes | 2026-06-10 15:11:40 |  | 2026-05-31 | 2026-06-10 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:15:41 | Yes | Yes | 2026-06-10 17:14:11 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-05-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-05-28 08:46:34 | Yes | Yes | 2026-05-26 13:52:14 |  | 2026-05-28 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-28 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-05-28 18:55:47 | No | No |  | new site change remote RRU to remote BBU |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-05-20 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-05-25 09:17:43 | Yes | Yes | 2026-05-24 17:20:22 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSTPM_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SAENG THIP |  |  |  |  | 2026-03-24 | 2026-03-24 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-02-21 | 2026-03-21 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:40:50 | Yes | Yes | 2026-03-23 15:40:51 |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-05-11 16:12:29 | Yes | Yes | 2026-05-19 17:38:52 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-08 | 2026-05-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-02-18 | 2026-02-18 | Chonradee Suwapan | Approved | Closed | 2026-02-25 20:42:19 | Yes | Yes | 2026-02-18 22:56:32 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-05 19:48:28 | No | No |  | 5 Feb 2026 Add AAU5768 sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SSWNH_2026 Capacity Expansion Ph1_EXP_SR | Soi Suwannahong | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-07-31 | 2026-07-26 | 2026-08-05 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-05 17:59:52 | Yes | Yes | 2026-08-06 22:28:42 |  | 2026-08-17 | 2026-08-27 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-02 13:10:28 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-08-17 | 2026-08-17 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-17 13:17:43 |  | 2026-07-26 | 2026-08-31 | 2026-07-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-26 18:30:45 | No | No |  |  |  |  | 2026-07-26 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-26 18:08:13 | No | No |  | Rep UBBPd6*1 to UBBPh2a*1 S2 MB > Rep Ant to 8 Port S2 > Rep RRU&Ant 3953*1 to 5516LB > Ant Co MB S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STAWM_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI SAENG TAWAN | [5 empty] | 2026-08-18 | 2026-08-18 | Thossapan Chaloemrit | N/A | Closed | 2026-08-18 00:14:15 | No | No |  |  |  | 2026-08-31 | 2026-08-19 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-21 20:27:38 | Yes | Yes | 2026-08-24 11:03:32 |  | 2026-08-25 | 2026-08-25 | Teloneer Company Limited | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-25 16:47:23 | 1.Wrong site name in pg-5#，6#，7#，8#，9#，10#，55. 2.Need yellow colour in install AAU5775 INV.(pg-6) 3.Revise remove filter unit in pg-9. 4.Need After: RRU 2nd: SN no. in pg-31. 5.Wrong After: RRU 2nd: SN no. in pg-32. 6.Mismatch RRU qty in RQ checklist and INV file in pg-6. 7.Need to see clearly new install RRU SN at S3 in pg-33. 8.Need red at install BBU#，BBPg3#，BBPh3a in pg-34. 9.Need BBPg3 SN in pg-35. 10.Need RRU1 socket right side and RRU2 socket left and right side photos in pg-37. 11.Need RRU2 socket left and right side photos in pg-39. 12.Need RRU 2pcs of S3 photos completely in pg-41#，42. 13.Wrong After: Position: UPEU #， Slot 18#， 19 in pg-46. 14.Need to see clearly After : Rectifier View Photo C2 in pg-47. 15.Need red mark at change breaker in pg-50. 16.Need red mark at install DCDU 2pcs in pg-51. 17.Need Mounting Dismantle photo in pg-58. 18.Need BBP SN in pg-59. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-27 10:29:29 |  |  | 2026-06-30 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 17:50:36 | No | No |  |  |  |  | 2026-08-01 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-08-01 12:17:22 | No | No |  | 01-08-2026. Replace RRU3962 to RRU5507 Sec.1#， 2#， to AAU5775 Sec.3#， RRU3953 to RRU5516 Sec.1#， 2#， 3 #， Ant.8 port Sec.1#， 2 30-Jul-2026 *** Pending DMM ///Add UBBPh3a g3 RMV d5 =2 Done 29-Jul-26 install only |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-18 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:00:10 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STGGV_2026 Capacity Expansion Ph1_EXP_SR | Sri Trang Gloves | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-31 | 2026-08-01 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-01 17:51:36 | Yes | Yes | 2026-08-10 10:58:38 |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-11 02:00:35 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:22 | No | No |  |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-11 01:20:36 |  | 2026-07-31 | 2026-08-31 | 2026-07-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-31 14:02:17 | No | No |  |  |  |  | 2026-07-31 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-07-31 17:28:56 | No | No |  | 31 July 2026 Add RRU5516 sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STMLM_2026 Capacity Expansion Modernize_EXP_ER | Soi Moo Ban Thamrong Nong Tamlueng | 2026-08-17 | Team : thcp_pooriwat.k Tel : 0925094222 | Install & Integrate |  | 2026-08-20 | 2026-08-17 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-08-18 08:59:40 | No | No |  |  |  | 2026-08-20 | 2026-08-18 | 2026-08-19 | Teloneer Company Limited | N/A | Closed | 2026-08-19 20:56:22 | Yes | Yes | 2026-08-24 20:44:52 |  | 2026-08-20 | 2026-08-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:46:54 | Yes | Yes | 2026-08-30 12:12:51 |  | Pass |  |  | ABC THAI COMPANY LIMITED | N/A | Not assigned |  | No | No |  |  |  |  | ABC THAI COMPANY LIMITED | N/A | Not assigned |  | No | No |  |  |  | 2026-09-11 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-18 16:56:59 | No | No |  |  | 2026-08-20 | 2026-08-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-18 09:06:05 |  |  | 2026-08-20 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-17 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-17 12:53:51 | No | No |  | Add UBBPg3a + Replace RRU RRU5505 x 2 + 4T4R_STMLM_H_1 Replace RRU RRU5505 x 2 + 4T4R_STMLM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_STMLM_H_3 Add RRU5508 x 1 + Co NR07 + 4T4R_STMLM_L_1 Co L21F2 All Sector |  | 2026-08-18 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-18 16:23:27 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STN3M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SOM PRATTANA YAK 3 |  |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:45:35 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:18:01 | Yes | Yes | 2026-03-23 15:18:02 |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-04-30 13:43:18 | Yes | Yes | 2026-03-24 21:32:38 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-24 21:49:36 |  | 2026-02-19 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-19 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-19 17:09:54 | No | No |  | 19-Feb-26 Replace AAU5768 DMM S2 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STRXM_2025 Capacity Expansion NW Modernization_EXP_BKK | SITHARA PLACE |  |  |  |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 08:45:35 | No | No |  |  |  | 2026-02-28 | 2026-03-23 | 2026-03-24 | V Contribute Co., Ltd | N/A | Closed | 2026-03-24 11:25:10 | Yes | Yes | 2026-03-24 11:25:10 |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-04-29 10:30:22 | Yes | Yes | 2026-04-02 13:53:44 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-24 | 2026-03-24 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-24 21:50:13 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-19 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-19 17:54:56 | No | No |  | 19-Feb-26 Add AAU5768 S2 S3 Remove RRU5526 *1 RRU3962 *3 Add g3a Remove eb |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
STSGM_2025 Coverage Expansion Ph1_New Site_Remote-BBU_ER | Soi Sibsam Tub Song | 2026-05-28 |  | Install & Integrate |  | 2026-05-31 | 2026-05-28 | 2026-05-28 | Teloneer Company Limited | N/A | Closed | 2026-05-28 18:57:06 | No | No |  |  |  | 2026-05-31 | 2026-05-29 | 2026-06-02 | Teloneer Company Limited | N/A | Closed | 2026-06-02 15:56:17 | Yes | Yes | 2026-06-04 18:02:30 |  | 2026-05-31 | 2026-06-11 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:57:06 | Yes | Yes | 2026-06-11 10:25:55 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-18 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-05-31 | 2026-06-14 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:37:15 | Yes | Yes | 2026-05-28 16:47:22 |  | 2026-05-28 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-05-28 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-05-28 18:55:47 | No | No |  | new site change remote RRU to remote BBU |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-05-20 | Angsana Jituafua WX1434741 | Approved | Closed | 2026-05-25 09:17:43 | Yes | Yes | 2026-05-24 17:20:41 |  |  |  |  | N/A | Not assigned |  | No | No |  |  |  | Day1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUKSB_2026 Capacity Expansion Ph1_EXP_SR | Suk Sabai Maenchan | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-14 | 2026-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-15 16:42:37 | Yes | Yes | 2026-08-23 10:12:51 |  | 2026-08-23 | 2026-08-23 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-28 12:45:33 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-07-31 | 2026-08-23 | Aomchun Jittreemit(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-23 23:07:08 |  | 2026-08-04 | 2026-08-31 | 2026-08-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-04 20:19:12 | No | No |  |  |  |  | 2026-08-04 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-04 18:00:01 | No | No |  | Rep Card UBBPeb*1 to UBBPh2a*1 Rep Ant MB S1 to Ant 8 Port S1 > RRU5516LB*1 > Ant Combine S1 MB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNGM_2025 Capacity Expansion Ph8_EXP_ER | Ban Hang Sung | 2026-05-06 |  | Clear Pending |  | 2026-02-28 | 2026-02-04 | 2026-02-04 | Teloneer Company Limited | N/A | Closed | 2026-02-04 11:58:36 | No | No |  |  |  | 2026-02-28 | 2026-02-05 | 2026-02-11 | Teloneer Company Limited | N/A | Closed | 2026-02-11 17:40:32 | Yes | Yes | 2026-09-18 22:29:13 |  | 2026-02-28 | 2026-02-25 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-25 11:22:57 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:26 | Yes | Yes | 2026-03-24 18:25:06 |  | 2026-02-28 | 2026-02-07 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:16:52 | Yes | Yes | 2026-02-07 12:12:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-03 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-03 18:04:57 | No | No |  | Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 90 + Remove RRU5505 x 2_SUNGM_H_2 Remove Antenna + (New AAU5768) + Main Dir = 270 + Remove RRU5505 x 2_SUNGM_H_4 (Co AAU5768) + Main Dir = 90 + Remove RRU5516 x 1_SUNGM_H_7 (Co AAU5768) + Main Dir = 270 + Remove RRU5516 x 1_SUNGM_H_9 New Sector J (Co AAU5768) + Main Dir = 90_SUNGM_H_J New Sector K (Co AAU5768) + Main Dir = 90_SUNGM_H_K New Sector I (Co AAU5768) + Main Dir = 270_SUNGM_H_I New Sector L (Co AAU5768) + Main Dir = 270_SUNGM_H_L |  | 2026-02-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-03 18:04:57 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUNTM_2026 Capacity Expansion Ph1_EXP_SR | Ban Suntinimit | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-19 | 2026-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-19 20:21:46 | Yes | Yes | 2026-08-24 11:12:18 |  | 2026-08-24 | 2026-08-24 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-24 15:27:41 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-24 | 2026-08-24 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-24 15:31:42 |  | 2026-08-21 | 2026-08-31 | 2026-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-19 15:02:35 | No | No |  |  |  |  | 2026-08-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-19 18:30:56 | No | No |  | S3 >AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUT1M_2025 Capacity Expansion NW Modernization_EXP_BKK | SOI SUTTHIPORN 1 |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-02-19 | 2026-02-19 | 2026-02-21 | 2026-03-05 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-05 14:35:14 | Yes | Yes | 2026-03-05 14:36:41 |  | 2026-03-26 | 2026-03-27 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 17:39:55 | Yes | Yes | 2026-03-27 13:57:39 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:29:42 | Yes | Yes | 2026-08-01 20:02:06 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-18 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-18 17:25:10 | No | No |  | 18-Feb-2026 Add AAU5768 S1 S2 Remove RRU5502 *1 RRU5507*2 #， RRU5502 *2 Add RRU5507*2 Sector 3 Remove RRU3962*2 Add g3a=2 Remove d6 d5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SUTNM_2026 Capacity Expansion Ph1_EXP_SR | SUAN TUN | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-28 | 2026-08-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-14 18:04:15 | Yes | Yes | 2026-08-20 15:27:00 |  | 2026-08-23 | 2026-08-26 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-26 13:09:46 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-08-23 | 2026-08-23 | Muhamadnase Chesamae | Approving | Assigned |  | Yes | Yes | 2026-08-23 11:42:24 |  | 2026-07-30 | 2026-08-31 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 16:53:20 | No | No |  |  |  |  | 2026-07-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-28 16:00:52 | No | No |  | S2 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SVPHM_2026 Capacity Expansion Ph2_EXP_ER | Sukhumvit Pattaya 85 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SW12M_2026 Capacity Expansion Ph2_BKK | SOI SUWINTHAWONG 12 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWAPM_2026 Capacity Expansion Ph2_BKK | SUK SAWAT APARTMENT | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWE1M_2026 Capacity Expansion Ph1_EXP_SR | SAWI 1 | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-16 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | Need to upload reposition antenna & RRU photo at AD & fill remark V or H. Need before AC box photo at before section. Need to upload EPS100D & module photo at AD & fill remark. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-15 | 2026-08-31 | 2026-09-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-16 17:04:07 | No | No |  |  |  |  | 2026-09-15 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-15 17:32:45 | No | No |  | Rep eb*1 to h3a*1 Re MB S2&S3 > S4&S9#， S4>S2// S2 MB Ant no ret S3 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWPPM_2026 Capacity Expansion NW Modernization_EXP_BKK | SUWAN PLAPPLA SCHOOL | [5 empty] | 2026-08-21 | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-24 21:24:24 | No | No |  |  |  | 2026-08-31 | 2026-08-31 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 20:10:26 | Yes | Yes | 2026-09-25 20:10:37 | 1.Install rru overview pto 2#，you fill 3 at install eq#，pls fill completely. 2.Need install breaker overview pto at eq. 3.Need install bbp sn and overview pto at eq. 4.Need bf c2 ptos. 5.Plz show red mark dis items. Need completely upload indoor/outdoor label at after on ground. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-19 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-08-19 15:13:02 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-27 10:26:21 |  |  | 2026-06-30 | 2026-08-29 | Teloneer Company Limited | N/A | Closed | 2026-08-29 15:05:18 | No | No |  |  |  |  | 2026-08-19 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-08-19 17:36:07 | No | No |  | 2026-09-16_Fix Alarm VSWR S3 19-08-2026 Clear vswr done 18-08-2026. ***ค้าง VSWR 900 Sec.2 //Replace RRU3962 to AAU5775 S.2#， 3#， RRU5362 to RRU5516 S.3#， Add RRU3953 S.2 2026-08-17 s1 rmv RRU3962*2 add AAU5775 #，rmv RRU3953*1 add RRU5516*1 replace ant 8 port s6 rmv RRU3962*1 ****pending s2 rmv RRU5516 add AAU5775 #，add RRU3953*1 add RRU5516*1 s3 rmv RRU3962*2 add AAU5775#，rmv RRU3953*1 add RRU5516*1 s8 rmv RRU3962*2 pending tilt AAU #，RET sector can't scan#，tilt 10 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-21 | Teloneer Company Limited | N/A | Closed | 2026-08-25 12:02:43 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWPPM_2026 Capacity Expansion Ph2_BKK | SUWAN PLAPPLA SCHOOL | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWRDM_2026 Capacity Expansion Ph2_BKK | SUWINTHAWONG ROAD | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWSWM_2026 Capacity Expansion Ph1_EXP_BKK | SOIWATSRIWAREENOI 2 | [5 empty] | 2026-06-25 | 2026-06-25 | Nattawoot Suwan | N/A | Closed | 2026-06-26 14:56:52 | No | No |  |  |  | 2026-07-31 | 2026-06-25 | 2026-06-25 | Teloneer Company Limited | N/A | Closed | 2026-06-25 19:55:12 | Yes | Yes | 2026-06-30 09:24:09 |  | 2026-06-30 | 2026-07-23 | Teloneer Company Limited | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 12:54:00 | Page no.35#， need to fill remark for breaker activity. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-09 | 2026-07-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-06-19 18:01:22 |  |  | 2026-06-30 | 2026-06-30 | Teloneer Company Limited | N/A | Closed | 2026-06-30 11:57:50 | No | No |  |  |  |  | 2026-06-23 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-06-23 20:07:18 | No | No |  | 30 Jun 2026 Clear pending 2026-06-23_Replace UBBPd5 to UBBPh2a#， Add AAU5656 Sector 1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-07 | Nattawoot Suwan | N/A | Closed | 2026-07-07 14:46:00 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SWSWM_2026 Capacity Expansion Ph2_BKK | SOIWATSRIWAREENOI 2 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYANM_2026 Capacity Expansion Ph2_EXP_ER | Sam Yan | 2026-09-30 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | Yes | 2026-09-22 13:36:29 |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : น้ำท่วม | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYBKG_2026 Capacity Expansion Ph1_EXP_SR | Si Yaek Banklang | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-07-31 | 2026-07-27 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 18:42:20 | Yes | Yes | 2026-08-07 19:14:29 |  | 2026-08-07 | 2026-08-18 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-08-28 16:01:52 | Yes | Yes | 2026-08-08 14:23:35 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:05 | No | No |  |  | 2026-08-07 | 2026-08-08 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-08 14:25:11 |  | 2026-07-27 | 2026-08-31 | 2026-07-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-27 18:27:39 | No | No |  |  |  |  | 2026-07-27 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-27 17:26:58 | No | No |  | Rep Ant MB S2 to 8 Port S2 > Rep RRU&Ant 3953*2 to RRU5516LB*1 > Ant Combine MB S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYCPH_2026 Capacity Expansion Ph1_EXP_SR | Si Yaek Chumphon Hospital | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-12 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | 1.Need to removed remark OPM 1pcs in EQ. 2.Need to upload EPS 100D start point and end point photos in QC. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-14 | 2026-08-31 | 2026-09-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-14 21:14:57 | No | No |  |  |  |  | 2026-09-14 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-14 18:08:01 | No | No |  | Rep eb*1 to h3a*1 Remove S3 MB S3 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYKYM_2026 Capacity Expansion Modernize_EXP_ER | Si Yaek Khoa Makok Pattaya | 2026-07-28 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-07-31 | 2026-07-29 | 2026-07-29 | Teloneer Company Limited | N/A | Closed | 2026-07-29 17:38:20 | No | No |  |  |  | 2026-07-31 | 2026-08-04 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 23:53:00 | Yes | Yes | 2026-08-08 20:07:53 |  | 2026-08-20 | 2026-08-11 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:58:26 | Yes | Yes | 2026-08-12 07:52:02 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:10 | No | No |  |  | 2026-07-31 | 2026-07-28 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-28 10:53:00 |  |  | 2026-07-31 | 2026-07-28 | Teloneer Company Limited | N/A | Closed | 2026-07-28 15:42:34 | No | No |  |  |  |  | 2026-07-28 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-28 17:14:35 | No | No |  | Add UBBPh3a Add RRU5505 x 1 + 4T4R_SYKYM_H_3 Remove Antenna + (New AAU5775) + Main Dir = 250 + Remove RRU x 2_SYKYM_H_4 Remove Antenna + (Co AAU5775) + Main Dir = 250 + Remove RRU x 2_SYKYM_H_9 New Sector I (Co AAU5775) + Main Dir = 250_SYKYM_H_I New Sector L (Co AAU5775) + Main Dir = 250_SYKYM_H_L Co L21F2 S1#，2#，3 |  | 2026-07-29 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-29 19:23:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYKYM_2026 Capacity Expansion Ph2_EXP_ER | Si Yaek Khoa Makok Pattaya |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYLLM_2026 Capacity Expansion Modernize_EXP_ER | SiYaek LangLae | 2026-08-04 | Team : thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 17:34:48 | No | No |  |  |  | 2026-08-15 | 2026-08-05 | 2026-08-06 | Teloneer Company Limited | N/A | Closed | 2026-08-06 10:33:57 | Yes | Yes | 2026-08-09 15:13:15 |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:55:21 | Yes | Yes | 2026-08-12 20:30:53 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:23 | Yes | Yes | 2026-08-12 17:07:34 |  |  | 2026-08-15 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 10:08:42 | No | No |  |  |  |  | 2026-08-04 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-04 10:29:23 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_SYLLM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_SYLLM_H_3 Co L21F2 All Sector |  | 2026-08-05 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-05 17:32:43 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYMTP_2025 Capacity Expansion NW Modernization_EXP_BKK | SAMYAN MITRTOWN |  |  |  |  | 2026-02-17 | 2026-02-17 | 2026-02-17 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-02-17 16:22:25 | No | No |  |  |  | 2026-02-06 | 2026-02-11 | 2026-02-12 | V Contribute Co., Ltd | N/A | Closed | 2026-02-12 11:16:55 | Yes | Yes | 2026-02-12 11:16:56 | SQC Close | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-02-20 15:41:49 | Yes | Yes | 2026-02-16 22:11:13 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-20 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:32:57 | Yes | Yes | 2026-04-09 13:35:10 |  | 2026-02-16 | 2026-02-16 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:04:45 | Yes | Yes | 2026-02-16 22:25:05 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-02 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-02 17:52:51 | No | No |  | 2 Feb 2026 Add 2UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYNYM_2026 Capacity Expansion Ph1_EXP_SR | Sam Yeak Na Yoong | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-02 | 2026-08-04 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-04 00:40:04 | Yes | Yes | 2026-08-07 19:39:52 |  | 2026-08-10 | 2026-08-10 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 20:18:48 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-08-13 | 2026-08-13 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 20:20:36 |  | 2026-08-02 | 2026-08-31 | 2026-08-02 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-02 14:57:41 | No | No |  |  |  |  | 2026-08-02 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-02 17:57:31 | No | No |  | S2 > Rep RRU&Ant 3953*2 to 5516LB*1 > Ant 8 Port Rep Ant S4 MB to Ant 8 Port S4 > RRU5516LB*1 > Ant Combine MB S4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYSAM_2026 Capacity Expansion Ph1_EXP_SR | Siyeak Srapet | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-04 | 2026-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-15 18:19:43 | Yes | Yes | 2026-08-17 14:10:16 |  | 2026-08-18 | 2026-08-18 | Charuwan Limsaihua | Approving | Assigned |  | Yes | Yes | 2026-08-18 15:13:34 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-06 | 2026-08-31 | 2026-08-06 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-06 17:15:02 | No | No |  |  |  |  | 2026-08-05 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-05 17:34:32 | No | No |  | 6 Aug 2026 Clear pending VSWR 5 Aug 2026 Add RRU5516 sector4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
SYTTO_2026 Capacity Expansion NW Modernization_EXP_SR | Sam Yaek Tonto | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-09-05 | 2026-08-22 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | Need to upload EHS photo completely. Need open RRU cover with plug in CPRI and socket DC for sec-1&4 at after section. Need after ground bar photo at after section. Need install RRU under label for sec-1 at after section. Need grounding kit photo for install RRU at after section. Need indoor label for install RRU from DCDU side & BBU side at after section. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-20 | 2026-08-31 | 2026-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-20 21:49:55 | No | No |  |  |  |  | 2026-08-20 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-20 17:27:40 | No | No |  | Rep RRU MB S2 // Clear Alarm RRU 20 Aug 2026 Replace RRU3962 sector1#，2#，3#，4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TANGM_2026 Capacity Expansion Ph1_EXP_SR | Ban Ta Ngoh | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-29 | 2026-08-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-30 10:06:04 | Yes | Yes | 2026-09-02 21:37:11 |  | 2026-09-08 | 2026-09-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-11 04:04:48 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-08 | 2026-09-08 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-08 22:34:01 |  | 2026-08-28 | 2026-08-31 | 2026-08-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-28 15:00:10 | No | No |  |  |  |  | 2026-08-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-28 17:54:54 | No | No |  | Rep Card g2*1 to h2a*1 S2 > Rep RRU3953*2 To RRU5516*1 > Ex Ant |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TANKM_2026 Capacity Expansion Ph1_EXP_SR | Ban Tan Kaew | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  | 2026-07-26 | 2026-07-26 | 2026-07-27 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 15:23:26 | Yes | Yes | 2026-08-10 10:56:16 |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-09-04 11:11:26 | Yes | Yes | 2026-08-11 12:46:51 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-01 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-03 17:02:36 | No | No |  |  | 2026-08-11 | 2026-08-11 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-11 11:56:39 |  | 2026-07-30 | 2026-08-31 | 2026-07-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-27 17:55:30 | No | No |  |  |  |  | 2026-07-27 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-27 17:25:16 | No | No |  | S4 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TANPM_2026 Capacity Expansion Modernize_EXP_ER | TaladNam 4 Prak Pattaya | 2026-07-27 | Team : Team_Pooriwat Tel : 0925094222 |  |  | 2026-07-31 | 2026-07-28 | 2026-07-28 | Teloneer Company Limited | N/A | Closed | 2026-07-28 16:32:04 | No | No |  |  |  | 2026-08-20 | 2026-08-04 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 14:47:14 | Yes | Yes | 2026-08-08 20:08:09 |  | 2026-08-20 | 2026-08-11 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:58:26 | Yes | Yes | 2026-08-25 09:31:46 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-07-31 | 2026-07-27 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-27 23:14:38 |  |  | 2026-07-31 | 2026-07-27 | Teloneer Company Limited | N/A | Closed | 2026-07-27 17:31:33 | No | No |  |  |  |  | 2026-07-27 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-27 21:34:34 | No | No |  | Add UBBPh3a Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_TANPM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 250 + Remove RRU x 2_TANPM_H_4 (Co AAU5775) + Main Dir = 250 + Remove RRU x 2_TANPM_H_9 Replace RRU (RRU5516_900) + Co L07 + 4T4R_TANPM_L_1 Replace RRU (RRU5516_900) + 4T4R_TANPM_L_2 Replace RRU (RRU5516_900) + 4T4R_TANPM_L_3 New Sector I (Co AAU5775) + Main Dir = 250_TANPM_H_I New Sector L (Co AAU5775) + Main Dir = 250_TANPM_H_L |  | 2026-07-29 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-29 19:23:10 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TB45M_2026 Capacity Expansion Ph2_BKK | SOI THETSABAN BANG PU 45 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TB51M_2026 Capacity Expansion Ph2_BKK | SOI THETSABAN BANG PU 51 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBALO_2026 Capacity Expansion Ph1_EXP_SR | Tambon Ba Loi | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-12 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-11 | 2026-08-31 | 2026-09-14 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-14 10:05:17 | No | No |  |  |  |  | 2026-09-10 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-10 20:14:29 | No | No |  | S4 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBENA_2026 Capacity Expansion NW Modernization_EXP_BKK | TEAKBENCH RATCHADA | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBKBM_2026 Capacity Expansion Modernize_EXP_ER | Tung Bangkrabang | 2026-08-13 | Team : thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-08-20 | 2026-08-13 | 2026-08-13 | Teloneer Company Limited | N/A | Closed | 2026-08-13 17:37:42 | No | No |  |  |  | 2026-08-20 | 2026-08-15 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 10:09:54 | Yes | Yes | 2026-08-17 17:50:29 |  | 2026-08-20 | 2026-08-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:43:43 | Yes | Yes | 2026-09-04 21:05:41 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-10 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-15 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 14:26:52 |  |  | 2026-08-20 | 2026-08-13 | Teloneer Company Limited | N/A | Closed | 2026-08-13 11:21:24 | No | No |  |  |  |  | 2026-08-13 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-13 12:26:12 | No | No |  | Replace Antenna (LB) + Replace RRU5516_900 + Co L07 + NR07 + 4T4R_TBKBM_L_4 Co L21F2 All sector |  | 2026-08-14 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-14 17:43:01 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBNCM_2026 Capacity Expansion Modernize_EXP_ER | Tha Bon Ko Sichang | 2026-09-09 | Team: THCP_Wachira.s Tel :0657649919 | Install & Integrate |  | 2026-09-20 | 2026-09-09 | 2026-09-09 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-09 17:43:17 | No | No |  |  |  | 2026-09-20 | 2026-09-10 | 2026-09-10 | Teloneer Company Limited | N/A | Closed | 2026-09-10 19:46:50 | Yes | Yes | 2026-09-12 18:53:30 |  | 2026-09-20 | 2026-09-15 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:44:26 | Yes | Yes | 2026-09-15 21:35:18 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-20 | 2026-09-09 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-14 08:46:21 | Yes | Yes | 2026-09-09 15:36:53 |  |  | 2026-09-20 | 2026-09-10 | Teloneer Company Limited | N/A | Closed | 2026-09-10 11:51:02 | No | No |  |  |  |  | 2026-09-09 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-09 17:37:36 | No | No |  | Replace Antenna (MB) + Replace5505 to RRU5526 + 4T4R_TBNCM_H_1 Replace Antenna (MB) + Replace5505 to RRU5526 + 4T4R_TBNCM_H_3 Replace Antenna (Co Antenna)_TBNCM_N_1 Co L21F2 all sector |  | 2026-09-10 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-10 16:03:31 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBSVM_2025 Capacity Expansion Ph8_EXP_ER | Tedsaban Sathavorn1 school |  |  | Cancel |  |  | 2026-05-22 | 2026-05-22 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-05-22 17:58:19 | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-02-28 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBSVM_2026 Capacity Expansion Modernize_EXP_ER | Tedsaban Sathavorn1 school |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBSVM_2026 Capacity Expansion Ph1_EXP_ER | Tedsaban Sathavorn1 school | 2026-06-08 | Team : THCP_Wachira.s Tel : 065-7649919 | Clear Pending |  | 2026-06-30 | 2026-06-03 | 2026-06-03 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-06 19:22:46 | No | No |  |  |  | 2026-06-30 | 2026-06-04 | 2026-06-08 | Teloneer Company Limited | N/A | Closed | 2026-06-08 15:13:46 | Yes | Yes | 2026-06-10 09:33:14 |  | 2026-06-30 | 2026-06-12 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-15 14:57:06 | Yes | Yes | 2026-06-12 10:49:41 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-06-22 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-07 15:06:00 | No | No |  |  | 2026-06-30 | 2026-06-03 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:31 | Yes | Yes | 2026-06-03 11:19:21 |  | 2026-06-04 | 2026-06-30 | 2026-06-08 | Teloneer Company Limited | N/A | Closed | 2026-06-08 10:07:16 | No | No |  |  |  |  | 2026-06-03 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-03 18:23:20 | No | No |  | Add UBBPh2a + Replace Antenna (Dualband)_TBSVM_H_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_TBSVM_L_1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBTHM_2026 Capacity Expansion Ph1_EXP_SR | Talat Bo Thong | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-08-25 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-23 | 2026-08-31 | 2026-08-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-25 14:30:25 | No | No |  |  |  |  | 2026-08-23 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-23 18:12:01 | No | No |  | S7 > RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TBYJM_2026 Capacity Expansion Modernize_EXP_ER | Tesabal Road 1 Soi 27 | 2026-07-30 | Team : thcp_jaran.s Tel : 0988500996 |  |  | 2026-07-31 | 2026-07-30 | 2026-07-30 | Teloneer Company Limited | N/A | Closed | 2026-07-30 18:03:27 | No | No |  |  |  | 2026-08-20 | 2026-08-05 | 2026-08-07 | Teloneer Company Limited | N/A | Closed | 2026-08-07 20:06:09 | Yes | Yes | 2026-08-08 20:06:53 |  | 2026-08-20 | 2026-08-08 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:54:09 | Yes | Yes | 2026-08-13 07:32:37 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-20 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:25 | No | No |  |  | 2026-07-31 | 2026-07-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-30 08:18:15 |  |  | 2026-07-31 | 2026-07-30 | Teloneer Company Limited | N/A | Closed | 2026-07-30 19:10:57 | No | No |  |  |  |  | 2026-07-30 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-30 18:00:09 | No | No |  | Add UBBPg2 + Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_TBYJM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_TBYJM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_TBYJM_H_3 Replace RRU (RRU5516_900) + Co L07 + 4T4R_TBYJM_L_1 Replace RRU (RRU5516_900) + Co L07 + 4T4R_TBYJM_L_2 Replace RRU (RRU5516_900) + Co L07 + 4T4R_TBYJM_L_3 Co L21F2 Sec.1#，2 |  | 2026-08-03 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-03 18:37:40 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TC42M_2026 Capacity Expansion Ph2_BKK | SOI THEP KUNCHON 42 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TCA1B_2026 Capacity Expansion NW Modernization_EXP_BKK | THE COAST BANGKOK TOWER A | [5 empty] | 2026-09-28 | 2026-09-28 | Thossapan Chaloemrit | N/A | Closed | 2026-09-28 16:14:22 | No | No |  |  | 2026-09-03 | 2026-09-30 | 2026-09-03 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 17:53:00 |  |  | 2026-09-30 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 14:38:29 | No | No |  |  |  |  | 2026-09-28 | Pakin Klantip WX1491930 | N/A | Closed | 2026-09-28 13:01:54 | No | No |  | 2026-09-28 SB Replace RRU3962 to RRU5526 ================ 3-Sep-2026 ***Pending Add RRU5526 SB Rmv RRU3962 ///Add RRU5526 SA Rmv RRU3962 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TCBBB_2026 Capacity Expansion NW Modernization_EXP_BKK | THE COAST BANGKOK TOWER B | [5 empty] | 2026-09-03 | 2026-09-03 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-09-30 | 2026-09-08 | 2026-09-10 | Teloneer Company Limited | N/A | Closed | 2026-09-10 16:22:56 | Yes | Yes | 2026-09-16 10:49:37 |  | 2026-09-20 | 2026-09-20 | Nattawoot Suwan | Approving | Assigned |  | Yes | Yes | 2026-09-20 15:33:04 | page.34 need to upload add brekaer | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 23:58:10 |  |  | 2026-09-30 | 2026-09-04 | Teloneer Company Limited | N/A | Closed | 2026-09-04 11:10:10 | No | No |  |  |  |  | 2026-09-03 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-03 16:51:01 | No | No |  | 3-Sep-2026 Add g3 Rmv d5 Add RRU5526 SA SB Rmv RRU3962 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-03 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:11:38 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TCM1M_2026 Capacity Expansion NW Modernization_EXP_BKK | THAI COM 1 | [5 empty] | 2026-09-17 | 2026-09-17 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:54:25 | Yes | Yes | 2026-09-20 17:53:49 |  |  | 2026-10-10 | 2026-09-23 | Teloneer Company Limited | N/A | Closed | 2026-09-23 10:49:48 | No | No |  |  |  |  | 2026-09-17 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-09-17 20:30:37 | No | No |  | 2026-09-17 S1 Add RRU3953 (900 2T) S2 Remove RRU5526 > Add AAU5775 S3 Remove RRU3962 > Add AAU5775 S7 Remove RRU3962*2 S8 Remove RRU3962 ----------------------------------------------------------------------------------------- ----------------------------------------------------------------------------------------- 2026-09-16 S1 REP RRU3962*2 to AAU5775 S6 RMV RRU5516*1 RMV g3*2//add h3a#， d6 ----------------------------- Pending S1 ADD RRU3953 ตัวที่ 2 S2 REP RRU5526*1 to AAU5775 S3 REP RRU3962*2 to AAU5775 S7 RMV RRU3962*1 S8 RMV RRU3962*2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-17 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:27:23 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TCM1M_2026 Capacity Expansion Ph2_BKK | THAI COM 1 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-10 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-10-01 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-10-01 17:02:08 | No | No |  | 2026-10-01 Sec.6 add AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TDP2B_2026 Capacity Expansion NW Modernization_EXP_BKK | TRUE DIGITAL PARK (PHASE 2) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-27 13:53:32 |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TECBA_2026 Capacity Expansion NW Modernization_EXP_BKK | THE ESCAPE CONDOMINIUM BUILDING B | [5 empty] | 2026-08-01 | 2026-08-01 | Thossapan Chaloemrit | N/A | Closed | 2026-08-03 16:03:00 | No | No |  |  |  | 2026-08-31 | 2026-07-31 | 2026-07-31 | Teloneer Company Limited | N/A | Closed | 2026-07-31 16:43:26 | Yes | Yes | 2026-08-07 11:09:58 |  | 2026-08-10 | 2026-08-10 | Teloneer Company Limited | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 12:54:33 | Page 5 Need to fill remark. Page 28 Need to Upload all position POE/POR C1 #， C2 and C3 . Page 34 Need to fill remark. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-27 10:29:07 |  |  | 2026-06-30 | 2026-07-25 | Teloneer Company Limited | N/A | Closed | 2026-07-25 22:17:30 | No | No |  |  |  |  | 2026-07-23 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-07-23 18:37:21 | No | No |  | 2026-07-23 SA Remove RRU3962 > Add RRU5526 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-04 16:07:52 | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TECDA_2026 Capacity Expansion NW Modernization_EXP_BKK | THE ESCAPE CONDOMINIUM BUILDING D | [5 empty] | 2026-08-01 | 2026-08-01 | Thossapan Chaloemrit | N/A | Closed | 2026-08-03 16:03:00 | No | No |  |  |  | 2026-08-31 | 2026-07-27 | 2026-07-31 | Teloneer Company Limited | N/A | Closed | 2026-07-31 15:42:04 | Yes | Yes | 2026-08-07 11:12:14 |  | 2026-08-10 | 2026-08-10 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-09-03 14:40:56 | Page 5 Need to fill remark. Page 26 before DC-RRU Photo. Page 33 Need to fill remark. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-27 10:27:48 |  |  | 2026-06-30 | 2026-07-25 | Teloneer Company Limited | N/A | Closed | 2026-07-25 16:46:58 | No | No |  |  |  |  | 2026-07-23 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-07-23 18:37:49 | No | No |  | 2026-07-23 SB Remove RRU3962 > Add RRU5526 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-04 16:07:52 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TESBI_2026 Capacity Expansion NW Modernization_EXP_BKK | Temporary Electric Pole Sathorn Bridge, Krung Thonburi Road (Inbound) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TESBO_2026 Capacity Expansion NW Modernization_EXP_BKK | Temporary Electric Pole Sathorn Bridge, Krung Thonburi Road (Outbound) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-10-03 |  | Teloneer Company Limited | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-31 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TESEA_2026 Capacity Expansion NW Modernization_EXP_BKK | THE ESCAPE CONDOMINIUM BUILDING E | [5 empty] | 2026-07-28 | 2026-08-03 | Thossapan Chaloemrit | N/A | Closed | 2026-08-03 16:03:00 | No | No |  |  |  | 2026-08-31 | 2026-07-27 | 2026-07-27 | Teloneer Company Limited | N/A | Closed | 2026-07-27 15:50:26 | Yes | Yes | 2026-07-30 10:18:49 |  | 2026-07-30 | 2026-07-30 | Teloneer Company Limited | Approved | Closed | 2026-08-31 10:54:41 | Yes | Yes | 2026-08-26 10:41:32 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-21 11:33:37 | Yes | Yes | 2026-07-27 10:28:42 |  |  | 2026-06-30 | 2026-07-25 | Teloneer Company Limited | N/A | Closed | 2026-07-25 20:38:17 | No | No |  |  |  |  | 2026-07-23 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-07-23 18:38:13 | No | No |  | 2026-07-23 SC Remove RRU3962 > Add RRU5526 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-04 16:07:52 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TESHM_2026 Capacity Expansion NW Modernization_EXP_BKK | The Embassy Sathon Hotel Macro | [5 empty] | 2026-07-28 | 2026-08-03 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-08-03 16:03:00 | No | Yes | 2026-07-10 22:24:03 |  |  | 2026-08-31 | 2026-07-22 | 2026-07-22 | Teloneer Company Limited | N/A | Closed | 2026-07-22 20:03:04 | Yes | Yes | 2026-07-27 11:06:56 |  | 2026-07-30 | 2026-07-30 | Teloneer Company Limited | Approved | Closed | 2026-08-31 10:55:08 | Yes | Yes | 2026-08-26 10:41:57 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-08-19 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-08-19 15:13:02 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-10 | Teloneer Company Limited | Approved | Closed | 2026-07-17 12:57:51 | Yes | Yes | 2026-07-10 22:26:23 |  |  | 2026-06-30 | 2026-07-22 | Teloneer Company Limited | N/A | Closed | 2026-07-22 21:10:17 | No | No |  |  |  |  | 2026-07-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-07-20 18:42:53 | No | No |  | 20-07-2026. Replace Ant.8 port Sec.1#， 3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-17 | Teloneer Company Limited | N/A | Closed | 2026-07-21 12:50:22 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TGKMN_2026 Capacity Expansion Ph1_EXP_SR | Mu 6 Thung Khamin | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-18 | 2026-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-19 15:43:23 | Yes | Yes | 2026-08-26 18:50:14 |  | 2026-08-30 | 2026-08-30 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-30 07:08:56 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-29 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-30 13:04:17 | No | No |  |  | 2026-08-30 | 2026-08-30 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-30 07:10:32 |  | 2026-08-18 | 2026-08-31 | 2026-08-18 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-18 15:41:38 | No | No |  |  |  |  | 2026-08-18 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-18 16:38:53 | No | No |  | 18 Aug 2026 Replace RRU5516 sector1 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THLHB_2025 Capacity Expansion NW Modernization_EXP_BKK | THE LINE PHAHON-PRADIPAT |  |  |  |  | 2026-03-24 | 2026-03-02 | 2026-03-24 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-25 10:44:08 | No | No |  |  |  | 2026-03-14 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:46:03 | Yes | Yes | 2026-03-23 15:46:03 |  | 2026-04-10 | 2026-04-09 | Chonradee Suwapan | Approved | Closed | 2026-07-20 09:43:13 | Yes | Yes | 2026-04-10 00:05:09 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-09 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-10 | 2026-04-09 | Chonradee Suwapan | Approved | Closed | 2026-05-01 10:35:45 | Yes | Yes | 2026-04-10 00:23:12 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-02 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-03-02 16:53:35 | No | No |  | 02-03-2026. Replace RRU3962 to RRU5526#， Ant.4 port Sec.A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
THMDM_KKN_2025_RepSGR_NER | THAMADUE |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-15 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 21:24:27 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-22 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-15 | Teloneer Company Limited | N/A | Closed | 2026-09-15 14:00:05 | No | No |  |  | DTH1202609100009 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
TIRAT_2026 Capacity Expansion Ph1_EXP_SR | Trairat Road | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-13 | 2026-08-15 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-15 14:40:11 | Yes | Yes | 2026-08-21 01:48:41 |  | 2026-08-25 | 2026-08-25 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-25 14:10:31 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-25 | 2026-08-25 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-25 14:13:33 |  | 2026-08-13 | 2026-08-31 | 2026-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-13 13:57:10 | No | No |  |  |  |  | 2026-08-13 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-13 17:59:57 | No | No |  | 13 Aug 2026 Add RRU5516 sector2 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TITHM_2026 Capacity Expansion NW Modernization_EXP_BKK | Ti Thong Rd. | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:43:41 | No | No |  |  | 2026-08-24 | 2026-08-28 | 2026-09-10 | 2026-09-25 | Nammon Manakiat(Teloneer Company Limited) | N/A | Closed | 2026-09-25 19:49:35 | Yes | Yes | 2026-09-25 19:49:45 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:55:19 | Yes | Yes | 2026-09-20 17:54:35 |  |  | 2026-08-28 | 2026-08-29 | Teloneer Company Limited | N/A | Closed | 2026-08-29 13:54:36 | No | No |  |  |  |  | 2026-08-25 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-08-25 17:33:59 | No | No |  | 25-Aug-2026 s2 replace RRU3953*1 to RRU5516 s2 replace RRU3962*1 to RRU5507*2 replace ant8 port s2 co 1800900 Clear vswr 1800/2100s1#2 port A 2026-08-24 s1#，s3 replace RRU3953*1 to RRU5516 s1#，s3 replace RRU3962*1 to RRU5507*2 add UBBPg3a#，replace ant8 port s1#，3 ***pending s2 replace RRU3953*1 to RRU5516 s2 replace RRU3962*1 to RRU5507*2 replace ant8 port s2 vswr 1800/2100s1#2 port A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-04 16:14:27 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TJHTM_2026 Capacity Expansion Modernize_EXP_ER | TJ Hotel Pattaya | 2026-07-25 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-07-31 | 2026-07-25 | 2026-07-25 | Teloneer Company Limited | N/A | Closed | 2026-07-25 12:51:54 | No | No |  |  |  | 2026-07-31 | 2026-07-29 | 2026-07-31 |  | N/A | Closed | 2026-07-31 15:06:48 | Yes | Yes | 2026-08-02 21:57:33 |  | 2026-07-31 | 2026-08-05 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-06 11:44:21 | Yes | Yes | 2026-08-05 23:50:47 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-19 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:25 | No | No |  |  | 2026-07-20 | 2026-07-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-25 12:10:05 | Yes | Yes | 2026-07-24 21:35:57 |  |  | 2026-07-31 | 2026-07-25 | Teloneer Company Limited | N/A | Closed | 2026-07-25 14:47:06 | No | No |  |  |  |  | 2026-07-25 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-25 12:44:15 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_TJHTM_H_3 |  | 2026-07-30 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-30 19:06:52 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TKBRM_2026 Capacity Expansion Ph1_EXP_SR | Talad Kraburi | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-04 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | CPRI cable photo is not standard. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-04 | 2026-08-31 | 2026-09-02 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-02 16:49:38 | No | No |  |  |  |  | 2026-09-02 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-02 17:36:08 | No | No |  | 2 Sep 2026 Add AAU5656 sector2 add 1UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TKNDM_2026 Capacity Expansion Modernize_EXP_ER | BanTeenKhao Nongmaidaeng | 2026-08-01 | Team : Team_Pooriwat Tel : 0925094222 | Install & Integrate |  | 2026-08-15 | 2026-08-01 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 20:19:39 | No | No |  |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 18:29:52 | Yes | Yes | 2026-08-05 08:57:06 |  | 2026-08-15 | 2026-08-06 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-08-16 19:01:41 | Yes | Yes | 2026-08-11 10:50:02 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:10 | No | No |  |  | 2026-08-15 | 2026-08-06 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-06 11:37:47 | Yes | Yes | 2026-08-06 09:51:10 |  |  | 2026-08-15 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 12:10:38 | No | No |  |  |  |  | 2026-08-01 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-01 12:19:23 | No | No |  | Add RRU5505 x 1 + 4T4R_TKNDM_H_2 Add RRU5505 x 1 + 4T4R_TKNDM_H_8 |  | 2026-08-01 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-01 12:19:23 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TKPOA_2026 Capacity Expansion NW Modernization_EXP_BKK | TALAT KHWAN POST OFFICE | [5 empty] | 2026-09-19 | 2026-09-19 | Thossapan Chaloemrit | N/A | Closed | 2026-09-21 12:53:19 | No | No |  |  |  | 2026-10-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:55:19 | Yes | Yes | 2026-09-20 17:55:28 |  |  | 2026-10-03 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 16:18:00 | No | No |  |  |  |  | 2026-09-19 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-09-19 20:32:11 | No | No |  | 2026-09-19 SA Replace RRU3962 to RRU5502 SB Replace RRU3962 to RRU5502 SC Replace RRU3962 to RRU5507 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-22 11:27:23 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TKS1B_2026 Capacity Expansion NW Modernization_EXP_BKK | The Key Sathorn Ratchapreuk (Carpark) | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TKUMM_2026 Capacity Expansion Modernize_EXP_ER | THE KUMP CONDOMINIUM H | 2026-08-10 | Team : thcp_watcharin.k Tel :0925546852 |  |  | 2026-08-20 | 2026-08-10 | 2026-08-10 | Teloneer Company Limited | N/A | Closed | 2026-08-10 18:07:18 | No | No |  |  |  | 2026-08-20 | 2026-08-11 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 12:20:12 | Yes | Yes | 2026-08-17 18:54:51 |  | 2026-08-20 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:50 | Yes | Yes | 2026-08-17 20:59:06 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-20 | 2026-08-14 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:52:24 | Yes | Yes | 2026-08-14 15:24:08 |  |  | 2026-08-20 | 2026-08-10 | Teloneer Company Limited | N/A | Closed | 2026-08-10 11:32:14 | No | No |  |  |  |  | 2026-08-10 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-10 17:59:03 | No | No |  | Add UBBPh2a Replace RRU5508 to (RRU5516_900) + Co NR07 + 4T4R_TKUMM_L_1 Replace RRU5508 to (RRU5516_900) + Co L07 + NR07 + 4T4R_TKUMM_L_2 Replace RRU5508 to (RRU5516_900) + Co L07 + NR07 + 4T4R_TKUMM_L_3 site config : TKUMM-PSNDM_2 RET : BBU TKUMM-PSNDM |  | 2026-08-19 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-19 15:53:51 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TL3CB_2026 Capacity Expansion NW Modernization_EXP_BKK | THE LOG 3 | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TL64M_2026 Capacity Expansion NW Modernization_EXP_BKK | The Link Sukhumvit 64 |  |  |  | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-31 | Mahadee Japakiya | N/A | Closed | 2026-08-04 19:33:03 | No | No |  |  | 2026-07-20 | 2026-07-20 | 2026-07-24 | 2026-08-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-08-10 12:08:42 | Yes | Yes | 2026-08-19 15:43:26 |  | 2026-08-25 | 2026-08-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-25 11:19:24 | 1.Removed ANT are AMB..-2pcs#，ADU..-2pcs#，A79..-1pc.Revise in pg-6. 2.Need to fill remove breaker 32A/1P-2pcs in pg-6. 3.Need to fill module EPS SN in pg-57. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-11 | 2026-08-11 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approving | Assigned |  | Yes | Yes | 2026-08-11 10:12:21 |  |  | 2026-07-21 | 2026-07-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-07-26 21:35:40 | No | No |  |  |  |  | 2026-07-21 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-07-21 17:43:23 | No | Yes | 2026-08-19 16:16:26 | 21-07-2026. Replace RRU5507 to AAU5775 Sec.2#， RRU3953 to RRU5516#， Sec.1#， 2#， 3#， Ant.8 port Sec.1#， 3#， UBBPg2#， UBBPd5 to UBBPh2a#， UBBPh3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TLBGN_2026 Capacity Expansion Ph1_EXP_SR | Taladsod Municipality Bang Namchuet | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-05 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | North CPRI photo is not standard. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-04 | 2026-08-31 | 2026-09-02 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-02 17:09:40 | No | No |  |  |  |  | 2026-09-02 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-02 17:36:08 | No | No |  | 2 Sep 2026 Add AAU5656 sector2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TLK6M_2026 Capacity Expansion Ph2_BKK | THANONLIAB KLONG 6 WA | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TLKHM_RET_2025_RepSGR_NER | TALAD KHO |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-22 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 12:26:30 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-25 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-21 | Teloneer Company Limited | N/A | Closed | 2026-09-21 19:00:03 | No | No |  |  | DTH1202609100018 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
TLKSA_2026 Capacity Expansion Ph1_EXP_SR | Talat Khian Sa | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-11 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-14 | 2026-08-31 | 2026-09-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-16 12:14:04 | No | No |  |  |  |  | 2026-09-11 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-11 18:07:20 | No | No |  | Rep BBU5900#，add h2a*1#，add gps Rep Ant MB S1 S1 > RRU5516*1 > Ant Combine MB S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TLTAI_2026 Capacity Expansion Ph1_EXP_SR | Talat Tai Community Tambon Prik | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-07-31 | 2026-07-27 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 14:50:51 | Yes | Yes | 2026-08-07 18:44:08 |  | 2026-08-11 | 2026-08-13 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-08-28 16:05:28 | Yes | Yes | 2026-08-13 21:24:03 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:05 | No | No |  |  | 2026-08-13 | 2026-08-13 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 21:24:49 |  | 2026-07-27 | 2026-08-31 | 2026-07-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-28 09:59:57 | No | No |  |  |  |  | 2026-07-27 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-27 17:27:07 | No | No |  | S1 > Rep RRU3953*2 to RRU5516LB*1 > Ex Ant Combine MB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TLVWM_2026 Capacity Expansion Modernize_EXP_ER | Talad Veerawan | 2026-08-14 | Team : Thcp_phet.sa Tel : 0924272237 |  |  | 2026-08-20 | 2026-08-14 | 2026-08-14 | Teloneer Company Limited | N/A | Closed | 2026-08-14 17:29:28 | No | No |  |  |  | 2026-08-20 | 2026-08-15 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 19:05:22 | Yes | Yes | 2026-08-21 10:32:27 |  | 2026-08-20 | 2026-08-27 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:46:54 | Yes | Yes | 2026-08-31 10:09:05 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-20 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 14:27:18 |  |  | 2026-08-20 | 2026-08-14 | Teloneer Company Limited | N/A | Closed | 2026-08-14 15:10:15 | No | No |  |  |  |  | 2026-08-14 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-14 14:35:24 | No | No |  | Add UBBPh2a_TLVWM_H_1 Replace RRU (RRU5516_900) + Co NR07 + 4T4R_TLVWM_L_1 Co NR07_TLVWM_L_2 Replace RRU (RRU5516_900) + Co NR07 + 4T4R_TLVWM_L_3 |  | 2026-08-17 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-17 17:25:00 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TLYRU_2026 Capacity Expansion NW Modernization_EXP_SR | Talat Yai Ruai | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-09-05 | 2026-08-26 | 2026-08-27 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-27 11:08:42 | Yes | Yes | 2026-09-10 22:36:14 |  | 2026-09-11 | 2026-09-11 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-11 03:01:16 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-11 | 2026-09-11 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-11 03:04:21 |  | 2026-08-26 | 2026-08-31 | 2026-08-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-26 20:44:10 | No | No |  |  |  |  | 2026-08-26 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-26 17:45:51 | No | No |  | 26 Aug 2026 Replace RRU3962 sector1#，2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMFTM_2026 Capacity Expansion Modernize_EXP_ER | Triumph Motorcycles (Thailand) Co., Ltd._Factory3 | 2026-09-24 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-09-30 | 2026-09-24 | 2026-09-24 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-24 18:25:32 | No | No |  |  |  | 2026-09-30 | 2026-09-25 | 2026-09-27 | Teloneer Company Limited | N/A | Closed | 2026-09-27 20:49:11 | Yes | Yes | 2026-09-30 21:14:58 |  | 2026-09-30 | 2026-09-30 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-30 23:38:04 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-22 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:42:32 | Yes | Yes | 2026-09-22 15:53:21 |  |  | 2026-09-30 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-24 16:39:06 | No | No |  |  |  |  | 2026-09-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-09-24 16:59:50 | No | No |  | Replace Antenna (MB) + Replace5505 to RRU5513 + 4T4R_TMFTM_H_B Co L21F2 S.A#，B ์No RET |  | 2026-09-25 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-25 16:16:43 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-24 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-25 11:27:00 | No | No |  |  | SQC closed | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMK1M_2026 Capacity Expansion NW Modernization_EXP_BKK | THUNG MANGKORN 1 |  |  |  | 2026-06-26 |  | 2026-06-26 | 2026-06-26 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-06-26 15:01:08 | No | No |  |  |  | 2026-08-31 | 2026-06-26 | 2026-06-29 | Teloneer Company Limited | N/A | Closed | 2026-06-29 11:24:57 | Yes | Yes | 2026-07-07 09:28:15 |  | 2026-07-07 | 2026-07-23 | Teloneer Company Limited | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 12:59:40 | Pg-5 Remove antenna model was wrong #， Pg-78- All of Dismantle SN photos need to complete.(Need DCDU SN) | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-09 | 2026-07-09 | Nattawoot Suwan(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-06-19 18:07:59 |  |  | 2026-06-30 | 2026-06-26 | Teloneer Company Limited | N/A | Closed | 2026-06-26 14:25:08 | No | No |  |  |  |  | 2026-06-24 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-06-24 19:13:14 | No | No |  | 24 Jun 2026 Add AAU5775 sector1#，2#，3 replace RRU5516 sector1#，2#，3 replace ANT add 1UBBPh3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-07 | Nattawoot Suwan | N/A | Closed | 2026-07-07 14:46:00 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMK1M_2026 Capacity Expansion Ph2_BKK | THUNG MUNG KORN 1 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TMKCM_2026 Capacity Expansion Ph1_EXP_ER | Ban ThaBunmi Ko Chan | 2026-06-09 | Team : thcp_anat.sri Tel : 0629861985 | Take Photo & Clear Pending |  | 2026-06-30 | 2026-06-06 | 2026-06-06 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-06 19:20:31 | No | No |  |  |  | 2026-06-30 | 2026-06-08 | 2026-06-09 | Teloneer Company Limited | N/A | Closed | 2026-06-09 13:11:46 | Yes | Yes | 2026-06-10 09:33:01 |  | 2026-06-30 | 2026-06-15 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:17:04 | Yes | Yes | 2026-06-15 17:17:30 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-03 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-07 15:06:00 | No | No |  |  | 2026-06-30 | 2026-06-05 | Palagon Prommueangma(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:20 | Yes | Yes | 2026-06-05 14:11:25 |  | 2026-06-06 | 2026-06-30 | 2026-06-06 | Teloneer Company Limited | N/A | Closed | 2026-06-06 15:54:18 | No | No |  |  |  |  | 2026-06-06 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-06-06 18:19:27 | No | No |  | "Replace RRU (RRU5516_900) + 4T4R_TMKCM_L_1 Replace RRU (RRU5516_900) + 4T4R_TMKCM_L_2" |  | 2026-06-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-08 19:38:43 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TNATM_2026 Capacity Expansion Ph1_EXP_SR | Thap Namtao | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-12 | 2026-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-13 18:36:38 | Yes | Yes | 2026-08-15 11:22:15 |  | 2026-08-15 | 2026-08-18 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-18 13:55:05 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-15 | 2026-08-15 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-15 15:16:23 |  | 2026-08-19 | 2026-08-31 | 2026-08-13 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-13 21:28:17 | No | No |  |  |  |  | 2026-08-13 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-13 17:59:57 | No | No |  | 13 Aug 2026 Add RRU5516 sector3 replace BBU5900 add GPS rollback |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TNBAM_2026 Capacity Expansion Modernize_EXP_ER | Tanon Ban Kao Soi 5 | 2026-08-14 | Team : Thcp_phet.sa Tel : 0924272237 |  |  | 2026-08-20 | 2026-08-14 | 2026-08-14 | Teloneer Company Limited | N/A | Closed | 2026-08-14 17:29:28 | No | No |  |  |  | 2026-08-20 | 2026-08-15 | 2026-08-15 | Teloneer Company Limited | N/A | Closed | 2026-08-15 19:18:09 | Yes | Yes | 2026-08-19 22:09:02 |  | 2026-08-20 | 2026-08-21 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-06 18:46:54 | Yes | Yes | 2026-08-27 21:39:48 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-20 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 14:27:42 |  |  | 2026-08-20 | 2026-08-14 | Teloneer Company Limited | N/A | Closed | 2026-08-14 16:59:59 | No | No |  |  |  |  | 2026-08-14 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-14 16:59:30 | No | No |  | Replace RRU (RRU5516_900) + Co L07 + NR07 + 4T4R_TNBAM_L_1 Co L21F2 Sec.1#，6#，G#，H |  | 2026-08-17 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-17 17:25:00 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TNPYM_2026 Capacity Expansion Ph1_EXP_SR | Thanon Phi Sit Phayaban | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-29 | 2026-08-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-30 16:06:48 | Yes | Yes | 2026-09-03 08:49:40 |  | 2026-09-08 | 2026-09-08 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-08 08:58:08 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 | 2026-09-08 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-08 09:01:14 |  | 2026-08-29 | 2026-08-31 | 2026-08-29 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-29 13:50:22 | No | No |  |  |  |  | 2026-08-29 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-29 19:12:43 | No | No |  | Rep d6*1 to g2*1 (Out of plan) for On NR700 S2 > Rep RRU3953*1 to RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TOSMP_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | The Old Siam Plaza | [5 empty] | 2026-09-09 | 2026-09-09 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-08-08 | 2026-09-18 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 12:06:47 | Yes | Yes | 2026-09-25 12:06:55 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:31:49 |  |  | 2026-08-08 | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-08 21:09:55 | No | No |  |  |  |  | 2026-09-08 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-09-08 18:57:46 | No | No |  | 2026-09-08 Replace by BBU5900 + Replace by UMPTg2 Replace + Add Card to UBBPd5#， UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:28:40 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TOSMP_L1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | The Old Siam Plaza | [5 empty] | 2026-09-09 | 2026-09-09 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-08-08 | 2026-09-24 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 20:27:18 | Yes | Yes | 2026-09-25 20:27:27 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:32:16 |  |  | 2026-08-08 | 2026-09-08 | Teloneer Company Limited | N/A | Closed | 2026-09-08 21:12:16 | No | No |  |  |  |  | 2026-09-08 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-09-08 19:39:10 | No | No |  | 08-09-2026. Replace BBU5900#， UMPTg2#， Add UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-06 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:28:40 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPLBM_2026 Capacity Expansion Ph2_EXP_ER | Trailer truck parking lot , Laem Chabang Port |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPPAM_2026 Capacity Expansion Ph2_EXP_ER | Soi Thetsaban Pimpa 2 | 2026-09-29 | Team: THCP_Wachira.s Tel :0657649919 | Clear Pending |  | 2026-09-30 | 2026-09-21 | 2026-09-21 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-22 07:14:32 | No | No |  |  |  | 2026-09-30 | 2026-09-23 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 11:16:23 | Yes | Yes | 2026-09-30 23:23:01 | Fill quantity reposition AAU at EQ check list. AAU was install or not? IF install please upload model & SN photo at EQ check list. Need BBU close view photo clearly at before section. | 2026-09-30 | 2026-10-01 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-10-01 07:54:59 |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-21 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-23 00:42:32 | Yes | Yes | 2026-09-21 14:27:47 |  |  | 2026-09-30 | 2026-09-21 | Teloneer Company Limited | N/A | Closed | 2026-09-21 18:24:20 | No | No |  |  |  |  | 2026-09-21 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-21 18:20:33 | No | No |  | ReDirection 0 to 320_TPPAM_N_1 New L26F5 + NR26 (New AAU5656)_TPPAM_N_2 New L26F5 + NR26 (New AAU5656)_TPPAM_N_6 |  | 2026-09-22 | Reungsak Junkong 00927496 | N/A | Closed | 2026-09-22 16:05:29 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% , Day2 : Clear work | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPRTM_2025 Capacity Expansion Ph8_EXP_ER | Wat Traphang Thong | 2026-02-14 | Thcp_phet.sa | Clear Alarm |  | 2026-02-28 | 2026-02-05 | 2026-02-05 | Teloneer Company Limited | N/A | Closed | 2026-02-05 15:20:30 | No | No |  |  |  | 2026-02-28 | 2026-02-15 | 2026-02-15 | Teloneer Company Limited | N/A | Closed | 2026-02-15 16:23:06 | Yes | Yes | 2026-02-16 19:27:41 |  | 2026-02-28 | 2026-02-20 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-05 11:15:11 | Yes | Yes | 2026-02-20 19:15:46 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-04 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:25 | Yes | Yes | 2026-03-24 18:48:15 |  | 2026-02-28 | 2026-02-07 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-10 09:16:52 | Yes | Yes | 2026-02-07 15:15:01 |  | 2026-02-14 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-14 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-14 17:38:01 | No | No |  | 14 feb 2026 Replace Ant sector 1 Clear VSWR /// New L26F5 + NR26 (New RRU5818) + Co Antenna_TPRTM_N_1 New L26F5 + NR26 (New RRU5818) + Co Antenna_TPRTM_N_2 New L26F5 + NR26 (Co RRU5818) + Co Antenna_TPRTM_N_3 |  | 2026-02-14 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-03-17 11:57:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPSEM_2025 Capacity Expansion Ph8_EXP_ER | Thepprasit 11 | 2026-02-18 | THCP_Wachira.s | Clear Pending | 2026-02-17 | 2026-02-28 | 2026-02-18 | 2026-02-19 | Teloneer Company Limited | N/A | Closed | 2026-02-19 09:21:14 | No | No |  |  | 2026-02-17 | 2026-02-28 | 2026-02-18 | 2026-02-18 | Teloneer Company Limited | N/A | Closed | 2026-02-18 13:23:11 | Yes | Yes | 2026-02-20 21:31:25 |  | 2026-02-28 | 2026-03-02 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-12 11:06:39 | Yes | Yes | 2026-03-02 20:50:56 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-03-05 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:25 | Yes | Yes | 2026-03-24 18:48:47 |  | 2026-02-28 | 2026-02-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-02-20 08:59:31 | Yes | Yes | 2026-02-17 18:54:07 |  | 2026-02-17 |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-17 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-17 17:34:27 | No | No |  | "Add UBBPg3a Remove Antenna + (New AAU5768) + Main Dir = 190 + Remove RRU x 2_TPSEM_H_2 Remove Antenna + (Co AAU5768) + Main Dir = 190 + Remove RRU x 2_TPSEM_H_7 New Sector J (Co AAU5768) + Main Dir = 190_TPSEM_H_J New Sector K (Co AAU5768) + Main Dir = 190_TPSEM_H_K" |  | 2026-02-17 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-03-17 11:57:47 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPSEM_2026 Capacity Expansion Ph2_EXP_ER | Thepprasit 11 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TPUPE_2026 Capacity Expansion Ph1_EXP_SR | Talat Phru Phi_DTAC | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-24 | 2026-09-28 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-28 15:07:57 | Yes | Yes | 2026-09-28 15:12:22 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-31 |  | Subpoa Limsaihua(Future Telecom Co.,Ltd.) | N/A | Assigned |  | Yes | No |  |  | 2026-09-28 | 2026-08-31 | 2026-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-24 15:47:40 | No | No |  |  |  |  | 2026-09-22 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-22 17:56:48 | No | No |  | Rep BBU5900#，-WBBPF3*1#，add g3a*1#，add gps Rep Ant MB S1&3 S1&S3 RRU5872(1) > Ant Combine MB &LB |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRAPM_2026 Capacity Expansion Modernize_EXP_ER | Thammarat Apartment Don Hua Lo | 2026-08-12 |  |  |  | 2026-08-20 | 2026-08-12 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 18:06:16 | No | No |  |  |  | 2026-08-20 | 2026-08-14 | 2026-08-14 | Teloneer Company Limited | N/A | Closed | 2026-08-14 10:56:50 | Yes | Yes | 2026-08-16 13:51:46 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:50 | Yes | Yes | 2026-08-16 17:17:49 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-09 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-15 | 2026-08-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:54:31 | Yes | Yes | 2026-08-17 14:28:04 |  |  | 2026-08-20 | 2026-08-12 | Teloneer Company Limited | N/A | Closed | 2026-08-12 11:05:27 | No | No |  |  |  |  | 2026-08-12 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-12 11:38:00 | No | No |  | Replace RRU (RRU5516_900) + Co NR07 + 4T4R_TRAPM_L_1 Co L21F2 All Sector |  | 2026-08-19 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-19 16:16:01 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRCGM_2026 Capacity Expansion Ph1_EXP_SR | Tharong Chang | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-10 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-10 | 2026-08-31 | 2026-09-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-10 20:43:33 | No | No |  |  |  |  | 2026-09-10 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-10 20:14:29 | No | No |  | Rep d5*1 to h3a*1 MB remove ANT dualbeam +RRU5507x4 S1 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TRKOM_2026 Capacity Expansion Ph1_EXP_SR | Tharua Koh | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-07-31 | 2026-08-07 | 2026-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-10 19:48:07 | Yes | Yes | 2026-08-13 19:01:40 |  | 2026-08-13 | 2026-08-13 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 21:21:33 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-13 | 2026-08-13 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 21:24:40 |  | 2026-08-03 | 2026-08-31 | 2026-08-03 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-03 14:47:43 | No | No |  |  |  |  | 2026-08-03 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-03 19:39:38 | No | No |  | Rep Card UBBPd6*1 to UBBPh2a*1 Rep Ant MB S4 to 8 Port S4 > RRU5516LB *1 > Ant Combine MB S4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TSHSM_2026 Capacity Expansion Ph1_EXP_SR | Thasae Hospital | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-17 | 2026-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-20 18:50:05 | Yes | Yes | 2026-08-24 14:00:23 |  | 2026-08-25 | 2026-09-04 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-09-04 14:59:53 | Drawing page azimuth value for new install antenna and AAU mismatch with actual. Antenna activity page need. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-25 | 2026-08-25 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-25 16:59:37 |  | 2026-08-19 | 2026-08-31 | 2026-08-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-17 16:31:43 | No | No |  |  |  |  | 2026-08-17 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-17 17:19:15 | No | No |  | Rep UBBPg3*1 to UBBPd6*1 slot 4 Rep Ant MB S8 S8 > RRU5516*1 > Ant Combine MB S8 S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TSKIM_RET_2025_RepSGR_NER | THA SA MAK KHI |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-14 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 21:16:09 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-22 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-14 | Teloneer Company Limited | N/A | Closed | 2026-09-14 16:40:02 | No | No |  |  | DTH1202609100007 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
TSLNT_2025 Coverage Expansion (Co NT)_New_SR | Thongsala_Co-NT | [8 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-09 | 2026-04-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | Pramot Phanphongwong WX1324034 | N/A | Not assigned |  | No | No |  | **Pending ON RRU S2#，S3 LB&MB BBU3910#，UBBPd5*1#，UBBPd6*1 S1 > RRU3953 > Ant 4 port S1 > RRU5516 > Ant 4 port |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-04-08 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-04-08 12:27:10 | Yes | Yes | 2026-04-08 12:02:40 |  |  |  |  | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
TSOWM_2026 Capacity Expansion Ph2_EXP_ER | Ban Tha Sao Wang Chan |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TSSCM_2026 Capacity Expansion Modernize_EXP_ER | Talad Sabsin Chonburi | 2026-08-08 | Team : Thcp_phet.sa Tel : 0924272237 |  |  | 2026-08-20 | 2026-08-09 | 2026-08-09 | Teloneer Company Limited | N/A | Closed | 2026-08-09 11:10:45 | No | No |  |  |  | 2026-08-20 | 2026-08-10 | 2026-08-10 | Teloneer Company Limited | N/A | Closed | 2026-08-10 15:38:36 | Yes | Yes | 2026-08-13 12:34:45 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:55:50 | Yes | Yes | 2026-08-16 17:19:19 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:23 | Yes | Yes | 2026-08-13 11:59:04 |  |  | 2026-08-20 | 2026-08-08 | Teloneer Company Limited | N/A | Closed | 2026-08-08 12:44:58 | No | No |  |  |  |  | 2026-08-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-08 18:10:26 | No | No |  | Add RRU5505 x 1 + 4T4R_TSSCM_H_1 Add RRU5505 x 1 + 4T4R_TSSCM_H_2 Add RRU5505 x 1 + 4T4R_TSSCM_H_3 New L21(F2) SeC.1#，2#，3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% , Day2 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TSTMM_2025 Capacity Expansion Ph5_EXP_ER_Add | Chum Chon Ta Sit Moo 2 | 2026-04-01 | Thcp_phet.sa | Install & Integrate |  | 2026-04-03 | 2026-03-31 | 2026-04-01 | Teloneer Company Limited | N/A | Closed | 2026-04-01 15:07:40 | No | No |  |  |  | 2026-04-10 | 2026-04-01 | 2026-04-02 | Teloneer Company Limited | N/A | Closed | 2026-04-02 11:07:59 | Yes | Yes | 2026-04-02 20:53:43 |  | 2026-04-10 | 2026-04-17 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-04-27 09:18:13 | Yes | Yes | 2026-04-17 17:54:14 |  | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-04-23 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-31 | 2026-03-30 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-04-01 00:13:26 | Yes | Yes | 2026-03-30 12:37:59 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-31 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-03-31 17:58:13 | No | No |  | Replace Ant 18/21_TSTMM_H_2 Add RRU (RRU5508 x 1) + 4T4R_TSTMM_L_1 Replace RRU (RRU5508 x 2) + Co L07 + 4T4R_TSTMM_L_4 New L0709 + 4T4R + (RRU5508 x 2) + (Co Antenna)_TSTMM_L_2 |  | 2026-04-08 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-04-08 16:08:16 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TSTMM_2026 Capacity Expansion Ph2_EXP_ER | Chum Chon Ta Sit Moo 2 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TTKNT_2025 Coverage Expansion (Co NT)_New_SR | Thongtakian_Co-NT | [5 empty] | 2026-05-22 | 2026-05-22 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-05-22 17:58:19 | No | No |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-02-24 | Laddawan Wannasri WX1434742 | Approved | Closed | 2026-02-24 15:05:19 | Yes | Yes | 2026-02-24 13:43:42 |  |  |  |  | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | No | No
TTMYN_2026 Capacity Expansion Ph1_EXP_SR | TA TONG MAI YEK NAI | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-06-30 | 2026-07-25 | 2026-07-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-26 21:05:10 | Yes | Yes | 2026-08-07 19:11:46 |  | 2026-08-08 | 2026-08-18 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-13 10:46:49 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-08 | 2026-08-08 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-08 11:13:43 |  | 2026-07-31 | 2026-08-31 | 2026-07-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-26 18:50:22 | No | No |  |  |  |  | 2026-07-25 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-07-25 17:34:46 | No | No |  | Rep UBBPd5*1 to UBBPg3a*1 S3 > AAU5656 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TTP2M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI TEETIP2 | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:43:41 | No | No |  |  |  | 2026-09-30 | 2026-09-10 | 2026-09-12 | Teloneer Company Limited | N/A | Closed | 2026-09-12 15:35:08 | Yes | Yes | 2026-09-16 10:46:40 | "1.Checklist need to fill correct and dismantle RRU over view photo mismatch with onsite information 2.New install RRU socket left /right side view photo and 18mm view photo need to upload 3.NEW install RRU BBU indoor label need to upload show clear " | 2026-09-20 | 2026-09-20 | Nattawoot Suwan | Approving | Assigned |  | Yes | Yes | 2026-09-20 16:24:45 | Page.5 need to revise RRU5507 2pcs | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:55:19 | Yes | Yes | 2026-09-20 17:56:32 |  |  | 2026-09-30 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 11:55:16 | No | No |  |  |  |  | 2026-08-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-08-28 20:01:04 | No | No |  | 28-Aug-2026 Add RRU5507 S1 Rmv RRU3962 Add RRU5507 S2 Rmv RRU3962 Add RRU5526 S3 Rmv RRU3962 *2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-04 16:14:27 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TTSAM_2026 Capacity Expansion Ph1_EXP_SR | Talad Thasae | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-21 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-20 | 2026-08-31 | 2026-09-21 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-21 18:00:35 | No | No |  |  |  |  | 2026-09-20 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-20 19:56:55 | No | No |  | Rep d5*1 to h3a*1 Re LB S1>S2#， S2>S1 ReMB S1&S6 > S2>S7 S1 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TUGMM_2026 Capacity Expansion Modernize_EXP_ER | Tung Klom | 2026-07-29 | Team : Team_Pooriwat Tel : 0925094222 |  |  | 2026-07-31 | 2026-07-29 | 2026-07-29 | Teloneer Company Limited | N/A | Closed | 2026-07-29 20:34:20 | No | No |  |  |  | 2026-07-31 | 2026-08-03 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 20:52:29 | Yes | Yes | 2026-08-08 20:08:30 |  | 2026-08-20 | 2026-08-09 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:54:09 | Yes | Yes | 2026-08-13 07:33:06 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-20 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:25 | No | No |  |  | 2026-07-31 | 2026-07-29 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-29 12:07:40 |  |  | 2026-07-31 | 2026-07-29 | Teloneer Company Limited | N/A | Closed | 2026-07-29 21:37:53 | No | No |  |  |  |  | 2026-07-29 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-29 19:32:48 | No | No |  | Add RRU5505 x 1 + 4T4R_TUGMM_H_2 >21 Add RRU5505 x 1 + 4T4R_TUGMM_H_3 >22 Replace RRU (RRU5516_900) + 4T4R_TUGMM_L_1 Replace RRU (RRU5516_900) + 4T4R_TUGMM_L_2 Replace RRU (RRU5516_900) + 4T4R_TUGMM_L_3 |  | 2026-07-30 | Reungsak Junkong 00927496 | N/A | Closed | 2026-07-30 19:06:52 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TUGMM_2026 Capacity Expansion Ph2_EXP_ER | Tung Klom |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TUGNM_2026 Capacity Expansion Ph2_EXP_ER | Ban Thung Noi | 2026-10-02 | Team : Thcp_phet.sa Tel : 0924272237 | Clear Pending |  | 2026-10-15 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-10-15 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-10-15 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-29 | Boonchot Boriwut(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-29 13:54:32 |  |  | 2026-10-15 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TUHGM_2026 Capacity Expansion Ph1_EXP_ER | Tung Hiang | 2026-06-08 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-06-30 | 2026-06-08 | 2026-06-08 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-09 16:13:45 | No | No |  |  |  | 2026-06-30 | 2026-06-09 | 2026-06-10 | Teloneer Company Limited | N/A | Closed | 2026-06-10 12:02:35 | Yes | Yes | 2026-06-11 12:56:10 |  | 2026-06-30 | 2026-06-11 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:16:05 | Yes | Yes | 2026-06-11 19:38:48 |  | First Time Pass | 2026-07-20 | 2026-07-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-20 17:23:49 | No | Yes | 2026-07-20 17:23:38 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-08 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-14 15:06:51 | No | No |  |  | 2026-06-30 | 2026-06-04 | Palagon Prommueangma(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:20 | Yes | Yes | 2026-06-05 15:15:39 |  | 2026-06-09 | 2026-06-30 | 2026-06-08 | Teloneer Company Limited | N/A | Closed | 2026-06-08 16:11:06 | No | No |  |  |  |  | 2026-06-08 | Reungsak Junkong 00927496 | N/A | Closed | 2026-06-08 19:38:28 | No | No |  | Add UBBPg2 + Replace Antenna (Dualbeam)_TUHGM_H_1 Replace Antenna (Dualbeam)_TUHGM_H_2 Replace Antenna (Dualbeam)_TUHGM_H_3 Replace Antenna (Dualbeam)_TUHGM_H_4 ReSectorname S9 to S6_TUHGM_H_6 ReSectorname S2 to S6_TUHGM_L_6 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_TUHGM_H_7 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_TUHGM_H_8 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_TUHGM_H_9 New L21(5M) all sector |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TUNMM_2026 Capacity Expansion Modernize_EXP_ER | TukNam | 2026-08-04 | Team : thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 17:34:48 | No | No |  |  |  | 2026-08-20 | 2026-08-10 | 2026-08-10 | Teloneer Company Limited | N/A | Closed | 2026-08-10 21:07:23 | Yes | Yes | 2026-08-13 12:34:15 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:56:12 | Yes | Yes | 2026-08-16 17:21:01 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-15 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:23 | Yes | Yes | 2026-08-13 11:59:04 |  |  | 2026-08-15 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 18:12:17 | No | No |  |  |  |  | 2026-08-04 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-04 12:50:18 | No | No |  | Add RRU5505 x 1 + 4T4R_TUNMM_H_8 |  | 2026-08-04 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-04 12:50:29 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TVBCM_2026 Capacity Expansion NW Modernization_EXP_BKK | THE VILE BANGCHAK | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:32:47 |  |  | 2026-06-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TWCHM_2025 Capacity Expansion NW Modernization_EXP_BKK | TAWEECHAI HOUSE |  |  |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-18 15:59:49 | No | No |  |  | 2026-02-27 | 2026-02-27 | 2026-02-27 | 2026-03-01 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-01 12:35:05 | Yes | Yes | 2026-03-04 14:03:10 |  | 2026-03-30 | 2026-03-30 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-04 20:50:30 | Yes | Yes | 2026-03-30 11:37:45 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-03-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-08-01 20:02:21 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-25 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-25 16:43:36 | No | No |  | 25-Feb-26 Replace RRU5507 To DDM S1 S2 S3 Add UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TYOGM_2026 Capacity Expansion Ph1_EXP_SR | Tanyongyaha | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 |  |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-21 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-20 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-20 17:08:58 | No | No |  | 20 Aug 2026 Add AAU5656 sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TYTKM_2026 Capacity Expansion Ph1_EXP_SR | Talad Yantakao | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-19 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-19 | 2026-08-31 | 2026-09-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-19 20:45:53 | No | No |  |  |  |  | 2026-09-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-19 18:49:02 | No | No |  | Rep d5*1 to h3a*1 Remove MB S1#，S3#，S4 S1 > AAU5775 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UAICI_2026 Capacity Expansion Ph1_EXP_SR | Auychai | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-10 | 2026-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-11 20:51:59 | Yes | Yes | 2026-08-20 12:45:34 |  | 2026-08-21 | 2026-08-27 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-27 13:46:10 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-21 | 2026-08-21 | Duangden Manas(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-21 01:40:15 |  | 2026-08-10 | 2026-08-31 | 2026-08-10 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-10 14:04:29 | No | No |  |  |  |  | 2026-08-10 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-10 18:36:04 | No | No |  | 10 Aug 2026 Replace RRU5516 sector1 add 1UBBPh2 Re dir only |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UK54M_D2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | UDOMSUK SOI 54 |  |  |  | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-06-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-26 18:54:47 | No | No |  |  | 2026-06-23 | 2026-06-23 | 2026-06-25 | 2026-06-26 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-06-26 17:37:59 | Yes | Yes | 2026-07-02 09:47:59 |  | 2026-07-03 | 2026-07-08 | Mahadee Japakiya(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-08-31 18:21:36 | Yes | Yes | 2026-07-08 22:02:11 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-03 17:02:38 | No | No |  |  | 2026-07-08 | 2026-07-08 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-07-08 21:50:43 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-06-20 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-06-20 18:43:06 | No | No |  | 20-06-2026. Add UBBPg2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNMAP_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | UNION MALL | [5 empty] | 2026-09-03 | 2026-09-03 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-08-08 | 2026-09-10 | 2026-09-11 | Teloneer Company Limited | N/A | Closed | 2026-09-11 14:52:19 | Yes | Yes | 2026-09-17 09:17:07 |  | 2026-09-17 | 2026-09-17 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-09-17 10:55:35 | Need to upload INV page. Page 20#，21#， need to fill project name. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:33:22 |  |  | 2026-08-08 | 2026-09-03 | Teloneer Company Limited | N/A | Closed | 2026-09-03 17:36:14 | No | No |  |  |  |  | 2026-09-03 | Autumporn Masing WX1434753 | N/A | Closed | 2026-09-03 17:07:17 | No | No |  | 2026-09-03 RMV d6//add g3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-03 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:11:38 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNMAP_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | UNION MALL | [5 empty] | 2026-09-03 | 2026-09-03 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-08-08 | 2026-09-11 | 2026-09-11 | Teloneer Company Limited | N/A | Closed | 2026-09-11 13:36:57 | Yes | Yes | 2026-09-17 09:17:20 |  | 2026-09-17 | 2026-09-17 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-09-17 10:56:49 | Inventory no found | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:30:50 | Yes | Yes | 2026-08-17 22:33:48 |  |  | 2026-08-08 | 2026-09-03 | Teloneer Company Limited | N/A | Closed | 2026-09-03 15:36:25 | No | No |  |  |  |  | 2026-09-03 | Autumporn Masing WX1434753 | N/A | Closed | 2026-09-03 17:07:17 | No | No |  | 2026-09-03 add h2a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-03 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:11:38 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
UNMAP_D2_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | UNION MALL | [5 empty] | 2026-09-03 | 2026-09-03 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-08-08 | 2026-09-08 | 2026-09-19 | Teloneer Company Limited | N/A | Closed | 2026-09-19 09:58:32 | Yes | Yes | 2026-09-29 09:32:40 | 1.Found BBP g3a and ph3a add in QC can't found BBP g3 in QC 2.BBP miss mark at Before and QC. Need to revise. | 2026-10-01 | 2026-10-01 | Teloneer Company Limited | Ready To Approve | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:30:50 | Yes | Yes | 2026-08-17 22:34:29 |  |  | 2026-08-08 | 2026-09-03 | Teloneer Company Limited | N/A | Closed | 2026-09-03 15:51:02 | No | No |  |  |  |  | 2026-09-03 | Autumporn Masing WX1434753 | N/A | Closed | 2026-09-03 17:07:17 | No | No |  | 2026-09-03 add g3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-03 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:11:38 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VALHB_2025 Capacity Expansion NW Modernization_EXP_BKK | VALIA HOTEL BANGKOK |  |  |  | 2026-05-22 | 2026-05-22 | 2026-05-22 | 2026-05-22 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-22 15:32:04 | No | No |  |  | 2026-05-31 | 2026-05-31 | 2026-05-27 | 2026-05-27 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-27 20:43:48 | Yes | Yes | 2026-07-07 14:46:09 |  | 2026-07-14 | 2026-07-14 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approving | Assigned |  | Yes | Yes | 2026-07-14 15:25:44 | page.7#，48 need to revise 16A/1P 3pcs | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-14 | 2026-07-14 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:30:49 | Yes | Yes | 2026-07-14 22:58:38 |  |  | 2026-05-31 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-05-21 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-05-21 18:23:53 | No | No |  | 21-May-26 Replace BBU5900 Add UBBPg2 Replace RRU3962>>RRU5526 SA SB Replace RRU3962>>RRU5507*2 SC |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VDE1M_2026 Capacity Expansion NW Modernization_EXP_BKK | WIPHAWADI 1 | [5 empty] | 2026-09-24 | 2026-09-24 | Thossapan Chaloemrit | N/A | Closed | 2026-09-28 16:14:22 | No | No |  |  |  | 2026-10-10 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-10-10 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 16:05:03 | No | No |  |  |  |  | 2026-09-23 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-23 17:28:54 | No | No |  | 23-Sep-2026 Add UBBPh3a Add AAU5775 S1 Rmv RRU5507 *2 Add AAU5775 S2 Rmv RRU5507 *2 Add RRU5507 *2 S3 Rmv RRU3962*2 Rmv RRU5507 *2 S6 Rmv RRU5507 *2 S7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VHCSA_2026 Capacity Expansion NW Modernization_EXP_BKK | VAJIRA HOSPITAL CENTRAL STERILE SUPPLY DEPARTMENT (Small Cell) | [5 empty] | 2026-09-04 | 2026-09-04 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-09-30 | 2026-09-11 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 19:52:42 | Yes | Yes | 2026-09-25 19:53:25 | revise 2.S2 socket left/right and 18 mm view photo need to upload because you upload photo same S1 need to revise correct photo for S2 3.BBP card mismatch with EQ and checklist d5 d5 eb d5 d5 g3a g2 h2a d5 eb d5 d5 g3a g2 |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:55:19 | Yes | Yes | 2026-09-20 17:57:16 |  |  | 2026-09-30 | 2026-09-04 | Teloneer Company Limited | N/A | Closed | 2026-09-04 21:40:40 | No | No |  |  |  |  | 2026-09-04 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-09-04 18:19:10 | No | No |  | 2026-09-04 sA replace RRU3962 to RRU5507*2 sB replace RRU3962 to RRU5507*2 add UBBPg3a#，UBBPeb/rmv UBBPg2#，UBBPd6 vswr 1800/2100 sA#2 port A 1800/2100 sB#1 port B#， 1800/2100 sB#2 port B |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-04 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:12:35 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VJRHP_2026 Capacity Expansion NW Modernization_EXP_BKK | VAJIRA HOSPITAL | [5 empty] | 2026-09-04 | 2026-09-04 | Thossapan Chaloemrit | N/A | Closed | 2026-09-07 21:43:07 | No | No |  |  |  | 2026-09-30 | 2026-09-08 | 2026-09-09 | Teloneer Company Limited | N/A | Closed | 2026-09-09 18:37:10 | Yes | Yes | 2026-09-10 12:47:38 |  | 2026-10-03 | 2026-09-10 | Payon Thappat(Teloneer Company Limited) | Approving | Assigned |  | Yes | Yes | 2026-09-10 13:56:16 | need to revise inventory file. page.12 need to upload before and after Alarm Krone | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:55:19 | Yes | Yes | 2026-09-20 17:58:04 |  |  | 2026-08-31 | 2026-09-04 | Teloneer Company Limited | N/A | Closed | 2026-09-04 20:41:21 | No | No |  |  |  |  | 2026-09-04 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-09-04 18:19:52 | No | No |  | 2026-09-04 add UBBPh2a/rmv UBBPd5 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-04 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:12:35 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
VSTNM_2026 Capacity Expansion Ph2_BKK | VAT SAO TONG NOK | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WABNB_2026 Capacity Expansion NW Modernization_EXP_BKK | WAT BANG NA NAI | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-02 16:55:09 | No | No |  |  |  | 2026-08-31 | 2026-09-11 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 20:36:25 | Yes | Yes | 2026-09-25 20:36:36 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:55:19 | Yes | Yes | 2026-09-20 17:58:56 |  |  | 2026-06-30 | 2026-08-27 | Teloneer Company Limited | N/A | Closed | 2026-08-27 20:14:51 | No | No |  |  |  |  | 2026-08-27 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-08-27 19:17:52 | No | No |  | 2026-08-27 Replace RRU3962 > RRU5526 (18/21 4T) + Replace Ant to 4port No RET Replace Card UBBPg3*2 > UBBPd6#，UBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:27:43 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WAGWM_2026 Capacity Expansion Ph1_EXP_ER | Wat Ang Wian | 2026-06-02 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-06-30 | 2026-06-02 | 2026-06-02 | Palagon Prommueangma(Teloneer Company Limited) | N/A | Closed | 2026-06-04 17:52:42 | No | No |  |  |  | 2026-06-30 | 2026-06-04 | 2026-06-04 | Teloneer Company Limited | N/A | Closed | 2026-06-04 17:37:04 | Yes | Yes | 2026-06-04 18:00:15 |  | 2026-06-30 | 2026-06-16 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:17:04 | Yes | Yes | 2026-06-16 08:52:21 |  | Pass | 2026-07-20 | 2026-07-20 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-20 17:24:37 | No | Yes | 2026-07-20 17:24:27 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-06-22 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-07 15:06:00 | No | No |  |  | 2026-06-30 | 2026-06-02 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:31 | Yes | Yes | 2026-06-02 12:42:50 |  | 2026-06-04 | 2026-06-30 | 2026-06-08 | Teloneer Company Limited | N/A | Closed | 2026-06-08 15:18:08 | No | No |  |  |  |  | 2026-06-02 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-06-02 17:32:02 | No | No |  | "Add UBBPh2a Replace Antenna (Dualband)_WAGWM_H_1 Add RRU5505 x 1 + 4T4R_WAGWM_H_2 Replace Antenna (Co Antenna)_WAGWM_N_1 New L0709 + NR07 + 4T4R + (RRU5516_900) + (Co Antenna)_WAGWM_L_1" |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-20 | Nattawoot Suwan | N/A | Closed | 2026-06-20 11:07:58 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WBACM_2026 Capacity Expansion Ph2_BKK | SOI WAT BANG AOI CHANG | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WBCNM_2026 Capacity Expansion Ph1_EXP_BKK | WAT BANG CHALONG NOK | [5 empty] | 2026-08-03 | 2026-08-03 | Thossapan Chaloemrit | N/A | Closed | 2026-08-03 16:03:00 | No | No |  |  |  | 2026-07-31 | 2026-07-31 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 21:05:55 | Yes | Yes | 2026-08-07 11:14:51 |  | 2026-08-11 | 2026-08-11 | Teloneer Company Limited | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 13:00:01 | Page 5 Need to Delete Add CB63A2P And Reposition AAU Need to fill. Page 17 and 18 Site Name Not Found . Page 22 Need to Upload Connection under AAU Photo. Page 50 Photo Wrong Need to Upload Provisional Acceptance Test Photo . | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-20 11:33:07 |  |  | 2026-06-30 | 2026-07-28 | Teloneer Company Limited | N/A | Closed | 2026-07-28 10:51:26 | No | No |  |  |  |  | 2026-07-25 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-07-25 17:15:38 | No | No |  | 25-Jul-26 ADD 5516 s2 #，rmv 5508#，3953 Add AAU5656 s7 24-Jul-26 add UBBPh3a slot4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-04 16:07:52 | No | No |  |  | SQC closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WBENM_2026 Capacity Expansion NW Modernization_EXP_BKK | WAT BENCHAMABOPIT DUSIT WANARAM | [5 empty] | 2026-09-11 | 2026-09-11 | Thossapan Chaloemrit(Teloneer Company Limited) | N/A | Closed | 2026-09-21 12:47:10 | No | No |  |  |  | 2026-09-30 | 2026-09-14 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 19:56:46 | Yes | Yes | 2026-09-25 19:57:45 | 1.Need clear breaker photo at after sec. 2. 2.Site code wrong. 3.Need Ground- DCDU#， label at after on ground. 4.Need EPS- Rectifier#， Rectifier- EPS#， EPS - Ground#， Ground - EPS label at after. 5#，.Dis RRU overview and SN photo not complete at before on tower. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:55:19 | Yes | Yes | 2026-09-20 18:00:07 |  |  | 2026-09-30 | 2026-09-11 | Teloneer Company Limited | N/A | Closed | 2026-09-11 13:46:33 | No | No |  |  |  |  | 2026-09-10 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-09-10 12:47:35 | No | No |  | 10-Sep-2026 Add UBBPh3a UBBPg2 Rmv d5 =2 Add AAU5775 S1 Rmv RRU3962 Add RRU5507*2 S2 Rmv RRU3962 *2 Add AAU5775 S3 Rmv RRU3962 Rmv RRU3962 S6 Rmv RRU3962*2 S7 Rmv RRU3962 S8 Down grade S7 Add RRU5516 S1 s2 s3 Rmv RRU3953 *3 2026-09-09_Pre work |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-12 | Teloneer Company Limited | N/A | Closed | 2026-09-16 12:30:25 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WBLKM_2026 Antenna Dualbeam_Replacement_BKK | WAT BUAKWAN LAT LUM KAEW |  |  |  | 2026-04-23 | 2026-04-23 | 2026-04-23 | 2026-04-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-23 14:59:53 | No | No |  |  | 2026-05-09 | 2026-05-23 | 2026-05-10 | 2026-05-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-10 16:09:20 | Yes | Yes | 2026-05-11 11:47:38 |  | 2026-05-12 | 2026-05-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-17 16:25:33 | Yes | Yes | 2026-05-20 18:18:07 | 1.Page 29#，In EQ ANT model wrong. | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 21:57:19 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-04 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-04-04 19:20:29 | No | No |  | 04-04-2026. Replace Ant.12 port Sec.3#， Config 2T4R //3-Apr-2026 Replace Ant 12port S1 S6 Remove Ant 4port *1 Done |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WBMGM_2026 Capacity Expansion Ph2_BKK | WAT BANG MUANG | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WCHRM_2026 Capacity Expansion NW Modernization_EXP_BKK | WACHIRA | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:43:41 | No | No |  |  |  | 2026-09-30 | 2026-09-12 | 2026-09-25 | Teloneer Company Limited | N/A | Closed | 2026-09-25 19:45:09 | Yes | Yes | 2026-09-25 19:45:56 | 1.Not matched with on side data at eq. 2.Need RRU (1.1#， 1.2#，2.1#，2.2)socket wire strip#， left and right side view photo at after sec 1#，2#，pls reupload at after sec#， no need to upload at eq. 3.Need AAU socket wire strip#， leftand right side view photo at after sec 3. 4.Need install and dismantle breaker overview photo at eq. 5.Need DCDU-Rectifier#， DCDU-Ground at after c1. 6.Wrong panorama photo at 210 degree. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:55:19 | Yes | Yes | 2026-09-20 18:00:55 |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  |  | 2026-08-26 | Chirapat Khaokaew WX1514512 | N/A | Closed | 2026-08-26 18:29:00 | No | No |  | 2026-08-26 add S1 RRU5507 ตัวที่ 2 on 4T 2026-08-25 S1 REP RRU3962*1 to RRU5507*1 On 2T S2 REP RRU3962*2 to RRU5507*2 S3 REP RRU3962*2 to AAU5775 S8 RMV RRU3962*1 S1 REP ANT 8 port rmv d5// add h3a ************Pending S1 RRU5507 ตัวที่ 2 on 4T |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-04 16:14:27 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WCHRM_D1_2026 Capacity Expansion NW Modernization_BBU-Board_BKK | WACHIRA | [5 empty] | 2026-09-01 | 2026-09-01 | Thossapan Chaloemrit | N/A | Closed | 2026-09-01 17:52:00 | No | No |  |  |  | 2026-08-08 | 2026-09-04 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 17:19:58 | Yes | Yes | 2026-09-29 09:35:34 | >> Need to upload EHS photo. >>Can't see clearly GPS and Surge GPS in Equip checklist. >>Need to upload AC box in BF and AF section. >>Need to upload Alarm Krone in BF section. >>Need to upload DCDU overview in BF section. >>Need to uploa Cabinet ground bar in BF section. >>Need to uploaCabinet Inlet/Outlet in BF section. | 2026-10-01 | 2026-10-01 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-10-01 18:11:14 | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-17 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:28:45 | Yes | Yes | 2026-08-17 22:34:57 |  |  | 2026-08-08 | 2026-08-27 | Teloneer Company Limited | N/A | Closed | 2026-08-27 11:42:01 | No | No |  |  |  |  | 2026-08-06 | Walwisa Kawpong WX1345404 | N/A | Closed | 2026-08-31 19:50:39 | No | No |  | 6-Aug-2026 Replace BBU5900 UMPTg2 Add GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-09-01 | Teloneer Company Limited | N/A | Closed | 2026-09-08 12:10:40 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WCKRM_2026 Capacity Expansion Ph2_BKK | WAT CHOTIKARAM | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WCWPT_RET_2025_RepSGR_NER | WATSRICHUMPOL WAPIPATHUM |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-18 | 2026-09-24 | Teloneer Company Limited | N/A | Closed | 2026-09-24 21:01:16 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-12-29 |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-24 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-18 | Teloneer Company Limited | N/A | Closed | 2026-09-18 10:20:02 | No | No |  |  | DTH1202609100005 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
WDAOM_2026 Antenna Dualbeam_Replacement_BKK | WAT DAO RUEANG |  |  |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-12 13:15:06 | No | No |  |  | 2026-05-31 | 2026-05-31 | 2026-05-09 | 2026-05-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-10 09:52:26 | Yes | Yes | 2026-05-11 09:15:43 |  | 2026-05-12 | 2026-05-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-09-04 20:50:30 | Yes | Yes | 2026-05-12 13:14:54 | PAT pass | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-06 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 21:57:34 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-29 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-04-29 16:56:30 | No | No |  | 29-Apr-26 Replace Ant S1 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WFMPM_2026 Capacity Expansion Ph2_EXP_ER | Wat NongFab Mabpai |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHCMM_2026 Capacity Expansion Ph2_EXP_ER | WHA Co Tower , Beside MAXXIS |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHCSM_2026 Capacity Expansion Ph2_EXP_ER | WHA Co Tower , Service Road No.4 |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHCWM_2026 Capacity Expansion Ph2_EXP_ER | WHA Co Tower , WTP |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WHYIM_2026 Capacity Expansion Ph1_EXP_SR | WATHATYAI NAI | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-09 | 2026-08-17 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-17 14:13:48 | Yes | Yes | 2026-08-19 21:26:56 |  | 2026-08-21 | 2026-08-27 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-27 08:49:35 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-28 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  |  | 2026-08-27 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-27 08:50:57 |  | 2026-08-09 | 2026-08-31 | 2026-08-09 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-09 18:52:34 | No | No |  |  |  |  | 2026-08-09 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-09 19:16:21 | No | No |  | Rep eb*1 to h2a*1 S3 > Rep RRU3953*1 toRRU5516LB*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WIHHB_2026 Capacity Expansion NW Modernization_EXP_BKK | WIH INTERNATIONAL HOSPITAL | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-31 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-20 | Teloneer Company Limited | Approved | Closed | 2026-09-20 18:53:43 | Yes | Yes | 2026-09-20 18:01:54 |  |  | 2026-06-30 | 2026-09-04 | Teloneer Company Limited | N/A | Closed | 2026-09-04 11:16:30 | No | No | [6 empty] | N/A | Not assigned |  | No | No |  | 2026-09-02 SA REP RRU3962 to RRU5526 on 2T SB REP RRU3839 to RRU5526 on 2T Need Re-config to 4T after Swap BBU *******Pending Swap BBU |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKD2M_2026 Capacity Expansion Ph2_BKK | WAT KOAT KAN UDOM (STATION2) | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKHYM_2026 Capacity Expansion Ph1_EXP_ER | Wat KhaoHaYod | 2026-07-22 | Team : thcp_apichat.f Tel : 0960126111 |  |  | 2026-07-31 | 2026-07-22 | 2026-07-22 | Teloneer Company Limited | N/A | Closed | 2026-07-22 18:28:56 | No | No |  |  |  | 2026-07-31 | 2026-07-22 | 2026-07-23 | Teloneer Company Limited | N/A | Closed | 2026-07-23 16:39:55 | Yes | Yes | 2026-07-28 14:56:49 |  | 2026-07-31 | 2026-07-28 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:01:23 | Yes | Yes | 2026-07-28 16:58:22 |  | First Time Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:34:22 | No | Yes | 2026-09-12 10:33:31 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:15 | No | No |  |  | 2026-07-20 | 2026-07-21 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:15:49 | Yes | Yes | 2026-07-21 11:10:49 |  |  | 2026-07-31 | 2026-07-27 | Teloneer Company Limited | N/A | Closed | 2026-07-27 11:47:53 | No | No |  |  |  |  | 2026-07-22 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-07-22 14:14:16 | No | No |  | Add UBBPg3a at slot5 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WKHYM_H_4 >> 4port4 Replace RRU (RRU5516_900) +4T4R_WKHYM_L_1 New L26F5 + NR26 (New AAU5656)_WKHYM_N_2 Co L21(F2) all sector |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 50% , Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKKHM_2026 Antenna Dualbeam_Replacement_BKK | WAT KHLONG KHWANG |  |  |  | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-07 14:11:57 | No | No |  |  | 2026-04-30 | 2026-04-30 | 2026-04-09 | 2026-04-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-10 11:58:10 | Yes | Yes | 2026-04-27 09:12:49 |  | 2026-05-07 | 2026-05-07 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-17 16:25:33 | Yes | Yes | 2026-05-07 14:11:42 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 21:57:50 |  |  | 2026-04-30 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-04-03 | Paphawarin Yoopoo WX1434740 | N/A | Closed | 2026-04-03 17:03:08 | No | No |  | 2026-04-03_Replace to Ant 4x4 (ODHI2-32R18J65R16M-GQ-TH) Sector 1#，2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKKOB_2026 Capacity Expansion Ph1_EXP_SR | Wat Khao Kob | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-01 | 2026-08-01 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-01 18:17:29 | Yes | Yes | 2026-08-07 19:11:53 |  | 2026-08-08 | 2026-08-18 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-08 14:34:19 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-21 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-29 09:33:26 | No | No |  |  | 2026-08-08 | 2026-08-08 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-08 14:36:03 |  | 2026-08-01 | 2026-08-31 | 2026-08-01 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-01 13:29:21 | No | No |  |  |  |  | 2026-08-01 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-01 17:51:46 | No | No |  | Rep Ant MB S3 to Ant 8 Port S3 > Rep RRU&Ant 3953*1 to 5516LB*1 > Ant Combine MB S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKNSI_2026 Capacity Expansion Ph1_EXP_SR | Wat Khuan Si | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-12 | 2026-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-12 20:48:23 | Yes | Yes | 2026-08-15 12:25:48 |  | 2026-08-16 | 2026-08-16 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-16 19:53:50 | Review and Revise / PAT and INV Done | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-16 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-16 19:54:41 |  | 2026-08-17 | 2026-08-31 | 2026-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-12 14:51:18 | No | No |  |  |  |  | 2026-08-12 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-12 19:27:23 | No | No |  | Rep BBU5900#，add h2a*1#，add gps S2 > 5516*LB > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKPTM_2026 Capacity Expansion Ph2_EXP_ER | Wat KhaoPhoThong |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKSTG_2026 Capacity Expansion Ph1_EXP_SR | Wat Khuan Sao Thong | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-19 | 2026-08-20 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-20 12:06:37 | Yes | Yes | 2026-08-24 14:58:33 |  | 2026-09-02 | 2026-09-02 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-05 20:20:42 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-02 | 2026-09-02 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-02 08:57:38 |  | 2026-08-19 | 2026-08-31 | 2026-08-19 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-19 17:56:20 | No | No |  |  |  |  | 2026-08-19 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-19 18:30:56 | No | No |  | Add UBBPh2a*1 Rep Ant MB S3 S3 > RRU3953*2 to RRU5516*1 > Ant Combine MB S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WKTNM_2025 Capacity Expansion NW Modernization_EXP_BKK | WAT KLONG TAEY NOK | [5 empty] | 2026-04-05 | 2026-04-05 | Akhom Srinara | N/A | Closed | 2026-04-21 20:45:20 | No | No |  |  |  | 2026-02-24 | 2026-03-25 | 2026-04-02 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-04-02 10:47:20 | Yes | Yes | 2026-04-02 12:01:12 |  | 2026-04-05 | 2026-04-07 | Charuwan Limsaihua(Future Telecom Co.,Ltd.) | Approved | Closed | 2026-07-31 18:23:03 | Yes | Yes | 2026-04-07 12:35:20 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-31 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-04-21 | 2026-04-21 | Charuwan Limsaihua | Approved | Closed | 2026-06-19 15:27:18 | Yes | Yes | 2026-04-21 15:47:36 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-03-17 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-03-17 17:37:37 | No | No |  | 17-Mar-26 Replace RRU3953 > RRU5516 S1 S2 Replace RRU3962 >> RRU5526 S1 Replace Ant S1 S2 2026-03-16_Replace RRU3953 to RRU5508 Sector 3#， *** Pending Replace RRU3962 to RRU5526 Sector 1#， Replace RRU3953 to RRU5516(LB) Sector 1#，2#， Replace Ant to 8 port Sector 1#，2 //24-Feb-26 Replace RRU3962 To AAU568 S3 #，Add UBBPg2 //Pending Replace RRU3953 S1 S2 TO RRU5516 S1 S2 #，Replace RRU3953 S3 TO RRU5508 #，Replace RRU3962 To RRU5526 S1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WLBKM_2026 Capacity Expansion Ph2_BKK | Wat Lat Bua Khao | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WLGTM_2025 Coverage Expansion Ph2_New Site_Remote-BBU_ER | Wellgrow Industrial Estate Water Tank P5 |  |  |  |  | 2026-08-20 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-08-20 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-08-20 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-20 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WLGWM_2026 Capacity Expansion Ph2_EXP_ER | Wellgrow |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WMCRM_2026 Capacity Expansion Ph2_BKK | WAT MAI CHAROENRAT | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WMSGM_2026 Antenna Dualbeam_Replacement_BKK | WAT MASONG |  |  |  | 2026-05-07 | 2026-05-07 | 2026-05-07 | 2026-05-07 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-07 14:11:57 | No | No |  |  | 2026-04-30 | 2026-04-30 | 2026-04-09 | 2026-04-10 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-04-10 11:51:06 | Yes | Yes | 2026-04-27 15:20:36 |  | 2026-05-07 | 2026-05-07 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-06-17 16:25:33 | Yes | Yes | 2026-05-07 14:46:27 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 21:58:08 |  |  | 2026-04-30 |  | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-04-04 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-04-04 19:20:29 | No | No |  | 04-04-2026. Replace Ant.12 port Sec.1#， 3#， Config 2T4R |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WNBGM_2026 Capacity Expansion Ph1_EXP_ER | Wat Nong Bondaeng | 2026-07-24 | Team : Team_Pooriwat Tel : 0925094222 | Install & Integrate |  | 2026-07-31 | 2026-07-24 | 2026-07-24 | Teloneer Company Limited | N/A | Closed | 2026-07-24 16:36:40 | No | No |  |  |  | 2026-07-31 | 2026-07-28 | 2026-07-30 | Teloneer Company Limited | N/A | Closed | 2026-07-30 14:34:49 | Yes | Yes | 2026-08-01 21:11:13 |  | 2026-07-31 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-16 18:58:26 | Yes | Yes | 2026-08-12 12:59:32 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-24 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-27 14:04:05 | No | No |  |  | 2026-07-31 | 2026-07-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-25 12:10:05 | Yes | Yes | 2026-07-24 10:26:03 |  |  | 2026-07-31 | 2026-07-24 | Teloneer Company Limited | N/A | Closed | 2026-07-24 19:09:25 | No | No |  |  |  |  | 2026-07-24 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-24 15:30:05 | No | No |  | Add UBBPg3a + Replace UBBPg1 to UBBPg2 + Replace Antenna (Dualband Dualbeam)_WNBGM_H_1 Off Service Sector + Remove Antenna + Remove RRU x 1_zz-Offservice H8 Replace Antenna (Co Antenna)_WNBGM_L_1 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_WNBGM_H_6 New L26F5 + NR26 (New AAU5656)_WNBGM_N_2 Co L21F2 Sec.6 |  | 2026-07-27 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-27 20:48:17 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WNBGM_2026 Capacity Expansion Ph2_EXP_ER | Wat Nong Bondaeng |  |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | No | No |  |  |  | 2026-09-30 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WNIBM_2026 Capacity Expansion Ph1_EXP_ER | Wat Ban Nai Bon | 2026-07-06 | Team :thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-07-15 | 2026-07-06 | 2026-07-06 | Teloneer Company Limited | N/A | Closed | 2026-07-06 17:51:20 | No | No |  |  |  | 2026-07-20 | 2026-07-07 | 2026-07-09 | Teloneer Company Limited | N/A | Closed | 2026-07-09 12:07:46 | Yes | Yes | 2026-07-09 12:13:12 |  | 2026-07-15 | 2026-07-16 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-07-23 08:18:40 | Yes | Yes | 2026-07-16 09:39:36 |  | Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-07 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-10 16:09:40 | No | No |  |  | 2026-07-31 | 2026-07-03 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-05 20:51:42 | Yes | Yes | 2026-07-03 12:37:50 |  |  | 2026-07-15 | 2026-07-06 | Teloneer Company Limited | N/A | Closed | 2026-07-06 18:37:12 | No | No |  |  |  |  | 2026-07-06 | Pakin Klantip WX1491930 | N/A | Closed | 2026-07-06 17:01:04 | No | No |  | Add UBBPg3a_WNIBM_H_1 New L26F5 + NR26 (New RRU5872) + Co Antenna_WNIBM_N_1 New L26F5 + NR26 (Co RRU5872) + Co Antenna_WNIBM_N_3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-31 | 2026-07-08 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-07-13 04:19:49 | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WNSWM_2026 Capacity Expansion Modernize_EXP_ER | Wat Noensutthawas | 2026-06-17 | Team : Thcp_phet.sa Tel : 0924272237 | Install & Integrate |  | 2026-06-30 | 2026-06-17 | 2026-06-17 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-17 21:12:35 | No | No |  |  |  | 2026-06-30 | 2026-06-17 | 2026-06-18 | Teloneer Company Limited | N/A | Closed | 2026-06-18 09:25:59 | Yes | Yes | 2026-06-24 13:59:38 |  | 2026-06-30 | 2026-06-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-28 22:14:03 | Yes | Yes | 2026-06-25 08:03:22 |  | First Time Pass | 2026-09-12 | 2026-09-12 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-12 10:39:05 | No | Yes | 2026-09-12 10:38:00 |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-16 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-16 16:50:00 | No | No |  |  | 2026-06-30 | 2026-06-17 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:11:17 | Yes | Yes | 2026-06-17 10:29:43 |  | 2026-06-19 | 2026-06-30 | 2026-06-17 | Teloneer Company Limited | N/A | Closed | 2026-06-17 13:28:35 | No | No |  |  |  |  | 2026-06-17 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-06-17 19:50:29 | No | No |  | Replace Antenna (Dualbeam)_WNSWM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WNSWM_H_7 1/4 New L18L21 + 4T4R+ Add RRU5505 x 2 + Co Antenna_WNSWM_H_6 1/0#，1/3 Co L21F2 all sector |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-06-20 | Nattawoot Suwan | N/A | Closed | 2026-06-20 11:07:58 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WNUKM_2025 Capacity Expansion Ph8_EXP_ER | Wattananukij | 2026-02-25 | Thcp_phet.sa | Take Photo & Clear Pending |  | 2026-02-28 | 2026-02-24 | 2026-02-24 | Teloneer Company Limited | N/A | Closed | 2026-02-24 17:00:25 | No | No |  |  |  | 2026-02-28 | 2026-02-24 | 2026-02-25 | Teloneer Company Limited | N/A | Closed | 2026-02-25 12:13:41 | Yes | Yes | 2026-07-21 09:53:55 |  | 2026-02-28 | 2026-02-26 | Thanakit Chaleechai(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:23:34 | Yes | Yes | 2026-03-11 16:36:46 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-14 | 2026-03-13 | Jutatip Tiprean 84012709 | Approved | Closed | 2026-04-09 20:33:02 | Yes | Yes | 2026-04-09 11:37:35 |  | 2026-02-28 | 2026-02-26 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-03-02 11:21:34 | Yes | Yes | 2026-02-26 07:41:27 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-24 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-02-27 16:25:38 | No | No |  | Add UBBPg3a New L26F5 + NR26 (New RRU5818) + Co Antenna_WNUKM_N_3 New L26F5 + NR26 (Co RRU5818) + Co Antenna_WNUKM_N_8 |  | 2026-02-27 | Reungsak Junkong 00927496 | N/A | Closed | 2026-02-27 16:25:33 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WPASM_2025 Capacity Expansion NW Modernization_EXP_BKK | WAT PHRAYA YANG SCHOOL |  |  |  | 2026-02-11 | 2026-02-11 | 2026-03-25 | 2026-03-25 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | N/A | Closed | 2026-03-25 13:32:02 | No | No |  |  | 2026-02-11 | 2026-02-11 | 2026-02-21 | 2026-03-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-03-23 15:08:54 | Yes | Yes | 2026-03-23 15:11:24 |  | 2026-04-03 | 2026-04-22 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 17:39:55 | Yes | Yes | 2026-04-22 14:57:06 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-14 | 2026-03-26 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 20:03:35 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-11 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-02-11 18:04:08 | No | No |  | 11-Feb-2026 Add AAU5768 S3 Remove RRU5502 *2 Add RRU5502 *1 sector 1 Remove RRU5507 *1 RRU3962*2 Sector 1 Add g3a Remove d6 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WPHKN_2026 Capacity Expansion Ph1_EXP_SR | WAT PHUKHAO NOY | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-23 | 2026-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-24 19:24:51 | Yes | Yes | 2026-09-30 10:49:35 | 1.Need to upload install RRU overview photos in EQ. 2.Need to red mark install RRU ground bar in QC. and Before and QC tower ground are the same#， why? 3. Need to upload ground bar 2 in Before section. |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-23 | 2026-08-31 | 2026-09-24 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-24 12:28:31 | No | No |  |  |  |  | 2026-09-23 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-23 18:28:56 | No | No |  | 23 Sep 2026 Add RRU5516 sector1 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WPKRA_2026 Capacity Expansion Ph1_EXP_SR | Wat Photi Ka Ram | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-11 | 2026-08-16 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-16 12:47:24 | Yes | Yes | 2026-08-17 16:19:07 |  | 2026-08-19 | 2026-08-25 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-25 17:52:56 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-08-19 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-19 09:38:17 |  | 2026-08-11 | 2026-08-31 | 2026-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-11 20:46:25 | No | No |  |  |  |  | 2026-08-11 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-11 17:32:03 | No | No |  | 11 Aug 2026 Add RRU5516 sector3 res3>8 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WPPNM_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI WIRAPHAPPHUNPHIN | [5 empty] | 2026-07-01 | 2026-07-01 | Teloneer Company Limited | N/A | Closed | 2026-07-01 09:33:49 | No | No |  |  |  | 2026-08-31 | 2026-06-30 | 2026-07-02 | Teloneer Company Limited | N/A | Closed | 2026-07-02 16:15:23 | Yes | Yes | 2026-07-09 09:49:25 |  | 2026-07-09 | 2026-07-30 | Teloneer Company Limited | Approved | Closed | 2026-08-31 10:55:21 | Yes | Yes | 2026-08-26 11:29:12 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-08 | 2026-07-09 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-07-09 10:30:24 |  |  | 2026-06-30 | 2026-06-29 | Teloneer Company Limited | N/A | Closed | 2026-06-29 14:07:01 | No | No |  |  |  |  | 2026-06-27 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-06-27 21:54:30 | No | No |  | 27-Jun-2026 Replace port to 10G Add UBBPh3a Remove g3 Add AAU5726 S1 Remove RRU5516 AAU5726 S2 Remove RRU5516 Remove Ant 8port S1 Remove RRU5516 S6 Remove RRU5516 S7 26 Jun 2026 Prework |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-09 | Teloneer Company Limited | N/A | Closed | 2026-07-09 10:14:19 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WPPSM_RET_2025_RepSGR_NER | WAPI PATHUM SCHOOL |  |  |  | 2026-09-12 | 2026-09-30 | 2026-09-23 | 2026-09-26 | Teloneer Company Limited | N/A | Closed | 2026-09-26 15:18:29 | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-26 |  |  |  | N/A | Not assigned |  | No | No |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | N/A | Not assigned |  | No | No |  |  |  |  | 2026-09-19 | 2026-09-22 | Teloneer Company Limited | N/A | Closed | 2026-09-22 19:50:02 | No | No |  |  | DTH1202609100008 | Shipped | To X-Docking(Subcon pick up to site) | 2026/09/11 16:39:31 | 2026/09/12 08:30:05
WPRNM_2026 Capacity Expansion Ph2_BKK | WAT PRACHA RANGSAN | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WRDRM_2026 Capacity Expansion Modernize_EXP_ER | Wat Radbamrung | 2026-08-06 | Team : THCP_Wachira.s Tel : 065-7640019 |  |  | 2026-08-15 | 2026-08-04 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 17:34:48 | No | No |  |  |  | 2026-08-20 | 2026-08-10 | 2026-08-13 | Teloneer Company Limited | N/A | Closed | 2026-08-13 14:14:45 | Yes | Yes | 2026-08-17 18:53:40 |  | 2026-08-20 | 2026-08-18 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-28 23:20:17 | Yes | Yes | 2026-08-18 21:27:52 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-20 | 2026-08-12 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-13 08:52:23 | Yes | Yes | 2026-08-12 17:09:43 |  |  | 2026-08-15 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 17:55:18 | No | No |  |  |  |  | 2026-08-04 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-04 14:13:13 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WRDRM_H_A Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WRDRM_H_B Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WRDRM_H_C Co L21F2 All Sector |  | 2026-08-05 | Pakin Klantip WX1491930 | N/A | Closed | 2026-08-05 17:32:43 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1: 100% , Day2 : ไม่เข้าClear pending | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WRSTM_2025 Capacity Expansion Ph8_EXP_BKK | WAT RAT SATTHA THAM |  |  |  |  | 2026-03-04 | 2026-03-04 | 2026-03-04 | Annop Auyto | N/A | Closed | 2026-03-09 18:10:08 | No | No |  |  |  | 2026-03-31 | 2026-04-16 | 2026-06-02 | V Contribute Co., Ltd | N/A | Closed | 2026-06-02 17:26:58 | Yes | Yes | 2026-06-02 17:26:58 |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-05-27 09:05:16 | Yes | Yes | 2026-03-07 19:39:52 | PAT pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-22 | 2026-05-27 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-07 | 2026-03-07 | Chonradee Suwapan | Approved | Closed | 2026-03-12 10:16:39 | Yes | Yes | 2026-03-07 19:52:27 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-13 | Chatnapatt Sukcheunrat WX1328849 | N/A | Closed | 2026-02-13 18:58:33 | No | No |  | 13-Feb-26 Add AAU5636w S8 AddUBBPg3a |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WRTPM_2026 Antenna Dualbeam_Replacement_BKK | WAT RAT SATTHATHAM (Bang Luang-Pathum Thani) |  |  |  | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-12 12:53:58 | No | No |  |  | 2026-05-15 | 2026-05-15 | 2026-05-09 | 2026-05-09 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-05-09 18:07:34 | Yes | Yes | 2026-05-11 11:49:47 |  | 2026-05-12 | 2026-05-12 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | Approved | Closed | 2026-06-17 16:24:50 | Yes | Yes | 2026-05-12 12:53:19 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-06-17 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 21:58:22 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-04-28 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-04-28 16:50:48 | No | No |  | 28-Apr-2026 Replace Ant Sector 1#，3 1#，6 3#，8 S1 SFN |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WSLKM_2026 Capacity Expansion Ph2_BKK | WAT SALI KHO PITARAM | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WSSWN_2026 Capacity Expansion Ph1_EXP_SR | Wat Si Suwan | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-08-11 | 2026-08-11 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-11 19:58:40 | Yes | Yes | 2026-08-11 20:01:50 |  | 2026-08-19 | 2026-08-19 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-09-10 17:01:23 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-19 | 2026-08-19 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-19 12:25:14 |  | 2026-08-13 | 2026-08-31 | 2026-08-12 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-08-12 10:03:25 | No | No |  |  |  |  | 2026-08-11 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-08-11 17:32:03 | No | No |  | 11 Aug 2026 Replace RRU5516 sector3 replace BBU5900 add GPS add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WT32M_2026 Capacity Expansion NW Modernization_EXP_BKK | SOI WACHIRATHAM SATHIT32 | [5 empty] | 2026-08-03 | 2026-08-03 | Thossapan Chaloemrit | N/A | Closed | 2026-08-03 16:03:00 | No | No |  |  |  | 2026-08-31 | 2026-07-31 | 2026-08-04 | Teloneer Company Limited | N/A | Closed | 2026-08-04 15:04:25 | Yes | Yes | 2026-08-07 11:12:03 |  | 2026-08-11 | 2026-08-11 | Teloneer Company Limited | Approving | Assigned |  | Yes | Yes | 2026-08-11 22:56:53 | Page 35 RRU plug in Photo Need. | Not Pass |  |  |  | N/A | Not assigned |  | No | No |  |  |  | 2026-08-19 | Juntima Charsingkaew WX1436671 | N/A | Closed | 2026-08-19 15:13:02 | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-27 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-27 10:27:07 |  |  | 2026-06-30 | 2026-07-25 | Teloneer Company Limited | N/A | Closed | 2026-07-25 18:00:41 | No | No |  |  |  |  | 2026-07-25 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-07-25 17:57:18 | No | No |  | 25-07-2026. Combine Ant.8 port to RRU900 Sec.2#， เก็บงาน 24-07-2026. Replace RRU3826 to RRU5526#， Ant.8 port Sec.2#， 4 23-Jul-26 add UBBPh3a slot4 remove UBBPg3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-04 16:07:52 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTC2M_2026 Capacity Expansion Ph1_EXP_BKK | WONG WAEN DAN TUB CHANG STATION 2 | [5 empty] | 2026-08-03 | 2026-08-03 | Thossapan Chaloemrit | N/A | Closed | 2026-08-03 16:03:00 | No | No |  |  |  | 2026-07-31 | 2026-08-04 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 12:13:28 | Yes | Yes | 2026-08-07 11:18:23 |  | 2026-08-11 | 2026-08-11 | Teloneer Company Limited | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-26 09:56:25 | 1.Need to fill install 63A/2P=1pc#，install triple mounting=2 sets#，remove double mountung=2set and remove 32A/1P=2pcs in pg-49. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-07-20 | Thossapan Chaloemrit | Approved | Closed | 2026-08-28 15:27:33 | Yes | Yes | 2026-07-20 11:32:35 |  |  | 2026-06-30 | 2026-08-01 | Teloneer Company Limited | N/A | Closed | 2026-08-01 19:40:30 | No | No |  |  |  |  | 2026-08-01 | Wandee Thongpoon WX1039557 | N/A | Closed | 2026-08-01 15:54:03 | No | No |  | 2026-08-03 Clear Pending ----------------------------------------------------------------------------------------- ----------------------------------------------------------------------------------------- 1-Aug-2026 Add UBBPg3a Rmv d5 Add AAU5656 S1 S2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-04 16:07:52 | No | No |  |  | SQC Closed |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTC2M_2026 Capacity Expansion Ph2_BKK | WONG WAEN DAN TUB CHANG STATION 2 | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTKOM_2026 Capacity Expansion Ph2_BKK | WAT KO SUWANNARAM | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTMKM_2026 Capacity Expansion Ph2_BKK | WAT PRA THAMMA KAI | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTMPG_2026 Capacity Expansion Ph1_EXP_SR | Wat Tha Mapring | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  |  | 2026-08-31 | 2026-07-30 | 2026-07-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-31 14:14:24 | Yes | Yes | 2026-08-11 20:14:16 |  | 2026-08-14 | 2026-08-19 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-19 11:29:03 | Review and Revise / PAT and INV Done | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-08-14 | 2026-08-14 | Mattura Habayae(Future Telecom Co.,Ltd.) | Approving | Assigned |  | Yes | Yes | 2026-08-14 11:04:39 |  | 2026-07-31 | 2026-08-31 | 2026-07-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-30 18:28:02 | No | No |  |  |  |  | 2026-07-30 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-07-30 18:10:30 | No | No |  | 30 July 2026 Add AAU5656 sector1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTNLM_2026 Capacity Expansion Ph1_EXP_ER | Lung Wat Nong Ngu Luam | 2026-06-23 | Team : Thcp_phet.sa Tel : 0924272237 | Clear Alarm |  | 2026-06-30 | 2026-06-04 | 2026-06-04 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-06-06 19:22:46 | No | No |  |  |  | 2026-06-30 | 2026-06-08 | 2026-06-08 | Teloneer Company Limited | N/A | Closed | 2026-06-08 10:23:38 | Yes | Yes | 2026-06-09 09:02:30 |  | 2026-06-30 | 2026-06-10 | Apichart Kampuang(Teloneer Company Limited) | Approved | Closed | 2026-06-19 18:16:05 | Yes | Yes | 2026-06-10 17:14:32 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-07-03 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-07-07 15:06:00 | No | No |  |  | 2026-06-30 | 2026-06-03 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-06-10 21:43:20 | Yes | Yes | 2026-06-05 17:27:59 |  | 2026-06-23 | 2026-06-30 | 2026-06-04 | Teloneer Company Limited | N/A | Closed | 2026-06-04 17:48:42 | No | No |  |  |  |  | 2026-06-23 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-06-23 19:36:23 | No | No |  | Add RRU5505 x 1 + 4T4R_WTNLM_H_1 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% , Day2 : Clear alarm | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTNSM_2025 Capacity Expansion NW Modernization_EXP_BKK | WATTANASIN SCHOOL |  |  |  | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-23 16:26:40 | No | No |  |  |  | 2026-02-28 | 2026-02-19 | 2026-02-20 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd. | N/A | Closed | 2026-02-20 14:40:12 | Yes | Yes | 2026-02-24 13:05:49 |  | 2026-03-26 | 2026-03-26 | Suriya Ritthapan(Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.) | Approved | Closed | 2026-09-04 20:51:35 | Yes | Yes | 2026-03-26 11:55:51 | PAT pass. | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-13 | 2026-03-30 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-08-01 | 2026-08-01 | Mahadee Japakiya | Approved | Closed | 2026-08-04 21:32:15 | Yes | Yes | 2026-08-01 20:22:31 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-19 | Panupong Saiyod WX1434739 | N/A | Closed | 2026-02-19 23:08:13 | No | No |  | 19-Feb-2026 Add 1RRU3953 sector 3.2 18-Feb-26 Replace RRU5507 To AAU5768 S1 S2 S3 //Pending Add RRU3953 S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTPBM_2026 Capacity Expansion Modernize_EXP_ER | wat thepphabut | 2026-07-28 | Team : Team_Pooriwat Tel : 0925094222 |  |  | 2026-07-31 | 2026-07-29 | 2026-07-29 | Teloneer Company Limited | N/A | Closed | 2026-07-29 17:38:20 | No | No |  |  |  | 2026-07-31 | 2026-08-02 | 2026-08-03 | Teloneer Company Limited | N/A | Closed | 2026-08-03 15:11:18 | Yes | Yes | 2026-08-05 20:45:24 |  | 2026-07-31 | 2026-08-05 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-11 09:07:01 | Yes | Yes | 2026-08-05 22:09:03 |  | First Time Pass |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  | 2026-08-18 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-08-20 17:30:25 | No | No |  |  | 2026-07-31 | 2026-07-28 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-07-31 17:00:10 | Yes | Yes | 2026-07-28 10:14:26 |  |  | 2026-07-31 | 2026-07-28 | Teloneer Company Limited | N/A | Closed | 2026-07-28 16:10:51 | No | No |  |  |  |  | 2026-07-28 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-28 17:14:35 | No | No |  | Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WTPBM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WTPBM_H_3 |  | 2026-07-28 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-07-28 17:14:59 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : ไม่เข้า0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTPGM_2026 Capacity Expansion Ph2_BKK | WAT TRAPHANG | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTPNM_2026 Capacity Expansion Modernize_EXP_ER | Wat Taopoon | 2026-08-05 | Team : thcp_pooriwat.k Tel : 0925094222 |  |  | 2026-08-15 | 2026-08-05 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 18:01:59 | No | No |  | Add UBBPh2a Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WTPNM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WTPNM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WTPNM_H_3 Replace Antenna (LB) + Replace 3953x1 to RRU5508 x 2 + Co L07 + NR07 + 4T4R_WTPNM_L_1 Add RRU5508 x 1 + Co NR07 + 4T4R_WTPNM_L_2 Add RRU5508 x 1 + Co L07 + NR07 + 4T4R_WTPNM_L_3 Co L21F2 all sector |  | 2026-08-20 | 2026-08-10 | 2026-08-11 | Teloneer Company Limited | N/A | Closed | 2026-08-11 12:30:04 | Yes | Yes | 2026-08-15 19:42:52 |  | 2026-08-20 | 2026-08-16 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-23 21:56:12 | Yes | Yes | 2026-08-16 12:27:17 |  | First Time Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-04 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-10 16:31:33 | No | No |  |  | 2026-08-15 | 2026-08-05 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-08-06 11:38:04 | Yes | Yes | 2026-08-05 15:13:39 |  |  | 2026-08-15 | 2026-08-05 | Teloneer Company Limited | N/A | Closed | 2026-08-05 16:16:11 | No | No |  |  |  |  | 2026-08-05 | Angsana Jituafua WX1434741 | N/A | Closed | 2026-08-05 19:56:31 | No | No |  | Add UBBPh2a Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WTPNM_H_1 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WTPNM_H_2 Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WTPNM_H_3 Replace Antenna (LB) + Replace 3953x1 to RRU5508 x 2 + Co L07 + NR07 + 4T4R_WTPNM_L_1 Add RRU5508 x 1 + Co NR07 + 4T4R_WTPNM_L_2 Add RRU5508 x 1 + Co L07 + NR07 + 4T4R_WTPNM_L_3 Co L21F2 all sector |  | 2026-08-10 | Reungsak Junkong 00927496 | N/A | Closed | 2026-08-10 17:48:21 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WTSTM_2026 Capacity Expansion NW Modernization_EXP_BKK | WACHIRATHAM SATIT | [5 empty] | 2026-07-03 | 2026-07-03 | Teloneer Company Limited | N/A | Closed | 2026-07-03 08:59:10 | No | No |  |  |  | 2026-08-31 | 2026-07-06 | 2026-07-08 | Teloneer Company Limited | N/A | Closed | 2026-07-08 16:16:07 | Yes | Yes | 2026-07-13 09:01:11 |  | 2026-07-13 | 2026-07-21 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-08-31 11:01:28 | Yes | Yes | 2026-08-28 13:00:36 | Page 6#，7#，8#，9 Need to fill Site Name . Need red mark at install DCDU in pg-54. | Not Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-07-08 | 2026-07-09 | Thossapan Chaloemrit(Teloneer Company Limited) | Approved | Closed | 2026-07-09 10:41:47 | Yes | Yes | 2026-07-09 10:30:57 |  |  | 2026-06-30 | 2026-07-01 | Teloneer Company Limited | N/A | Closed | 2026-07-01 13:15:23 | No | No |  |  |  |  | 2026-06-30 | Puthipat Thanosawan WX630156 | N/A | Closed | 2026-06-30 18:58:54 | No | No |  | 30-06-2026. Replace RRU3962 to RRU5507 Sec.2#， 3#， RRU3953 to RRU5516#， Ant.8 port Sec.1#， 2#， 3 //Remove Sec.6#， 7 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-07-09 | Teloneer Company Limited | N/A | Closed | 2026-07-09 10:14:19 | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WWNTM_2026 Capacity Expansion Ph2_BKK | WONG WAEN-NAWATHANIGOLF | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WWTRM_2026 Capacity Expansion Ph2_EXP_ER | Wastewater Treatment plant RIL | 2026-09-28 | Team : thcp_apichat.f Tel : 0960126111 | Install & Integrate |  | 2026-09-30 | 2026-09-28 | 2026-09-28 | Boonchot Boriwut(Teloneer Company Limited) | N/A | Closed | 2026-09-29 07:57:32 | No | No |  |  |  | 2026-09-30 | 2026-09-29 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No |  |  | 2026-09-30 |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | Teloneer Company Limited | N/A | Not assigned |  | No | No |  |  |  |  | Teloneer Company Limited | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-09-30 | 2026-09-24 | Boonchot Boriwut(Teloneer Company Limited) | Approved | Closed | 2026-09-25 17:31:42 | Yes | Yes | 2026-09-24 13:09:53 |  |  | 2026-09-30 | 2026-09-28 | Teloneer Company Limited | N/A | Closed | 2026-09-28 17:06:35 | No | No |  |  |  |  | 2026-09-28 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-28 17:04:29 | No | No |  | Replace BBU5900A to BBU5900 add 1ubbpha Replace Antenna (MB) + Add RRU5505 x 1 + 4T4R_WWTRM_H_1 Remove Antenna + (New AAU5775) + Main Dir = 285 + Remove RRU x 2_WWTRM_H_3 New Sector 8 (Co AAU5775) + Main Dir = 285_WWTRM_H_8 New Sector M (Co AAU5775) + Main Dir = 285_WWTRM_H_M New Sector N (Co AAU5775) + Main Dir = 285_WWTRM_H_N Co L21(F2) S1 |  | 2026-09-29 | Siriwan Srimabut WX1522702 | N/A | Closed | 2026-09-29 15:27:39 | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | Day1 : 70% , Day2 : ฝนตก , Day3 : 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
WYN1B_2025 Capacity Expansion NW Modernization_EXP_BKK | WYNE by Sansiri |  |  |  |  | 2026-03-05 | 2026-03-05 | 2026-03-05 | Annop Auyto(V Contribute Co., Ltd) | N/A | Closed | 2026-03-16 17:11:05 | No | No |  |  |  | 2026-02-28 | 2026-03-22 | 2026-03-23 | V Contribute Co., Ltd | N/A | Closed | 2026-03-23 15:59:44 | Yes | Yes | 2026-03-23 15:59:45 |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-05-08 09:30:04 | Yes | Yes | 2026-05-06 01:07:49 | PAT Pass | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  | 2026-04-30 | 2026-05-13 | Jutatip Tiprean 84012709 | Approving | Assigned |  | No | No |  |  | 2026-03-10 | 2026-03-10 | Chonradee Suwapan | Approved | Closed | 2026-03-31 09:26:56 | Yes | Yes | 2026-03-10 22:22:46 | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | 2026-02-12 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-02-12 18:19:34 | No | No |  | 12 Feb 2026 Replace BBU5900 add GPS |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YBNUE_2026 Capacity Expansion Ph1_EXP_SR | Yaek Ban Nuea | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-03 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-02 | 2026-08-31 | 2026-09-02 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-02 18:18:31 | No | No |  |  |  |  | 2026-09-02 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-02 17:36:08 | No | No |  | 2 Sep 2026 Replace RRU5516 sector3 add 1UBBPh2 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YKTTM_2026 Capacity Expansion Ph2_BKK | YUKHANTHAWAT TEMPLE | [8 empty] | N/A | Not assigned |  | No | No | [7 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YMWNM_2026 Capacity Expansion Ph1_EXP_SR | Yaek Muang Wan | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-30 | 2026-09-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-30 20:03:23 | Yes | Yes | 2026-09-30 20:04:31 |  |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-08-28 | 2026-08-31 | 2026-09-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-30 21:17:59 | No | No |  |  |  |  | 2026-08-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-08-28 17:53:23 | No | No |  | S2 > RRU5516*1 > Ant 8 Port |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YNGNM_2026 Capacity Expansion Ph1_EXP_SR | Yaek Nongnin | [5 empty] | 2026-08-31 | 2026-08-31 | Subpoa Limsaihua | N/A | Closed | 2026-08-31 16:02:31 | No | No |  |  | 2026-07-26 | 2026-07-26 | 2026-07-29 | 2026-07-31 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-31 18:31:47 | Yes | Yes | 2026-08-06 22:28:52 |  | 2026-08-17 | 2026-08-24 | Aomchun Jittreemit | Approved | Closed | 2026-09-04 11:12:15 | Yes | Yes | 2026-08-24 14:02:49 | PAT pass wait revise INV | Pass |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-09-01 | Jutatip Tiprean 84012709 | N/A | Closed | 2026-09-03 17:02:38 | No | No |  |  | 2026-08-17 | 2026-08-17 | Aomchun Jittreemit | Approving | Assigned |  | Yes | Yes | 2026-08-17 13:18:36 |  | 2026-07-30 | 2026-08-31 | 2026-07-30 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-07-30 15:41:23 | No | No |  |  |  |  | 2026-07-30 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-07-30 18:10:30 | No | No |  | 30 July 2026 Replace RRU5516 sector4 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YNGPS_2026 Capacity Expansion Ph1_EXP_SR | Yi Ngo Police Station | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-22 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-14 | 2026-08-31 | 2026-09-25 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-25 20:04:37 | No | No |  |  |  |  | 2026-09-14 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-14 18:08:01 | No | No |  | add h2a*1 Rep Ant MB S3 S3 > RRU5516*1 > Ant Combine MB S3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YPYRM_2026 Capacity Expansion Ph1_EXP_SR | Yeak Pong Yu Rai | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-27 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-28 | 2026-08-31 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | No | No |  |  |  |  | 2026-09-28 | Pramot Phanphongwong WX1324034 | N/A | Closed | 2026-09-28 20:24:41 | No | No |  | Re LB S3>S1#， S1>S3 Re MB S1&S6> S3&S8 S1 > AAU5775 27 Sep 2026 ***Add UBBPh3 only |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YRAGM_2026 Capacity Expansion Ph1_EXP_SR | YARANG | [5 empty] | 2026-09-29 | 2026-09-29 | Subpoa Limsaihua | N/A | Closed | 2026-09-29 17:50:28 | No | No |  |  |  | 2026-08-31 | 2026-09-30 |  | Future Telecom Co.,Ltd. | N/A | Assigned |  | Yes | No |  | 1. Team member is two or three? 2.Need to upload Site Overview before on ground 3.Need to upload EPS 100D and Module SN photo in additional work |  |  |  | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  | 2026-09-26 | 2026-08-31 | 2026-09-26 | Future Telecom Co.,Ltd. | N/A | Closed | 2026-09-26 17:41:11 | No | No |  |  |  |  | 2026-09-26 | Laddawan Wannasri WX1434742 | N/A | Closed | 2026-09-26 16:31:07 | No | No |  | 26 Sep 2026 Add DMM add AAU5775 sector2 add 1UBBPh3 |  |  |  | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
YWBGM_2026 Capacity Expansion Ph2_BKK | YAEK WATBUNG | [8 empty] | N/A | Not assigned |  | No | No |  |  |  | 2026-11-07 |  |  | Teloneer Company Limited | N/A | Assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | Yes | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No |  |  |  | 2026-11-07 |  | Teloneer Company Limited | N/A | Assigned |  | No | No | [6 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | No | No | [5 empty] | N/A | Not assigned |  | Yes | No | [5 empty] | N/A | Not assigned |  | No | No |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Enum (hidden)
Install & Integrate
Clear Pending
Take Photo & Clear Pending
Commissionning
Clear Alarm
Add Card CE
Add GPS
QA
Take Photo
Training
Dismantel
Cancel
Not Pass
Pass
First Time Pass

## Subcontractor
Subcontractor Code | Subcontractor
HuaWei
886523 | Wire & Wireless Co.,Ltd.
572002 | Broadband Engineering Service Telecommunication Co.,Ltd.
572004 | Turnkey Communication Services Public Company Limited.
572005 | Real Time Access Communications Co.,Ltd.
572008 | Mobicrat Company Limited
572010 | Power Telco Co.,Ltd.
572076 | THAITECHSERVE INTER CO., LTD.
5N2013 | Air Connect Engineering (Thailand) Co., Ltd.
A00504 | Neonworx Communications (Thailand) Ltd.
A03297 | Group Tech Solutions Co., Ltd.
A03695 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.
A03845 | Promt Management Service Company Limited.
A04307 | CCS Comservice (Thailand) Ltd.
A04343 | Future Telecom Co.,Ltd.
A04675 | Linetech Consultant Co.,Ltd.
A04924 | FOPC Co., Ltd.
A06259 | AC Progress Technology Co., Ltd.
A06260 | MAC ENVI Technology Co., Ltd.
Z00LX1 | WNP World Wide Co., Ltd.
Z00QHY | V Contribute Co., Ltd
W00036 | Z Cell Solutions Co., Ltd.
W0003M | Comtech Association Co.,Ltd.
W0004M | Teloneer Company Limited
Z01F5Q | vServePlus Co., Ltd.
Z027SS | Suzaku Company Limited
Z029LP | SOURCE INTERCONNECTION(THAILAND) CO.LTD
Z0760D | Jaya Communications Co., Ltd.
Z077LW | VPRO NETWORK CO., LTD.
Z078BZ | PINE ENGINEERING NETWORK SOLUTION CO., LTD.
Z07BCN | NY CABLE CO., LTD.
Z07BVY | Siwat Business Company Limited
Z07C4C | SEMS Company Limited
Z07DZC | CC TELECOM CO., LTD.
Z07FYM | PENTOR JGL TELECOM CO.,LTD.
Z07IST | ABC THAI COMPANY LIMITED
Z07Y0W | YOUPENG INFORMATION TECHNOLOGY (THAILAND) COMPANY LIMITED