## PlanFileName (hidden)
isdp_boonchot.b_56A0UPS_20261001200516 | 56A0UPS | V3 | 133 | 70 | 70 | M3T1A1969N1312524914840514740 | M3T1A1969N1312524915544141833
|  |  | {"headerType":"extarr","itemName":"DU ID","itemChildName":"","activityId":null,"id":"DUCODE","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96904561123 | BKB1043_Flash_RAN_BMA R2
|  |  | {"headerType":"extarr","itemName":"Customer Site ID","itemChildName":"","activityId":null,"id":"SITEID","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96899518123 | BKB7126_Flash_RAN_BMA R2
|  |  | {"headerType":"extarr","itemName":"Site Issues","itemChildName":"","activityId":null,"id":"SITEISSUE","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96912503123 | BKB7176_Flash_RAN_BMA R2
|  |  | {"headerType":"extarr","itemName":"Subcontractor","itemChildName":"","activityId":null,"id":"taskFlowNode_1481126123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1481126123","fieldType":null,"attributeType":"5","sourceType":"1","templateFieldId":null,"standardName":"Subcontractor","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 96928507123 | BKB7251_Flash_RAN_BMA R2
|  |  | {"headerType":"extarr","itemName":"Site Owner","itemChildName":"","activityId":null,"id":"SITEOWNER","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96862593123 | BKB7532_Flash_RAN_BMA R2
|  |  | {"headerType":"extarr","itemName":"Daily Plan","itemChildName":"","activityId":null,"id":"taskFlowNode_1518119123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1518119123","fieldType":null,"attributeType":"2","sourceType":"4","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96891509123 | BKB8616_Flash_RAN_BMA R2
|  |  | {"headerType":"extarr","itemName":"THCP","itemChildName":"","activityId":null,"id":"taskFlowNode_1521050123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1521050123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 96962481123 | BKBC127_Flash_RAN_BMA R2
|  |  | {"headerType":"extarr","itemName":"TL Name&Tel","itemChildName":"","activityId":null,"id":"taskFlowNode_1521051123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1521051123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96862584123 | BKBC275_Flash_RAN_BMA R2
|  |  | {"headerType":"activity","itemName":"KCP1 Rollout Go/No Go","itemChildName":"Plan Start Date","activityId":"107693123","id":"planStart_107693123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96919598123 | BKBC451_Flash_RAN_BMA R2
|  |  | {"headerType":"activity","itemName":"KCP1 Rollout Go/No Go","itemChildName":"Plan End Date","activityId":"107693123","id":"plan_107693123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96882500123 | CBR0389_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP1 Rollout Go/No Go","itemChildName":"Actual Start Date","activityId":"107693123","id":"actualStart_107693123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 102556453123 | CBR1005_Flash_Battery_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP1 Rollout Go/No Go","itemChildName":"Actual End Date","activityId":"107693123","id":"actual_107693123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96962466123 | CBR1005_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP1 Rollout Go/No Go","itemChildName":"Owner","activityId":"107693123","id":"resPonsible_107693123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96933505123 | CBR5558_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP1 Rollout Go/No Go","itemChildName":"Remarks","activityId":"107693123","id":"remarks_107693123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 101512455123 | CBR7015_Flash_Battery_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP2 On Site Implementation Solution Review","itemChildName":"Plan Start Date","activityId":"107694123","id":"planStart_107694123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96963455123 | CBR7015_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP2 On Site Implementation Solution Review","itemChildName":"Plan End Date","activityId":"107694123","id":"plan_107694123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 98934454123 | CBR7347_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP2 On Site Implementation Solution Review","itemChildName":"Actual Start Date","activityId":"107694123","id":"actualStart_107694123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96951489123 | CBR7972_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP2 On Site Implementation Solution Review","itemChildName":"Actual End Date","activityId":"107694123","id":"actual_107694123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96894499123 | CBR8626_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP2 On Site Implementation Solution Review","itemChildName":"Owner","activityId":"107694123","id":"resPonsible_107694123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 98942452123 | CBR8790_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP2 On Site Implementation Solution Review","itemChildName":"Remarks","activityId":"107694123","id":"remarks_107694123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 98939454123 | CBRA441_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP3 Cutover Decision","itemChildName":"Plan Start Date","activityId":"107695123","id":"planStart_107695123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 98942454123 | CBRA516_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"KCP3 Cutover Decision","itemChildName":"Plan End Date","activityId":"107695123","id":"plan_107695123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96954495123 | KKN0184_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"KCP3 Cutover Decision","itemChildName":"Actual Start Date","activityId":"107695123","id":"actualStart_107695123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 98519455123 | KKN0201_Flash_Battery_NEA R5
|  |  | {"headerType":"activity","itemName":"KCP3 Cutover Decision","itemChildName":"Actual End Date","activityId":"107695123","id":"actual_107695123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96884475123 | KKN0201_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"KCP3 Cutover Decision","itemChildName":"Owner","activityId":"107695123","id":"resPonsible_107695123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96944483123 | KKN0428_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"KCP3 Cutover Decision","itemChildName":"Remarks","activityId":"107695123","id":"remarks_107695123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96933470123 | KKN1512_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"09 Site Integration","itemChildName":"Plan Start Date","activityId":"107569123","id":"planStart_107569123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 105510452123 | KKN1622_FlashRevisit_NEA R5
|  |  | {"headerType":"activity","itemName":"09 Site Integration","itemChildName":"Plan End Date","activityId":"107569123","id":"plan_107569123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96893525123 | KKN1622_Flash_Battery_NEA R5
|  |  | {"headerType":"activity","itemName":"09 Site Integration","itemChildName":"Actual Start Date","activityId":"107569123","id":"actualStart_107569123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96957455123 | KKN1622_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"09 Site Integration","itemChildName":"Actual End Date","activityId":"107569123","id":"actual_107569123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96956471123 | KKN1805_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"09 Site Integration","itemChildName":"Owner","activityId":"107569123","id":"resPonsible_107569123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96919487123 | KKN7005_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"09 Site Integration","itemChildName":"Remarks","activityId":"107569123","id":"remarks_107569123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96893520123 | KKN7115_Flash_Battery_NEA R5
|  |  | {"headerType":"activity","itemName":"08.1 SmartQC (AOR-INS-SAP)","itemChildName":"RFX Ratio","activityId":"107574123","id":"depend_rate_107574123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96873502123 | KKN7115_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"08.1 SmartQC (AOR-INS-SAP)","itemChildName":"Smart QC Power","activityId":"107574123","id":"depend_status_80123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96943458123 | KKN7125_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"08.1 SmartQC (AOR-INS-SAP)","itemChildName":"Smart QC iDMU","activityId":"107574123","id":"depend_status_81123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96913531123 | KKN7197_Flash_Battery_NEA R5
|  |  | {"headerType":"activity","itemName":"08.1 SmartQC (AOR-INS-SAP)","itemChildName":"Plan End Date","activityId":"107574123","id":"plan_107574123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96873495123 | KKN7197_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"08.1 SmartQC (AOR-INS-SAP)","itemChildName":"Actual End Date","activityId":"107574123","id":"actual_107574123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96921529123 | KKN7307_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"08.1 SmartQC (AOR-INS-SAP)","itemChildName":"Owner","activityId":"107574123","id":"resPonsible_107574123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96940461123 | KKN7991_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"08.1 SmartQC (AOR-INS-SAP)","itemChildName":"Remarks","activityId":"107574123","id":"remarks_107574123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Hardware Installation","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96940460123 | KKN8218_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"AOR","itemChildName":"Plan End Date","activityId":"107568123","id":"plan_107568123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 105508454123 | KKN8563_FlashRevisit_NEA R5
|  |  | {"headerType":"activity","itemName":"AOR","itemChildName":"Actual End Date","activityId":"107568123","id":"actual_107568123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 100810457123 | KKN8563_Flash_Battery_NEA R5
|  |  | {"headerType":"activity","itemName":"AOR","itemChildName":"Owner","activityId":"107568123","id":"resPonsible_107568123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96930455123 | KKN8563_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"AOR","itemChildName":"Remarks","activityId":"107568123","id":"remarks_107568123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96940467123 | KKNA002_Flash_RAN_NEA R5
|  |  | {"headerType":"extarr","itemName":"Full AOR Review Rejected Category","itemChildName":"","activityId":null,"id":"taskFlowNode_1516753123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1516753123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96892488123 | KKNA010_Flash_RAN_NEA R5
|  |  | {"headerType":"extarr","itemName":"Integration alarm category","itemChildName":"","activityId":null,"id":"taskFlowNode_1518136123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1518136123","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"","enumValueArray":null,"beginRownum":1,"endRownum":105,"editFlag":false} | 96954484123 | KKNC069_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"14.1 A129 PAT Site Folder","itemChildName":"Plan End Date","activityId":"107551123","id":"plan_107551123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96948455123 | KKNC091_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"14.1 A129 PAT Site Folder","itemChildName":"Actual End Date","activityId":"107551123","id":"actual_107551123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96948454123 | KKNC092_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"14.1 A129 PAT Site Folder","itemChildName":"Owner","activityId":"107551123","id":"resPonsible_107551123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96948453123 | KKNC098_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"14.1 A129 PAT Site Folder","itemChildName":"Remarks","activityId":"107551123","id":"remarks_107551123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96948452123 | KKNC099_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"Smart QC Power","itemChildName":"Plan End Date","activityId":"107662123","id":"plan_107662123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96954471123 | KKNC112_Flash_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"Smart QC Power","itemChildName":"Actual End Date","activityId":"107662123","id":"actual_107662123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 105236511123 | MHR0012_Dismantle_NEA R6
|  |  | {"headerType":"activity","itemName":"Smart QC Power","itemChildName":"Owner","activityId":"107662123","id":"resPonsible_107662123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 102230458123 | MHR7907_Relocate_NEA R6
|  |  | {"headerType":"activity","itemName":"Smart QC Power","itemChildName":"Remarks","activityId":"107662123","id":"remarks_107662123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 98476453123 | NKI6732_Reach_RAN_NEA R5
|  |  | {"headerType":"activity","itemName":"A129.1 Power PAT Site Folder","itemChildName":"Plan End Date","activityId":"107663123","id":"plan_107663123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96900515123 | PTT8679_Flash_RAN_BMA R1
|  |  | {"headerType":"activity","itemName":"A129.1 Power PAT Site Folder","itemChildName":"Actual End Date","activityId":"107663123","id":"actual_107663123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96944472123 | RYG0404_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"A129.1 Power PAT Site Folder","itemChildName":"Owner","activityId":"107663123","id":"resPonsible_107663123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96952478123 | RYG0571_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"A129.1 Power PAT Site Folder","itemChildName":"Remarks","activityId":"107663123","id":"remarks_107663123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 105507453123 | RYG0627_FlashRevisit_EAS R3
|  |  | {"headerType":"activity","itemName":"07.2 DIsmantle Equipment","itemChildName":"Plan End Date","activityId":"107576123","id":"plan_107576123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96952473123 | RYG0627_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"07.2 DIsmantle Equipment","itemChildName":"Actual End Date","activityId":"107576123","id":"actual_107576123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96919498123 | RYG0654_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"07.2 DIsmantle Equipment","itemChildName":"Owner","activityId":"107576123","id":"resPonsible_107576123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 100041462123 | RYG0757_Flash_Battery_EAS R3
|  |  | {"headerType":"activity","itemName":"07.2 DIsmantle Equipment","itemChildName":"Remarks","activityId":"107576123","id":"remarks_107576123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96933511123 | RYG0757_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"07 MS110 Installation","itemChildName":"Plan End Date","activityId":"107567123","id":"plan_107567123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96933460123 | RYG1830_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"07 MS110 Installation","itemChildName":"Actual End Date","activityId":"107567123","id":"actual_107567123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96933456123 | RYG4003_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"07 MS110 Installation","itemChildName":"Owner","activityId":"107567123","id":"resPonsible_107567123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 101302455123 | RYG7984_Flash_RAN_EAS R3
|  |  | {"headerType":"activity","itemName":"07 MS110 Installation","itemChildName":"Remarks","activityId":"107567123","id":"remarks_107567123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"Installation-Completed","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96948520123 | SMP0595_Flash_RAN_BMA R2
|  |  | {"headerType":"activity","itemName":"Verify Photo","itemChildName":"Plan End Date","activityId":"107608123","id":"plan_107608123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96868525123 | SMP1092_Flash_RAN_BMA R2
|  |  | {"headerType":"activity","itemName":"Verify Photo","itemChildName":"Actual End Date","activityId":"107608123","id":"actual_107608123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 99340462123 | SMP8577_Flash_Battery_BMA R2
|  |  | {"headerType":"activity","itemName":"Verify Photo","itemChildName":"Owner","activityId":"107608123","id":"resPonsible_107608123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 96924503123 | SMP8577_Flash_RAN_BMA R2
|  |  | {"headerType":"activity","itemName":"Verify Photo","itemChildName":"Remarks","activityId":"107608123","id":"remarks_107608123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false} | 100260459123 | SMPC018_Flash_Battery_BMA R2
|  |  | {"headerType":"extarr","itemName":"Date Of Site Verify","itemChildName":"","activityId":null,"id":"taskFlowNode_1481088123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1481088123","fieldType":null,"attributeType":"4","sourceType":"3","templateFieldId":null,"standardName":"Date Of Site Verify","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true} | 96883496123 | SMPC018_Flash_RAN_BMA R2
{"headerType":"extarr","itemName":"Status Of Site Verify","itemChildName":"","activityId":null,"id":"taskFlowNode_1481121123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1481121123","fieldType":null,"attributeType":"4","sourceType":"3","templateFieldId":null,"standardName":"Status Of Site Verify","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true}
{"headerType":"activity","itemName":"02 RF FEA","itemChildName":"Plan End Date","activityId":"107594123","id":"plan_107594123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"02 RF FEA","itemChildName":"Actual End Date","activityId":"107594123","id":"actual_107594123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"02 RF FEA","itemChildName":"Owner","activityId":"107594123","id":"resPonsible_107594123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"02 RF FEA","itemChildName":"Remarks","activityId":"107594123","id":"remarks_107594123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"site installation design","itemChildName":"Plan End Date","activityId":"107617123","id":"plan_107617123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"site installation design","itemChildName":"Actual End Date","activityId":"107617123","id":"actual_107617123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"site installation design","itemChildName":"Owner","activityId":"107617123","id":"resPonsible_107617123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"site installation design","itemChildName":"Remarks","activityId":"107617123","id":"remarks_107617123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"LLD Design","itemChildName":"Plan End Date","activityId":"107598123","id":"plan_107598123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"LLD Design","itemChildName":"Actual End Date","activityId":"107598123","id":"actual_107598123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"LLD Design","itemChildName":"Owner","activityId":"107598123","id":"resPonsible_107598123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"LLD Design","itemChildName":"Remarks","activityId":"107598123","id":"remarks_107598123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09.1 CDD Ready","itemChildName":"Plan End Date","activityId":"107607123","id":"plan_107607123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09.1 CDD Ready","itemChildName":"Actual End Date","activityId":"107607123","id":"actual_107607123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09.1 CDD Ready","itemChildName":"Owner","activityId":"107607123","id":"resPonsible_107607123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09.1 CDD Ready","itemChildName":"Remarks","activityId":"107607123","id":"remarks_107607123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"extarr","itemName":"★ Script Readiness","itemChildName":"","activityId":null,"id":"taskFlowNode_1517743123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1517743123","fieldType":null,"attributeType":"2","sourceType":"4","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Pre-SID","itemChildName":"Plan End Date","activityId":"107737123","id":"plan_107737123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Pre-SID","itemChildName":"Actual End Date","activityId":"107737123","id":"actual_107737123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Pre-SID","itemChildName":"Owner","activityId":"107737123","id":"resPonsible_107737123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Pre-SID","itemChildName":"Remarks","activityId":"107737123","id":"remarks_107737123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"extarr","itemName":"Material Forecast Week","itemChildName":"","activityId":null,"id":"taskFlowNode_1532136123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1532136123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":true}
{"headerType":"activity","itemName":"Site Design","itemChildName":"Plan End Date","activityId":"107712123","id":"plan_107712123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Site Design","itemChildName":"Actual End Date","activityId":"107712123","id":"actual_107712123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Site Design","itemChildName":"Owner","activityId":"107712123","id":"resPonsible_107712123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Site Design","itemChildName":"Remarks","activityId":"107712123","id":"remarks_107712123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 External Alarm Test","itemChildName":"Plan Start Date","activityId":"107650123","id":"planStart_107650123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 External Alarm Test","itemChildName":"Plan End Date","activityId":"107650123","id":"plan_107650123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 External Alarm Test","itemChildName":"Actual Start Date","activityId":"107650123","id":"actualStart_107650123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 External Alarm Test","itemChildName":"Actual End Date","activityId":"107650123","id":"actual_107650123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 External Alarm Test","itemChildName":"Owner","activityId":"107650123","id":"resPonsible_107650123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 External Alarm Test","itemChildName":"Remarks","activityId":"107650123","id":"remarks_107650123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Battery IP Readiness","itemChildName":"Plan End Date","activityId":"109036123","id":"plan_109036123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Battery IP Readiness","itemChildName":"Actual End Date","activityId":"109036123","id":"actual_109036123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Battery IP Readiness","itemChildName":"Owner","activityId":"109036123","id":"resPonsible_109036123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Battery IP Readiness","itemChildName":"Remarks","activityId":"109036123","id":"remarks_109036123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 Cross Sector Verification","itemChildName":"Plan Start Date","activityId":"107625123","id":"planStart_107625123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 Cross Sector Verification","itemChildName":"Plan End Date","activityId":"107625123","id":"plan_107625123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 Cross Sector Verification","itemChildName":"Actual Start Date","activityId":"107625123","id":"actualStart_107625123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 Cross Sector Verification","itemChildName":"Actual End Date","activityId":"107625123","id":"actual_107625123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 Cross Sector Verification","itemChildName":"Owner","activityId":"107625123","id":"resPonsible_107625123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"09 Cross Sector Verification","itemChildName":"Remarks","activityId":"107625123","id":"remarks_107625123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"extarr","itemName":"Donor Code List","itemChildName":"","activityId":null,"id":"taskFlowNode_1511522123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1511522123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"extarr","itemName":"Latitude","itemChildName":"","activityId":null,"id":"taskFlowNode_1532137123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1532137123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"extarr","itemName":"Longtitude","itemChildName":"","activityId":null,"id":"taskFlowNode_1532138123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1532138123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"extarr","itemName":"Script Omc","itemChildName":"","activityId":null,"id":"taskFlowNode_1560320123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1560320123","fieldType":null,"attributeType":"2","sourceType":"4","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"BSC/RNC Script","itemChildName":"Plan End Date","activityId":"107618123","id":"plan_107618123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"BSC/RNC Script","itemChildName":"Actual End Date","activityId":"107618123","id":"actual_107618123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"BSC/RNC Script","itemChildName":"Owner","activityId":"107618123","id":"resPonsible_107618123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"BSC/RNC Script","itemChildName":"Remarks","activityId":"107618123","id":"remarks_107618123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"extarr","itemName":"Script/LLD ver. (OMC)","itemChildName":"","activityId":null,"id":"taskFlowNode_1518144123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1518144123","fieldType":null,"attributeType":"2","sourceType":"1","templateFieldId":null,"standardName":null,"enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"extarr","itemName":"Script 2300 Readiness Category","itemChildName":"","activityId":null,"id":"taskFlowNode_1518141123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1518141123","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"{780271123:\"05. No LLD\",780269123:\"03. No FEA\",780267123:\"01. CDD/IP/FEA/LLD Ready\",780270123:\"04. No IP\",780268123:\"02. No CDD\",780266123:\"00. Script Ready\"}","enumValueArray":["05. No LLD","04. No IP","03. No FEA","01. CDD/IP/FEA/LLD Ready","02. No CDD","00. Script Ready"],"beginRownum":106,"endRownum":112,"editFlag":false}
{"headerType":"extarr","itemName":"Script Omc Remark","itemChildName":"","activityId":null,"id":"taskFlowNode_1560321123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1560321123","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"{807232123:\"Site Down\",807230123:\"CDD\",807275123:\"Ready\",807231123:\"IPRAN\",807229123:\"LLD\"}","enumValueArray":["Ready","Site Down","IPRAN","CDD","LLD"],"beginRownum":113,"endRownum":118,"editFlag":false}
{"headerType":"extarr","itemName":"Script Readiness Category","itemChildName":"","activityId":null,"id":"taskFlowNode_1517747123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":"1517747123","fieldType":null,"attributeType":"2","sourceType":"5","templateFieldId":null,"standardName":null,"enumValue":"{782277123:\"04. No IP\",782275123:\"02. No CDD\",782273123:\"00. Script Ready\",782278123:\"05. No LLD\",782276123:\"03. No FEA\",782274123:\"01. CDD/IP/LLD/FEA Ready\"}","enumValueArray":["05. No LLD","04. No IP","03. No FEA","02. No CDD","01. CDD/IP/LLD/FEA Ready","00. Script Ready"],"beginRownum":119,"endRownum":125,"editFlag":false}
{"headerType":"activity","itemName":"Decom material inbound warehouse","itemChildName":"Plan End Date","activityId":"107711123","id":"plan_107711123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Decom material inbound warehouse","itemChildName":"Actual End Date","activityId":"107711123","id":"actual_107711123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Decom material inbound warehouse","itemChildName":"Owner","activityId":"107711123","id":"resPonsible_107711123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"Decom material inbound warehouse","itemChildName":"Remarks","activityId":"107711123","id":"remarks_107711123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"A129 PAT Ready to submit","itemChildName":"Plan End Date","activityId":"107721123","id":"plan_107721123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"A129 PAT Ready to submit","itemChildName":"Actual End Date","activityId":"107721123","id":"actual_107721123","width":null,"colStyle":"date","valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"A129 PAT Ready to submit","itemChildName":"Owner","activityId":"107721123","id":"resPonsible_107721123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}
{"headerType":"activity","itemName":"A129 PAT Ready to submit","itemChildName":"Remarks","activityId":"107721123","id":"remarks_107721123","width":null,"colStyle":null,"valueFormatter":null,"toolName":null,"sourceFieldAttribute":null,"gapType":null,"attrId":null,"fieldType":null,"attributeType":null,"sourceType":null,"templateFieldId":null,"standardName":"","enumValue":null,"enumValueArray":null,"beginRownum":0,"endRownum":0,"editFlag":false}

## Site Rollout Plan
DU ID | Customer Site ID | Site Issues | Subcontractor | Site Owner | Daily Plan | THCP | TL Name&Tel | KCP1 Rollout Go/No Go | [5 empty] | KCP2 On Site Implementation Solution Review | [5 empty] | KCP3 Cutover Decision | [5 empty] | 09 Site Integration | [5 empty] | 08.1 SmartQC (AOR-INS-SAP) | [6 empty] | AOR |  |  |  | Full AOR Review Rejected Category | Integration alarm category | 14.1 A129 PAT Site Folder |  |  |  | Smart QC Power |  |  |  | A129.1 Power PAT Site Folder |  |  |  | 07.2 DIsmantle Equipment |  |  |  | 07 MS110 Installation |  |  |  | Verify Photo |  |  |  | Date Of Site Verify | Status Of Site Verify | 02 RF FEA |  |  |  | site installation design |  |  |  | LLD Design |  |  |  | 09.1 CDD Ready |  |  |  | ★ Script Readiness | Pre-SID |  |  |  | Material Forecast Week | Site Design |  |  |  | 09 External Alarm Test | [5 empty] | Battery IP Readiness |  |  |  | 09 Cross Sector Verification | [5 empty] | Donor Code List | Latitude | Longtitude | Script Omc | BSC/RNC Script |  |  |  | Script/LLD ver. (OMC) | Script 2300 Readiness Category | Script Omc Remark | Script Readiness Category | Decom material inbound warehouse |  |  |  | A129 PAT Ready to submit
[8 empty] | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Owner | Remarks | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Owner | Remarks | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Owner | Remarks | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Owner | Remarks | RFX Ratio | Smart QC Power | Smart QC iDMU | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks |  |  | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks |  |  | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks |  | Plan End Date | Actual End Date | Owner | Remarks |  | Plan End Date | Actual End Date | Owner | Remarks | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Owner | Remarks |  |  |  |  | Plan End Date | Actual End Date | Owner | Remarks |  |  |  |  | Plan End Date | Actual End Date | Owner | Remarks | Plan End Date | Actual End Date | Owner | Remarks
BKB1043_Flash_RAN_BMA R2 | BKB1043 | N/A | Teloneer Company Limited | [24 empty] | 2025-08-20 | 2025-08-20 | Amonthep Saengsuk WX1461877 | Ready : 10G SA/NSA | 0/2 | Not Completed | Not Completed |  | 2025-09-08 | Teloneer Company Limited |  |  | 2025-09-15 | Teloneer Company Limited |  |  | 00. No alarm | [13 empty] | 2025-09-21 | Narusorn Phattharajaruk 00928167 |  | 2026-05-05 | 2026-05-05 | service revenue team |  |  | 2025-08-20 | Teloneer Company Limited |  |  |  |  | 2025-06-12 | Kulchaya Srichavanant 84433803 | need RF upload the old project of FEA files in DU Flash#， already swap AAU2300/2600 done since conso/unpair. (No need to do more solution) | [13 empty] | N/A | N/A | N/A | N/A | WK2627 | [6 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No check status clock |  | 2026-05-26 | Narusorn Phattharajaruk 00928167 | Existing IP |  |  | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test cross sector |  | 13.745551 | 100.566371 |  | N/A | N/A | N/A | N/A | [5 empty] | 2025-09-22 | Ekkarin Tidkratok 84433232 |  |  | 2025-09-23 | Narusorn Phattharajaruk 00928167
BKB7126_Flash_RAN_BMA R2 | BKB7126 | N/A | Teloneer Company Limited | [24 empty] | 2025-08-13 | 2025-08-13 | Amonthep Saengsuk WX1461877 | Ready : 10G SA/NSA | 0/2 | Not Completed | Not Completed |  | 2025-10-06 | Teloneer Company Limited |  |  | 2025-10-03 | Teloneer Company Limited |  |  | 00. No alarm | [13 empty] | 2025-09-21 | Narusorn Phattharajaruk 00928167 |  | 2026-05-12 | 2026-05-12 | service revenue team |  |  | 2025-08-13 | Teloneer Company Limited |  |  |  |  | 2025-06-04 | Kulchaya Srichavanant 84433803 | need RF upload the old project of FEA files in DU Flash#， already swap AAU2300/2600 done since conso/unpair. (No need to do more solution) | [13 empty] | N/A | N/A | N/A | N/A | WK2623 | [6 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test external alarm |  | 2026-09-01 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=1649806517#gid=1649806517 |  |  | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test cross sector |  | 13.742344 | 100.583391 |  | N/A | N/A | N/A | N/A | [5 empty] | 2025-09-22 | Ekkarin Tidkratok 84433232 |  |  | 2025-10-11 | Narusorn Phattharajaruk 00928167
BKB7176_Flash_RAN_BMA R2 | BKB7176 | N/A | Teloneer Company Limited | [24 empty] | 2025-08-11 | 2025-08-11 | Amonthep Saengsuk WX1461877 | Ready : 10G SA/NSA | 0/2 | Not Completed | Not Completed |  | 2025-10-07 | Teloneer Company Limited |  |  | 2025-10-03 | Teloneer Company Limited |  |  | 00. No alarm | [13 empty] | 2025-09-18 | Narusorn Phattharajaruk 00928167 |  | 2026-05-14 | 2026-05-14 | service revenue team |  |  | 2025-08-11 | Teloneer Company Limited |  |  |  |  | 2025-06-09 | Kulchaya Srichavanant 84433803 | need RF upload the old project of FEA files in DU Flash#， already swap AAU2300/2600 done since conso/unpair. (No need to do more solution) | [13 empty] | N/A | N/A | N/A | N/A | WK2627 | [6 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test external alarm |  | 2026-05-26 | Narusorn Phattharajaruk 00928167 | Existing IP |  |  | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test cross sector |  | 13.742533 | 100.576394 |  | N/A | N/A | N/A | N/A | [5 empty] | 2025-09-22 | Ekkarin Tidkratok 84433232 |  |  | 2025-10-10 | Narusorn Phattharajaruk 00928167
BKB7251_Flash_RAN_BMA R2 | BKB7251 | N/A | Teloneer Company Limited | [24 empty] | 2025-08-14 | 2025-08-14 | Amonthep Saengsuk WX1461877 | Ready : 10G SA/NSA | 0/2 | Not Completed | Not Completed |  | 2025-10-07 | Teloneer Company Limited |  |  | 2025-10-02 | Teloneer Company Limited |  |  | 00. No alarm | [13 empty] | 2025-09-18 | Narusorn Phattharajaruk 00928167 |  | 2026-05-16 | 2026-05-16 | service revenue team |  |  | 2025-08-14 | Teloneer Company Limited |  |  |  | 2026-03-09 | 2026-03-09 | Montri Tangprayoonlert WX1480443 | need RF upload the old project of FEA files in DU Flash#， already swap AAU2300/2600 done since conso/unpair. (No need to do more solution) | [13 empty] | N/A | N/A | N/A | N/A | [7 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test external alarm | [6 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test cross sector |  | 13.727461 | 100.597815 |  | N/A | N/A | N/A | N/A | [5 empty] | 2025-09-22 | Jiraporn Chantasil WX1462181 |  |  | 2025-10-11 | Narusorn Phattharajaruk 00928167
BKB7532_Flash_RAN_BMA R2 | BKB7532 | N/A | Teloneer Company Limited | [24 empty] | 2026-05-13 | 2026-05-13 | Kullaphat Yana WX1494386 | 2026-05-13 Subcon on site BBU integration – Done RRU integration – Done Cell integration - Done 10G cutover - Done Others : - 2300 RET config - At AAU Cross Sector - Checked and Confirmed CDD Check - Checked and Confirmed Today : 10G cut over finished Alarm : Clear | 0/2 | Not Completed | Not Completed |  | 2025-09-08 | Teloneer Company Limited |  |  | 2025-09-23 | Teloneer Company Limited |  |  | 00. No alarm | [13 empty] | 2000-01-01 | Ekkarin Tidkratok 84433232 |  | 2026-05-11 | 2026-05-11 | service revenue team |  |  | 2025-07-31 | Teloneer Company Limited |  |  |  |  | 2025-06-16 | Kulchaya Srichavanant 84433803 | need RF upload the old project of FEA files in DU Flash#， already swap AAU2300/2600 done since conso/unpair. (No need to do more solution) |  | 2000-01-01 | Grid Chaitrakul WX1461879 | Site freeze no need to output |  | 2000-01-01 | Grid Chaitrakul WX1461879 | Site freeze no need to output | [5 empty] | N/A | N/A | N/A | N/A | WK2631 | [6 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test external alarm |  | 2026-08-19 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=1649806517#gid=1649806517 |  |  | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test cross sector | BKB7532 | 13.724918 | 100.579364 |  | N/A | N/A | N/A | N/A |  |  | LLD |  |  | 2026-07-08 | Ekkarin Tidkratok 84433232 |  |  | 2025-10-24 | Narusorn Phattharajaruk 00928167
BKB8616_Flash_RAN_BMA R2 | BKB8616 | N/A | Teloneer Company Limited | [6 empty] | 2026-08-21 | 2026-08-21 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-05-12 | 2026-05-12 | Akaradech Sonamthiang WX1494384 | 2026-05-12 Subcon on site BBU integration – Done RRU integration – Done Cell integration - Done 10G cutover - Done Others : - 2300 RET config - At AAU Cross Sector - Checked and Confirmed CDD Check - Checked and Confirmed Today : 10G cut over finished Alarm : Clear | 0/2 | Not Completed | Not Completed |  | 2025-09-30 | Teloneer Company Limited |  |  | 2025-09-29 | Teloneer Company Limited |  |  | 00. No alarm | [13 empty] | 2025-09-21 | Narusorn Phattharajaruk 00928167 |  | 2026-05-10 | 2026-05-10 | service revenue team |  |  | 2025-07-21 | Teloneer Company Limited |  |  |  | 2025-05-20 | 2025-05-20 | Montri Tangprayoonlert WX1480443 | need RF upload the old project of FEA files in DU Flash#， already swap AAU2300/2600 done since conso/unpair. (No need to do more solution) |  | 2000-01-01 | Grid Chaitrakul WX1461879 | Site freeze no need to output |  | 2000-01-01 | Grid Chaitrakul WX1461879 | Site freeze no need to output | [5 empty] | N/A | N/A | N/A | N/A | [7 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test external alarm | [6 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test cross sector |  | 13.735140 | 100.605500 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-07-08 | Ekkarin Tidkratok 84433232 |  |  | 2025-09-23 | Narusorn Phattharajaruk 00928167
BKBC127_Flash_RAN_BMA R2 | BKBC127 | N/A | Teloneer Company Limited | [6 empty] | 2026-08-21 | 2026-08-21 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-05-12 | 2026-05-12 | Kullaphat Yana WX1494386 | 2026-05-12 Subcon on site BBU integration – Done RRU integration – Done Cell integration - Done 10G cutover - Done Others : - 2300 RET config - At AAU Cross Sector - Checked and Confirmed CDD Check - Checked and Confirmed Today : 10G cut over finished Alarm : Clear | 0/2 | Not Completed | Not Completed |  | 2025-10-08 | Teloneer Company Limited |  |  | 2025-10-08 | Teloneer Company Limited |  |  | 00. No alarm | [13 empty] | 2025-09-21 | Narusorn Phattharajaruk 00928167 |  | 2026-05-10 | 2026-05-10 | service revenue team |  |  | 2025-07-24 | Teloneer Company Limited |  |  |  | 2025-06-15 | 2025-06-15 | Montri Tangprayoonlert WX1480443 | need RF upload the old project of FEA files in DU Flash#， already swap AAU2300/2600 done since conso/unpair. (No need to do more solution) |  | 2000-01-01 | Grid Chaitrakul WX1461879 | Site freeze no need to output |  | 2000-01-01 | Grid Chaitrakul WX1461879 | Site freeze no need to output | [5 empty] | N/A | N/A | N/A | N/A | [7 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test external alarm | [6 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test cross sector |  | 13.729981 | 100.603011 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-07-08 | Ekkarin Tidkratok 84433232 |  |  | 2025-10-04 | Narusorn Phattharajaruk 00928167
BKBC275_Flash_RAN_BMA R2 | BKBC275 | N/A | Teloneer Company Limited |  | 2026-06-11 | [22 empty] | 2025-07-24 | 2025-07-24 | Amonthep Saengsuk WX1461877 | Ready : 10G SA/NSA | 0/2 | Not Completed | Not Completed |  | 2025-09-16 | Teloneer Company Limited |  |  | 2025-09-13 | Teloneer Company Limited |  |  | 00. No alarm | [13 empty] | 2025-09-21 | Narusorn Phattharajaruk 00928167 |  | 2026-05-23 | 2026-05-23 | service revenue team |  |  | 2025-07-26 | Teloneer Company Limited |  |  |  |  | 2025-06-16 | Kulchaya Srichavanant 84433803 | need RF upload the old project of FEA files in DU Flash#， already swap AAU2300/2600 done since conso/unpair. (No need to do more solution) | [13 empty] | N/A | N/A | N/A | N/A | WK2630 | [6 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test external alarm |  |  |  | Request New IP |  |  | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test cross sector | BKBC275 | 13.740706 | 100.563110 |  | N/A | N/A | N/A | N/A | [5 empty] | 2025-09-22 | Ekkarin Tidkratok 84433232 |  |  | 2025-10-17 | Narusorn Phattharajaruk 00928167
BKBC451_Flash_RAN_BMA R2 | BKBC451 | N/A | Teloneer Company Limited | [24 empty] | 2025-07-26 | 2025-07-26 | Amonthep Saengsuk WX1461877 | Ready : 10G SA/NSA | 0/2 | Not Completed | Not Completed |  | 2025-10-02 | Teloneer Company Limited |  |  | 2025-10-02 | Teloneer Company Limited |  |  | 00. No alarm | [13 empty] | 2025-09-22 | Ekkarin Tidkratok WX1539755 |  | 2026-05-25 | 2026-05-25 | service revenue team |  |  | 2025-08-02 | Teloneer Company Limited |  |  |  |  | 2025-06-15 | Kulchaya Srichavanant 84433803 | need RF upload the old project of FEA files in DU Flash#， already swap AAU2300/2600 done since conso/unpair. (No need to do more solution) | [13 empty] | N/A | N/A | N/A | N/A | WK2626 | [6 empty] | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test external alarm |  | 2020-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2000-01-01 | 2000-01-01 | Amonthep Saengsuk WX1461877 | DU-Freeze - Cut Over 10GB Only : No test cross sector |  | 13.732911 | 100.574831 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-11 | Ekkarin Tidkratok WX1539755 |  |  | 2025-09-23 | Narusorn Phattharajaruk 00928167
CBR0389_Flash_RAN_EAS R3 | CBR0389 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-03 | thcp_wachira s |  |  |  | 2026-08-03 | 2026-08-03 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-08-29 | 2026-08-29 | Akaradech Sonamthiang WX1494384 | 2026-09-03 Site : CBR0389X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : 10G cut over done URL Ticket : https://wongla.com/chat?id=4884225&category=Ticket%20Update Alarm : Clear Remarks : . | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-31 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-31 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-07 | Kaung Htet San WX1440182 | Line HSSE Photo not have | [8 empty] | 2026-08-31 | 2026-09-01 | Boonchot Boriwut |  | 2026-08-08 | 2026-08-29 |  |  | 2026-08-31 | 2026-08-31 | Teloneer Company Limited |  |  |  |  | 2026-02-19 | Kulchaya Srichavanant 84433803 |  |  | 2026-03-23 | China GSC Survey Design Team |  |  | 2026-02-24 | zhangguanglin WX1251498 |  |  | 2026-06-12 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2636 |  | 2026-03-23 | China GSC Survey Design Team |  |  |  | 2026-08-29 | 2026-08-29 | Akaradech Sonamthiang WX1494384 | 2026-08-30 Site CBR0389X_2NB01 Cabinet 1 slot 18 : N/A Cabinet 1 slot 19 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-08-29 | 2026-08-29 | Akaradech Sonamthiang WX1494384 | 2026-08-29 Site CBR0389X_2NB01 Serial ascending order : Done DSP serial match : Done |  | 12.919921 | 100.920481 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-18 | 2026-09-18 | Sahadsavat Deesupat WX1462179 |  |  | 2026-09-07 | Kaung Htet San WX1440182 | Line HSSE Photo not have
CBR1005_Flash_Battery_EAS R3 | CBR1005 | N/A |  | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | RAN OMC |  | 0/0 | N/A | N/A | [14 empty] | N/A | N/A | N/A | N/A | [18 empty] | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 12.929621 | 100.893961 |  | N/A | N/A | N/A | N/A
CBR1005_Flash_RAN_EAS R3 | CBR1005 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-05 | thcp_wachira s |  |  |  | 2026-08-25 | 2026-08-25 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-09-04 | 2026-09-04 | 2026-09-04 | Chadathan Thumsawat WX1461876 | 2026-09-04 Site : CBR1005X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : - Today : Integrate 1800 2100 2300 2600 done URL Ticket : https://wongla.com/chat?id=4908312&category=Ticket%20Update alarm - Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-09-30 | 2026-09-08 | Teloneer Company Limited |  | 2026-09-30 | 2026-09-13 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-15 | Kaung Ko Ko WX1541657 | HSSE Line Photo not have. | [8 empty] | 2026-09-30 | 2026-09-07 | Boonchot Boriwut |  | 2026-09-04 | 2026-09-04 |  |  | 2026-09-30 | 2026-09-05 | Teloneer Company Limited |  |  |  |  | 2026-06-26 | Settha Prompunjai WX1438714 |  |  | 2026-08-18 | renqijing WX1507439 |  |  | 2026-08-17 | yangzhi WX1171682 |  |  | 2026-08-31 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2641 |  | 2026-08-18 | renqijing WX1507439 |  |  |  | 2026-09-04 | 2026-09-04 | Chadathan Thumsawat WX1461876 |  |  |  | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=1649806517#gid=1649806517 |  |  | 2026-09-04 | 2026-09-04 | Chadathan Thumsawat WX1461876 |  |  | 12.929621 | 100.893961 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-18 | 2026-09-18 | Sahadsavat Deesupat WX1462179 |  |  | 2026-09-15 | Kaung Ko Ko WX1541657
CBR5558_Flash_RAN_EAS R3 | CBR5558 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-24 | thcp_wachira s |  |  |  | 2026-07-14 | 2026-07-14 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-08-16 | 2026-08-17 | 2026-08-17 | Akaradech Sonamthiang WX1494384 | 2026-08-17 Site : CBR5558L_6NB02 Test External alarm : PASS 2026-08-17 Site : CBR5558L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Integrate 2300 and 2600 Done URL Ticket : https://wongla.com/chat?id=4829109&category=Ticket%20Update Alarm : Clear Remarks : Pending Test External alarm and photo azimuth | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-19 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-19 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-20 | Kaung Ko Ko WX1541657 | HSSE Line Photo no have | [8 empty] | 2026-08-31 | 2026-08-21 | Boonchot Boriwut | 1.RET dismantle or not?? | 2026-08-08 | 2026-08-16 |  |  | 2026-08-31 | 2026-08-17 | Teloneer Company Limited |  |  |  |  | 2026-02-23 | Kulchaya Srichavanant 84433803 |  |  | 2026-06-29 | yangshuanghong WX1009887 |  |  | 2026-06-26 | zhangguanglin WX1251498 |  |  | 2026-07-15 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2632 |  | 2026-06-29 | yangshuanghong WX1009887 |  |  |  | 2026-08-17 | 2026-08-17 | Supatong Juntorn WX1461874 | 2026-08-17 Site CBR5558 Cabinet 1 : Pending Cabinet 2 : Pending |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-08-17 | 2026-08-24 | Akaradech Sonamthiang WX1494384 | 2026-08-24 share Azimuth : PASS 2026-08-17 Site CBR5558L_6NB02 Serial ascending order : Done DSP serial match : Done Azimuth : Pending |  | 12.692511 | 100.908881 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-18 | 2026-09-18 | Sahadsavat Deesupat WX1462179 |  |  | 2026-09-15 | Okkar Kyaw WX1404297
CBR7015_Flash_Battery_EAS R3 | CBR7015 | N/A |  | Teloneer Company Limited | 2026-09-19 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | RAN OMC |  | 0/0 | N/A | N/A | 2026-08-31 | 2026-09-21 | Teloneer Company Limited |  | 2026-08-31 |  | Teloneer Company Limited |  |  |  |  | 2026-09-25 | Teloneer Company Limited |  | N/A | N/A | N/A | N/A |  | 2026-09-25 | Teloneer Company Limited |  | 2026-08-31 | 2026-09-25 | Boonchot Boriwut | [5 empty] | 2026-08-31 | 2026-09-19 | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A |  | 2026-08-18 | Rachapol Lekduwee 84315610 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 13.019931 | 100.949351 |  | N/A | N/A | N/A | N/A
CBR7015_Flash_RAN_EAS R3 | CBR7015 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-17 |  |  |  |  | 2026-08-21 | 2026-08-21 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-09-16 | 2026-09-16 | Chadathan Thumsawat WX1461876 | 2026-09-16 Site : CBR7015X_2NB01 Today : Integrate 2600 Done 10G : Done Alarm : Clear Pending : URL Ticket - https://wongla.com/chat?id=4955394&category=Ticket%20Update | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-09-22 | Teloneer Company Limited |  | 2026-08-31 | 2026-09-18 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-24 | Kaung Htet San WX1440182 | Line HSSE Photo not have in EHS Task | [8 empty] | 2026-08-31 | 2026-09-25 | Boonchot Boriwut | 1.plz confirm for Ant model | 2026-09-30 | 2026-09-17 | Chootinatcha Supphapongpak 84433801 |  | 2026-08-31 | 2026-09-16 | Teloneer Company Limited |  |  |  |  | 2026-06-23 | Settha Prompunjai WX1438714 |  |  | 2026-08-16 | renqijing WX1507439 |  |  | 2026-08-12 | zhangguanglin WX1251498 | 20260910 FEA revised version no impact for LLD. |  | 2026-08-22 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2648 |  | 2026-08-16 | renqijing WX1507439 |  |  |  | 2026-09-16 | 2026-09-16 | Chadathan Thumsawat WX1461876 |  |  | 2026-08-19 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=1649806517#gid=1649806517 |  |  | 2026-09-16 | 2026-09-16 | Chadathan Thumsawat WX1461876 |  |  | 13.019931 | 100.949351 | 2026-08-13 | N/A | N/A | N/A | N/A |  |  | Ready
CBR7347_Flash_RAN_EAS R3 | CBR7347 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-24 | thcp_wachira s |  |  |  | 2026-07-07 | 2026-07-07 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-07-16 | 2026-07-16 | Kullaphat Yana WX1494386 | 2026-09-24 Site : CBR7347L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Test alarm node 2600 done URL Ticket : https://wongla.com/chat?id=4737638&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-23 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-22 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-25 | Su Myat Aung WX1480913 | HSSE photo not have | [8 empty] | 2026-08-31 | 2026-07-24 | Boonchot Boriwut |  |  | 2026-07-16 |  |  | 2026-07-31 | 2026-07-25 | Teloneer Company Limited |  |  |  |  | 2026-06-05 | Settha Prompunjai WX1438714 |  |  | 2026-06-15 | xinghaixia WX1519428 |  |  | 2026-06-12 | yangzhi WX1171682 |  |  | 2026-07-13 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2628 |  | 2026-06-15 | xinghaixia WX1519428 |  |  |  | 2026-07-21 | 2026-07-21 | Chadathan Thumsawat WX1461876 |  |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-07-16 | 2026-07-16 | Kullaphat Yana WX1494386 | 2026-07-15 Site CBR7347L_6NB02 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 13.021811 | 101.078321 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-03 | Sahadsavat Deesupat WX1462179 |  |  | 2026-07-29 | Okkar Kyaw WX1404297
CBR7972_Flash_RAN_EAS R3 | CBR7972 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-28 | thcp_wachira s |  |  |  | 2026-08-03 | 2026-08-03 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-08-19 | 2026-08-19 | Jirawan Tantimethanon 84318961 | 2026-08-19 Site : CBR7972L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done RET/BFANT : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Integrate 2300+2600 done URL Ticket : https://wongla.com/chat?id=4838009&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-09-02 | Teloneer Company Limited |  | 2026-08-31 | 2026-09-01 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-08 | Kaung Htet San WX1440182 | Line HSSE Photo not have | [8 empty] | 2026-08-31 | 2026-09-02 | Boonchot Boriwut | 1.CPRI are dismantle or not? | 2026-08-31 | 2026-08-19 |  |  | 2026-08-31 | 2026-09-01 | Teloneer Company Limited |  |  |  |  | 2026-06-12 | Settha Prompunjai WX1438714 |  |  | 2026-07-28 | jiaozelin WX1343901 |  |  | 2026-07-28 | wangchengdu WX1289449 |  |  | 2026-08-05 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2634 |  | 2026-07-28 | jiaozelin WX1343901 |  |  |  | 2026-08-18 | 2026-08-18 | Piyachon Kerdseng 84345719 | 2026-08-18 BBU2100 : Done BBU2600 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-08-19 | 2026-08-19 | Jirawan Tantimethanon 84318961 | 2026-08-19 Serial ascending order : Done DSP serial match : Done Azimuth : Done | CBR7972 | 12.897291 | 100.870351 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-18 | 2026-09-18 | Sahadsavat Deesupat WX1462179 |  |  | 2026-09-13 | Okkar Kyaw WX1404297
CBR8626_Flash_RAN_EAS R3 | CBR8626 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-27 | thcp_wachira s |  |  |  | 2026-08-03 | 2026-08-03 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-08-20 | 2026-08-20 | 2026-08-20 | Kullaphat Yana WX1494386 | 2026-08-20 Site : CBR8626X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Integrate 2300 Done URL Ticket : https://wongla.com/chat?id=4842401&category=Ticket%20Update Today : Clear pending Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-22 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-22 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-25 | Kaung Htet San WX1440182 | [9 empty] | 2026-08-31 | 2026-08-24 | Boonchot Boriwut | 1.wait SQC | 2026-08-08 | 2026-08-20 |  |  | 2026-08-31 | 2026-08-20 | Teloneer Company Limited |  |  |  |  | 2026-04-15 | Kulchaya Srichavanant 84433803 |  |  | 2026-07-23 | renqijing WX1507439 |  |  | 2026-07-22 | wangchengdu WX1289449 |  |  | 2026-07-24 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2636 |  | 2026-07-23 | renqijing WX1507439 |  |  |  | 2026-08-20 | 2026-08-20 | Kullaphat Yana WX1494386 |  |  | 2026-06-16 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=1649806517#gid=1649806517 |  |  | 2026-08-20 | 2026-08-20 | Kullaphat Yana WX1494386 | 2026-08-20 Site CBR8626X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 12.936667 | 100.912778 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-09-21 | Phumin Sritasaen WX1462185 |  |  | 2026-09-03 | Okkar Kyaw WX1404297
CBR8790_Flash_RAN_EAS R3 | CBR8790 | N/A | Teloneer Company Limited |  | 2026-09-22 | thcp_wachira s |  |  |  | 2026-07-10 | 2026-07-10 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-07-12 | 2026-07-12 | Akaradech Sonamthiang WX1494384 | 2026-07-13 Site : CBR8790L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Clear pending URL Ticket : https://wongla.com/chat?id=4726888&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-07-24 | Teloneer Company Limited |  | 2026-06-10 | 2026-07-25 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-27 | Su Myat Aung WX1480913 | HSSE photo not have | [8 empty] | 2026-08-31 | 2026-07-25 | Boonchot Boriwut |  | 2026-07-18 | 2026-07-12 | Chootinatcha Supphapongpak 84433801 |  | 2026-08-31 | 2026-07-13 | Teloneer Company Limited |  |  |  | 2026-06-08 | 2026-06-08 | Santi Rodjanachalee WX1291343 |  |  | 2026-06-18 | xinghaixia WX1519428 |  |  | 2026-06-16 | yangzhi WX1171682 |  |  | 2026-07-06 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2628 |  | 2026-06-18 | xinghaixia WX1519428 |  |  |  | 2026-07-12 | 2026-07-12 | Akaradech Sonamthiang WX1494384 | 2026-07-12 Site CBR8790 Cabinet 1 CBR8790X_2NB01 : Done Cabinet 2 CBR8790L_6NB02 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-07-12 | 2026-07-12 | Akaradech Sonamthiang WX1494384 | 2026-07-12 Site CBR8790L_6NB02 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 13.040601 | 101.104441 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-03 | Sahadsavat Deesupat WX1462179 |  |  | 2026-07-30 | Okkar Kyaw WX1404297
CBRA441_Flash_RAN_EAS R3 | CBRA441 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-25 | thcp_wachira s |  |  |  | 2026-07-07 | 2026-07-07 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-07-14 | 2026-07-18 | Akaradech Sonamthiang WX1494384 | 2026-09-21 Site : CBRA441X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Clear pending URL Ticket : https://wongla.com/chat?id=4744173&category=Ticket%20Update Alarm : Clear Remarks : . | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-24 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-24 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-28 | Su Myat Aung WX1480913 | HSSE photo not have | [8 empty] | 2026-08-31 | 2026-07-24 | Boonchot Boriwut |  | 2026-07-24 | 2026-07-18 | Chootinatcha Supphapongpak 84433801 |  | 2026-07-31 | 2026-07-18 | Teloneer Company Limited |  |  |  |  | 2026-06-08 | Chanakan Ratanachiwapong 84115359 |  |  | 2026-06-16 | wangchengdu WX1289449 |  |  | 2026-06-16 | yangzhi WX1171682 |  |  | 2026-07-06 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2628 |  | 2026-06-16 | wangchengdu WX1289449 |  |  |  | 2026-07-18 | 2026-07-18 | Akaradech Sonamthiang WX1494384 | 2026-07-18 Site CBRA441X_2NB01 Cabinet 1 slot 18 : Done Cabinet 2 slot 19 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-07-14 | 2026-07-18 | Akaradech Sonamthiang WX1494384 | 2026-07-18 Site CBRA441X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 13.037070 | 101.074638 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-03 | Sahadsavat Deesupat WX1462179 |  |  | 2026-07-30 | Okkar Kyaw WX1404297
CBRA516_Flash_RAN_EAS R3 | CBRA516 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-24 | thcp_wachira s |  |  |  | 2026-07-07 | 2026-07-07 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-07-10 | 2026-07-10 | Pongsak Wunkong WX1461875 | KCP 4 2026-07-122 Site : CBRA516 Subcon : Huawei CR/SSA/TT : CRQ000006175964 Material : SID Version 1 ------------------------------------------ BBU integration : Done RRU integration : Done Cell integration : Done 2300 RET/BFANT : Done Cut 10G : Done Cross Sector : Done Post Check : Done CDD Compare : Done Reused Hardware Faulty : Today : Test External alarm URL Ticket : https://wongla.com/chat?id=4721120&category=Ticket%20Update | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-23 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-23 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-25 | Su Myat Aung WX1480913 | HSSE photo not have | [8 empty] | 2026-08-31 | 2026-07-24 | Boonchot Boriwut |  | 2026-07-18 | 2026-07-10 | Chootinatcha Supphapongpak 84433801 |  | 2026-07-31 | 2026-07-10 | Teloneer Company Limited |  |  |  | 2026-06-05 | 2026-06-05 | Santi Rodjanachalee WX1291343 |  |  | 2026-06-16 | jiaozelin WX1343901 |  |  | 2026-06-16 | yangzhi WX1171682 |  |  | 2026-07-06 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2628 |  | 2026-06-16 | jiaozelin WX1343901 |  |  |  | 2026-07-22 | 2026-07-22 | Kullaphat Yana WX1494386 |  |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-07-10 | 2026-07-10 | Pongsak Wunkong WX1461875 | 2026-07-10 Site : CBRA516 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 13.043410 | 101.100690 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-03 | Sahadsavat Deesupat WX1462179 |  |  | 2026-07-29 | Okkar Kyaw WX1404297
KKN0184_Flash_RAN_NEA R5 | KKN0184 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-09 | thcp_chalit.sar |  |  |  | 2026-07-07 | 2026-07-07 | Jirawan Tantimethanon 84318961 |  |  | 2026-07-07 | 2026-07-07 | 2026-07-07 | Tinnakorn Konseela 84060525 | KCP 2 KKN0184 MBB:Install & Integrate KCP 2 Readiness by PE & Decision by OMC Site : KKN0184 Subcon : TLN CR/SSA/TT : ------------------------------------------ 1. Material Check Material : SID version_V1 RRU : Match ANT : Match iDMU : No Install New Cabinet : No Battery Work : No 2300 Hot Swap : No RRU/ANT Space : Yes S/N : AAU5685md_2300+2600 S1 2102315NDH10S3100944 S2 2102315NDH10S3100951 S3 2102315NDH10S3100960 Port Cal : No ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 0.5 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [8 empty] | 2026-07-09 | 2026-07-09 | Chadathan Thumsawat WX1461876 | 2026-07-10 Site : KKN0184X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Pending photo azimuth Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : - Today : Integrate 2300 and 2600 Done URL Ticket : https://wongla.com/chat?id=4717317&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-10 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-09 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-15 | Su Myat Aung WX1480913 | FBOM FMR Generate file not ready HSSE photo not have | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-07-31 | 2026-07-14 | Auttaseth Klomthaisong |  | 2026-07-12 | 2026-07-09 | Chootinatcha Supphapongpak 84433801 |  | 2026-07-31 | 2026-07-09 | Teloneer Company Limited |  |  |  |  | 2026-04-29 | Sunisa Worathongchai WX1291720 |  |  | 2026-06-22 | xinghaixia WX1519428 |  |  | 2026-06-18 | yangzhi WX1171682 |  |  | 2026-07-06 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2632 |  | 2026-06-22 | xinghaixia WX1519428 |  |  |  | 2026-07-10 | 2026-07-10 | Akaradech Sonamthiang WX1494384 | 2026-07-10 Site KKN0184X_2NB01 Cabinet 1 slot 18 : N/A Cabinet 2 slot 19 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-07-14 | 2026-07-14 | Kullaphat Yana WX1494386 |  |  | 16.459422 | 102.796801 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-07-23 | 2026-07-23 | Jiraporn Chantasil WX1462181 |  |  | 2026-07-19 | Okkar Kyaw WX1404297
KKN0201_Flash_Battery_NEA R5 | KKN0201 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-24 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | 2026-07-24 | Jirawan Tantimethanon 84318961 |  | 0/0 | N/A | N/A | 2026-07-31 | 2026-07-26 | Teloneer Company Limited |  | 2026-07-31 |  | Teloneer Company Limited |  |  | 01. No alarm (Before) |  |  |  |  | N/A | N/A | N/A | N/A | 2026-07-31 | 2026-08-21 | Teloneer Company Limited |  | 2026-07-31 | 2026-08-19 | Auttaseth Klomthaisong |  |  | 2026-07-24 |  |  | 2026-07-31 | 2026-07-24 | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A |  | 2026-06-30 | xinghaixia WX1519428 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 16.440698 | 102.828472 |  | N/A | N/A | N/A | N/A
KKN0201_Flash_RAN_NEA R5 | KKN0201 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-20 | thcp_anat.sri |  |  |  | 2026-07-14 | 2026-07-14 | Jirawan Tantimethanon 84318961 |  | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-24 | Tinnakorn Konseela 84060525 | KCP 2 KKN0201 MBB:Install & Integrate KCP 2 Readiness by PE & Decision by OMC Site : KKN0201 Subcon : TLN CR/SSA/TT : ------------------------------------------ 1. Material Check Material : SID version_V1 RRU : Match ANT : Match iDMU : No Install New Cabinet : No Battery Work : No 2300 Hot Swap : No RRU/ANT Space : Yes S/N : AAU5685md_2300+2600 S1 – 2102315NDH10S3100723 S2 – 2102315NDH10S3100728 S3 – 2102315NDH10S3100739 Port Cal : No ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 0.5 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [7 empty] | 2026-07-25 | 2026-07-24 | 2026-07-24 | Akaradech Sonamthiang WX1494384 | 2026-07-25 Site : KKN0201X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Test External alarm and verify cross sector. Done URL Ticket : https://wongla.com/chat?id=4760347&category=Ticket%20Update Alarm : Clear Remarks : * | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-27 | Teloneer Company Limited |  | 2026-07-31 | 2026-08-20 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-27 | Kaung Htet San WX1440182 | [9 empty] | 2026-07-31 | 2026-08-20 | Auttaseth Klomthaisong |  |  | 2026-07-24 |  |  | 2026-07-31 | 2026-07-24 | Teloneer Company Limited |  |  |  |  | 2026-05-19 | Sunisa Worathongchai WX1291720 |  |  | 2026-07-06 | xinghaixia WX1519428 |  |  | 2026-06-29 | zhangguanglin WX1251498 |  |  | 2026-07-15 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2635 |  | 2026-07-06 | xinghaixia WX1519428 |  |  |  | 2026-07-25 | 2026-07-25 | Akaradech Sonamthiang WX1494384 | 2026-07-25 Site KKN0201 Cabinet 1 slot 18 : N/A Cabinet 1 slot 19 : Done |  | 2026-08-06 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=1649806517#gid=1649806517 |  |  | 2026-07-24 | 2026-07-25 | Akaradech Sonamthiang WX1494384 | 2026-07-24 Site KKN0201X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 16.440698 | 102.828472 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-26 | Phumin Sritasaen WX1462185 |  |  | 2026-09-12 | Okkar Kyaw WX1404297
KKN0428_Flash_RAN_NEA R5 | KKN0428 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-18 | thcp_anat.sri |  |  |  | 2026-06-17 | 2026-06-17 | Jirawan Tantimethanon 84318961 |  | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-16 | Tinnakorn Konseela 84060525 | Site : KKN0428_Flash_RAN_NEA R5 Subcon : TLN CR/SSA/TT : ------------------------------------------ 1. Material Check Material : SID version_V1 RRU : Match ANT : Match iDMU : No Install New Cabinet : No 2300 Hot Swap : No RRU/ANT Space :Yes S/N : AAU5685md_2300+2600 S1 – 2102315NDH10S3100225- done S2 – 2102315NDH10S3100230- done S3 – 2102315NDH10S3100247- done ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 1 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [8 empty] | 2026-06-17 | 2026-06-17 | Pongsak Wunkong WX1461875 | KCP 4 2026-06-19 Site : KKN0428 Subcon : NWC CR/SSA/TT : CRQ000006144023 Material : SID version_V1 ------------------------------------------ BBU integration : Done RRU integration : Done Cell integration : Done 2300 RET/BFANT : S1#，S2#，S3 done 2600 RET/BFANT : S1#，S2#，S3 done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : No ------------------------------------------ Today : Cross sector test#， External alarm test Done Pending : URL Ticket : https://wongla.com/chat?id=4665010&category=Ticket%20Update | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-06-24 | Teloneer Company Limited |  | 2026-07-31 | 2026-06-20 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-06-24 | Kaung Htet San WX1440182 |  | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-06-24 | 2026-06-26 | Auttaseth Klomthaisong |  | 2026-06-22 | 2026-06-17 | Chootinatcha Supphapongpak 84433801 |  | 2026-07-31 | 2026-06-18 | Teloneer Company Limited |  | 2026-09-09 | Entirely Completed |  | 2026-04-29 | Sunisa Worathongchai WX1291720 |  |  | 2026-06-01 | yangshuanghong WX1009887 |  |  | 2026-06-01 | zhangguanglin WX1251498 |  |  | 2026-06-12 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2624 |  | 2026-06-01 | yangshuanghong WX1009887 |  |  |  | 2026-06-19 | 2026-06-19 | Peerapol Prapai 84315924 | AC Main (T/D) =Can't Rect urgent (T/D) Door (T/D) Battery Stolen (T/D) =Can't Smoke (True) Low voltage (True) Rect non urgent (True) SPD (True) Confirm by PE |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-06-17 | 2026-06-19 | Pongsak Wunkong WX1461875 | 2026-06-17 Site KKN0428 Serial ascending order : Done DSP serial match : Done Azimuth : Pending |  | 16.466804 | 102.757911 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-07-03 | 2026-07-03 | Jiraporn Chantasil WX1462181 |  |  | 2026-06-30 | Okkar Kyaw WX1404297
KKN1512_Flash_RAN_NEA R5 | KKN1512 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-09 | thcp_chalit.sar |  |  |  | 2026-07-01 | 2026-07-01 | Jirawan Tantimethanon 84318961 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | Tinnakorn Konseela 84060525 | KKN1512 MBB:Install & Integrate KCP 2 Readiness by PE & Decision by OMC Site : KKN1512 Subcon : TLN CR/SSA/TT : ------------------------------------------ 1. Material Check Material : SID version_V2 RRU : Match ANT : Match iDMU : No Install New Cabinet : No Battery Work : No 2300 Hot Swap : No RRU/ANT Space : Yes S/N : AAU5685md_2300+2600 S1 – 2102315NDH10S3100268 S2 – 2102315NDH10S3100272 S3 - 2102315NDH10S3100274 S4 – 2102315NDH10S3101121 Port Cal : No ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 0.5 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [8 empty] | 2026-07-02 | 2026-07-03 | Pongsak Wunkong WX1461875 | 2026-07-07 Site : KKN1512 Subcon : TLN CR/SSA/TT : CRQ000006160169 Material : SID version_V2 ------------------------------------------ BBU integration : Done RRU integration : Pending Cell integration : Pending 2600 RET/BFANT : S1 Done Partial S2#，S3#，S4 2300 RET/BFANT : S1 Done Partial S2#，S3#，S4 Cut 10G : NA Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : No ------------------------------------------ Today : Test external alarm done URL Ticket : https://wongla.com/chat?id=4699038&category=Ticket%20Update | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-09 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-07 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-15 | Su Myat Aung WX1480913 | FBOM FMR Generate file not ready | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-07-31 | 2026-07-13 | Auttaseth Klomthaisong |  | 2026-07-05 | 2026-07-03 | Chootinatcha Supphapongpak 84433801 |  | 2026-07-31 | 2026-07-03 | Teloneer Company Limited |  |  |  |  | 2026-06-12 | Sunisa Worathongchai WX1291720 |  |  | 2026-06-23 | wangchengdu WX1289449 |  |  | 2026-06-22 | zhangguanglin WX1251498 |  |  | 2026-06-28 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2624 |  | 2026-06-23 | wangchengdu WX1289449 |  |  |  | 2026-07-07 | 2026-07-07 | Piyachon Kerdseng 84345719 | 2026-07-07 Test external alarm done |  | 2020-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-07-03 | 2026-07-03 | Pongsak Wunkong WX1461875 | 2026-07-03 Site KKN1512 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 16.432801 | 102.770001 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-07-23 | 2026-07-23 | Jiraporn Chantasil WX1462181 |  |  | 2026-07-19 | Okkar Kyaw WX1404297
KKN1622_FlashRevisit_NEA R5 | KKN1622 | N/A | Teloneer Company Limited | Teloneer Company Limited | [27 empty] | 0/2 | Not Completed | Not Completed | 2026-10-31 |  | Teloneer Company Limited |  | 2026-10-31 |  | Teloneer Company Limited | [15 empty] | 2026-10-31 |  |  | Teloneer Company Limited |  |  |  |  | 2026-10-31 |  | Teloneer Company Limited | [20 empty] | N/A | N/A | N/A | N/A | [22 empty] | 16.450401 | 102.808001 |  | N/A | N/A | N/A | N/A
KKN1622_Flash_Battery_NEA R5 | KKN1622 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-25 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | 2026-07-28 | Kullaphat Yana WX1494386(RAN OMC) | 2026-07-28 Today : Integrate Batt done | 0/0 | N/A | N/A | 2026-07-31 | 2026-08-04 | Teloneer Company Limited |  | 2026-07-31 |  | Teloneer Company Limited | [7 empty] | N/A | N/A | N/A | N/A | 2026-07-31 | 2026-08-28 | Teloneer Company Limited |  | 2026-07-31 | 2026-08-19 | Auttaseth Klomthaisong | 1.tray lock is dismantle or not?? |  | 2026-07-28 |  |  | 2026-07-31 | 2026-07-27 | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A |  | 2026-06-23 | yangshuanghong WX1009887 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 16.450401 | 102.808001 |  | N/A | N/A | N/A | N/A
KKN1622_Flash_RAN_NEA R5 | KKN1622 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-25 | thcp_anat.sri |  |  |  | 2026-07-07 | 2026-07-07 | Jirawan Tantimethanon 84318961 |  |  | 2026-07-07 | 2026-07-07 | 2026-07-07 | Tinnakorn Konseela 84060525 | KCP 2 KKN1622 MBB:Install & Integrate KCP 2 Readiness by PE & Decision by OMC Site : KKN1622 Subcon : TLN CR/SSA/TT : ------------------------------------------ 1. Material Check Material : SID version_V2 RRU : Match ANT : Match iDMU : No Install New Cabinet : No Battery Work : No 2300 Hot Swap : No RRU/ANT Space : Yes S/N : AAU5636 2300 S1 2102313HCL10RA100290 S2 2102313HCL10RA100304 S3 2102313HCL10RA100305 Port Cal : No ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 0.5 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [8 empty] | 2026-07-18 | 2026-07-18 | Chadathan Thumsawat WX1461876 | 2026-07-22 Site : KKN1622L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : - Today : 10G cutover done URL Ticket : https://wongla.com/chat?id=4744332&category=Ticket%20Update Alarm : Clear Alarm before -BBU CPRI Interface Error [slot3 port 2 BBU2100] Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-23 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-20 | Teloneer Company Limited |  |  | 01. No alarm (Before) |  | 2026-07-25 | Su Myat Aung WX1480913 | HSSE photo not have | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-07-21 | 2026-07-24 | Auttaseth Klomthaisong |  | 2026-07-11 | 2026-07-21 | Chootinatcha Supphapongpak 84433801 |  | 2026-07-31 | 2026-07-21 | Teloneer Company Limited |  | 2026-07-21 | Entirely Completed |  | 2026-03-06 | Kulchaya Srichavanant 84433803 |  |  | 2026-06-22 | yangshuanghong WX1009887 |  |  | 2026-06-17 | yangzhi WX1171682 |  |  | 2026-06-20 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2632 |  | 2026-06-22 | yangshuanghong WX1009887 |  |  |  | 2026-07-22 | 2026-07-22 | Akaradech Sonamthiang WX1494384 | 2026-07-22 Site KKN1622 Cabinet 1 : Done Cabinet 2 : Done |  | 2026-06-23 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=1649806517#gid=1649806517 |  |  | 2026-07-18 | 2026-07-18 | Chadathan Thumsawat WX1461876 |  | KKN1622 | 16.450401 | 102.808001 | 2026-07-09 | N/A | N/A | N/A | N/A |  |  | Ready |  | 2026-08-07 | 2026-08-07 | Jiraporn Chantasil WX1462181 |  |  | 2026-08-12 | Okkar Kyaw WX1404297
KKN1805_Flash_RAN_NEA R5 | KKN1805 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-15 | thcp_anat.sri |  |  |  | 2026-07-22 | 2026-07-22 | Jirawan Tantimethanon 84318961 |  | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-29 | Tinnakorn Konseela 84060525 | [8 empty] | 2026-07-30 | 2026-07-29 | 2026-07-29 | Pongsak Wunkong WX1461875 | KCP 4 2026-07-30 Site : KKN1805 Subcon : TLN CR/SSA/TT : CRQ000006209562 Material : SID version_V1 ------------------------------------------ BBU integration : Done RRU integration : Done Cell integration : Done BF Ant 2300 : S1#，S2#，S3 Done BF Ant 2600 : S1#，S2#，S3 Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : No ------------------------------------------ Today : Cut over 10G done Alarm : Clear Pending : URL Ticket : https://wongla.com/chat?id=4931718&category=Ticket%20Update | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-08-04 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-31 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-05 | Su Myat Aung WX1480913 |  | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-07-31 | 2026-08-05 | Auttaseth Klomthaisong | 1.if AMPF bracket dismantle#， need photo view 2.need to add BBU 3.need to add GPS-FYGE << FYMA is one or two ?? 4.Nk-BBU#， boards's photo are missing at SQC & FMR 5.need to SFP 10G |  | 2026-07-29 |  |  | 2026-07-31 | 2026-07-30 | Teloneer Company Limited |  |  |  |  | 2026-02-24 | Kulchaya Srichavanant 84433803 |  |  | 2026-07-16 | yangshuanghong WX1009887 |  |  | 2026-07-16 | zhangguanglin WX1251498 |  |  | 2026-07-27 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2632 |  | 2026-07-16 | yangshuanghong WX1009887 |  |  |  | 2026-07-30 | 2026-07-30 | Chadathan Thumsawat WX1461876 |  |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-07-29 | 2026-07-30 | Pongsak Wunkong WX1461875 | 2026-07-29 Site KKN1805L_6NB03 Serial ascending order : Pending DSP serial match : Done Azimuth : Pending | KKN1805 | 16.483311 | 102.816901 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-08-07 | 2026-08-07 | Jiraporn Chantasil WX1462181 |  |  | 2026-08-28 | Okkar Kyaw WX1404297
KKN7005_Flash_RAN_NEA R5 | KKN7005 | N/A |  |  | 2026-09-24 | [26 empty] | 0/2 | Not Completed | Not Completed | [53 empty] | N/A | N/A | N/A | N/A | [21 empty] | KKN7005 | 16.438018 | 102.835537 |  | N/A | N/A | N/A | N/A
KKN7115_Flash_Battery_NEA R5 | KKN7115 | N/A | Teloneer Company Limited | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | RAN OMC |  | 0/0 | N/A | N/A | 2026-07-31 |  | Teloneer Company Limited |  | 2026-07-31 |  | Teloneer Company Limited | [7 empty] | N/A | N/A | N/A | N/A | [12 empty] | 2026-07-31 |  | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A |  | 2026-06-03 | yangshuanghong WX1009887 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A
KKN7115_Flash_RAN_NEA R5 | KKN7115 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-18 | thcp_chalit.sar |  |  |  | 2026-06-16 | 2026-06-16 | Jirawan Tantimethanon 84318961 |  | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | Tinnakorn Konseela 84060525 | Site : KKN7115_Flash_RAN_NEA R5 Subcon : WNP CR/SSA/TT : CRQ000006136024 ------------------------------------------ 1. Material Check Material : SID version_V1 RRU : Match ANT : Match iDMU : No Install New Cabinet : No 2300 Hot Swap : No RRU/ANT Space :Yes S/N : AAU5685md_2300+2600 S1 – 2102315NDH1053100202- done S2 – 2102315NDH10S3100206- done S3 – 2102315NDH10S3100217- done ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 1 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [8 empty] | 2026-06-18 | 2026-06-18 | Akaradech Sonamthiang WX1494384 | 2026-06-22 Site : KKN7115L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Test External alarm done URL Ticket : https://wongla.com/chat?id=4661873&category=Ticket%20Update Alarm : Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-06-22 | Teloneer Company Limited |  | 2026-07-31 | 2026-06-23 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-06-24 | Kaung Htet San WX1440182 |  | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-06-23 | 2026-06-25 | Auttaseth Klomthaisong |  | 2026-06-18 | 2026-06-16 | Chootinatcha Supphapongpak 84433801 |  | 2026-07-31 | 2026-06-18 | Teloneer Company Limited |  | 2026-09-09 | Entirely Completed |  | 2026-03-05 | Kulchaya Srichavanant 84433803 |  |  | 2026-06-01 | jinwen WX1379399 |  |  | 2026-06-01 | zhangguanglin WX1251498 |  |  | 2026-06-12 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2624 |  | 2026-06-01 | jinwen WX1379399 |  |  |  | 2026-06-22 | 2026-06-22 | Peerapol Prapai 84315924 | 2026-06-22 Site KKN7115 Cabinet 1 BBU2100 : done Cabinet 2 BBU2600 : done |  | 2026-06-23 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=0#gid=0 |  |  | 2026-06-18 | 2026-06-18 | Akaradech Sonamthiang WX1494384 | 2026-06-18 Site KKN7115L_6NB02 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 16.471283 | 102.796432 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-07-03 | 2026-07-03 | Jiraporn Chantasil WX1462181 |  |  | 2026-06-26 | Okkar Kyaw WX1404297
KKN7125_Flash_RAN_NEA R5 | KKN7125 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-22 | thcp_anat.sri |  |  |  | 2026-08-17 | 2026-08-17 | Jirawan Tantimethanon 84318961 |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Tinnakorn Konseela 84060525 | [9 empty] | 2026-08-22 | 2026-08-22 | Jirawan Tantimethanon 84318961 | 2026-08-22 Site : KKN7125 donor KKNA066X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done RET/BFANT : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Integrate 2600 URL Ticket : https://wongla.com/chat?id=4852255&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-24 | 2026-08-24 | Teloneer Company Limited |  | 2026-09-30 | 2026-08-25 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-26 | Kaung Htet San WX1440182 | 09 Site Integration not have 09 Cross Sector Verification not have | [8 empty] | 2026-08-31 | 2000-01-01 | Teloneer Company Limited |  |  | 2026-08-22 |  |  | 2026-08-22 | 2026-08-23 | Teloneer Company Limited |  |  |  |  | 2026-04-29 | Sunisa Worathongchai WX1291720 |  |  | 2026-07-30 | wangweihao WX1465967 |  |  | 2026-07-29 | yangzhi WX1171682 |  |  | 2026-08-16 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2633 |  | 2026-07-30 | wangweihao WX1465967 |  |  |  | 2000-01-01 | 2000-01-01 | Jirawan Tantimethanon 84318961 |  |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | DPU Work No Battery |  |  | 2026-08-22 | 2026-08-22 | Jirawan Tantimethanon 84318961 | 2026-08-22 Serial ascending order : Done DSP serial match : Done Azimuth : Done | KKNA066 | 16.478061 | 102.817901 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-15 | Ekkarin Tidkratok WX1539755 |  |  | 2026-09-12 | Okkar Kyaw WX1404297
KKN7197_Flash_Battery_NEA R5 | KKN7197 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-06-26 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | 2026-06-26 | Akaradech Sonamthiang WX1494384 | 2026-06-26 Site : KKN7197X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Integrate Battery done URL Ticket : https://wongla.com/chat?id=4685868&category=Ticket%20Update Alarm : Clear Remarks : | 0/0 | N/A | N/A | 2026-07-31 | 2026-06-30 | Teloneer Company Limited |  | 2026-07-31 |  | Teloneer Company Limited |  |  | 00. No alarm |  |  |  |  | N/A | N/A | N/A | N/A | 2026-07-01 | 2026-07-10 | Teloneer Company Limited | Cover Sheet: Battery must be Swap 1 Add 3 Picture Installation Batt#1 Sheet: Before Battery SN photo must be only 1 After Cabinet + New Battery Cabinet#1 Must be One photo Battery Bus bar Cabinet#1 photo is wrong Material Dismantle photo must be only one photo Need TOPO from RMS Box Power Design Sheet: Need to fill existing battery model | 2026-09-30 | 2026-09-14 | Auttaseth Klomthaisong |  |  | 2026-06-25 |  |  | 2026-07-31 | 2026-06-26 | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A |  | 2026-06-03 | yangshuanghong WX1009887 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 16.477201 | 102.774001 |  | N/A | N/A | N/A | N/A
KKN7197_Flash_RAN_NEA R5 | KKN7197 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-18 | thcp_chalit.sar |  |  |  | 2026-06-19 | 2026-06-19 | Jirawan Tantimethanon 84318961 |  | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-19 | Tinnakorn Konseela 84060525 | Site : KKN7197_Flash_RAN_NEA R5 Subcon : TLN CR/SSA/TT : CRQ000006142872 ------------------------------------------ 1. Material Check Material : SID version_V1 RRU : Match ANT : Match iDMU : No Install New Cabinet : No 2300 Hot Swap : No RRU/ANT Space :Yes S/N : AAU5636 S1 – 2102313HCL10RB100598- done S2 – 2102313HCL10RB100608- done S3 – 2102313HCL10RB100609- done ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 1 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [8 empty] | 2026-06-20 | 2026-06-20 | Akaradech Sonamthiang WX1494384 | 2026-06-30 Site : KKN7197X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Clear pending done URL Ticket : https://wongla.com/chat?id=4667348&category=Ticket%20Update Alarm : Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-06-25 | Teloneer Company Limited |  | 2026-07-31 | 2026-06-25 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-06-30 | Kaung Htet San WX1440182 | 1;Mtilt mismatch with FEA in Sec 2 | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-06-24 | 2026-06-29 | Auttaseth Klomthaisong |  | 2026-06-19 | 2026-06-19 | Teloneer Company Limited |  | 2026-07-31 | 2026-06-20 | Teloneer Company Limited |  |  |  |  | 2026-02-24 | Kulchaya Srichavanant 84433803 |  |  | 2026-06-02 | yangshuanghong WX1009887 |  |  | 2026-06-01 | zhangguanglin WX1251498 |  |  | 2026-06-12 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2624 |  | 2026-06-02 | yangshuanghong WX1009887 |  |  |  | 2026-06-25 | 2026-06-25 | Peerapol Prapai 84315924 | 2026-06-20 Site KKN7197X_2NB01 Cabinet 1 slot 18 : N/A Cabinet 1 slot 19 : Done |  | 2026-06-23 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=0#gid=0 |  |  | 2026-06-20 | 2026-06-20 | Akaradech Sonamthiang WX1494384 | 2026-06-20 Site KKN7197X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 16.477201 | 102.774001 | 2000-01-01 | N/A | N/A | N/A | N/A |  |  | Ready |  | 2026-07-03 | 2026-07-03 | Jiraporn Chantasil WX1462181 |  |  | 2026-07-03 | Okkar Kyaw WX1404297 | 1;Mtilt mismatch with FEA in Sec 2
KKN7307_Flash_RAN_NEA R5 | KKN7307 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-18 | thcp_anat.sri |  |  |  | 2026-07-14 | 2026-07-14 | Jirawan Tantimethanon 84318961 |  | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | Tinnakorn Konseela 84060525 | [9 empty] | 2026-07-17 | 2026-07-17 | Piyachon Kerdseng 84345719 | 2026-07-17 Site : KKN7307 Subcon : TLN CR/SSA/TT : CRQ000006185713 Material : SID version_V1 ------------------------------------------ BBU integration : Done RRU integration : Done Cell integration : Done Cut 10G : NA Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : - ------------------------------------------ Today : Integrate 2300 done Pending : - Alarm : Clear URL Ticket : https://wongla.com/chat?id=4740661&category=Ticket%20Update | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-20 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-20 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-21 | Su Myat Aung WX1480913 | HSSE photo not have | [8 empty] | 2026-07-21 | 2000-01-01 | Teloneer Company Limited |  |  | 2026-07-16 |  |  | 2026-07-31 | 2026-07-17 | Teloneer Company Limited |  |  |  |  | 2026-05-07 | Teeranun Suksom WX1454012 |  |  | 2026-06-18 | xinghaixia WX1519428 |  |  | 2026-06-17 | zhangguanglin WX1251498 |  |  | 2026-07-15 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2635 |  | 2026-06-18 | xinghaixia WX1519428 |  |  |  | 2000-01-01 | 2000-01-01 | Piyachon Kerdseng 84345719 | Remote site |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | DPU Work No Battery |  |  | 2026-07-17 | 2026-07-17 | Piyachon Kerdseng 84345719 |  | KKN8649 | 16.444614 | 102.826672 | 2026-07-09 | N/A | N/A | N/A | N/A |  |  | Ready |  |  | 2026-07-21 | Ekkarin Tidkratok 84433232 |  |  | 2026-07-24 | Okkar Kyaw WX1404297
KKN7991_Flash_RAN_NEA R5 | KKN7991 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-15 | thcp_anat.sri |  |  |  | 2026-08-14 | 2026-08-14 | Jirawan Tantimethanon 84318961 |  | 2026-08-15 | 2026-08-15 | 2026-08-15 | 2026-08-15 | Tinnakorn Konseela 84060525 | [9 empty] | 2026-08-14 | 2026-08-15 | Chadathan Thumsawat WX1461876 | 2026-08-15 Site : KKN1805L_6NB03 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : NA Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : - Today : Integrate 1800 2100 2300 done URL Ticket :https://wongla.com/chat?id=4818725&category=Ticket%20Update alarm BBU2600- Rectifier Non Urgent Alarm [before donor] alarm BBU2100- Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-24 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-21 | Teloneer Company Limited |  |  | 01. No alarm (Before) |  | 2026-08-26 | Kaung Htet San WX1440182 | Line HSSE photo not have | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-08-31 | 2026-08-27 | Auttaseth Klomthaisong | 1.need photo view for CPRI & Power cable |  | 2026-08-14 |  |  | 2026-08-31 | 2026-08-16 | Teloneer Company Limited |  |  |  |  | 2026-02-24 | Kulchaya Srichavanant 84433803 |  |  | 2026-07-16 | sunjiayu WX1433921 |  |  | 2026-07-16 | zhangguanglin WX1251498 |  |  | 2026-08-08 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2632 |  | 2026-07-16 | sunjiayu WX1433921 |  |  |  | 2000-01-01 | 2000-01-01 | Chadathan Thumsawat WX1461876 |  |  | 2026-06-05 | Narusorn Phattharajaruk 00928167 | DPU Work No Battery |  |  | 2026-08-14 | 2026-08-15 | Chadathan Thumsawat WX1461876 | Pending photo azimuth & integrate 2100 | KKN1805 | 16.485468 | 102.817141 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-01 | 2026-09-01 | Jiraporn Chantasil WX1462181 |  |  | 2026-08-29 | Okkar Kyaw WX1404297
KKN8218_Flash_RAN_NEA R5 | KKN8218 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-10 | thcp_anat.sri |  |  |  | 2026-07-22 | 2026-07-22 | Jirawan Tantimethanon 84318961 |  | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | Tinnakorn Konseela 84060525 | [8 empty] | 2026-08-06 | 2026-08-11 | 2026-08-11 | Jirawan Tantimethanon 84318961 | 2026-08-11 Site : KKN8218 donor KKN1805X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done RET : Done Cut 10G : Done Cross Sector : Pending Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Cutover 10GB Done URL Ticket : https://wongla.com/chat?id=4931718&category=Ticket%20Update Alarm - Clear Pending : Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-08-17 | Teloneer Company Limited |  | 2026-07-31 | 2026-08-13 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-19 | Kaung Ko Ko WX1541657 | S3 Antenna view photo not have | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-07-31 | 2026-08-20 | Auttaseth Klomthaisong | 1.need power connector view 2.sfp are 3 nos or 6 nos?? 3.need CPRI#，RET photos | 2026-08-09 | 2026-08-11 |  |  | 2026-07-31 | 2026-08-12 | Teloneer Company Limited |  |  |  |  | 2026-06-12 | Sunisa Worathongchai WX1291720 |  |  | 2026-07-16 | shaoyuanqiao WX1507430 |  |  | 2026-07-16 | zhangguanglin WX1251498 |  |  | 2026-07-27 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2632 |  | 2026-07-16 | shaoyuanqiao WX1507430 |  |  |  | 2026-08-12 | 2026-08-12 | Pongsak Wunkong WX1461875 | Site remote no test external alarm |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-08-11 | 2026-08-12 | Jirawan Tantimethanon 84318961 | 2026-08-12 Site KKN8218 donor KKN1805X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done | KKN1805 | 16.485990 | 102.816431 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-08-26 | 2026-08-26 | Sahadsavat Deesupat WX1462179 |  |  | 2026-08-28 | Okkar Kyaw WX1404297
KKN8563_FlashRevisit_NEA R5 | KKN8563 | N/A | Teloneer Company Limited | Teloneer Company Limited | [27 empty] | 0/2 | Not Completed | Not Completed | 2026-10-31 |  | Teloneer Company Limited |  | 2026-10-31 |  | Teloneer Company Limited | [15 empty] | 2026-10-31 |  |  | Teloneer Company Limited |  |  |  |  | 2026-10-31 |  | Teloneer Company Limited | [20 empty] | N/A | N/A | N/A | N/A | [22 empty] | 16.421101 | 102.779481 |  | N/A | N/A | N/A | N/A
KKN8563_Flash_Battery_NEA R5 | KKN8563 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-06 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | 2026-08-06 | Akaradech Sonamthiang WX1494384 | 2026-08-06 Today : Integrate battery done URL : https://wongla.com./chat?id=4792289&category=Ticket%20Update | 0/0 | N/A | N/A | 2026-07-31 | 2026-08-04 | Teloneer Company Limited |  | 2026-07-31 |  | Teloneer Company Limited |  |  | 00. No alarm |  |  |  |  | N/A | N/A | N/A | N/A | 2026-07-31 | 2026-08-21 | Teloneer Company Limited |  | 2026-07-31 | 2026-08-19 | Auttaseth Klomthaisong |  |  | 2026-08-05 |  |  | 2026-07-31 | 2026-07-28 | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A |  | 2026-06-26 | xinghaixia WX1519428 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 16.421101 | 102.779481 |  | N/A | N/A | N/A | N/A
KKN8563_Flash_RAN_NEA R5 | KKN8563 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-04 | thcp_anat.sri |  |  |  | 2026-07-01 | 2026-07-01 | Jirawan Tantimethanon 84318961 |  | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | Tinnakorn Konseela 84060525 | KKN8563 MBB:Install & Integrate KCP 2 Readiness by PE & Decision by OMC Site : KKN8563 Subcon : TLN CR/SSA/TT : ------------------------------------------ 1. Material Check Material : SID version_V1 RRU : Match ANT : Match iDMU : No Install New Cabinet : No Battery Work : No 2300 Hot Swap : No RRU/ANT Space : Yes S/N : AAU5685md_2300+2600 S1 – 2102315NDH10S3100493 S2 – 2102315NDH10S3100494 S3 – 2102315NDH10S3100495 RRU5513w for Multi-mode 1800MHz~2100MHz S4 - 2102313UUQ10QC100335 Port Cal : No ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 0.5 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [8 empty] | 2026-07-04 | 2026-07-06 | Jirawan Tantimethanon 84318961 | 2026-07-06 Site : KKN8563X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done 2600 RET/BFANT : Done 2300 RET/BFANT : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Integrate 18002100 S54 done URL Ticket : https://wongla.com/chat?id=4707655&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-08 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-08 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-15 | Kaung Htet San WX1440182 | 09 Cross Sector Verification Not have | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-07-31 | 2026-07-14 | Auttaseth Klomthaisong |  | 2026-07-05 | 2026-07-06 | Chootinatcha Supphapongpak 84433801 |  | 2026-07-31 | 2026-07-04 | Teloneer Company Limited |  |  |  |  | 2026-06-12 | Teeranun Suksom WX1454012 |  |  | 2026-06-23 | xinghaixia WX1519428 |  |  | 2026-06-22 | zhangguanglin WX1251498 |  |  | 2026-06-28 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2624 |  | 2026-06-23 | xinghaixia WX1519428 |  |  |  | 2026-07-04 | 2026-07-06 | Jirawan Tantimethanon 84318961 | 2026-07-04 KKN8563L_6NB02 Slot 19 : Done KKN8563X_2NB01 Pending Off main test alarm แล้ว site down Confirm Battery ไม่เก็บไฟครับ Tinnakorn_PE · 12:18:21 PM |  | 2026-08-06 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=1649806517#gid=1649806517 |  |  | 2026-07-04 | 2026-07-04 | Jirawan Tantimethanon 84318961 | 2026-07-04 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 16.421101 | 102.779481 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-07-23 | 2026-07-23 | Jiraporn Chantasil WX1462181 |  |  | 2026-07-22 | Okkar Kyaw WX1404297
KKNA002_Flash_RAN_NEA R5 | KKNA002 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-18 | thcp_chalit.sar |  |  |  | 2026-08-17 | 2026-08-17 | Jirawan Tantimethanon 84318961 |  | 2026-08-25 | 2026-08-25 | 2026-08-25 | 2026-08-25 | Tinnakorn Konseela 84060525 | [9 empty] | 2026-08-25 | 2026-08-25 | Akaradech Sonamthiang WX1494384 | 2026-08-26 Site : KKNA002X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Integrate 2300/2600 and 1800/2100 Done [Remote to node] URL Ticket : https://wongla.com/chat?id=4861723&category=Ticket%20Update Today : Clear pending Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-09-30 | 2026-08-27 | Teloneer Company Limited |  | 2026-09-30 | 2026-08-27 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-31 | Kaung Ko Ko WX1541657 | [9 empty] | 2026-09-30 | 2026-08-28 | Auttaseth Klomthaisong | 1.need photos [SFP-fosc#， ASIB#， FYMA-GPS] |  | 2026-08-25 |  |  | 2026-09-30 | 2026-08-25 | Teloneer Company Limited |  |  |  |  | 2026-02-19 | Kulchaya Srichavanant 84433803 |  |  | 2026-03-09 | China GSC Survey Design Team |  |  | 2026-02-25 | yangzhi WX1171682 |  |  | 2026-08-16 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2633 |  | 2026-03-09 | China GSC Survey Design Team |  |  |  | 2026-08-25 | 2026-08-25 | Akaradech Sonamthiang WX1494384 | 2026-08-25 Site KKNA002X_2NB01 Cabinet 1 slot 18 : N/A Cabinet 1 slot 19 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-08-25 | 2026-08-26 | Akaradech Sonamthiang WX1494384 | 2026-08-25 Site KKNA002X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done | KKNA001 | 16.467801 | 102.811801 | 2026-08-11 | N/A | N/A | N/A | N/A |  |  | Ready |  | 2026-09-01 | 2026-09-01 | Jiraporn Chantasil WX1462181 |  |  | 2026-09-11 | Okkar Kyaw WX1404297
KKNA010_Flash_RAN_NEA R5 | KKNA010 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-22 | [21 empty] | 2026-09-19 | 2026-09-19 | 2026-09-19 | Akaradech Sonamthiang WX1494384 | 2026-09-19 Site : KKNA010 Remote from KKNC069L_6NB02 Today : Integrate 2300 and 2600 Done 10G : Done Alarm : RET Antenna Not Calibrated Pending : 1. Check antenna 2123 S2 URL Ticket https://wongla.com/chat?id=4968446&category=Ticket%20Update | 0/2 | Not Completed | Not Completed | 2026-09-30 | 2026-09-25 | Teloneer Company Limited |  | 2026-09-30 | 2026-09-23 | Teloneer Company Limited |  |  | 04. ALM - RET/ALD | [12 empty] | 2026-09-30 | 2026-09-28 | Auttaseth Klomthaisong | 1.need photos [6*SFP#， 3*RRU's brackets#， 4*boards#， 3*power connectors#， single mount] >> QC & FMR have nothing photos >> how do to review?? |  | 2026-09-18 |  |  | 2026-09-30 | 2026-09-19 | Chalit Sarawohan(Teloneer Company Limited) |  |  |  |  | 2026-03-10 | Kulchaya Srichavanant 84433803 |  |  | 2026-07-30 | jinwen WX1379399 |  |  | 2026-07-30 | yangzhi WX1171682 |  |  | 2026-09-15 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2633 |  | 2026-07-30 | jinwen WX1379399 |  |  |  | 2000-01-01 | 2000-01-01 | Akaradech Sonamthiang WX1494384 | Remote site |  | 2026-06-05 | Narusorn Phattharajaruk 00928167 | DPU Work No Battery |  |  | 2026-09-19 | 2026-09-19 | Akaradech Sonamthiang WX1494384 | KKNA010 Remote from KKNC069L_6NB02 | KKNC069 | 16.475191 | 102.822721 | 2026-07-29 | N/A | N/A | N/A | N/A |  |  | Ready
KKNC069_Flash_RAN_NEA R5 | KKNC069 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-30 |  |  |  |  | 2026-08-25 | 2026-08-25 | Jirawan Tantimethanon 84318961 |  | 2026-09-15 | 2026-09-15 | 2026-09-15 | 2026-09-15 | Tinnakorn Konseela 84060525 | [8 empty] | 2026-09-19 | 2026-09-16 | 2026-09-16 | Chadathan Thumsawat WX1461876 | 2026-09-30 Site : KKNC069L_6NB02 Integrate 2300/2600 Done Today : Clear pending 10G : Done Alarm : Clear Pending : URL Ticket - https://wongla.com/chat?id=4976629&category=Ticket%20Update | 0/2 | Not Completed | Not Completed | 2026-09-30 | 2026-09-30 | Teloneer Company Limited |  | 2026-09-30 | 2026-09-26 | Teloneer Company Limited |  |  | 00. No alarm | [12 empty] | 2026-09-30 | 2026-10-01 | Auttaseth Klomthaisong | 1.wait QC 2.need 6*SFP25G photo |  | 2026-09-16 |  |  | 2026-09-30 | 2026-09-21 | Teloneer Company Limited |  |  |  |  | 2026-05-09 | Sunisa Worathongchai WX1291720 |  |  | 2026-07-29 | qinyutong WX1433920 |  |  | 2026-07-29 | yangzhi WX1171682 |  |  | 2026-09-15 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2633 |  | 2026-07-29 | qinyutong WX1433920 |  |  |  | 2026-09-22 | 2026-09-22 | Peerapol Prapai 84315924 | Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-09-16 | 2026-09-16 | Chadathan Thumsawat WX1461876 |  | KKNC069 | 16.472401 | 102.823401 | 2026-08-05 | N/A | N/A | N/A | N/A |  |  | Ready
KKNC091_Flash_RAN_NEA R5 | KKNC091 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-16 | thcp_chalit.sar |  |  |  | 2026-07-13 | 2026-07-13 | Jirawan Tantimethanon 84318961 |  | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | Tinnakorn Konseela 84060525 | KCP 2 KKNC091 MBB:Install & Integrate KCP 2 Readiness by PE & Decision by OMC Site : KKNC091 Subcon : TLN CR/SSA/TT : ------------------------------------------ 1. Material Check Material : SID version_V2 RRU : Match ANT : Match iDMU : No Install New Cabinet : No Battery Work : No 2300 Hot Swap : Yes RRU/ANT Space : Yes S/N : RRU5818_2300MHz S1 - 2102313BDDDUS1001545 S2 - 2102313BDDDUS1001580 S3 - 2102313BDDDUS1001598 Port Cal : Yes S/N : RRU5258_2600MHz S1 - 2102312QFQ10MC100765 S2 - 2102312QFQ10N5100298 S3 - 21023120FQ10M1001793 Port Cal : Yes ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 0.5 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [8 empty] | 2026-07-16 | 2026-07-17 | Akaradech Sonamthiang WX1494384 | 2026-07-17 Site : KKNC091 remote from KKN1622L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Integrate 2300 Done URL Ticket : https://wongla.com/chat?id=4740399&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-23 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-22 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-27 | Kaung Htet San WX1440182 | [9 empty] | 2026-07-21 | 2026-07-24 | Auttaseth Klomthaisong |  |  | 2026-07-16 |  |  | 2026-07-31 | 2026-07-20 | Teloneer Company Limited |  |  |  |  | 2026-02-20 | Kulchaya Srichavanant 84433803 |  |  | 2026-06-17 | yangshuanghong WX1009887 |  |  | 2026-06-17 | yangzhi WX1171682 |  |  | 2026-07-09 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2632 |  | 2026-06-17 | yangshuanghong WX1009887 |  |  |  | 2000-01-01 | 2000-01-01 | Akaradech Sonamthiang WX1494384 | Remote site |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | DPU Work No Battery |  |  | 2026-07-17 | 2026-07-17 | Akaradech Sonamthiang WX1494384 | 2026-07-17 Site KKNC091 Serial ascending order : Done DSP serial match : Done Azimuth : Done | KKN1622 | 16.451478 | 102.815314 | 2026-07-10 | N/A | N/A | N/A | N/A |  |  | Ready |  | 2026-08-07 | 2026-08-07 | Jiraporn Chantasil WX1462181 |  |  | 2026-08-12 | Okkar Kyaw WX1404297
KKNC092_Flash_RAN_NEA R5 | KKNC092 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-31 | thcp_chalit.sar |  |  |  | 2026-07-13 | 2026-07-13 | Jirawan Tantimethanon 84318961 |  | 2026-07-21 | 2026-07-21 | 2026-07-21 | 2026-07-21 | Tinnakorn Konseela 84060525 | KCP 2 KKNC092 MBB:Install & Integrate KCP 2 Readiness by PE & Decision by OMC Site : KKNC092 Subcon : TLN CR/SSA/TT : ------------------------------------------ 1. Material Check Material : SID version_V2 RRU : Match ANT : Match iDMU : No Install New Cabinet : No Battery Work : No 2300 Hot Swap : Yes RRU/ANT Space : Yes S/N : RRU5818_2300MHz S1 2102313BDDDUS1001697 S2 2102313BDDDUS1001701 S3 2102313BDDDUS1001719 Port Cal : Yes S/N : RRU5258_2600MHz S1 2102312QFQ10N5100250 S2 2102312QFQ10N6100349 S3 2102312QFQ10N6100435 Port Cal : Yes ------------------------------------------ 2. Downtime Evaluation Downtime Est.(Per Sector) : 0.5 Hr ------------------------------------------ 3. Cut-over window/Condition On-site working hours until : 18:00 PM Weather Condition : OK ------------------------------------------ Ready to install & integrate : Yes | [7 empty] | 2026-07-22 | 2026-07-22 | 2026-07-22 | Akaradech Sonamthiang WX1494384 | 2026-07-27 Site : KKNC092 remote from KKN1622L_6NB02 Confirm Azimuth follow FEA 2026-07-22 Site : KKNC092 remote from KKN1622L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Subcon take a photo URL Ticket : https://wongla.com/chat?id=4754313&category=Ticket%20Update Alarm : Clear Remarks : Pending photo direction | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-31 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-24 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-03 | Kaung Htet San WX1440182 | HSSE Line Photo not have | [8 empty] | 2026-08-04 | 2026-08-05 | Auttaseth Klomthaisong | 1.SFP photos are missing 2.GPS & power connector are dismantle or not?? SFP-FOSC is dismantle or not?? |  | 2026-07-21 |  |  | 2026-07-31 | 2026-07-23 | Teloneer Company Limited |  |  |  |  | 2026-02-20 | Kulchaya Srichavanant 84433803 |  |  | 2026-06-17 | jinwen WX1379399 |  |  | 2026-06-17 | yangzhi WX1171682 |  |  | 2026-07-09 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2632 |  | 2026-06-17 | jinwen WX1379399 |  |  |  | 2000-01-01 | 2000-01-01 | Akaradech Sonamthiang WX1494384 | Remote site |  | 2026-06-05 | Narusorn Phattharajaruk 00928167 | DPU Work No Battery |  |  | 2026-07-22 | 2026-07-27 | Akaradech Sonamthiang WX1494384 | 2026-07-21 Site KKNC092 Serial ascending order : Done DSP serial match : Done Azimuth : Pending | KKN1622 | 16.454984 | 102.815151 | 2026-07-10 | N/A | N/A | N/A | N/A |  |  | Ready |  | 2026-08-07 | 2026-08-07 | Jiraporn Chantasil WX1462181 |  |  | 2026-08-11 | Okkar Kyaw WX1404297
KKNC098_Flash_RAN_NEA R5 | KKNC098 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-13 | thcp_chalit.sar |  |  |  | 2026-08-10 | 2026-08-10 | Jirawan Tantimethanon 84318961 |  | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2026-08-12 | Tinnakorn Konseela 84060525 | [9 empty] | 2026-08-11 | 2026-08-12 | Akaradech Sonamthiang WX1494384 | 2026-08-12 Site : KKNC098 Remote from KKN7117L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : 2100 combi new antenna done URL Ticket : https://wongla.com/chat?id=4807499&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-17 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-13 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-19 | Kaung Ko Ko WX1541657 | Line HSSE Photo not have | [8 empty] | 2026-08-31 | 2026-08-20 | Auttaseth Klomthaisong | KKNC098_Flash_RAN_NEA R5 (FMR) 1.need photos SFP-fosc photos 2.RET and GPS are dismantle or not? 3.DCDU have 3 pcs or 2 pcs?? [need to upload clear view for this devices] | 2026-08-23 | 2026-08-12 |  |  | 2026-08-31 | 2026-08-12 | Teloneer Company Limited |  |  |  |  | 2026-02-20 | Kulchaya Srichavanant 84433803 |  |  | 2026-07-30 | wangweihao WX1465967 |  |  | 2026-07-30 | yangzhi WX1171682 |  |  | 2026-08-08 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2637 |  | 2026-07-30 | wangweihao WX1465967 |  |  |  | 2000-01-01 | 2000-01-01 | Akaradech Sonamthiang WX1494384 |  |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | DPU Work No Battery |  |  | 2026-08-11 | 2026-08-13 | Akaradech Sonamthiang WX1494384 | 2026-08-11 Site KKNC098 Serial ascending order : Done DSP serial match : Done Azimuth : Done | KKN7117 | 16.466667 | 102.827272 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-08-26 | 2026-08-26 | Sahadsavat Deesupat WX1462179 |  |  | 2026-08-28 | Okkar Kyaw WX1404297
KKNC099_Flash_RAN_NEA R5 | KKNC099 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-31 | thcp_chalit.sar |  |  |  | 2026-08-10 | 2026-08-10 | Jirawan Tantimethanon 84318961 |  | 2026-08-22 | 2026-08-22 | 2026-08-22 | 2026-08-22 | Tinnakorn Konseela 84060525 | [9 empty] | 2026-08-21 | 2026-08-22 | Akaradech Sonamthiang WX1494384 | 2026-08-31 Site : KKNC099 Remote from KKN7117L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Integrate 2300 and 2600 Done URL Ticket : https://wongla.com/chat?id=4852014&category=Ticket%20Update Today : Clear alarm VSWR done Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-28 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-28 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-01 | Su Myat Aung WX1480913 | [9 empty] | 2026-08-31 | 2026-09-02 | Auttaseth Klomthaisong | 1.RET is dismantle or not?? 2.FPAA is 2 or 3 3.FPFH is dismantle or not?? << need clear view 4.FMFA is dismantel or not?? | 2026-08-23 | 2026-08-16 |  |  | 2026-08-31 | 2026-08-23 | Chalit Sarawohan(Teloneer Company Limited) |  |  |  |  | 2026-03-10 | Kulchaya Srichavanant 84433803 |  |  | 2026-07-31 | qinyutong WX1433920 |  |  | 2026-07-30 | yangzhi WX1171682 |  |  | 2026-08-08 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2637 |  | 2026-07-31 | qinyutong WX1433920 |  |  |  | 2000-01-01 | 2000-01-01 | Akaradech Sonamthiang WX1494384 | Remote |  | 2026-06-05 | Narusorn Phattharajaruk 00928167 | DPU Work No Battery |  |  | 2026-08-22 | 2026-08-26 | Akaradech Sonamthiang WX1494384 | 2026-08-21 Site KKNC099 Serial ascending order : Done DSP serial match : Done Azimuth : Done | KKN7117 | 16.470718 | 102.828131 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-03 | 2026-09-03 | Jiraporn Chantasil WX1462181 |  |  | 2026-09-02 | Hsu Myat Tun WX1538578
KKNC112_Flash_RAN_NEA R5 | KKNC112 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-28 |  |  |  |  | 2026-07-22 | 2026-07-22 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-07-30 |  |  |  |  | 0/2 | Not Completed | Not Completed | 2026-07-31 |  | Teloneer Company Limited |  | 2026-07-31 |  | Teloneer Company Limited | [7 empty] | 2026-07-31 |  | Teloneer Company Limited | [5 empty] | 2026-07-31 |  | Teloneer Company Limited |  | 2026-08-09 |  |  |  | 2026-07-31 |  | Teloneer Company Limited |  |  |  |  | 2026-02-20 | Kulchaya Srichavanant 84433803 |  |  | 2026-07-15 | jinwen WX1379399 |  |  | 2026-07-14 | yangzhi WX1171682 |  |  | 2026-07-27 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2632 |  | 2026-07-15 | jinwen WX1379399 | [8 empty] | 2000-01-01 | Narusorn Phattharajaruk 00928167 | DPU Work No Battery | [6 empty] | KKN8595 | 16.480567 | 102.826843 |  | N/A | N/A | N/A | N/A
MHR0012_Dismantle_NEA R6 | MHR0012 | N/A | Teloneer Company Limited | Teloneer Company Limited | [27 empty] | 0/2 | Not Completed | Not Completed | 2026-10-31 |  | Teloneer Company Limited | [50 empty] | N/A | N/A | N/A | N/A | [25 empty] | N/A | N/A | N/A | N/A
MHR7907_Relocate_NEA R6 | MHR7907 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-10-02 | [10 empty] | 2026-09-25 | 2026-09-25 | Wiriya Putsisen 84433800 | Site : MHR7907 Subcon : TLN CR/SSA/TT : CRQ000006304292 ------------------------------------------ 1. Material Check Material : MHR7907_Relocate_NEA R6_TSSR_TRUE-DTAC Relocate Project FEA_V1_20260615 RRU : Match ANT : Match iDMU : No Install New Cabinet : No Battery Work : No | [8 empty] | 2026-09-30 | 2026-09-30 | Piyachon Kerdseng 84345719(RAN OMC) | 2026-10-01 Site : MHR7907X_2NB01 Relocate from MHR0012X_2NB01 Today : Integrate 791236 Done 10G : Done Alarm : Clear Pending : 2300 S1 port A high URL Ticket : https://wongla.com/chat?id=5003967&category=Ticket%20Update | 0/2 | Not Completed | Not Completed | 2026-10-31 |  | Teloneer Company Limited |  | 2026-10-31 |  | Teloneer Company Limited |  |  | 05. ALM - VSWR | [20 empty] | 2026-09-30 |  | Teloneer Company Limited |  |  |  |  | 2026-07-15 | Kingkan Wangdee 60047396 |  |  | 2026-09-01 | xinghaixia WX1519428 |  |  | 2026-08-31 | yangzhi WX1171682 |  |  | 2026-09-14 | wangpengtao WX1304110 |  | 2026-09-17 | N/A | N/A | N/A | N/A |  |  | 2026-09-01 | xinghaixia WX1519428 |  |  |  | 2026-10-01 | 2026-10-01 | Piyachon Kerdseng 84345719 | 2026-10-01 Test external alarm done | [6 empty] | 2026-10-01 | 2026-10-01 | Piyachon Kerdseng 84345719 | 2026-10-01 Test cross done |  | 16.233500 | 103.273833 | 2026-09-16 | N/A | N/A | N/A | N/A |  |  | Ready
NKI6732_Reach_RAN_NEA R5 | NKI6732 | N/A |  |  | 2026-08-27 | [24 empty] | RAN OMC |  | 0/2 | Not Completed | Not Completed | [53 empty] | N/A | N/A | N/A | N/A | [22 empty] | 17.857691 | 102.843861 |  | N/A | N/A | N/A | N/A
PTT8679_Flash_RAN_BMA R1 | PTT8679 | N/A | Teloneer Company Limited | Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited | 2026-08-25 | THCP_xaiphone.k |  |  |  | 2026-08-18 | 2026-08-18 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-08-24 | 2026-08-24 | 2026-08-24 | Akaradech Sonamthiang WX1494384 | 2026-08-25 Site : PTT8679L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Integrate 2300 and 2600 Done URL Ticket : https://wongla.com/chat?id=4856798&category=Ticket%20Update Today : Clear pending Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-31 | Teloneer Company Limited |  | 2026-08-31 | 2026-09-02 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-07 | Su Myat Aung WX1480913 | [9 empty] | 2026-09-19 | 2026-09-22 | Thossapan Chaloemrit | 01- E-Bracket (LTHBTES-SXK2006/1_OLD-D) 2 pcs of FMR was not have in QC #， Dismantle or not ?? Plz confirm |  | 2026-08-24 |  |  | 2026-08-31 | 2026-08-24 | Teloneer Company Limited |  |  |  |  | 2026-04-16 | Kulchaya Srichavanant 84433803 |  |  | 2026-08-14 | xujunliang WX1297747 |  |  | 2026-08-13 | yangzhi WX1171682 |  |  | 2026-08-16 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2644 |  | 2026-08-14 | xujunliang WX1297747 |  |  |  | 2026-08-25 | 2026-08-25 | Jirawan Tantimethanon 84318961 | 2026-08-24 Site PTT8679 Cabinet 1 : Done Cabinet 2 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-08-24 | 2026-08-25 | Akaradech Sonamthiang WX1494384 | 2026-08-24 Site PTT8679L_6NB02 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 14.100701 | 100.630801 |  | N/A | N/A | N/A | N/A | [9 empty] | 2026-09-24 | Okkar Kyaw WX1404297
RYG0404_Flash_RAN_EAS R3 | RYG0404 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-27 | thcp_wachira s |  |  |  | 2026-08-17 | 2026-08-17 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-08-24 | 2026-08-25 | 2026-08-25 | Akaradech Sonamthiang WX1494384 | 2026-08-27 Site : RYG0404X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Integrate 2300/2600 and 1800 Done URL Ticket : https://wongla.com/chat?id=4861710&category=Ticket%20Update Today : Clear pending Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-28 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-28 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-02 | Kaung Htet San WX1440182 | Line HSSE Photo not have | [8 empty] | 2026-08-31 | 2026-08-29 | Boonchot Boriwut |  |  | 2026-08-23 |  |  | 2026-08-31 | 2026-08-28 | Teloneer Company Limited |  |  |  | 2026-07-14 | 2026-07-14 | Santi Rodjanachalee WX1291343 |  |  | 2026-08-06 | qinyutong WX1433920 |  |  | 2026-08-06 | zhangguanglin WX1251498 |  |  | 2026-08-14 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2647 |  | 2026-08-06 | qinyutong WX1433920 |  |  |  | 2026-08-22 | 2026-08-22 | Jirawan Tantimethanon 84318961 |  |  | 2026-09-16 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-08-25 | 2026-08-25 | Akaradech Sonamthiang WX1494384 | 2026-08-25 Site RYG0404X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 13.032283 | 101.200205 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-18 | 2026-09-18 | Sahadsavat Deesupat WX1462179 |  |  | 2026-09-13 | Okkar Kyaw WX1404297
RYG0571_Flash_RAN_EAS R3 | RYG0571 | N/A | Teloneer Company Limited |  | 2026-08-05 | thcp_wachira s |  |  |  | 2026-07-14 | 2026-07-14 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-08-04 | 2026-08-04 | Akaradech Sonamthiang WX1494384 | 2026-08-04 Site : RYG0571X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Integrate 2300 Done URL Ticket : https://wongla.com/chat?id=4786042&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-09-30 | 2026-08-05 | Teloneer Company Limited |  | 2026-06-10 | 2026-08-05 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-07 | Kaung Htet San WX1440182 | 09 Site Integration not have HSSE Line Photo not have | [8 empty] | 2026-09-30 | 2026-08-06 | Boonchot Boriwut |  | 2026-08-08 | 2026-08-04 | Chootinatcha Supphapongpak 84433801 |  | 2026-09-30 | 2026-08-04 | Teloneer Company Limited |  | 2026-08-04 | Entirely Completed |  | 2026-06-04 | Settha Prompunjai WX1438714 |  |  | 2026-06-10 | xinghaixia WX1519428 |  |  | 2026-06-08 | zhangguanglin WX1251498 |  |  | 2026-06-12 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2630 |  | 2026-06-10 | xinghaixia WX1519428 |  |  |  | 2026-08-04 | 2026-08-04 | Akaradech Sonamthiang WX1494384 | 2026-08-04 Site RYG0571X_2NB01 Cabinet 1 slot 18 : N/A Cabinet 1 slot 19 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-08-04 | 2026-08-04 | Akaradech Sonamthiang WX1494384 | 2026-08-04 Site RYG0571X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 12.920277 | 101.200554 |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-18 | 2026-09-18 | Sahadsavat Deesupat WX1462179 |  |  | 2026-08-10 | Okkar Kyaw WX1404297
RYG0627_FlashRevisit_EAS R3 | RYG0627 | N/A |  | Teloneer Company Limited | 2026-10-01 | [22 empty] | 2026-10-01 | 2026-10-01 | Jirawan Tantimethanon 84318961 | 2026-10-01 เปลี่ยนสายDC+CPRIของ2300 -Sector 2#，3#，4 ครับ | 0/2 | Not Completed | Not Completed | 2026-10-10 |  | Teloneer Company Limited | [6 empty] | 00. No alarm | [20 empty] | 2026-10-10 |  | Teloneer Company Limited | [20 empty] | N/A | N/A | N/A | N/A | [7 empty] | 2000-01-01 | 2000-01-01 | Jirawan Tantimethanon 84318961 | [7 empty] | 2000-01-01 | 2000-01-01 | Jirawan Tantimethanon 84318961 |  |  | 12.93166 | 101.18485 |  | N/A | N/A | N/A | N/A
RYG0627_Flash_RAN_EAS R3 | RYG0627 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-07-01 | thcp_wachira s |  |  |  | 2026-06-25 | 2026-06-25 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-06-27 | 2026-06-27 | Akaradech Sonamthiang WX1494384 | 2026-07-01 Site : RYG0627X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : 10G cut over finished. URL Ticket : https://wongla.com/chat?id=4688283&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-01 | Teloneer Company Limited |  | 2026-07-31 | 2026-07-01 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-11 | Su Myat Aung WX1480913 | HSSE photo not have | [8 empty] | 2026-07-31 | 2026-07-02 | Boonchot Boriwut |  |  | 2026-06-28 |  |  | 2026-07-31 | 2026-06-27 | Teloneer Company Limited |  | 2026-06-28 | Entirely Completed |  | 2026-06-04 | Settha Prompunjai WX1438714 |  |  | 2026-06-09 | xinghaixia WX1519428 |  |  | 2026-06-08 | zhangguanglin WX1251498 |  |  | 2026-06-12 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2630 |  | 2026-06-09 | xinghaixia WX1519428 |  |  |  | 2026-06-29 | 2026-06-29 | Jirawan Tantimethanon 84318961 | 2026-06-27 Site RYG0627X_2NB01 Cabinet 1 slot 18 : N/A Cabinet 1 slot 19 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-06-27 | 2026-06-27 | Akaradech Sonamthiang WX1494384 | 2026-06-27 Site RYG0627X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 12.931660 | 101.184850 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-03 | Sahadsavat Deesupat WX1462179 |  |  | 2026-07-11 | Su Myat Aung WX1480913 | HSSE photo not have
RYG0654_Flash_RAN_EAS R3 | RYG0654 | N/A | Teloneer Company Limited |  | 2026-09-30 | thcp_wachira s |  |  |  | 2026-06-16 | 2026-06-16 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-06-17 | 2026-06-18 | Supatong Juntorn WX1461874 | 2026-09-30 Site : RYG0654X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done 2600 RET/BFANT : Done 2300 RET/BFANT : Done Cut 10G : Done Cross Sector : Done Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Clear pending URL Ticket : https://wongla.com/chat?id=4661890&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-06-20 | 2026-06-23 | Teloneer Company Limited |  | 2026-06-20 | 2026-06-22 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-06-27 | Kaung Htet San WX1440182 | [9 empty] | 2026-06-30 | 2026-06-23 | Boonchot Boriwut |  |  | 2026-06-18 |  |  | 2026-06-20 | 2026-06-18 | Teloneer Company Limited |  |  |  |  | 2026-02-18 | Kulchaya Srichavanant 84433803 |  |  | 2026-03-09 | China GSC Survey Design Team |  |  | 2026-02-19 | yangzhi WX1171682 |  |  | 2026-06-15 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2630 |  | 2026-03-09 | China GSC Survey Design Team |  |  |  | 2026-06-19 | 2026-06-19 | Peerapol Prapai 84315924 |  |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-06-18 | 2026-06-18 | Supatong Juntorn WX1461874 |  |  | 12.955068 | 101.112308 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-03 | Sahadsavat Deesupat WX1462179 |  |  | 2026-06-29 | Okkar Kyaw WX1404297
RYG0757_Flash_Battery_EAS R3 | RYG0757 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-01 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | RAN OMC |  | 0/0 | N/A | N/A | 2026-07-31 | 2026-08-03 | Teloneer Company Limited | [11 empty] | N/A | N/A | N/A | N/A |  | 2026-07-28 | Teloneer Company Limited | Wrong file Format | 2027-06-30 | 2026-08-03 | Boonchot Boriwut | [5 empty] | 2026-08-31 | 2026-07-27 | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A |  | 2026-06-12 | xinghaixia WX1519428 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 12.966819 | 101.159949 |  | N/A | N/A | N/A | N/A
RYG0757_Flash_RAN_EAS R3 | RYG0757 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-01 | thcp_wachira s |  |  |  | 2026-06-19 | 2026-06-19 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-07-08 | 2026-07-08 | Akaradech Sonamthiang WX1494384 | 2026-08-01 Site : RYG0757X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Clear pending URL Ticket : https://wongla.com/chat?id=4714205&category=Ticket%20Update Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-07-31 | 2026-07-28 | Teloneer Company Limited |  | 2026-06-10 | 2026-07-27 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-30 | Su Myat Aung WX1480913 | HSSE photo not have Clip Video not have | [8 empty] | 2026-07-31 | 2026-07-30 | Boonchot Boriwut |  | 2026-07-04 | 2026-07-08 |  |  | 2026-08-31 | 2026-07-08 | Teloneer Company Limited |  | 2026-09-09 | Entirely Completed |  | 2026-06-08 | Chanakan Ratanachiwapong 84115359 |  |  | 2026-06-11 | xinghaixia WX1519428 |  |  | 2026-06-10 | zhangguanglin WX1251498 |  |  | 2026-06-17 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2630 |  | 2026-06-11 | xinghaixia WX1519428 |  |  |  | 2026-07-25 | 2026-07-25 | Supatong Juntorn WX1461874 | 2026-07-08 Site RYG0757X_2NB01 Cabinet 1 slot18 : N/A Cabinet 1 slot19 : Done |  | 2026-06-10 | Narusorn Phattharajaruk 00928167 | Existing IP |  |  | 2026-07-08 | 2026-07-17 | Akaradech Sonamthiang WX1494384 | 2026-07-17 Site RYG0757X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 12.966819 | 101.159949 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-03 | Sahadsavat Deesupat WX1462179 |  |  | 2026-08-03 | Okkar Kyaw WX1404297
RYG1830_Flash_RAN_EAS R3 | RYG1830 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-23 | thcp_wachira s |  |  |  | 2026-07-14 | 2026-07-14 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-08-08 | 2026-08-08 | Chadathan Thumsawat WX1461876 | 2026-08-10 Site : RYG1830L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : - Today : Integrate 2300 2600 done URL Ticket : https://wongla.com/chat?id=4800144&category=Ticket%20Update alarm - Clear Remarks : Pending External alarm test | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-17 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-14 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-19 | Kaung Htet San WX1440182 | Line HSSE Photo not have | [8 empty] | 2026-09-30 | 2026-08-17 | Boonchot Boriwut | 1.Ant and Pipe are dismantle or not ?? | 2026-08-31 | 2026-08-08 |  |  | 2026-08-31 | 2026-08-14 | Teloneer Company Limited |  |  |  | 2026-06-04 | 2026-06-04 | Santi Rodjanachalee WX1291343 |  |  | 2026-06-09 | xinghaixia WX1519428 |  |  | 2026-06-08 | zhangguanglin WX1251498 |  |  | 2026-07-13 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2628 |  | 2026-06-09 | xinghaixia WX1519428 |  |  |  | 2000-01-01 | 2000-01-01 | Supatong Juntorn WX1461874 | 2026-08-24 Site RYG1830 Contron ext alarm fail before do activity. PE confirm no text ext alarm |  | 2026-09-09 | Narusorn Phattharajaruk 00928167 | Existing IP |  |  | 2026-08-08 | 2026-08-08 | Chadathan Thumsawat WX1461876 |  | RYG1830 | 12.985113 | 101.140527 | 2026-07-09 | N/A | N/A | N/A | N/A |  |  | Ready |  | 2026-09-18 | 2026-09-18 | Sahadsavat Deesupat WX1462179 |  |  | 2026-08-19 | Okkar Kyaw WX1404297
RYG4003_Flash_RAN_EAS R3 | RYG4003 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-08-09 | thcp_wachira s |  |  |  | 2026-06-16 | 2026-06-16 | Jirawan Tantimethanon 84318961 | [15 empty] | 2026-07-06 | 2026-07-06 | Akaradech Sonamthiang WX1494384 | 2026-07-09 Site : RYG4003L_6NB02 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Integrate 2300 and 2600 Done URL Ticket : https://wongla.com/chat?id=4707684&category=Ticket%20Update Alarm : RET Antenna Not Calibrated RYG7141_R03_900 [before] Remarks : | 0/2 | Not Completed | Not Completed | 2026-06-30 | 2026-07-13 | Teloneer Company Limited |  | 2026-06-30 | 2026-07-13 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-07-17 | Su Myat Aung WX1480913 | HSSE photo not have | [8 empty] | 2026-06-30 | 2026-07-14 | Palagon Prommueangma |  |  | 2026-07-06 |  |  | 2026-06-30 | 2026-07-06 | Teloneer Company Limited |  | 2026-09-09 | Entirely Completed |  | 2026-04-27 | Kulchaya Srichavanant 84433803 |  |  | 2026-06-09 | yangshuanghong WX1009887 |  |  | 2026-06-08 | zhangguanglin WX1251498 |  |  | 2026-06-12 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2630 |  | 2026-06-09 | yangshuanghong WX1009887 |  |  |  | 2026-07-09 | 2026-07-09 | Chadathan Thumsawat WX1461876 | 2026-07-06 Site RYG4003 Cabinet 1 RYG4003X_2NB01 : Pending Cabinet 2 RYG4003L_6NB02 : Pending |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-07-06 | 2026-07-06 | Akaradech Sonamthiang WX1494384 | 2026-07-06 Site RYG4003L_6NB02 Serial ascending order : Done DSP serial match : Done Azimuth : Done | RYG4003 | 12.959182 | 101.169191 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-03 | Sahadsavat Deesupat WX1462179 |  |  | 2026-07-23 | Okkar Kyaw WX1404297
RYG7984_Flash_RAN_EAS R3 | RYG7984 | N/A | Teloneer Company Limited | Teloneer Company Limited | 2026-09-23 | thcp_wachira s |  |  |  | 2026-08-03 | 2026-08-03 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-08-11 | 2026-08-11 | 2026-08-11 | Akaradech Sonamthiang WX1494384 | 2026-09-23 Site : RYG7984H_7NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Clear pending URL Ticket : https://wongla.com/chat?id=4807592&category=Ticket%20Update Alarm : RET Antenna Running Data and Configuration Mismatch Remarks : | 0/2 | Not Completed | Not Completed | 2026-09-30 | 2026-08-14 | Teloneer Company Limited |  | 2026-09-30 | 2026-08-14 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-08-15 | Kaung Htet San WX1440182 | Line HSSE Photo not have | [8 empty] | 2026-09-30 | 2000-01-01 | Teloneer Company Limited |  | 2026-08-08 | 2026-08-11 |  |  | 2026-09-30 | 2026-08-11 | Teloneer Company Limited |  |  |  | 2026-06-30 | 2026-06-30 | Santi Rodjanachalee WX1291343 |  |  | 2026-07-10 | wangchengdu WX1289449 |  |  | 2026-07-10 | yangzhi WX1171682 |  |  | 2026-08-03 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A |  |  | 2026-07-10 | wangchengdu WX1289449 |  |  |  | 2026-08-13 | 2026-08-13 | Peerapol Prapai 84315924 | 2026-08-12 Site RYG7984H_7NB01 Cabinet 1 slot 18 : N/A Cabinet 1 slot 19 : Done |  |  |  | Wait IPRAN Confirm CPE |  |  | 2026-08-11 | 2026-08-11 | Akaradech Sonamthiang WX1494384 | 2026-08-11 Site RYG7984H_7NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 12.924397 | 101.233666 |  | N/A | N/A | N/A | N/A | [5 empty] | 2026-08-14 | Ekkarin Tidkratok WX1539755 |  |  | 2026-08-17 | Okkar Kyaw WX1404297
SMP0595_Flash_RAN_BMA R2 | SMP0595 | N/A | Teloneer Company Limited | Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited | 2026-08-28 | THCP_Xaiphone.k |  |  |  | 2026-08-21 | 2026-08-21 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-08-26 | 2026-08-26 | 2026-08-26 | Kullaphat Yana WX1494386 | 2026-08-27 Site : SMP0595X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Test External Alarm Done URL Ticket : https://wongla.com/chat?id=4867581&category=Ticket%20Update Alarm : Remarks : | 0/2 | Not Completed | Not Completed | 2026-09-16 | 2026-09-17 | Teloneer Company Limited |  | 2026-09-16 | 2026-09-08 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-21 | Kaung Htet San WX1440182 | [9 empty] | 2026-09-16 | 2026-09-22 | Thossapan Chaloemrit |  |  | 2026-08-26 |  |  | 2026-09-16 | 2026-08-27 | Teloneer Company Limited |  |  |  |  | 2026-04-09 | Kulchaya Srichavanant 84433803 |  |  | 2026-07-01 | qinbinyan WX1490486 |  |  | 2026-07-01 | yangzhi WX1171682 |  |  | 2026-08-16 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2646 |  | 2026-07-01 | qinbinyan WX1490486 |  |  |  | 2026-08-27 | 2026-08-27 | Akaradech Sonamthiang WX1494384 | 2026-08-27 Site SMP0595 Cabinet 1 : Done Cabinet 2 : Done |  | 2000-01-01 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-08-26 | 2026-08-26 | Kullaphat Yana WX1494386 | 2026-08-26 Site SMP0595X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 13.626501 | 100.601651 |  | N/A | N/A | N/A | N/A | [9 empty] | 2026-09-24 | Hsu Myat Tun WX1538578
SMP1092_Flash_RAN_BMA R2 | SMP1092 | N/A | Teloneer Company Limited | Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited | 2026-09-09 | THCP_XAIPHONE.K | [20 empty] | 2026-09-05 | 2026-09-05 | 2026-09-05 | Akaradech Sonamthiang WX1494384 | 2026-09-09 Site : SMP1092X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Today : Config slot 18 done URL Ticket : https://wongla.com/chat?id=4912653&category=Ticket%20Update Alarm : Clear Remarks : NR26 all sector and L23 sector 3 can't mod power follow CDD | 0/2 | Not Completed | Not Completed | 2026-09-30 | 2026-09-18 | Teloneer Company Limited |  | 2026-09-30 | 2026-09-08 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-22 | Kaung Htet San WX1440182 | [9 empty] | 2026-09-30 | 2026-09-22 | Thossapan Chaloemrit | 1.power connector clear view | 2026-09-08 | 2026-09-05 |  |  | 2026-09-30 | 2026-09-06 | Teloneer Company Limited |  |  |  |  | 2026-06-09 | Teeranun Suksom WX1454012 |  |  | 2026-08-25 | renqijing WX1507439 |  |  | 2026-08-24 | zhangguanglin WX1251498 |  |  | 2026-08-31 | qianxing WX1280371 |  |  | N/A | N/A | N/A | N/A | WK2636 |  | 2026-08-25 | renqijing WX1507439 |  |  |  | 2026-09-05 | 2026-09-05 | Akaradech Sonamthiang WX1494384 | 2026-09-09 Site SMP1092X_2NB01 Cabinet 1 slot 18 : Done Cabinet 1 slot 19 : Done /// คอนเฟิมครับ BF ไม่มีแบตทั้งสองตู้ ไม่มีแผน Add alarm C2#， (ไม่มี#， UEIU+Lan ข้ามตู้) C2 ไม่มี SPD |  | 2026-06-16 | Narusorn Phattharajaruk 00928167 | No Activity |  |  | 2026-09-05 | 2026-09-05 | Akaradech Sonamthiang WX1494384 | 2026-09-05 Site SMP1092X_2NB01 Serial ascending order : Done DSP serial match : Done |  | 13.576436 | 100.611773 |  | N/A | N/A | N/A | N/A | [9 empty] | 2026-09-26 | Okkar Kyaw WX1404297
SMP8577_Flash_Battery_BMA R2 | SMP8577 | N/A | Teloneer Company Limited | Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited | 2026-08-18 | thcp_Xaiphone.k |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A |  | RAN OMC |  | 0/0 | N/A | N/A | 2026-08-31 |  | Teloneer Company Limited |  | 2026-08-31 |  | Teloneer Company Limited | [7 empty] | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-16 |  | Teloneer Company Limited |  | 2026-08-15 | 2026-08-14 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-14 | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A |  | 2026-08-03 | jiaozelin WX1343901 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-08-03 | jiaozelin WX1343901 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 13.642501 | 100.530801 |  | N/A | N/A | N/A | N/A
SMP8577_Flash_RAN_BMA R2 | SMP8577 | N/A | Teloneer Company Limited | Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited | 2026-09-01 | THCP_Xaiphone.k |  |  |  | 2026-08-10 | 2026-08-10 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-08-13 | 2026-08-13 | 2026-08-13 | Chadathan Thumsawat WX1461876 | 2026-08-18 Site : SMP8577X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : - Integrate 2300 2600 done URL Ticket : https://wongla.com/chat?id=4814363&category=Ticket%20Update Today : External alarm test C1 Alarm : BBU CPRI Interface Error [slot4 port5 - Alarm before] Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-09-08 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-14 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-14 | Kaung Htet San WX1440182 | HSSE Line Photo not have | [8 empty] | 2026-09-19 | 2026-09-22 | Thossapan Chaloemrit | 01-Power connector can't see clear pl upload closely. 02- E-BBU power cable#， Cable MU and Lan cable dismantle need in FMR. | 2026-08-15 | 2026-08-13 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-13 | Teloneer Company Limited |  |  |  |  | 2026-05-30 | Sunisa Worathongchai WX1291720 |  |  | 2026-07-29 | jiaozelin WX1343901 |  |  | 2026-07-29 | wangchengdu WX1289449 |  |  | 2026-08-06 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2647 |  | 2026-07-29 | jiaozelin WX1343901 |  |  |  | 2026-09-11 | 2026-09-11 | Jirawan Tantimethanon 84318961 |  |  | 2026-09-30 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=0#gid=0 |  |  | 2026-08-13 | 2026-08-13 | Chadathan Thumsawat WX1461876 |  |  | 13.642501 | 100.530801 |  | N/A | N/A | N/A | N/A
SMPC018_Flash_Battery_BMA R2 | SMPC018 | N/A | Teloneer Company Limited | Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited | 2026-08-25 | THCP_xaiphone.k |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | 2026-08-25 |  | 2026-08-25 Install & Integrate battery done URL : https://wongla.com/chat?id=4863193&category=Ticket%20Update | 0/0 | N/A | N/A | 2026-08-31 |  | Teloneer Company Limited |  | 2026-08-31 |  | Teloneer Company Limited |  |  | 00. No alarm |  |  |  |  | N/A | N/A | N/A | N/A |  |  |  |  | 2026-09-16 |  | Teloneer Company Limited |  |  | 2026-08-25 |  |  | 2026-08-31 | 2026-08-25 | Teloneer Company Limited |  |  |  | N/A | N/A | N/A | N/A |  | 2026-08-04 | xinghaixia WX1519428 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 13.599749 | 100.621349 |  | N/A | N/A | N/A | N/A
SMPC018_Flash_RAN_BMA R2 | SMPC018 | N/A | Teloneer Company Limited | Teloneer Company Limited;Teloneer Company Limited;Teloneer Company Limited | 2026-08-28 | THCP_xaiphone.k |  |  |  | 2026-08-18 | 2026-08-18 | Jirawan Tantimethanon 84318961 | [14 empty] | 2026-08-23 | 2026-08-20 | 2026-08-20 | Kullaphat Yana WX1494386 | 2026-08-28 Site : SMPC018X_2NB01 BBU integration : Done RRU integration : Done Cell integration : Done Status config RET : Done Cut 10G : Done Cross Sector : Checked and Confirmed Post Check : Checked and Confirmed CDD Compare : Checked and Confirmed Reused Hardware Faulty : Integrate 2300 Done URL Ticket : https://wongla.com/chat?id=4842358&category=Ticket%20Update Today : Clear pending Alarm : Clear Remarks : | 0/2 | Not Completed | Not Completed | 2026-08-31 | 2026-08-28 | Teloneer Company Limited |  | 2026-08-31 | 2026-08-28 | Teloneer Company Limited |  |  | 00. No alarm |  | 2026-09-02 | Kaung Htet San WX1440182 | Line HSSE Photo not have | [8 empty] | 2026-09-19 | 2026-09-22 | Thossapan Chaloemrit | 01-BB6630 Dismantle photo need in FMR. 02-Power connector can't see clear pl upload closely. 03- E-BBU power cable#， Cable MU and Lan cable dismantle need in FMR. |  | 2026-08-20 |  |  | 2026-08-31 | 2026-08-22 | Teloneer Company Limited |  |  |  |  | 2026-06-04 | Kasemsan Kongjam WX1302158 |  |  | 2026-08-04 | xinghaixia WX1519428 |  |  | 2026-08-04 | yangzhi WX1171682 | 20260826 FEA revised version no impact for LLD. |  | 2026-08-16 | youlvpeng WX1280811 |  |  | N/A | N/A | N/A | N/A | WK2642 |  | 2026-08-04 | xinghaixia WX1519428 |  |  |  | 2026-08-21 | 2026-08-21 | Jirawan Tantimethanon 84318961 | 2026-08-21 Cabinet 1 slot 18 : Done Cabinet 2 slot 19 : Done |  | 2026-06-23 | Narusorn Phattharajaruk 00928167 | https://docs.google.com/spreadsheets/d/1flt-BVy3ViegHWYtkNzM8P0w4XS2QzoLH6ffzBZ0qvs/edit?gid=1649806517#gid=1649806517 |  |  | 2026-08-20 | 2026-08-21 | Kullaphat Yana WX1494386 | 2026-08-20 Site SMPC018X_2NB01 Serial ascending order : Done DSP serial match : Done Azimuth : Done |  | 13.599749 | 100.621349 |  | N/A | N/A | N/A | N/A

## Enum (hidden)
00. No alarm
01. No alarm (Before)
02. QLT - Pending Cross Sector Verification
03. Pending External Alarm Test
03.1 ALM - Pending External Alarm
04. ALM - RET/ALD
05. ALM - VSWR
06. ALM - RTWP/RSSI
07. ALM - GPS
08. ALM - RRU/AAU down
09. ALM - RRU/AAU down cause by power issue
10. ALM - RRU/AAU alarm
11. ALM - BBU alarm
12. ALM - Site down with power issue
13. ALM - Site down with others caused
14. CFG - Pending IPRAN
15. CFG - Pending CDD/FEA revision
16. CFG - Pending Reconfiguration
17. HW - Hardware Lacking
18. HW - Wrong hardware type
19. QLT - Installation not complete
20. CFG - 10G cut-over pending
21. ALM - IPCLK Pending
22. SOL - Pending Remote (Donor no alarm)
23. ALM - alarm occurred after cell activated (cannot OA)
02. QLT - Pending Cross Sector Verification;00. No alarm
03. Pending External Alarm Test;01. No alarm (Before)
03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
03. Pending External Alarm Test;04. ALM - RET/ALD;02. QLT - Pending Cross Sector Verification
05. ALM - VSWR;03. Pending External Alarm Test
05. ALM - VSWR;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
06. ALM - RTWP/RSSI;03. Pending External Alarm Test
07. ALM - GPS;03. Pending External Alarm Test
07. ALM - GPS;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
08. ALM - RRU/AAU down;03. Pending External Alarm Test
10. ALM - RRU/AAU alarm;03. Pending External Alarm Test
10. ALM - RRU/AAU alarm;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
10. ALM - RRU/AAU alarm;06. ALM - RTWP/RSSI;03. Pending External Alarm Test
11. ALM - BBU alarm;02. QLT - Pending Cross Sector Verification
11. ALM - BBU alarm;03. Pending External Alarm Test
11. ALM - BBU alarm;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
16. CFG - Pending Reconfiguration;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
16. CFG - Pending Reconfiguration;08. ALM - RRU/AAU down;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
16. CFG - Pending Reconfiguration;10. ALM - RRU/AAU alarm;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
19. QLT - Installation not complete;03. Pending External Alarm Test
19. QLT - Installation not complete;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
19. QLT - Installation not complete;10. ALM - RRU/AAU alarm;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
19. QLT - Installation not complete;13. ALM - Site down with others caused
20. CFG - 10G cut-over pending;01. No alarm (Before)
20. CFG - 10G cut-over pending;02. QLT - Pending Cross Sector Verification
20. CFG - 10G cut-over pending;03. Pending External Alarm Test
20. CFG - 10G cut-over pending;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
20. CFG - 10G cut-over pending;10. ALM - RRU/AAU alarm;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
20. CFG - 10G cut-over pending;19. QLT - Installation not complete;02. QLT - Pending Cross Sector Verification
03.1 ALM - Pending External Alarm;02. QLT - Pending Cross Sector Verification
03.1 ALM - Pending External Alarm;02. QLT - Pending Cross Sector Verification;00. No alarm
03.1 ALM - Pending External Alarm;03. Pending External Alarm Test
03.1 ALM - Pending External Alarm;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
04. ALM - RET/ALD;02. QLT - Pending Cross Sector Verification
04. ALM - RET/ALD;03. Pending External Alarm Test
07. ALM - GPS;03.1 ALM - Pending External Alarm
10. ALM - RRU/AAU alarm;00. No alarm
10. ALM - RRU/AAU alarm;02. QLT - Pending Cross Sector Verification
10. ALM - RRU/AAU alarm;03.1 ALM - Pending External Alarm
10. ALM - RRU/AAU alarm;05. ALM - VSWR
11. ALM - BBU alarm;04. ALM - RET/ALD
11. ALM - BBU alarm;05. ALM - VSWR
11. ALM - BBU alarm;05. ALM - VSWR;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
11. ALM - BBU alarm;06. ALM - RTWP/RSSI;05. ALM - VSWR;02. QLT - Pending Cross Sector Verification
11. ALM - BBU alarm;10. ALM - RRU/AAU alarm
15. CFG - Pending CDD/FEA revision;03. Pending External Alarm Test
17. HW - Hardware Lacking;02. QLT - Pending Cross Sector Verification
17. HW - Hardware Lacking;03. Pending External Alarm Test
17. HW - Hardware Lacking;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
17. HW - Hardware Lacking;03.1 ALM - Pending External Alarm
19. QLT - Installation not complete;02. QLT - Pending Cross Sector Verification
19. QLT - Installation not complete;03.1 ALM - Pending External Alarm;02. QLT - Pending Cross Sector Verification
19. QLT - Installation not complete;04. ALM - RET/ALD;02. QLT - Pending Cross Sector Verification
19. QLT - Installation not complete;05. ALM - VSWR;04. ALM - RET/ALD;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
19. QLT - Installation not complete;10. ALM - RRU/AAU alarm;02. QLT - Pending Cross Sector Verification
19. QLT - Installation not complete;11. ALM - BBU alarm;03.1 ALM - Pending External Alarm
19. QLT - Installation not complete;17. HW - Hardware Lacking;03.1 ALM - Pending External Alarm;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
19. QLT - Installation not complete;17. HW - Hardware Lacking;04. ALM - RET/ALD;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
20. CFG - 10G cut-over pending;03.1 ALM - Pending External Alarm
20. CFG - 10G cut-over pending;03.1 ALM - Pending External Alarm;02. QLT - Pending Cross Sector Verification
20. CFG - 10G cut-over pending;03.1 ALM - Pending External Alarm;03. Pending External Alarm Test
20. CFG - 10G cut-over pending;04. ALM - RET/ALD;03. Pending External Alarm Test
20. CFG - 10G cut-over pending;10. ALM - RRU/AAU alarm
20. CFG - 10G cut-over pending;11. ALM - BBU alarm;00. No alarm
20. CFG - 10G cut-over pending;11. ALM - BBU alarm;03. Pending External Alarm Test
20. CFG - 10G cut-over pending;14. CFG - Pending IPRAN
20. CFG - 10G cut-over pending;16. CFG - Pending Reconfiguration
20. CFG - 10G cut-over pending;18. HW - Wrong hardware type
20. CFG - 10G cut-over pending;19. QLT - Installation not complete;03. Pending External Alarm Test;02. QLT - Pending Cross Sector Verification
20. CFG - 10G cut-over pending;19. QLT - Installation not complete;04. ALM - RET/ALD;02. QLT - Pending Cross Sector Verification
20. CFG - 10G cut-over pending;19. QLT - Installation not complete;18. HW - Wrong hardware type
21. ALM - IPCLK Pending;03. Pending External Alarm Test
21. ALM - IPCLK Pending;04. ALM - RET/ALD
21. ALM - IPCLK Pending;04. ALM - RET/ALD;03. Pending External Alarm Test
21. ALM - IPCLK Pending;19. QLT - Installation not complete
21. ALM - IPCLK Pending;20. CFG - 10G cut-over pending
02. QLT - Pending Cross Sector Verification;03. Pending External Alarm Test;05. ALM - VSWR
10. ALM - RRU/AAU alarm;11. ALM - BBU alarm
16. CFG - Pending Reconfiguration;19. QLT - Installation not complete
05. No LLD
04. No IP
03. No FEA
01. CDD/IP/FEA/LLD Ready
02. No CDD
00. Script Ready
Ready
Site Down
IPRAN
CDD
LLD
05. No LLD
04. No IP
03. No FEA
02. No CDD
01. CDD/IP/LLD/FEA Ready
00. Script Ready

## Subcontractor
Subcontractor Code | Subcontractor
HuaWei
572007 | NESIC (Thailand) Ltd.
886523 | Wire & Wireless Co.,Ltd.
886252 | Thai Te Technology(Thailand) Co., Ltd.
572004 | Turnkey Communication Services Public Company Limited.
572008 | Mobicrat Company Limited
572076 | THAITECHSERVE INTER CO., LTD.
5N2013 | Air Connect Engineering (Thailand) Co., Ltd.
A00504 | Neonworx Communications (Thailand) Ltd.
A03297 | Group Tech Solutions Co., Ltd.
A03579 | STADT TECH Co., Ltd.
A03695 | Gau Shyang Telecommunication Engineering (Thailand) Co., Ltd.
A03726 | Metro Global Services Limited
A03845 | Promt Management Service Company Limited.
A04307 | CCS Comservice (Thailand) Ltd.
A04343 | Future Telecom Co.,Ltd.
A04675 | Linetech Consultant Co.,Ltd.
A05079 | 54 Groups Co.,Ltd.
A05120 | Beyond Worldtech (Thailand) Co., Ltd.
A06259 | AC Progress Technology Co., Ltd.
A06260 | MAC ENVI Technology Co., Ltd.
Z00ISV | ABSO SUPPORT Co.,Ltd.
Z00LX1 | WNP World Wide Co., Ltd.
Z00QHY | V Contribute Co., Ltd
W0004M | Teloneer Company Limited
Z01NWJ | Yinda Technology (Thailand) Co., Ltd.
Z027SS | Suzaku Company Limited
Z029LP | SOURCE INTERCONNECTION(THAILAND) CO.LTD
Z077LW | VPRO NETWORK CO., LTD.
Z07BCN | NY CABLE CO., LTD.
Z07DZC | CC TELECOM CO., LTD.
Z07FYM | PENTOR JGL TELECOM CO.,LTD.
Z07IST | ABC THAI COMPANY LIMITED
Z07NSR | Girobumi Technologies (Thailand) co.,ltd.
Z07Y0W | YOUPENG INFORMATION TECHNOLOGY (THAILAND) COMPANY LIMITED